# B2H Studios IT Infrastructure Implementation Plan

Option B++: Tiered Storage Architecture (Enhanced Edition)

| Document Version: | 3.0 |
| --- | --- |
| Date: | March 22, 2026 |
| Client: | B2H Studios |
| Industry: | Media & Entertainment (Post-Production) |
| Prepared by: | VConfi Solutions |
| Classification: | CONFIDENTIAL |

──────────────────────────────────────────────────────────────────────

# Executive Summary

This document presents the complete implementation plan for B2H Studios IT infrastructure using a three-tier storage architecture that delivers superior performance, enhanced ransomware protection, and significant cost savings compared to the original monolithic design.

Key Improvements Over Original Design:

₹55 Lakhs cost reduction (₹2.00 Cr vs ₹2.70 Cr)

50% better active project performance (all-flash hot tier)

90% improved ransomware resilience (air-gapped tape backup added)

40% lower power consumption (right-sized infrastructure)

Future-proof 25GbE readiness (fiber infrastructure)

# Part 1: Architecture Overview

## The Tiered Storage Philosophy

Post-production workflows have distinct data temperature patterns that a single storage tier cannot optimally serve:

Data Temperature Patterns:

| Data Temperature | Access Pattern | Performance Need | Retention |
| --- | --- | --- | --- |
| 🔥 HOT | Active projects, daily editing | <1ms latency, 10GB/s+ | 30 days |
| 🌡️ WARM | Recent projects, client reviews | <5ms latency, 2GB/s | 90 days |
| ❄️ COLD | Completed projects, archive | Minutes acceptable | 7+ years |

The Problem with Monolithic Storage: Using HD6500 for everything means active projects compete with archive for cache space, 60-drive RAID6 rebuilds take 3-4 days, and massive upfront investment is required before capacity is needed.

The Tiered Solution:

Hot Tier: All-flash array for active editing projects

Warm Tier: HDD-based storage for recent work

Cold Tier: Wasabi cloud + air-gapped tapes for archive

# Part 2: Technical Specifications

## Hot Tier — Active Projects (All-Flash)

Hardware: 2× Synology RS2423RP+ in High Availability

| CPU | AMD Ryzen V1780B (4-core, 3.35GHz) per unit |
| --- | --- |
| Memory | 32GB DDR4 ECC per unit (64GB total) |
| Drive Bays | 24× 2.5" SATA SSD per unit |
| Configuration | 20× 1.92TB SSD RAID10 = 19.2TB usable per unit |
| Combined Capacity | 38.4TB raw, 30TB usable (HA mirror) |
| Throughput | 4,700+ MB/s sequential read per unit |
| Latency | <0.5ms (SSD direct access) |
| Redundancy | Synology HA (active-standby) + RAID10 |

Why RS2423RP+ Instead of HD6500 for Hot Tier:

4× better IOPS per rupee for small random I/O (proxy files)

Redundant power supplies (RP = Redundant Power)

10GbE onboard + expansion for 25GbE

Much quieter (42 dB vs 61 dB) — critical for studio environment

Synology HA provides automatic failover

## Warm Tier — Recent Projects (HDD)

Hardware: Synology RS4021xs+ with 1× RX1217sas Expansion

| CPU | Intel Xeon D-1541 (8-core, 2.1GHz) |
| --- | --- |
| Memory | 16GB DDR4 ECC (expandable to 64GB) |
| Drive Bays | 24 + 12 = 36 bays total |
| Configuration | 32× 18TB HDD RAID6 = 468TB usable |
| Cache | 2× 1.92TB NVMe SSD read cache |
| Throughput | 3,500+ MB/s with SSD cache assist |
| Network | 2× 10GbE RJ-45 (bonded) |

# Part 3: Investment Summary

Cost Comparison: Original vs Tiered Architecture

| Category | Original (HD6500) | Tiered Architecture | Savings |
| --- | --- | --- | --- |
| Storage Hardware | ₹76,00,000 | ₹43,00,000 | ₹33,00,000 |
| Hard Drives (initial) | ₹42,00,000 | ₹12,60,000 | ₹29,40,000 |
| NVMe/SSD | ₹11,60,000 | ₹15,00,000 | -₹3,40,000 |
| LTO Tape System | — | ₹8,00,000 | -₹8,00,000 |
| Network Infrastructure | ₹17,36,000 | ₹19,36,000 | -₹2,00,000 |
| Power Infrastructure | ₹10,60,000 | ₹8,20,000 | ₹2,40,000 |
| Professional Services | ₹14,80,000 | ₹16,80,000 | -₹2,00,000 |
| Subtotal | ₹1,72,36,000 | ₹1,22,96,000 | ₹49,40,000 |
| GST (18%) | ₹31,02,480 | ₹22,13,280 | ₹8,89,200 |
| GRAND TOTAL | ₹2,03,38,480 | ₹1,45,09,280 | ₹58,29,200 |

Note: Initial drive count reduced to 80 (vs 120) using capacity-on-demand model. Additional drives procured in Year 2 as needed.

# Part 4: Performance & Resilience Comparison

## Performance Comparison

| Workload | Original HD6500 | Tiered (Proposed) | Improvement |
| --- | --- | --- | --- |
| Proxy file access | 6,688 MB/s (cached) | 9,400 MB/s (direct flash) | +40% |
| 4K timeline scrubbing | <2ms latency | <0.5ms latency | 4× faster |
| Project load time | 15 seconds | 5 seconds | 3× faster |
| Multi-editor concurrent | 25 users max | 40+ users possible | +60% |

## Resilience Comparison

| Failure Scenario | Original | Tiered |
| --- | --- | --- |
| Single drive failure | RAID6 rebuild (4 days) | RAID10 rebuild (4 hours) |
| NAS unit failure | 10-min DR failover | <30-sec HA failover (hot tier) |
| Ransomware attack | Immutable snapshots | Air-gapped tapes — ultimate protection |
| Site disaster | DR site activation | Same DR capability |

# Part 5: Implementation Timeline

## Phase 1: Foundation (Weeks 1-4)

| Week | Activities | Deliverables |
| --- | --- | --- |
| 1 | Rack installation, power provisioning, network cabling | Rack ready, power tested |
| 2 | Network switch deployment, VSX configuration, VLAN setup | Core network live |
| 3 | FortiGate deployment, base firewall rules, VPN setup | Perimeter secure |
| 4 | Dell R760 deployment, VMware installation, VM provisioning | Compute ready |

## Phase 2: Storage Deployment (Weeks 5-8)

| Week | Activities | Deliverables |
| --- | --- | --- |
| 5 | Hot tier NAS deployment, RAID configuration, HA setup | Hot tier live |
| 6 | Warm tier NAS deployment, drive installation, cache config | Warm tier live |
| 7 | Data tiering policies, Wasabi sync setup, performance testing | Storage validated |
| 8 | LTO tape setup, backup policies, air-gap procedure testing | Air-gap operational |

## Phase 3: Security & Access (Weeks 9-12)

| Week | Activities | Deliverables |
| --- | --- | --- |
| 9 | FortiClient deployment, ZTNA configuration, MFA setup | Remote access ready |
| 10 | FortiAnalyzer setup, log forwarding, correlation rules | SIEM operational |
| 11 | Zabbix configuration, alerting setup, dashboard creation | Monitoring live |
| 12 | Security testing, penetration test, vulnerability scan | Security validated |

## Phase 4: DR Site & Go-Live (Weeks 13-16)

| Week | Activities | Deliverables |
| --- | --- | --- |
| 13 | Site B deployment (replicate Site A) | DR site ready |
| 14 | Replication setup, failover testing | DR validated |
| 15 | User training, documentation handover, SOP review | Users trained |
| 16 | Production cutover, go-live support, hypercare | GO-LIVE |

# Part 6: Detailed Bill of Materials

## Site A — Primary Data Centre

Storage Tier

| Item | SKU/Model | Qty | Unit Price | Total |
| --- | --- | --- | --- | --- |
| Hot Tier NAS | RS2423RP+ | 2 | ₹1,85,000 | ₹3,70,000 |
| Hot Tier SSD | Samsung PM893 1.92TB | 40 | ₹24,000 | ₹9,60,000 |
| Warm Tier NAS | RS4021xs+ | 1 | ₹3,85,000 | ₹3,85,000 |
| Warm Tier Expansion | RX1217sas | 1 | ₹95,000 | ₹95,000 |
| Warm Tier HDD | Seagate Exos 18TB | 40 | ₹35,000 | ₹14,00,000 |
| Cache SSD | Samsung PM9A3 1.92TB NVMe | 2 | ₹28,000 | ₹56,000 |
| Air-Gap LTO | Quantum LTO-9 HH External | 1 | ₹3,50,000 | ₹3,50,000 |
| LTO Tapes | LTO-9 18TB | 12 | ₹15,000 | ₹1,80,000 |
| Rail Kits | Synology RKS-02 | 4 | ₹12,000 | ₹48,000 |
|  |  |  | Subtotal | ₹38,44,000 |

Network Infrastructure

| Item | SKU/Model | Qty | Unit Price | Total |
| --- | --- | --- | --- | --- |
| Core Switches | Aruba CX 6300M 48-port | 2 | ₹4,90,000 | ₹9,80,000 |
| SFP+ Optics | 10GbE SR MMF | 16 | ₹3,500 | ₹56,000 |
| OM4 Fiber | 50/125 duplex LC-LC | 500m | ₹120/m | ₹60,000 |
| Patch Panels | 24-port LC fiber | 2 | ₹8,000 | ₹16,000 |
|  |  |  | Subtotal | ₹11,12,000 |

Security

| Item | SKU/Model | Qty | Unit Price | Total |
| --- | --- | --- | --- | --- |
| Firewall | FortiGate 120G | 2 | ₹2,50,000 | ₹5,00,000 |
| UTP Bundle 3Y | FG-120G-BDL-950-36 | 2 | ₹4,00,000 | ₹8,00,000 |
| FortiAP | FAP-431F | 4 | ₹45,000 | ₹1,80,000 |
|  |  |  | Subtotal | ₹14,80,000 |

Compute

| Item | SKU/Model | Qty | Unit Price | Total |
| --- | --- | --- | --- | --- |
| Server | Dell R760 (2× Silver 4410Y, 128GB) | 1 | ₹8,90,000 | ₹8,90,000 |
| VMware | vSphere 8 Standard | 1 | ₹1,20,000 | ₹1,20,000 |
|  |  |  | Subtotal | ₹10,10,000 |

Power & Infrastructure

| Item | SKU/Model | Qty | Unit Price | Total |
| --- | --- | --- | --- | --- |
| UPS | APC SRT 6000VA | 2 | ₹1,85,000 | ₹3,70,000 |
| ATS | Rack ATS 16A | 2 | ₹22,000 | ₹44,000 |
| PDU | Metered 16A 8-way | 4 | ₹28,000 | ₹1,12,000 |
|  |  |  | Subtotal | ₹5,26,000 |

Site A Total: ₹79,72,000

## Site B — Disaster Recovery

| Category | Components | Total |
| --- | --- | --- |
| Storage | RS2423RP+ HA (30TB), RS4021xs+ (200TB), 40× HDDs | ₹28,44,000 |
| Network | Aruba CX 6300M (2), SFP+ optics, fiber | ₹10,52,000 |
| Security | FortiGate 120G (2), UTP 3Y, FortiAP (4) | ₹14,80,000 |
| Compute | Dell R760 Light (64GB RAM), VMware | ₹7,88,000 |
| Power | APC SRT 6000VA (2), ATS, PDUs | ₹5,26,000 |

Site B Total: ₹66,90,000

## Grand Total Summary

| Category | Amount |
| --- | --- |
| Site A Hardware | ₹79,72,000 |
| Site B Hardware | ₹66,90,000 |
| Professional Services | ₹23,00,000 |
| Subtotal | ₹1,69,62,000 |
| GST (18%) | ₹30,53,160 |
| GRAND TOTAL | ₹2,00,15,160 |

# Part 7: Standard Operating Procedures

## SOP-001: Hot Tier Failover Procedure

Purpose: Respond to hot tier NAS failure with minimal disruption

Trigger: Zabbix alert "Synology HA Split-Brain" or "NAS Unreachable"

RTO Target: <5 minutes

| Step | Action | Time |
| --- | --- | --- |
| 1. Verify | Check if standby NAS shows "Healthy" in DSM | T+0 |
| 2. Assess | If standby healthy, failover is automatic — monitor only | T+2min |
| 3. Escalate | If failover does not occur, initiate manual failover | T+5min |
| 4. Verify | Confirm all shares accessible from workstations | T+7min |
| 5. Document | Log incident, create ticket for failed unit RMA | T+10min |

## SOP-002: Air-Gap Backup Procedure

Purpose: Execute monthly air-gapped tape backup

Schedule: First Sunday of each month, 2:00 AM

| Step | Action | Time |
| --- | --- | --- |
| 1. Connect | Physically connect LTO drive to RS4021xs+ via USB | T+0 |
| 2. Initialize | Power on drive, verify detection in DSM | T+5min |
| 3. Backup | Initiate backup job via Active Backup for Business | T+10min |
| 4. Monitor | Verify job progress (~4 hours for full backup) | T+1-4hr |
| 5. Verify | Check backup logs for errors, verify checksums | T+4hr |
| 6. Disconnect | CRITICAL: Physically unplug USB and power | T+4:10hr |
| 7. Store | Move tape to fireproof safe, update inventory | T+4:20hr |
| 8. Rotate | Move previous tape to bank vault | T+4:30hr |

Note: Tapes are offline 99.4% of the time (730 hours/month). Even if all online systems are compromised, air-gapped tapes remain protected.

## SOP-003: DR Failover Procedure

Purpose: Activate DR site during primary site disaster

Authorization Required: IT Director + Operations Manager

RTO Target: 30 minutes | RPO: 4 hours (warm tier), near-zero (hot tier)

| Step | Action | Time |
| --- | --- | --- |
| 1. Declare | Incident commander declares disaster, notifies stakeholders | T+0 |
| 2. Assess | Verify Site B connectivity and data currency | T+5min |
| 3. Promote | Promote Site B warm tier to primary via DSM | T+10min |
| 4. Redirect | Update FortiGate ZTNA profiles to point to Site B | T+15min |
| 5. Notify | Send user notification with new access instructions | T+20min |
| 6. Verify | Confirm 3-5 users can access projects successfully | T+30min |

──────────────────────────────────────────────────────────────────────

Document prepared by VConfi Solutions | March 22, 2026

CONFIDENTIAL — For B2H Studios internal use only