VConfi Solutions

IT Infrastructure Solutions

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Implementation Plan

IT Infrastructure Solution - Option B+ (Enhanced Edition)

| Client: | B2H Studios |
| --- | --- |
| Prepared By: | VConfi Solutions Team |
| Date: | March 22, 2026 |
| Classification: | CONFIDENTIAL |

# Table of Contents

This document contains the complete implementation plan. Refer to the section headings for navigation.

Right-click and select 'Update Field' to populate the Table of Contents

Part 1: Executive Summary, Architecture & ISO Compliance

# B2H Studios — IT Infrastructure Implementation Plan

## Part 1: Executive Summary, Architecture & ISO Compliance (Enhanced Edition)

Document Information

Client: B2H Studios

Industry: Media & Entertainment — Post-Production

Solution: Option B+ (Optimized Synology HD6500)

Document Version: 2.0 (Enhanced Edition)

Date: March 22, 2026

Prepared by: VConfi Solutions

Classification: CONFIDENTIAL

# 1. Document Control

## 1.1 Version History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 0.1 | March 15, 2026 | VConfi Solutions | Initial draft based on client requirements gathering |
| 0.2 | March 18, 2026 | VConfi Solutions | Added architecture diagrams and VLAN design |
| 0.3 | March 20, 2026 | VConfi Solutions | Incorporated ISO 27001 compliance mapping |
| 1.0 | March 22, 2026 | VConfi Solutions | Final review and approval release |
| 2.0 | March 22, 2026 | VConfi Solutions | **ENHANCED EDITION** — Added detailed reasoning, decision flowcharts, comprehensive architecture explanations |

## 1.2 Approval Signatures

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Solutions Architect | VConfi Solutions | [Digital Signature] | March 22, 2026 |
| IT Director (Client) | B2H Studios | _________________ | _______________ |
| Project Sponsor (Client) | B2H Studios | _________________ | _______________ |
| CISO / Security Lead | VConfi Solutions | [Digital Signature] | March 22, 2026 |

## 1.3 Distribution List

| Role | Organization | Purpose |
| --- | --- | --- |
| IT Director | B2H Studios | Primary recipient — implementation oversight |
| Project Sponsor | B2H Studios | Budget approval and strategic decisions |
| Finance Controller | B2H Studios | Payment authorization and TCO validation |
| Operations Manager | B2H Studios | Day-to-day operational planning |
| Solutions Architect | VConfi Solutions | Technical authority and escalation point |
| Project Manager | VConfi Solutions | Delivery coordination |
| Security Lead | VConfi Solutions | Compliance verification |
| Network Engineer | VConfi Solutions | Implementation execution |
| System Administrator | B2H Studios | Knowledge transfer and handover |

# 2. Executive Summary

## 2.1 Client Overview

B2H Studios is a Media & Entertainment post-production studio specializing in high-resolution video editing and content creation. With a team of 25 employees operating in a remote/hybrid model, the studio requires a robust, secure, and scalable IT infrastructure to support their proxy-first editing workflow.

### Current Challenges Addressed

Ransomware Risk: Previous concerns about data integrity and malicious encryption

Unpredictable Cloud Costs: Egress fee volatility affecting budget planning

Storage Complexity: Fragmented storage systems creating management overhead

Remote Access: Need for secure, high-performance access for distributed team

## 2.2 Selected Solution: Option B+ (Optimized Synology HD6500)

After comprehensive analysis of requirements, budget constraints, and growth projections, VConfi Solutions recommends Option B+ — an optimized Synology HD6500-based infrastructure with enhanced SSD cache and 25GbE upgrade path.

### Key Solution Highlights

| Feature | Specification |
| --- | --- |
| **Primary Storage** | Synology HD6500 (60-bay enterprise NAS) |
| **Total Capacity per Site** | 936TB usable (1,080TB raw, RAID6 56+4) |
| **NVMe Cache** | 30.72TB (4x 7.68TB SSDs) per site |
| **Deployment Model** | Site A (Primary) + Site B (DR) — Active-Standby |
| **Network Core** | HPE Aruba CX 6300M with VSX stacking |
| **Security Perimeter** | FortiGate 120G HA pair with SD-WAN |
| **Remote Access** | Zero Trust Network Access (ZTNA) — NO traditional VPN |
| **Cloud Tiering** | Wasabi Hot Cloud with zero egress fees |
| **Immutability** | Snapshot Lock for ransomware protection |

## 2.3 Investment Summary

| Financial Metric | Amount (INR) |
| --- | --- |
| **Total Initial Investment** | ₹2,04,03,994 (~₹2.04 Crore) |
| **Annual Operating Cost (Year 1)** | ₹19,79,520 |
| **5-Year Total Cost of Ownership** | ~₹3.4 Crore |
| **Cost per Employee (Initial)** | ₹8,16,160 |
| **Cost per TB (Usable)** | ₹21,795 |

### Investment Justification

The Option B+ solution delivers enterprise-grade capabilities at 18% of the cost of competing solutions (e.g., Dell PowerScale F710 at ₹12.28 Crore). The 5-year TCO includes all hardware, software subscriptions, cloud storage, professional services, and support contracts.

## 2.4 Strategic Benefits

Ransomware Immunity: Immutable snapshots with WORM (Write Once Read Many) protection ensure data cannot be encrypted by malicious actors

Zero Egress Costs: Wasabi Hot Cloud integration eliminates unpredictable cloud egress fees — critical for media workflows with large file transfers

15-Minute RPO: Real-time replication between Site A and Site B ensures minimal data loss in disaster scenarios

ZTNA Security: Modern zero-trust remote access replaces legacy VPN with device posture validation and least-privilege access

ISO 27001 Ready: Infrastructure designed to meet ISO 27001:2022 controls from day one

## 2.5 Why This Solution Was Designed This Way

### The Proxy-First Workflow Decision

The most critical factor enabling this architecture is B2H Studios' use of proxy-first editing workflow. This single characteristic fundamentally changes the storage performance requirements and makes the Synology HD6500 not just viable, but optimal.

Understanding Proxy-First Editing:

| Workflow Stage | Original Footage | Proxy Files |
| --- | --- | --- |
| Storage Location | NAS (VLAN 30) | Local Workstation SSD |
| Resolution | 8K RAW / ProRes 4444 | 1080p ProRes Proxy |
| File Size | 10-50 GB/minute | 500 MB-2 GB/minute |
| Bandwidth Need | 2,000+ MB/s sustained | 20-50 MB/s burst |

Why This Enables HD6500 Choice:

Traditional post-production workflows requiring direct 8K RAW editing from shared storage demand all-flash, ultra-low-latency solutions like Dell PowerScale F710 (₹12.28 Crore). However, with proxy-first workflow:

Editors work on lightweight proxy files stored locally

NAS only serves occasional original file access during conform/export

Sequential read performance of HD6500 (6,688 MB/s with cache) is 13x the requirement

HDD-based storage becomes not just acceptable — it's the economically rational choice

### Architecture Decision Comparison

The following table compares three architectural approaches evaluated for B2H Studios:

| Dimension | Option A (PowerScale) | Option B+ (HD6500) | "Overkill" Solution |
| --- | --- | --- | --- |
| **Storage Platform** | Dell PowerScale F710 | Synology HD6500 | Dell PowerScale F710 × 2 (Active-Active) |
| **Initial Cost** | ₹12.28 Crore | ₹2.04 Crore | ₹25+ Crore |
| **5-Year TCO** | ₹17.5 Crore | ₹3.4 Crore | ₹35+ Crore |
| **Performance** | 25GbE, 10M+ IOPS, <1ms latency | 10GbE, 6,688 MB/s seq, 2-3ms latency | 100GbE, 50M+ IOPS, sub-ms |
| **RTO Capability** | 10 minutes | 10 minutes | <30 seconds |
| **Management Complexity** | High (OneFS expertise required) | Medium (DSM GUI) | Very High (cluster specialists) |
| **Workflow Fit** | ✓ Supports any workflow | ✓ Perfect for proxy-first | ✓ Overkill for proxy-first |
| **Recommendation** | ❌ Unnecessary expense | ✅ **OPTIMAL** | ❌ Extreme over-engineering |

### Storage Architecture Decision Flowchart

flowchart TD
    Start[Storage Architecture Decision] --> Q1{Real-time 8K RAW<br/>editing from NAS?}
    
    Q1 -->|Yes| A1[Dell PowerScale F710<br/>Required<br/>₹12.28 Crore]
    Q1 -->|No| Q2{What is your<br/>workflow model?}
    
    Q2 -->|Proxy-first<br/>editing| A2[Synology HD6500<br/>Sufficient
Performance
₹2.04 Crore]
    Q2 -->|Mixed/Direct edit| Q3{Budget constraint?}
    
    Q3 -->|Unlimited| A1
    Q3 -->|Constrained| A2
    
    A1 --> C1[10M+ IOPS<br/>Sub-ms latency<br/>OneFS complexity<br/>₹10.24 Cr premium]
    
    A2 --> D1[6,688 MB/s seq<br/>13x headroom
DSM simplicity<br/>Acceptable latency]
    
    C1 --> Reject1[❌ Rejected<br/>Overkill for<br/>proxy workflow]
    D1 --> Select[✅ Option B+<br/>SELECTED
Optimal cost-performance
for B2H Studios]
    
    style Start fill:#e3f2fd,stroke:#1565c0
    style Select fill:#c8e6c9,stroke:#2e7d32,stroke-width:3px
    style Reject1 fill:#ffcdd2,stroke:#c62828

Explanation of Decision Flow:

The decision tree above illustrates the logical process that led to selecting the Synology HD6500. Starting with the fundamental question about workflow requirements, we first determine whether real-time 8K RAW editing from NAS is needed. For B2H Studios, the answer is no — they use proxy-first workflow. This immediately eliminates the need for all-flash, ultra-low-latency storage. The HD6500's sequential performance of 6,688 MB/s provides 13x headroom over the calculated 500 MB/s requirement, making it the optimal choice.

Key Insight: The ₹10.24 Crore saved by choosing HD6500 over PowerScale represents 409 years of Wasabi cloud storage costs (200TB × ₹498/TB/month × 12 months × 409 years = ₹10.24 Crore). This illustrates how understanding actual workflow requirements prevents catastrophic over-provisioning.

### Key Takeaways — Why This Solution Was Designed This Way

Proxy-first workflow is the enabler: Understanding that editors work on local proxies, not directly from NAS, reduces storage performance requirements by 50x

Right-sizing beats over-engineering: The HD6500 delivers 100% of required functionality at 18% of the cost

Cost savings fund operational excellence: The ₹10 Crore saved can fund 20+ years of operational improvements, training, and growth

Future-proof without waste: 25GbE upgrade path and 1.5PB capacity ceiling provide growth headroom without paying for unused capacity today

# 3. Architecture Overview

## 3.1 High-Level Design Description

The B2H Studios infrastructure implements a dual-site, active-standby architecture designed for high availability, disaster recovery, and secure remote access. The solution leverages enterprise-grade components while maintaining operational simplicity appropriate for a 25-user environment.

### Site A — Primary Data Centre

Site A serves as the primary production environment hosting all active workloads, user data, and application services. It is equipped with full redundancy at the network, storage, and power layers.

### Site B — Disaster Recovery Site

Site B operates in standby mode, receiving continuous replication from Site A. In the event of Site A failure, Site B can assume production responsibilities within 10 minutes (RTO target).

### Key Architectural Principles

Defense in Depth: Multiple security layers — perimeter firewall, network segmentation, endpoint protection, and data immutability

Redundancy by Design: No single point of failure at Site A; automatic failover to Site B

Simplicity: Synology DSM management reduces operational overhead compared to enterprise storage platforms

Future-Proof: 25GbE upgrade path and 1.5PB maximum capacity accommodate 5+ years of growth

## 3.2 Full Network Topology Diagram

flowchart TB
    subgraph Internet["Internet / WAN"]
        ISP1["ISP 1<br/>Primary Link"]
        ISP2["ISP 2<br/>Secondary Link"]
    end

    subgraph SiteA["Site A — Primary Data Centre"]
        subgraph FGHA["FortiGate 120G HA Pair"]
            FG1["FortiGate 120G-1<br/>Active"]
            FG2["FortiGate 120G-2<br/>Passive"]
            FG1 <-->|"HA Sync<br/>Heart-beat"| FG2
        end

        subgraph CoreA["HPE Aruba CX 6300M VSX Stack"]
            SW1["Switch-1<br/>6300M-1"]
            SW2["Switch-2<br/>6300M-2"]
            SW1 <-->|"VSX Stack<br/>ISL Links"| SW2
        end

        subgraph ServersA["Application Servers"]
            R760A["Dell R760<br/>VM Host"]
            subgraph VMsA["Virtual Machines"]
                Signiant["Signiant SDCX<br/>Jet v7.0"]
                FortiAnalyzer["FortiAnalyzer<br/>Log Collection"]
                FortiAuth["FortiAuthenticator<br/>MFA/RADIUS"]
                Vault["HashiCorp Vault<br/>Secrets Management"]
                EMS["FortiClient EMS<br/>Endpoint Mgmt"]
                Kaspersky["Kaspersky SC<br/>Antivirus"]
            end
            R760A --> VMsA
        end

        subgraph StorageA["Primary Storage"]
            HD6500A["Synology HD6500<br/>Site A<br/>936TB Usable"]
            SSDCacheA["NVMe Cache<br/>30.72TB"]
            HD6500A <-->|"SSD Cache<br/>Acceleration"| SSDCacheA
        end

        subgraph PowerA["Power Infrastructure"]
            UPS1A["UPS 1<br/>APC SRT 10kVA"]
            UPS2A["UPS 2<br/>APC SRT 10kVA"]
            ATSA["Rack ATS"]
            UPS1A --> ATSA
            UPS2A --> ATSA
        end

        FG1 & FG2 -->|"10GbE<br/>Trunk"| CoreA
        CoreA -->|"VLAN 10/20/30/40"| ServersA
        CoreA -->|"VLAN 30 Storage"| StorageA
        ATSA --> PowerADevices["Critical Equipment"]
    end

    subgraph SiteB["Site B — Disaster Recovery"]
        subgraph FGHAB["FortiGate 120G HA Pair"]
            FG1B["FortiGate 120G-1<br/>Active"]
            FG2B["FortiGate 120G-2<br/>Passive"]
            FG1B <-->|"HA Sync"| FG2B
        end

        subgraph CoreB["HPE Aruba CX 6300M VSX Stack"]
            SW1B["Switch-1<br/>6300M-1"]
            SW2B["Switch-2<br/>6300M-2"]
            SW1B <-->|"VSX Stack"| SW2B
        end

        subgraph ServersB["DR Application Server"]
            R760B["Dell R760 (Light)<br/>DR VM Host"]
        end

        subgraph StorageB["DR Storage"]
            HD6500B["Synology HD6500<br/>Site B<br/>936TB Usable"]
            SSDCacheB["NVMe Cache<br/>30.72TB"]
            HD6500B <-->|"SSD Cache"| SSDCacheB
        end

        subgraph PowerB["Power Infrastructure"]
            UPS1B["UPS 1<br/>APC SRT 10kVA"]
            UPS2B["UPS 2<br/>APC SRT 10kVA"]
            ATSB["Rack ATS"]
            UPS1B --> ATSB
            UPS2B --> ATSB
        end

        FG1B & FG2B -->|"10GbE<br/>Trunk"| CoreB
        CoreB -->|"VLAN 10/20/30/40"| ServersB
        CoreB -->|"VLAN 30 Storage"| StorageB
    end

    subgraph Cloud["Cloud Services"]
        Wasabi["Wasabi Hot Cloud<br/>s3.ap-southeast-1<br/>Archive Tier"]
        ZTNA["FortiGate ZTNA<br/>Remote Access Portal"]
    end

    subgraph RemoteUsers["Remote Users"]
        Editors["Video Editors<br/>FortiClient ZTNA"]
        Admin["IT Admins<br/>Secure Access"]
    end

    ISP1 -->|"Primary WAN"| FG1
    ISP2 -->|"Secondary WAN<br/>SD-WAN"| FG2
    ISP1 -->|"Primary WAN"| FG1B
    ISP2 -->|"Secondary WAN"| FG2B

    HD6500A -.->|"Replication<br/>RPO: 15 min"| HD6500B
    SiteA -.->|"Hybrid Share<br/>Cloud Tiering"| Wasabi
    SiteB -.->|"Hybrid Share<br/>Cloud Tiering"| Wasabi

    RemoteUsers -->|"ZTNA<br/>TLS 1.3"| ZTNA
    ZTNA -->|"Encrypted Tunnel"| FG1

    style SiteA fill:#e1f5ff,stroke:#01579b,stroke-width:2px
    style SiteB fill:#fff3e0,stroke:#e65100,stroke-width:2px
    style Internet fill:#f5f5f5,stroke:#616161,stroke-width:1px
    style Cloud fill:#e8f5e9,stroke:#2e7d32,stroke-width:1px
    style RemoteUsers fill:#f3e5f5,stroke:#6a1b9a,stroke-width:1px

## 3.3 Why Active-Standby DR (Not Active-Active)

### 3.3.1 Understanding RTO and RPO

Recovery Time Objective (RTO) and Recovery Point Objective (RPO) are the two critical metrics that define any disaster recovery strategy:

| Metric | Definition | B2H Studios Target | Business Impact |
| --- | --- | --- | --- |
| **RTO** | Maximum acceptable downtime after a disaster | 10 minutes | Determines workflow disruption |
| **RPO** | Maximum acceptable data loss (time window) | 15 minutes | Determines potential rework |

### 3.3.2 The Three DR Architecture Options

Three fundamental approaches exist for disaster recovery. The following analysis explains why Active-Standby was selected:

| Architecture | How It Works | Initial Cost | Annual Operating | RTO | RPO | Suitability |
| --- | --- | --- | --- | --- | --- | --- |
| **Single-Site + Cloud Backup** | Primary site only; backups to cloud; restore on disaster | ₹1.6 Crore | ₹15 Lakhs | 37 days | 24 hours | ❌ Unacceptable for post-production |
| **Active-Standby** | Primary active; DR site receives replication; manual/automated failover | ₹2.04 Crore | ₹28 Lakhs | 10 minutes | 15 minutes | ✅ **OPTIMAL** |
| **Active-Active Cluster** | Both sites active; synchronous replication; automatic failover | ₹8+ Crore | ₹80+ Lakhs | <30 seconds | Zero | ❌ Overkill for requirements |

### 3.3.3 Detailed Cost Comparison: Active-Standby vs Active-Active

The following breakdown shows why Active-Active was rejected due to cost without proportional benefit:

| Cost Component | Active-Standby | Active-Active | Difference |
| --- | --- | --- | --- |
| Storage Hardware (2 sites) | ₹1.08 Crore | ₹3.24 Crore | +₹2.16 Cr |
| Network Infrastructure | ₹42 Lakhs | ₹1.26 Crore | +₹84 L |
| Inter-site Dark Fiber (annual) | N/A | ₹18 Lakhs | +₹18 L/yr |
| VMware vSAN Licensing | N/A | ₹45 Lakhs | +₹45 L |
| Specialized Storage Admin (5yr) | ₹0 | ₹1.5 Crore | +₹1.5 Cr |
| **Total 5-Year Cost** | **₹3.4 Crore** | **₹12+ Crore** | **+₹8.6 Cr** |

The RTO Trade-off Analysis:

| Failover Time | Use Case | Cost Premium | B2H Studios Need |
| --- | --- | --- | --- |
| <30 seconds | Trading floors, emergency services | +₹8.6 Crore | ❌ Not required |
| 10 minutes | Post-production, general business | Baseline | ✅ **MATCHES REQUIREMENT** |
| 37 days | Non-critical archives, development | -₹44 Lakhs | ❌ Unacceptable |

### 3.3.4 DR Architecture Decision Flowchart

flowchart TD
    Start[DR Strategy Selection] --> Q1{What is your<br/>Recovery Time Objective?}
    
    Q1 -->|<1 minute| AA[Active-Active Cluster<br/>Synchronous Replication]
    Q1 -->|1-60 minutes| AS[Active-Standby<br/>Asynchronous Replication]
    Q1 -->|>1 day| CB[Cloud Backup Only<br/>Restore on Demand]
    
    AA --> AA1[Requires: Dark Fiber<br/>3x Storage Overhead<br/>Specialized Staff]
    AS --> AS1[Requires: Standard WAN<br/>2x Storage<br/>Standard IT Skills]
    CB --> CB1[Requires: Cloud Storage<br/>Backup Software<br/>Accept Data Loss]
    
    AA1 --> AACost[Cost: ₹8+ Crore<br/>RTO: <30 sec<br/>RPO: Zero]
    AS1 --> ASCost[Cost: ₹2.04 Crore<br/>RTO: 10 min<br/>RPO: 15 min]
    CB1 --> CBCost[Cost: ₹1.6 Crore<br/>RTO: 37 days<br/>RPO: 24 hours]
    
    AACost --> AAAnalysis{Is sub-minute<br/>failover worth<br/>4x cost increase?}
    ASCost --> ASAnalysis{Does 10-min RTO<br/>meet business needs?}
    CBCost --> CBAnalysis{Can business survive<br/>37 days downtime?}
    
    AAAnalysis -->|Yes for hospitals,<br/>trading floors| AASelect[Active-Active
Selected]
    AAAnalysis -->|No for post-production| AAReject[❌ Rejected
Overkill]
    
    ASAnalysis -->|Yes for B2H| ASSelect[✅ **ACTIVE-STANDBY**
**SELECTED**
Optimal cost-benefit]
    
    CBAnalysis -->|Yes for archives| CBSelect[Cloud Backup
Selected]
    CBAnalysis -->|No for production| CBReject[❌ Rejected
Too Risky]
    
    style Start fill:#e3f2fd,stroke:#1565c0
    style ASSelect fill:#c8e6c9,stroke:#2e7d32,stroke-width:3px
    style AAReject fill:#ffcdd2,stroke:#c62828
    style CBReject fill:#ffcdd2,stroke:#c62828

Explanation of DR Decision Process:

The decision flowchart above demonstrates the systematic evaluation of DR options. For B2H Studios, the 10-minute RTO of Active-Standby is acceptable because:

Post-production is not real-time critical (unlike stock trading or emergency services)

A 10-minute interruption allows time for editor notification, coffee break, or task switching

The ₹8+ Crore cost premium for Active-Active would fund 40 years of operations without providing proportional business value

Cloud-only backup's 37-day restore time would cause contract breaches and client loss

Warning: Do not let "future-proofing" justify Active-Active. If business requirements change to require <1-minute failover, the Active-Standby infrastructure can be upgraded incrementally. The sunk cost of over-provisioning Active-Active is irreversible.

### 3.3.5 How Active-Standby DR Works

Normal Operation:

Site A (Primary) handles all production workloads

Site B (DR) receives continuous replication from Site A

Site B NAS is in read-only mode

DR VMs are powered off (or running in minimal standby mode)

Failover Process (RTO: 10 minutes):

| Minute | Action | Responsible Component |
| --- | --- | --- |
| 0 | Site A failure detected | Zabbix monitoring |
| 0.5 | Alert sent to IT admin | FortiGate + Email |
| 1 | Replication paused at last consistent snapshot | Synology Replication Manager |
| 2 | Site B NAS promoted to read-write | Manual/Automated promotion |
| 3 | ZTNA profiles updated to point to Site B | FortiGate configuration |
| 5 | DR VMs powered on | VMware/vSphere |
| 7 | Services come online (DNS, authentication) | VMs boot sequence |
| 10 | Editors reconnect via FortiClient | User action |

### Key Takeaways — Active-Standby DR Decision

10-minute RTO matches business needs: Post-production can tolerate brief interruptions; trading floors cannot

₹8.6 Crore cost avoidance: The savings vs Active-Active fund 40+ years of operation or significant business expansion

15-minute RPO is acceptable: Maximum data loss equals one coffee break of work — easily recoverable

Upgrade path exists: If requirements change, infrastructure can evolve; over-provisioning cannot be undone

## 3.4 Two-Site Design Rationale

### 3.4.1 Why Not Single-Site with Cloud Backup Only?

A single-site design with cloud backup (e.g., AWS S3, Azure Blob) would save approximately ₹44 Lakhs in initial investment. However, this approach was rejected for critical operational reasons:

The Cloud Restore Time Problem:

| Scenario | Time to Restore | Business Impact |
| --- | --- | --- |
| Restore 400TB from AWS S3 at 1 Gbps | ~37 days | Contract breach, client loss |
| Restore 400TB from Wasabi at 1 Gbps | ~37 days | Same problem |
| Failover to Site B | 10 minutes | Minimal disruption |

Why Cloud Restore Is So Slow:

Even with "high-speed" 1 Gbps internet (125 MB/s):

400TB = 400,000 GB = 400,000,000 MB

400,000,000 MB ÷ 125 MB/s = 3,200,000 seconds

3,200,000 seconds ÷ 86,400 seconds/day = 37 days

In practice, restore speeds are often slower due to:

Cloud provider throttling

Network congestion

Small file overhead (metadata operations)

Verification and integrity checks

The Egress Cost Volatility:

| Cloud Provider | Storage Cost/TB/Month | Egress Cost/TB | 400TB Restore Cost |
| --- | --- | --- | --- |
| AWS S3 Standard | ₹2,300 | ₹8,000 | ₹32,00,000 surprise bill |
| Azure Hot | ₹2,100 | ₹7,500 | ₹30,00,000 surprise bill |
| Wasabi | ₹498 | ₹0 | ₹0 (included) |

While Wasabi eliminates egress fees, the restore time problem remains. A physical DR site provides instant availability without data movement costs.

### 3.4.2 The Two-Site Value Proposition

| Benefit | Single-Site + Cloud | Two-Site Active-Standby |
| --- | --- | --- |
| RTO (downtime) | 37 days | 10 minutes |
| RPO (data loss) | 24 hours | 15 minutes |
| Restore cost for 400TB | ₹0-32 Lakhs (surprise) | ₹0 (already replicated) |
| Metadata preservation | Risk of loss | 100% preserved |
| Client confidence | Low | High (demonstrable DR) |
| ISO 27001 compliance | Partial | Full (redundancy requirement) |

### 3.4.3 Data Flow Diagram: Ingest → Storage → DR → Cloud

flowchart LR
    subgraph Ingest["Ingest Layer"]
        DIT["Field DIT<br/>Camera Cards"]
        FASP["Signiant FASP<br/>UDP Acceleration"]
        SDCX["SDCX Server<br/>VLAN 10 DMZ"]
    end
    
    subgraph Primary["Site A — Primary"]
        NAS_A["Synology HD6500<br/>936TB Usable<br/>VLAN 30"]
        Cache_A["NVMe Cache<br/>30.72TB"]
        Snap_A["Immutable Snapshots<br/>WORM Protection"]
    end
    
    subgraph DR["Site B — DR"]
        NAS_B["Synology HD6500<br/>936TB Usable<br/>Read-Only"]
        Cache_B["NVMe Cache<br/>30.72TB"]
        Snap_B["Replica Snapshots"]
    end
    
    subgraph Cloud["Cloud Tier"]
        Wasabi["Wasabi Hot Cloud<br/>Immutable Buckets<br/>Zero Egress"]
    end
    
    subgraph Access["Access Layer"]
        ZTNA["FortiGate ZTNA<br/>Device Posture Check"]
        Editor["Remote Editor<br/>Proxy Workflow"]
    end
    
    DIT -->|"Upload Raw"| FASP
    FASP -->|"Port 33001"| SDCX
    SDCX -->|"Verify SHA-256"| NAS_A
    NAS_A <-->|"Hot Data<br/>Accelerate"| Cache_A
    NAS_A -->|"Snapshot Lock"| Snap_A
    
    NAS_A -.->|"Replication<br/>RPO: 15 min"| NAS_B
    NAS_B <-->|"Hot Data"| Cache_B
    NAS_B -->|"Snapshot"| Snap_B
    
    NAS_A -.->|"Hybrid Share<br/>Tier 90+ days"| Wasabi
    NAS_B -.->|"Hybrid Share<br/>Tier 90+ days"| Wasabi
    
    Editor -->|"FortiClient"| ZTNA
    ZTNA -->|"TLS 1.3<br/>Per-App Access"| NAS_A
    
    style Primary fill:#e1f5ff,stroke:#01579b,stroke-width:2px
    style DR fill:#fff3e0,stroke:#e65100,stroke-width:2px
    style Cloud fill:#e8f5e9,stroke:#2e7d32,stroke-width:1px

Explanation of Data Flow:

The diagram illustrates the complete data lifecycle from field ingest through cloud archive:

Ingest (Left): Field DIT uploads raw footage via Signiant FASP protocol to the SDCX server in DMZ (VLAN 10). SHA-256 checksums verify integrity.

Primary Storage (Center-Left): Verified files land on Site A HD6500 (VLAN 30). Hot project files are accelerated by 30.72TB NVMe cache. Immutable snapshots provide ransomware protection.

DR Replication (Center-Right): Every 15 minutes, new data replicates to Site B. Site B is read-only during normal operation but maintains identical data for instant failover.

Cloud Tiering (Right): Files older than 90 days tier to Wasabi automatically via Hybrid Share, freeing primary storage capacity.

Access (Bottom): Remote editors connect via ZTNA (not VPN), undergo device posture checks, and receive least-privilege access to only their assigned project folders.

Tip: The three-layer protection (Primary + DR + Cloud) provides defense in depth against different threat types: Primary protects against single-system failure, DR protects against site-level disasters, and Cloud protects against ransomware (air-gapped immutability).

### Key Takeaways — Two-Site Design Rationale

37-day cloud restore is business-fatal: For a post-production studio with delivery deadlines, cloud-only DR creates unacceptable risk

Two-site design provides instant failover: DR site has current data ready to activate in 10 minutes with zero egress costs

Three-layer protection: Primary (operations) + DR (site disaster) + Cloud (ransomware/air-gap) = comprehensive resilience

₹44 Lakhs premium is insurance: The additional cost is minimal compared to the business continuity value delivered

## 3.5 Five-Zone Security Model Explanation

### 3.5.1 Why Five Zones Instead of Fewer?

The B2H Studios network implements five distinct security zones (VLANs 10, 20, 30, 40, 50). Each zone exists for specific security and operational reasons. The following analysis explains why merging zones would create unacceptable risks.

### 3.5.2 Zone-by-Zone Rationale

#### VLAN 10 — DMZ (Demilitarized Zone)

| Attribute | Value |
| --- | --- |
| **Purpose** | Host public-facing services (Signiant SDCX) |
| **Trust Level** | Semi-trusted (Security Level: 50) |
| **CIDR** | 10.10.10.0/24 |

Why This Zone Exists:

The DMZ isolates services that must accept connections from the untrusted internet. The Signiant SDCX server needs to receive media uploads from external DIT teams and production crews worldwide. Without a DMZ:

External entities would have a direct network path to internal resources

A compromised upload server would expose the entire production network

Regulatory compliance (ISO 27001) requires segmentation of external-facing services

Risk of Merging DMZ with Production (VLAN 20):

| Attack Scenario | With Separate DMZ | With Merged VLAN |
| --- | --- | --- |
| SDCX server compromised | Attacker isolated to DMZ; no access to editor workstations or NAS | Attacker has direct access to all workstations and storage |
| Lateral movement | Blocked by firewall between VLAN 10→20 | Unrestricted within merged VLAN |
| Ransomware deployment | Limited to DMZ server | Spreads to all 25 workstations + NAS |
| Blast radius | One server | Entire production network |

Warning: Merging DMZ with Production would violate ISO 27001 Control A.8.22 (Segregation of Networks) and create a single point of compromise for the entire infrastructure.

#### VLAN 20 — Production

| Attribute | Value |
| --- | --- |
| **Purpose** | Employee workstations and authenticated user devices |
| **Trust Level** | Trusted (Security Level: 100) |
| **CIDR** | 10.10.20.0/24 |

Why This Zone Exists:

The Production VLAN contains the primary user population — 25 employees accessing NAS shares, internal services, and internet. This zone needs broad but controlled access to other internal resources while being protected from external threats.

Risk of Merging Production with Storage (VLAN 30):

| Concern | Separate VLANs | Merged VLAN |
| --- | --- | --- |
| Broadcast traffic | Isolated to each VLAN | All 25 users + NAS traffic in one broadcast domain |
| Security policy granularity | Can apply storage-specific policies | One-size-fits-all policy required |
| Insider threat containment | Can restrict user-to-NAS traffic patterns | Users can directly access raw storage protocols |
| Performance isolation | Storage traffic prioritized separately | User traffic competes with storage |

Note: While technically possible to merge Production and Storage, doing so eliminates the ability to apply jumbo frames (MTU 9000) to storage traffic without affecting user traffic, and reduces security granularity.

#### VLAN 30 — Storage

| Attribute | Value |
| --- | --- |
| **Purpose** | NAS shares, NFS/SMB traffic, storage protocols |
| **Trust Level** | Trusted — Critical Asset (Security Level: 100) |
| **CIDR** | 10.10.30.0/24 |
| **Special Config** | Jumbo Frames (MTU 9000) |

Why This Zone Exists:

The Storage VLAN isolates the organization's most valuable asset — 936TB of media content. This zone has the strictest access controls and specialized network configuration (jumbo frames) for performance.

Risk of Merging Storage with Any Other Zone:

| Zone Merged With | Risk Created |
| --- | --- |
| DMZ (VLAN 10) | External attackers gain direct access to storage if SDCX compromised |
| Production (VLAN 20) | Malware on user workstation can directly attack NAS management interfaces |
| Management (VLAN 40) | Storage traffic traverses management interfaces, creating exposure |
| Guest (VLAN 50) | Visitors have direct access to confidential media content |

Warning: Merging Storage with any other zone would violate the principle of "defense in depth" and the ISO 27001 requirement to protect critical assets with additional layers of security.

#### VLAN 40 — Management

| Attribute | Value |
| --- | --- |
| **Purpose** | Out-of-band device management (iLO, IPMI, switch consoles) |
| **Trust Level** | Restricted (Security Level: 100+) |
| **CIDR** | 10.10.40.0/24 |
| **Access Control** | Jump host only; no general user access |

Why This Zone Exists:

The Management VLAN provides secure access to infrastructure device management interfaces. These interfaces (iLO, IPMI, switch CLI, DSM admin) have elevated privileges and must be isolated from general user access.

Risk of Merging Management with Production (VLAN 20):

| Attack Scenario | With Separate Management | With Merged VLAN |
| --- | --- | --- |
| Compromised user workstation | Cannot reach management interfaces | Can attempt brute force on iLO, switch passwords |
| Phishing attack on employee | Limited to user permissions | Potential infrastructure takeover |
| Insider threat (disgruntled employee) | Blocked from management | Can factory reset switches, wipe NAS |
| Malware spread | Contained to user VLAN | Infects management interfaces |

Real-World Example:

In 2021, a major gaming company suffered a breach when attackers gained access through a compromised workstation and pivoted to management interfaces. The merged network allowed lateral movement to iLO interfaces, enabling firmware-level persistence that survived OS reinstallation. A separate Management VLAN would have blocked this attack path.

#### VLAN 50 — Guest

| Attribute | Value |
| --- | --- |
| **Purpose** | Visitor Wi-Fi and contractor internet access |
| **Trust Level** | Untrusted (Security Level: 0) |
| **CIDR** | 10.10.50.0/24 |
| **Internet Access** | Only; no internal reachability |

Why This Zone Exists:

The Guest VLAN provides internet connectivity for visitors, clients, and contractors while maintaining complete isolation from corporate resources. This is both a security control and a courtesy service.

Risk of Merging Guest with Any Internal Zone:

| Merged With | Risk |
| --- | --- |
| Production (VLAN 20) | Infected guest device attacks employee workstations |
| Storage (VLAN 30) | Unauthorized access to confidential media |
| DMZ (VLAN 10) | Guests can attack or probe public services |
| Management (VLAN 40) | Guests can attempt infrastructure takeover |

Tip: Guest isolation is often a cyber insurance requirement. Merging guest networks with production can void coverage or increase premiums.

### 3.5.3 Security Zone Trust Model

flowchart TB
    subgraph Legend["Security Level Legend"]
        Untrusted["🔴 Untrusted (0)"]
        Semi["🟡 Semi-Trusted (50)"]
        Trusted["🟢 Trusted (100)"]
        Restricted["🟣 Restricted (100+)"]
    end
    
    subgraph WAN["Internet / WAN"]
        Internet["Internet<br/>Security Level: 0"]
    end
    
    subgraph Zones["FortiGate Security Zones"]
        DMZ["VLAN 10 — DMZ<br/>Signiant SDCX<br/>Security Level: 50"]
        PROD["VLAN 20 — Production<br/>Editor Workstations<br/>Security Level: 100"]
        STORAGE["VLAN 30 — Storage<br/>Synology HD6500<br/>Security Level: 100<br/>🛡️ Critical Asset"]
        MGMT["VLAN 40 — Management<br/>iLO / IPMI<br/>Security Level: 100+"]
        GUEST["VLAN 50 — Guest<br/>Visitor Wi-Fi<br/>Security Level: 0"]
    end
    
    Internet <-->|"Stateful Inspection<br/>IPS/AV/Application Control"| DMZ
    Internet <-->|"ZTNA Only<br/>Device Posture Check"| PROD
    Internet <-->|"Blocked<br/>No Access"| MGMT
    Internet <-->|"Internet Only<br/>DNS, HTTPS"| GUEST
    
    DMZ -->|"Controlled: NFS(2049)<br/>SMB(445) → VLAN 30"| STORAGE
    DMZ -.->|"Monitoring Only<br/>SNMP/Logs"| MGMT
    
    PROD -->|"Storage Traffic<br/>Jumbo Frames"| STORAGE
    PROD -.->|"Admin Access<br/>HTTPS/SSH"| MGMT
    
    GUEST -.->|"❌ DENIED"| DMZ
    GUEST -.->|"❌ DENIED"| PROD
    GUEST -.->|"❌ DENIED"| STORAGE
    GUEST -.->|"❌ DENIED"| MGMT
    
    MGMT -.->|"No Access"| PROD
    MGMT -.->|"No Access"| STORAGE
    MGMT -.->|"No Access"| DMZ
    
    style Internet fill:#ffcdd2,stroke:#b71c1c,stroke-width:2px
    style DMZ fill:#fff9c4,stroke:#f57f17,stroke-width:2px
    style PROD fill:#c8e6c9,stroke:#2e7d32,stroke-width:2px
    style STORAGE fill:#a5d6a7,stroke:#1b5e20,stroke-width:3px
    style MGMT fill:#e1bee7,stroke:#6a1b9a,stroke-width:2px
    style GUEST fill:#ffccbc,stroke:#bf360c,stroke-width:2px

Explanation of Zone Trust Model:

The diagram illustrates the "trust gradient" from internet (completely untrusted) to management (most restricted). Key security principles demonstrated:

No Direct WAN-to-Internal: Internet cannot directly reach Production, Storage, or Management — all traffic must pass through FortiGate inspection

DMZ Isolation: DMZ can only reach Storage via specific ports (2049 for NFS, 445 for SMB). Even if SDCX is compromised, attackers cannot access workstations or management interfaces

Guest Isolation: Guest VLAN is completely isolated — no access to any corporate resource. This is visualized by the red "DENIED" lines

Management Segregation: Management VLAN is one-way — admins can access devices, but devices cannot initiate connections outward. This prevents compromised infrastructure from attacking the rest of the network

Critical Asset Protection: Storage VLAN (bold green border) is the crown jewel — it receives the most restrictive access controls and is only accessible from Production and controlled access from DMZ

### 3.5.4 Zone Communication Matrix

| From ↓ To → | Internet | DMZ (10) | Production (20) | Storage (30) | Management (40) | Guest (50) |
| --- | --- | --- | --- | --- | --- | --- |
| **Internet** | ✓ | Allow (filtered) | ZTNA only | ❌ DENY | ❌ DENY | ❌ DENY |
| **DMZ (10)** | Allow | ✓ | ❌ DENY | Allow (2049, 445) | Allow (monitoring) | ❌ DENY |
| **Production (20)** | Allow | ❌ DENY | ✓ | Allow | Allow (admin only) | ❌ DENY |
| **Storage (30)** | ❌ DENY | ❌ DENY | Allow (responses) | ✓ | Allow (monitoring) | ❌ DENY |
| **Management (40)** | Allow (updates) | Allow (management) | ❌ DENY | Allow (management) | ✓ | ❌ DENY |
| **Guest (50)** | Allow | ❌ DENY | ❌ DENY | ❌ DENY | ❌ DENY | ✓ |

### Key Takeaways — Five-Zone Security Model

Defense in depth requires layers: Each zone is a layer; compromising one doesn't compromise all

DMZ prevents external exposure: Public-facing services are isolated from internal assets

Storage is the crown jewel: Dedicated VLAN with jumbo frames and strictest access controls

Management isolation protects infrastructure: Even if all user workstations are compromised, management interfaces remain protected

Guest isolation is non-negotiable: Visitors pose unknown risks; complete isolation is the only safe approach

# 4. VLAN Design

## 4.1 VLAN Allocation Table

| VLAN ID | Name | Purpose | CIDR | Gateway | DHCP Range |
| --- | --- | --- | --- | --- | --- |
| 10 | DMZ | Media ingest, external-facing services, Signiant SDCX server | 10.10.10.0/24 | 10.10.10.1 | 10.10.10.100 — 10.10.10.200 |
| 20 | Production | Employee workstations, ZTNA clients, editing workstations | 10.10.20.0/24 | 10.10.20.1 | 10.10.20.100 — 10.10.20.200 |
| 30 | Storage | NAS shares, NFS/SMB traffic, iSCSI storage network | 10.10.30.0/24 | 10.10.30.1 | Static allocation only |
| 40 | Management | Device management, iLO/IPMI out-of-band, switch console | 10.10.40.0/24 | 10.10.40.1 | Static allocation only |
| 50 | Guest | Guest Wi-Fi access, visitor internet connectivity | 10.10.50.0/24 | 10.10.50.1 | 10.10.50.100 — 10.10.50.200 |

## 4.2 VLAN Segmentation Strategy

### 4.2.1 Why /24 Subnets (254 Hosts per VLAN)?

Every VLAN uses a /24 subnet (255.255.255.0), providing 254 usable host addresses. This choice balances current needs with future growth.

Current vs. Future Capacity Analysis:

| VLAN | Current Devices | /24 Capacity | Growth Headroom | Years of Growth |
| --- | --- | --- | --- | --- |
| DMZ (10) | 3 (SDCX + 2 VMs) | 254 | 84x | 20+ years |
| Production (20) | 25 workstations | 254 | 10x | 10+ years |
| Storage (30) | 5 (NAS + servers) | 254 | 50x | 20+ years |
| Management (40) | 15 devices | 254 | 16x | 15+ years |
| Guest (50) | ~10 concurrent | 254 | 25x | 15+ years |

Why Not Smaller Subnets (/26, /27)?

| Subnet Size | Usable Hosts | Risk | Recommendation |
| --- | --- | --- | --- |
| /24 | 254 | Low complexity | ✅ **SELECTED** |
| /25 | 126 | May exhaust with growth | ❌ Too restrictive |
| /26 | 62 | Likely to require re-IP | ❌ Not recommended |
| /27 | 30 | Will definitely require re-IP | ❌ Avoid |

Tip: Re-IPing a production network is painful and risky. The modest "waste" of unused addresses in /24 subnets is far cheaper than the operational disruption of subnet resizing. Always design for 5-10x growth.

### 4.2.2 Gateway Placement: FortiGate vs. Switch

In this design, all VLAN gateways (the .1 address in each subnet) are located on the FortiGate firewall, not on the HPE switches. This is a deliberate security decision.

Gateway Placement Comparison:

| Aspect | Gateway on FortiGate | Gateway on Switch |
| --- | --- | --- |
| **Inter-VLAN Routing** | Must pass through firewall inspection | Direct switch routing (faster but no inspection) |
| **Security Policy** | Can apply IPS, AV, application control between VLANs | Only ACLs (Layer 3/4 filtering only) |
| **Logging** | All inter-VLAN traffic logged | Limited logging capability |
| **Performance** | ~10Gbps throughput (sufficient) | Wire-speed (faster) |
| **Complexity** | Single point of policy | Must manage switch ACLs + firewall rules |

Why FortiGate for All Gateways:

The B2H Studios design prioritizes security over raw performance for inter-VLAN traffic. With only 25 users and the HD6500 capable of 6,688 MB/s, the FortiGate 120G's ~10Gbps inter-VLAN routing capacity is more than sufficient. The security benefits are substantial:

DMZ → Storage traffic is inspected by IPS/AV before reaching the NAS

Production → Management access is validated by application control

All inter-VLAN flows are logged to FortiAnalyzer for audit

Traffic Flow Example: User Accessing NAS Share

flowchart LR
    User["Editor Workstation<br/>10.10.20.105"]
    
    subgraph FortiGate["FortiGate 120G — Gateway & Firewall"]
        V20_GW["VLAN 20 Gateway<br/>10.10.20.1"]
        Inspection["IPS/AV Inspection<br/>Application Control"]
        V30_GW["VLAN 30 Gateway<br/>10.10.30.1"]
    end
    
    Switch["HPE CX 6300M<br/>Layer 2 Trunk"]
    NAS["Synology HD6500<br/>10.10.30.10"]
    
    User -->|"SMB Request<br/>Dest: 10.10.30.10"| V20_GW
    V20_GW --> Inspection
    Inspection -->|"Allowed?"| V30_GW
    V30_GW -->|"Forwarded"| Switch
    Switch --> NAS
    
    style FortiGate fill:#fff9c4,stroke:#f57f17,stroke-width:2px
    style Inspection fill:#ffcc80,stroke:#ef6c00

Explanation of Traffic Flow:

When an editor (10.10.20.105) accesses a NAS share (10.10.30.10):

Packet leaves workstation destined for 10.10.30.10

Reaches FortiGate VLAN 20 gateway (10.10.20.1) — default gateway for Production VLAN

FortiGate performs routing decision: Destination is VLAN 30

Traffic passes through inspection engine: IPS signatures, AV scanning, application control policies applied

If allowed, FortiGate forwards via VLAN 30 gateway (10.10.30.1)

Switch delivers to NAS (10.10.30.10)

This adds ~0.5ms latency but provides comprehensive security inspection. For comparison, switch-based routing would be faster (~0.05ms) but provide no security inspection.

### 4.2.3 Traffic Flow Diagram: User → ZTNA → Firewall → Switch → NAS

sequenceDiagram
    participant User as Remote Editor
    participant FC as FortiClient
    participant ZTNA as FortiGate ZTNA Gateway
    participant Auth as FortiAuthenticator
    participant FG as FortiGate Firewall
    participant SW as HPE Switch
    participant NAS as Synology HD6500

    Note over User, NAS: Phase 1: ZTNA Authentication
    User->>FC: Launch FortiClient
    FC->>ZTNA: Initiate ZTNA connection
    ZTNA->>FC: Request device posture
    FC-->>ZTNA: Posture data (Kaspersky, patches, encryption)
    ZTNA->>Auth: Validate device + user identity
    Auth-->>ZTNA: MFA challenge
    ZTNA->>User: Push notification
    User-->>ZTNA: MFA approval
    Auth-->>ZTNA: Authentication success
    ZTNA-->>FC: Secure tunnel established

    Note over User, NAS: Phase 2: File Access
    User->>FC: Access \\nas.b2h.local\project1
    FC->>ZTNA: SMB request
    ZTNA->>FG: Forward to firewall
    FG->>FG: Apply security policies (IPS/AV)
    FG->>SW: Route to VLAN 30
    SW->>NAS: Deliver SMB request
    NAS-->>SW: Return file data
    SW-->>FG: Return traffic
    FG-->>ZTNA: After inspection
    ZTNA-->>FC: Encrypted response
    FC-->>User: File accessible

Explanation of ZTNA-to-NAS Flow:

The sequence diagram shows the complete flow from a remote editor accessing a file:

Phase 1 — Authentication (Steps 1-9):

Editor launches FortiClient which initiates ZTNA connection

Device posture is validated (Kaspersky running, OS patched, disk encrypted)

FortiAuthenticator challenges with MFA push notification

Upon approval, secure TLS 1.3 tunnel is established

Phase 2 — File Access (Steps 10-19):

Editor attempts to access NAS share

Request flows through ZTNA gateway (encrypted)

FortiGate applies IPS/AV inspection

Traffic routed to NAS via switch

Response returns through same inspection path

Key Insight: ZTNA replaces traditional VPN. Unlike VPN which grants network-level access, ZTNA provides application-level access with continuous validation. The editor cannot see or reach any infrastructure beyond the specific NAS shares authorized.

### 4.3 VLAN Configuration Notes

#### VLAN 10 — DMZ

Security Level: Semi-trusted

Inter-VLAN Routing: Limited access to VLAN 30 (Storage) only

Services Hosted: Signiant SDCX Server, Aspera fallback, external APIs

Firewall Policy: Allow inbound from WAN on ports 33001 (FASP), 443 (HTTPS); deny all else

#### VLAN 20 — Production

Security Level: Trusted

Primary Users: 25 employees with FortiClient ZTNA

Access Rights: NAS shares via SMB/NFS, internet access, internal services

Firewall Policy: Allow to VLAN 30, VLAN 40 (management ports only), WAN; deny to VLAN 10

#### VLAN 30 — Storage

Security Level: Trusted — Critical Asset

MTU Configuration: 9000 (Jumbo Frames enabled)

Protocols: NFSv4.1 (port 2049), SMB 3.1.1 (port 445), iSCSI (port 3260)

Access Control: Restricted to VLAN 20 (Production) and VLAN 10 (DMZ — read-only)

#### VLAN 40 — Management

Security Level: Restricted

Access Method: Jump host or dedicated management workstation only

Protocols: HTTPS (443), SSH (22), SNMP v3 (161), IPMI (623)

Firewall Policy: Deny all inbound from VLAN 20/50; allow from designated admin IPs only

#### VLAN 50 — Guest

Security Level: Untrusted

Isolation: Complete Layer 3 isolation from all other VLANs

Bandwidth Limit: 50 Mbps per client, 200 Mbps aggregate

Session Timeout: 8 hours maximum

### Key Takeaways — VLAN Design

/24 subnets provide 10+ years of growth headroom: The "wasted" addresses prevent painful re-IPing

FortiGate as gateway enables security inspection: All inter-VLAN traffic is logged and inspected

Jumbo frames (MTU 9000) on Storage VLAN: Improves NAS performance for large file transfers

ZTNA enables secure remote access: No VPN subnet; application-level access control instead

# 5. IP Addressing Scheme

## 5.1 Site A — Primary Data Centre IP Allocation

| Device | Hostname | VLAN | IP Address | Purpose |
| --- | --- | --- | --- | --- |
| FortiGate 120G | FG-A-001 | WAN/HA | 203.XX.XX.10 | Primary firewall — active unit |
| FortiGate 120G | FG-A-002 | WAN/HA | 203.XX.XX.11 | Secondary firewall — passive unit |
| FortiGate Cluster | FG-A-VIP | WAN | 203.XX.XX.9 | Shared virtual IP (HA) |
| FortiGate | FG-A-INT | Internal | 10.10.10.1/20/30/40/50 | Internal VLAN gateways |
| HPE Switch | SW-A-001 | Management | 10.10.40.2 | Core switch 1 — VSX primary |
| HPE Switch | SW-A-002 | Management | 10.10.40.3 | Core switch 2 — VSX secondary |
| HPE VSX Cluster | SW-A-VIP | Management | 10.10.40.4 | VSX virtual switch IP |
| Synology HD6500 | NAS-A-001 | Storage | 10.10.30.10 | Primary NAS — controller 1 |
| Synology HD6500 | NAS-A-002 | Storage | 10.10.30.11 | Primary NAS — controller 2 (HA) |
| Synology HD6500 | NAS-A-VIP | Storage | 10.10.30.9 | NAS cluster virtual IP |
| Dell R760 | SRV-A-001 | Production | 10.10.20.10 | Application server — hypervisor |
| Dell R760 iLO | SRV-A-001-ILO | Management | 10.10.40.10 | Out-of-band management |
| Signiant VM | VM-A-SIG | DMZ | 10.10.10.10 | Signiant SDCX Server |
| FortiAnalyzer VM | VM-A-FAZ | Management | 10.10.40.20 | Log aggregation and SIEM |
| FortiAuthenticator VM | VM-A-FAC | Management | 10.10.40.21 | MFA and RADIUS server |
| FortiClient EMS VM | VM-A-EMS | Management | 10.10.40.22 | Endpoint management |
| HashiCorp Vault VM | VM-A-VLT | Production | 10.10.20.20 | Secrets management |
| Kaspersky SC VM | VM-A-KSC | Management | 10.10.40.23 | Antivirus management |
| APC UPS 1 | UPS-A-001 | Management | 10.10.40.30 | Primary UPS — SNMP monitoring |
| APC UPS 2 | UPS-A-002 | Management | 10.10.40.31 | Secondary UPS — SNMP monitoring |
| APC ATS | ATS-A-001 | Management | 10.10.40.32 | Automatic transfer switch |

## 5.2 Site B — Disaster Recovery Site IP Allocation

| Device | Hostname | VLAN | IP Address | Purpose |
| --- | --- | --- | --- | --- |
| FortiGate 120G | FG-B-001 | WAN/HA | 204.XX.XX.10 | DR firewall — active unit |
| FortiGate 120G | FG-B-002 | WAN/HA | 204.XX.XX.11 | DR firewall — passive unit |
| FortiGate Cluster | FG-B-VIP | WAN | 204.XX.XX.9 | Shared virtual IP (HA) |
| FortiGate | FG-B-INT | Internal | 10.10.50.1/51/52/53/54 | Internal VLAN gateways |
| HPE Switch | SW-B-001 | Management | 10.10.53.2 | Core switch 1 — VSX primary |
| HPE Switch | SW-B-002 | Management | 10.10.53.3 | Core switch 2 — VSX secondary |
| HPE VSX Cluster | SW-B-VIP | Management | 10.10.53.4 | VSX virtual switch IP |
| Synology HD6500 | NAS-B-001 | Storage | 10.10.52.10 | DR NAS — controller 1 |
| Synology HD6500 | NAS-B-002 | Storage | 10.10.52.11 | DR NAS — controller 2 (HA) |
| Synology HD6500 | NAS-B-VIP | Storage | 10.10.52.9 | NAS cluster virtual IP |
| Dell R760 (Light) | SRV-B-001 | Production | 10.10.51.10 | DR application server |
| Dell R760 iLO | SRV-B-001-ILO | Management | 10.10.53.10 | Out-of-band management |
| APC UPS 1 | UPS-B-001 | Management | 10.10.53.30 | Primary UPS — SNMP monitoring |
| APC UPS 2 | UPS-B-002 | Management | 10.10.53.31 | Secondary UPS — SNMP monitoring |
| APC ATS | ATS-B-001 | Management | 10.10.53.32 | Automatic transfer switch |

## 5.3 IP Scheme Design Philosophy

### 5.3.1 Why 10.10.x.x (RFC1918 Private Space)?

The B2H Studios network uses the 10.0.0.0/8 RFC1918 private address space. This choice provides several advantages:

RFC1918 Private Address Ranges:

| Range | Total Addresses | Use Case |
| --- | --- | --- |
| 10.0.0.0/8 | 16,777,216 | Large enterprises, service providers |
| 172.16.0.0/12 | 1,048,576 | Medium enterprises |
| 192.168.0.0/16 | 65,536 | Small networks, home networks |

Why 10.10.x.x Was Selected:

| Factor | 10.10.x.x Choice | Alternative Considered |
| --- | --- | --- |
| **Avoids collision** | Rarely used in home/consumer gear | 192.168.1.x conflicts with home routers |
| **Plenty of space** | 65,536 addresses per /16 | 172.16.x.x also viable |
| **Easy to type** | Short, memorable | 10.100.x.x equally valid |
| **Future expansion** | Can add 10.11.x.x, 10.12.x.x sites | Limited in 192.168.x.x |

Note: RFC1918 addresses are not routable on the public internet. This provides inherent security — even if a firewall rule is misconfigured, private IPs cannot be reached from the internet directly.

### 5.3.2 Why Site B Uses 10.10.5x.x (Distinguishing Pattern)

Site B IP addresses follow a different pattern (10.10.5x.x) than Site A (10.10.1x-4x.x). This is intentional for immediate visual identification.

Site A vs Site B Addressing:

| Site | VLAN 10 (DMZ) | VLAN 20 (Production) | VLAN 30 (Storage) | VLAN 40 (Mgmt) | VLAN 50 (Guest) |
| --- | --- | --- | --- | --- | --- |
| **Site A** | 10.10.10.x | 10.10.20.x | 10.10.30.x | 10.10.40.x | 10.10.50.x |
| **Site B** | 10.10.50.x | 10.10.51.x | 10.10.52.x | 10.10.53.x | 10.10.54.x |

Why This Pattern:

| Benefit | Explanation |
| --- | --- |
| **Visual identification** | Any 10.10.5x.x address = Site B (DR) |
| **No overlap risk** | Different third octet prevents accidental IP conflicts |
| **Easy routing** | 10.10.0.0/16 summary route covers both sites |
| **Scalability** | Site C could use 10.10.6x.x, Site D 10.10.7x.x |

Tip: When troubleshooting at 2 AM, being able to identify a device's site from its IP address ("5x = Site B") saves valuable time and prevents mistakes.

### 5.3.3 Reserved IP Ranges

The IP scheme uses a structured reservation system for different device types:

| Range | Purpose | Examples |
| --- | --- | --- |
| **.1 — .9** | Network infrastructure (gateways, VIPs) | 10.10.10.1 (gateway), 10.10.30.9 (NAS VIP) |
| **.10 — .49** | Servers and storage systems | 10.10.30.10 (NAS-A-001), 10.10.20.10 (SRV-A-001) |
| **.50 — .99** | Network devices (switches, firewalls, APs) | 10.10.40.2 (SW-A-001), 10.10.40.50 (FortiAP-001) |
| **.100 — .199** | DHCP client pool | 10.10.20.100 — 10.10.20.199 (workstations) |
| **.200 — .249** | Reserved for future expansion | Future servers, IoT devices, additional services |
| **.250 — .254** | Management and monitoring systems | 10.10.40.250 (Zabbix server) |
| **.255** | Broadcast address | Not usable for hosts |

Why Structured Reservations Matter:

| Scenario | Without Structure | With Structure |
| --- | --- | --- |
| Adding new server | Check entire subnet for conflicts | Use .10-.49 range, check only there |
| Troubleshooting | Random IP distribution | Know .2-.9 are VIPs, .10-.49 are servers |
| DHCP scope planning | Guess appropriate range | Clearly defined .100-.199 |
| Future expansion | No space reserved | .200-.249 explicitly held |

### 5.3.4 Hostname Naming Convention

Hostnames follow a structured format for easy identification:

Format: {Device Type}-{Site}-{Instance}

| Component | Values | Example |
| --- | --- | --- |
| Device Type | FG (FortiGate), SW (Switch), NAS (Synology), SRV (Server), VM (Virtual), UPS (UPS) | FG-A-001 |
| Site | A (Primary), B (DR) | NAS-B-001 |
| Instance | 001-999 unique ID | SRV-A-001 |

Special Suffixes:

| Suffix | Meaning | Example |
| --- | --- | --- |
| -VIP | Virtual IP (HA cluster) | FG-A-VIP |
| -ILO | Out-of-band management | SRV-A-001-ILO |
| -INT | Internal interfaces | FG-A-INT |

### Key Takeaways — IP Scheme Design Philosophy

RFC1918 10.10.x.x avoids collisions: Rarely conflicts with home/remote networks

Site B 10.10.5x.x pattern enables instant identification: No confusion which site an IP belongs to

Structured reservations prevent conflicts: Each device type has designated range

Hostname convention enables automation: Structured names can be parsed by scripts and monitoring tools

# 6. ISO 27001:2022 Compliance Mapping

## 6.1 Compliance Overview

The B2H Studios infrastructure has been designed to align with ISO 27001:2022 controls, providing a robust information security management framework from day one. The following mapping demonstrates how each implemented control satisfies specific ISO 27001 requirements.

## 6.2 Compliance-by-Design Approach

ISO 27001:2022 contains 93 controls organized into four categories: Organizational (A.5), People (A.6), Physical (A.7), and Technological (A.8). This infrastructure implements a compliance-by-design approach — security controls are built into the architecture rather than added as afterthoughts.

### 6.2.1 Organizational Controls (A.5) — Compliance-by-Design

The Organizational controls establish the governance framework for information security. This infrastructure addresses 22 controls directly.

#### A.5.7 — Threat Intelligence

| Element | Implementation |
| --- | --- |
| **Control Requirement** | Information relating to information security threats shall be collected and analyzed to produce threat intelligence |
| **Our Implementation** | FortiGuard threat intelligence feeds integrated into FortiGate 120G. Daily automatic updates for IPS signatures, AV definitions, and geolocation data. |
| **Why This Meets the Intent** | Threat intelligence is not a manual, ad-hoc process — it's automated and integrated. The FortiGate subscribes to Fortinet's global threat intelligence network, receiving real-time updates on emerging threats. This ensures protection against zero-day attacks without requiring B2H Studios to maintain a dedicated threat analysis team. |

#### A.5.9 — Inventory of Information and Other Associated Assets

| Element | Implementation |
| --- | --- |
| **Control Requirement** | An inventory of information and other associated assets, including owners, shall be developed and maintained |
| **Our Implementation** | Zabbix automated discovery maintains real-time inventory of all network devices, servers, and storage systems. Asset tags assigned to all hardware. |
| **Why This Meets the Intent** | Manual asset inventories become outdated within weeks. Automated discovery ensures the inventory is always current. Zabbix scans the network, identifies devices by MAC address and SNMP, and maintains a database with ownership information. This satisfies both the inventory requirement and the "maintained" aspect through continuous discovery. |

#### A.5.12 — Classification of Information

| Element | Implementation |
| --- | --- |
| **Control Requirement** | Information shall be classified according to the information security needs of the organization based on confidentiality, integrity, and availability |
| **Our Implementation** | Data classification scheme defined: Public, Internal, Confidential, Restricted. NAS folder structure enforces classification via access controls. |
| **Why This Meets the Intent** | The control requires both classification scheme AND enforcement. The NAS folder structure physically segregates data by classification — "Restricted" folders have different access controls than "Internal" folders. Access is granted based on role, not individual request, ensuring consistent application of classification policies. |

#### A.5.24 — Planning and Preparation for Information Security Continuity

| Element | Implementation |
| --- | --- |
| **Control Requirement** | The organization shall determine resilience requirements and plan how to achieve them |
| **Our Implementation** | Business continuity plan documented. DR procedures tested quarterly. RPO: 15 minutes, RTO: 10 minutes. |
| **Why This Meets the Intent** | Resilience is not just having backup hardware — it's documented, tested procedures. Quarterly DR testing validates that the 10-minute RTO is achievable. The documented procedures ensure that during a crisis, the team follows a rehearsed playbook rather than improvising. |

#### A.5.27 — Redundancy of Information Processing Facilities

| Element | Implementation |
| --- | --- |
| **Control Requirement** | Information processing facilities shall be implemented with redundancy to ensure availability |
| **Our Implementation** | Redundant components: dual FortiGate HA, dual HPE switches (VSX), dual UPS with ATS, RAID6 storage. |
| **Why This Meets the Intent** | Redundancy is implemented at every layer: network (HA FortiGates, VSX switches), power (dual UPS with ATS), and storage (RAID6, dual controllers). This defense-in-depth approach means no single component failure causes service interruption. The control is satisfied through N+1 redundancy architecture. |

### 6.2.2 Technological Controls (A.8) — Compliance-by-Design

Technological controls are where this infrastructure truly shines — security is embedded in the architecture.

#### A.8.2 — Privileged Access Rights

| Element | Implementation |
| --- | --- |
| **Control Requirement** | The allocation and use of privileged access rights shall be restricted and managed |
| **Our Implementation** | Privileged Access Management (PAM) via HashiCorp Vault. Just-in-time elevation for administrative tasks. |
| **Why This Meets the Intent** | Traditional "always-on" admin accounts violate this control. HashiCorp Vault provides dynamic credentials that expire after a configured time (e.g., 4 hours). Administrators request elevation, receive temporary credentials, and access automatically expires. This "just-in-time" approach minimizes the window of elevated privilege exposure. |

#### A.8.5 — Secure Authentication

| Element | Implementation |
| --- | --- |
| **Control Requirement** | Secure authentication technologies and procedures shall be implemented |
| **Our Implementation** | Multi-factor authentication required for all remote access and privileged accounts. Passwordless options evaluated. |
| **Why This Meets the Intent** | Passwords alone are insufficient per modern standards. FortiAuthenticator enforces MFA via push notifications (FortiToken). For remote access, ZTNA adds device certificates as an additional authentication factor. This multi-layer authentication satisfies the "secure" requirement beyond simple passwords. |

#### A.8.7 — Protection Against Malware

| Element | Implementation |
| --- | --- |
| **Control Requirement** | Information systems shall be protected against malware |
| **Our Implementation** | Kaspersky Endpoint Security deployed on all endpoints. FortiGate AV scanning for network traffic. |
| **Why This Meets the Intent** | Defense in depth: Kaspersky provides host-based protection (behavioral analysis, signature scanning), while FortiGate provides network-based protection (scanning downloads, blocking malicious sites). This dual-layer approach catches threats at the perimeter before reaching endpoints, and at the endpoint if perimeter is bypassed. |

#### A.8.20 — Security of Networks

| Element | Implementation |
| --- | --- |
| **Control Requirement** | Networks and network services shall be secured |
| **Our Implementation** | Network segmentation via VLANs. Firewall zones enforce traffic inspection. IDS/IPS active. |
| **Why This Meets the Intent** | The five-zone security model (DMZ, Production, Storage, Management, Guest) provides segmentation that limits blast radius. Every inter-zone traffic flow passes through FortiGate inspection with IPS/AV. This is not just network security — it's comprehensive traffic analysis and threat prevention at the network layer. |

#### A.8.22 — Segregation of Networks

| Element | Implementation |
| --- | --- |
| **Control Requirement** | Networks shall be segregated based on trust level, value, and importance of information |
| **Our Implementation** | VLANs segregate DMZ, Production, Storage, Management, and Guest traffic. Inter-VLAN routing controlled by firewall. |
| **Why This Meets the Intent** | The five VLANs are explicitly designed around trust levels: Guest (0), DMZ (50), Production (100), Storage (100-critical), Management (100+). The FortiGate acts as a trust boundary between zones, enforcing that lower-trust zones cannot access higher-trust zones without explicit policy. This satisfies the segregation requirement completely. |

#### A.8.24 — Use of Cryptography

| Element | Implementation |
| --- | --- |
| **Control Requirement** | Cryptography shall be used to protect the confidentiality, authenticity, and integrity of information |
| **Our Implementation** | TLS 1.3 for all encrypted communications. AES-256-GCM for data at rest. SHA-256 for integrity verification. |
| **Why This Meets the Intent** | Encryption is implemented end-to-end: data in transit (ZTNA uses TLS 1.3, NAS uses SMB 3.1.1 encryption), data at rest (Synology AES-256 volume encryption), and data integrity (SHA-256 checksums for file transfers). The use of current standards (TLS 1.3, not obsolete SSL) demonstrates appropriate cryptographic strength. |

### 6.2.3 Physical Controls (A.7) — Compliance-by-Design

#### A.7.5 — Protecting Against Physical and Environmental Threats

| Element | Implementation |
| --- | --- |
| **Control Requirement** | The organization shall protect against physical and environmental threats |
| **Our Implementation** | Fire suppression system (FM-200), water leak detection, temperature/humidity monitoring with alerting. |
| **Why This Meets the Intent** | Environmental threats (fire, water, temperature) can destroy data center infrastructure. FM-200 fire suppression is clean agent (no water damage). Water leak detection provides early warning. Temperature/humidity monitoring with SMS alerting ensures environmental parameters stay within equipment specifications. |

### 6.2.4 ISO 27001 Controls Summary

| Category | Implemented by VConfi | Client Responsibility | Not Applicable |
| --- | --- | --- | --- |
| **A.5 — Organizational** | 22 | 8 | 0 |
| **A.6 — People** | 2 | 6 | 0 |
| **A.7 — Physical** | 8 | 6 | 0 |
| **A.8 — Technological** | 24 | 6 | 4 |
| **Total** | **56** | **26** | **4** |

Overall Compliance Rate: 68% Implemented by VConfi, 32% Client Responsibilities

### Key Takeaways — Compliance-by-Design Approach

Compliance is built-in, not bolted-on: Every architectural decision considered ISO 27001 requirements

56 controls implemented automatically: Infrastructure deployment achieves 68% compliance immediately

Technology satisfies intent, not just letter: Each implementation addresses the "why" behind the control

26 client responsibilities remain: Policies, awareness training, and HR processes require client ownership

Audit-ready from day one: Infrastructure can demonstrate compliance to auditors without retrofitting

# 7. Document Conclusion

This Enhanced Part 1 document establishes the comprehensive foundation for the B2H Studios IT infrastructure implementation:

## Summary of Enhancements

| Section | Enhancement Added |
| --- | --- |
| **Executive Summary** | Added "Why This Solution" subsection with proxy-first workflow explanation, comparison table, and decision flowchart |
| **Architecture Overview** | Added detailed subsections on Active-Standby DR rationale, Two-Site design, and Five-Zone security model with risk analysis |
| **VLAN Design** | Added "VLAN Segmentation Strategy" with /24 rationale, gateway placement analysis, and traffic flow diagrams |
| **IP Addressing** | Added "IP Scheme Design Philosophy" explaining 10.10.x.x choice, Site B 10.10.5x.x pattern, and reservation structure |
| **ISO 27001** | Added "Compliance-by-Design Approach" with control-by-control explanation of requirement, implementation, and intent satisfaction |

## Key Architectural Decisions Validated

| Decision | Rationale | Outcome |
| --- | --- | --- |
| **Synology HD6500** | Proxy-first workflow eliminates need for all-flash | ₹10.24 Crore saved |
| **Active-Standby DR** | 10-minute RTO acceptable; Active-Active overkill | ₹8+ Crore avoided |
| **Two-Site Design** | 37-day cloud restore unacceptable for business | Business continuity guaranteed |
| **Five-Zone Security** | Defense in depth, blast radius containment | ISO 27001 A.8.22 compliance |
| **/24 Subnets** | 10+ years growth headroom | No re-IPing required |
| **FortiGate Gateways** | Inter-VLAN inspection vs. switch routing | Comprehensive security visibility |

## Investment and Value Summary

| Metric | Value |
| --- | --- |
| **Total Initial Investment** | ₹2,04,03,994 (~₹2.04 Crore) |
| **Savings vs Option A** | ₹10.24 Crore |
| **5-Year TCO** | ₹3.4 Crore (vs ₹17.5 Crore for Option A) |
| **ISO 27001 Controls Implemented** | 56 of 93 (60%) |
| **RTO / RPO** | 10 minutes / 15 minutes |
| **Total Capacity** | 936TB usable per site |

The design prioritizes security, availability, and operational simplicity — delivering enterprise-grade capabilities tailored for B2H Studios' 25-user media production environment while maintaining cost discipline and compliance readiness.

End of Part 1: Executive Summary, Architecture & ISO Compliance (Enhanced Edition)

VConfi Solutions | CONFIDENTIAL | March 22, 2026

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Part 2: Network, Wireless & Server Design

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

# Part 2: Enhanced Network Infrastructure, Wireless & Servers

## With Detailed Design Reasoning & Architecture Decisions

B2H Studios IT Infrastructure Implementation Plan — Enhanced Edition

Client: B2H Studios

Project: Option B+ (Optimized Synology HD6500 Solution)

Date: March 22, 2026

Prepared by: VConfi Solutions

Classification: CONFIDENTIAL

Document Version: 2.0 (Enhanced with Design Rationale)

## Table of Contents

[Firewall Design — FortiGate 120G](#1-firewall-design--fortigate-120g)

1.1 Hardware Specifications

1.2 HA Configuration (Active-Passive)

1.3 SD-WAN Dual ISP Configuration

1.4 Security Zones and Zone Policies

1.5 UTM Profiles

1.6 SSL Inspection Configuration

1.7 VPN/ZTNA Configuration

1.8 Firewall Rule Table

1.9 FortiGate Design Rationale ⭐ ENHANCED

[Switch Design — HPE Aruba CX 6300M](#2-switch-design--hpe-aruba-cx-6300m)

2.1 Hardware Specifications

2.2 VSX Stacking Configuration

2.3 LACP Configuration for HD6500 Connectivity

2.4 VLAN Trunk Configuration

2.5 Spanning-Tree Configuration

2.6 Jumbo Frames Configuration

2.7 Port Assignment Table

2.8 Switch Stacking/Interconnect Diagram

2.9 HPE Aruba Design Rationale ⭐ ENHANCED

[Cabling Schedule](#3-cabling-schedule)

3.1 Cable Inventory

3.2 Patch Panel Layout

3.3 Cable Labeling Scheme

3.4 Testing Procedures

3.5 Cable Plant Design Philosophy ⭐ ENHANCED

[Redundancy Scenarios](#4-redundancy-scenarios)

[Wireless Infrastructure](#5-wireless-infrastructure)

5.6 Wireless Architecture Reasoning ⭐ ENHANCED

[Server Infrastructure](#6-server-infrastructure)

6.6 Compute Infrastructure Reasoning ⭐ ENHANCED

[Mandatory Architecture Flow Charts](#7-mandatory-architecture-flow-charts) ⭐ ENHANCED

## 1. Firewall Design — FortiGate 120G

### 1.1 Hardware Specifications

| Specification | Value |
| --- | --- |
| **Model** | FortiGate 120G |
| **Form Factor** | 1U Rackmount |
| **Firewall Throughput** | 44 Gbps |
| **IPS Throughput** | 24 Gbps |
| **NGFW Throughput** | 18 Gbps |
| **Threat Protection** | 14 Gbps |
| **VPN Throughput (IPsec)** | 18 Gbps |
| **SSL Inspection** | 10 Gbps |
| **Concurrent Sessions** | 8 Million |
| **New Sessions/Second** | 500,000 |
| **Interfaces** | 8x GE RJ45, 8x GE SFP, 4x 10 GE SFP+ |
| **Dedicated Management** | 1x GE RJ45 |
| **Storage** | 480GB SSD (for logging) |
| **Memory** | 64GB DDR4 |
| **Redundant Power** | Hot-swappable dual PSU |
| **Operating Temp** | 0°C to 40°C |

### 1.2 HA Configuration (Active-Passive)

| Parameter | Setting |
| --- | --- |
| **HA Mode** | Active-Passive |
| **HA Group ID** | 1 |
| **HA Group Name** | B2H-FG-HA-01 |
| **Priority (Primary)** | 200 |
| **Priority (Secondary)** | 100 |
| **Heartbeat Interface** | Port 7-8 (dedicated) |
| **Session Pickup** | Enabled |
| **Configuration Sync** | Automatic |
| **VRRP Virtual MAC** | 00:09:0f:09:00:01 |

Failover Triggers:

Primary unit hardware failure

Link monitoring failure (2+ interfaces down)

Remote link failure (monitored via IP)

Manual failover (maintenance mode)

Failover Time: < 2 seconds (sub-second with session pickup)

### 1.3 SD-WAN Dual ISP Configuration

| ISP | Details |
| --- | --- |
| **ISP1 (Primary)** | Airtel Business - 1Gbps Fiber |
| **ISP1 IP** | Static /29 subnet |
| **ISP2 (Secondary)** | Jio Business - 1Gbps Fiber |
| **ISP2 IP** | Static /29 subnet |

Performance SLA Monitors:

| Monitor | Target | Protocol | Interval | Fail Threshold |
| --- | --- | --- | --- | --- |
| Google DNS | 8.8.8.8 | Ping | 1000ms | 3 failures |
| Cloudflare | 1.1.1.1 | Ping | 1000ms | 3 failures |
| Latency SLA | < 50ms | Ping | 5000ms | 5 failures |

SD-WAN Rules:

| Rule | Source | Destination | Strategy | Preferred |
| --- | --- | --- | --- | --- |
| 1 | All | Wasabi S3 | Best Quality | ISP1 |
| 2 | Signiant | Any | Lowest Cost | ISP1 |
| 3 | Video Streaming | Any | Lowest Latency | Auto |
| 4 | Default | Any | Best Quality | ISP1, ISP2 |

### 1.4 Security Zones and Zone Policies

Zone Definitions:

| Zone | Interfaces | Security Level | Member VLANs |
| --- | --- | --- | --- |
| **WAN** | port1, port2 | Untrusted | - |
| **DMZ** | port3 (VLAN 10) | Semi-Trusted | VLAN 10 (10.10.10.0/24) |
| **Internal** | port4 (VLAN 20, 30) | Trusted | VLAN 20 (10.10.20.0/24), VLAN 30 (10.10.30.0/24) |
| **Management** | port5 (VLAN 40) | Restricted | VLAN 40 (10.10.40.0/24) |
| **Guest** | port6 (VLAN 50) | Untrusted | VLAN 50 (10.10.50.0/24) |

Intra-Zone Policies:

| Source Zone | Destination Zone | Default Action | Logging |
| --- | --- | --- | --- |
| Internal | WAN | Allow | Yes |
| DMZ | WAN | Allow | Yes |
| Management | All | Allow | Yes |
| Guest | WAN | Allow | Yes |
| Guest | Internal | Deny | Alert |
| DMZ | Internal | Deny | Alert |
| WAN | DMZ | Deny (except rules) | Yes |
| WAN | Internal | Deny (except ZTNA) | Yes |

### 1.5 UTM Profiles

IPS Profile (IPS_Media_Production):

| Setting | Value |
| --- | --- |
| **Profile Name** | IPS_Media_Production |
| **Inspection Mode** | Proxy-based |
| **Filter** | High Security with Media exceptions |
| **Signatures** | All critical and high severity |
| **Action** | Block + Log |
| **Excluded Signatures** | Custom media streaming protocols |

Antivirus Profile (AV_Enterprise):

| Setting | Value |
| --- | --- |
| **Profile Name** | AV_Enterprise |
| **Inspection Mode** | Proxy-based |
| **Scan Mode** | Full Scan |
| **Engine** | FortiGuard + FortiSandbox Cloud |
| **Block Period** | 30 minutes |
| **FortiSandbox** | Enabled for unknown files |

### 1.6 SSL Inspection Configuration

| Setting | Value |
| --- | --- |
| **Mode** | Full SSL Inspection |
| **Certificate** | B2H-CA-Internal (deployed to all endpoints) |
| **Inspection Profile** | High Security |
| **Excluded Categories** | Banking, Health, Government |
| **Unsupported SSL** | Block |
| **Invalid Certificate** | Block |
| **Diffie-Hellman** | Block (unless PFS required) |

### 1.7 VPN/ZTNA Configuration

ZTNA Access Proxy Configuration:

| Parameter | Value |
| --- | --- |
| **Access Proxy Name** | ZTNA-NAS-Access |
| **External Interface** | Virtual-WAN (SD-WAN) |
| **External Port** | 443 |
| **Authentication** | FortiAuthenticator (MFA) |
| **Certificate** | Wildcard SSL (b2hstudios.com) |

ZTNA Policy Rules:

| Rule | User Group | Device Posture | Access | Resources |
| --- | --- | --- | --- | --- |
| 1 | Editors | Compliant | Full | NAS Shares (VLAN 30) |
| 2 | Management | Compliant | Full | All Internal |
| 3 | External DIT | Compliant | Limited | Signiant SDCX (DMZ) |
| 4 | Guest | Any | None | Internet Only |

Device Posture Checks:

| Check | Requirement |
| --- | --- |
| **Antivirus** | Kaspersky Active & Updated |
| **OS Version** | Windows 10/11 (Latest) or macOS 12+ |
| **Disk Encryption** | BitLocker/FileVault Enabled |
| **FortiClient** | Latest Version |
| **TPM** | Certificate Validation |

### 1.8 Firewall Rule Table

| Rule ID | Name | Source | Destination | Service | Action | Log |
| --- | --- | --- | --- | --- | --- | --- |
| 100 | Allow ZTNA | SSL-VPN | VLAN30 | SMB, NFS | Accept | Yes |
| 101 | Allow Signiant | Any | DMZ_SDCX | UDP/33001 | Accept | Yes |
| 102 | SDCX to NAS | DMZ_SDCX | NAS_Storage | NFS | Accept | Yes |
| 103 | Signiant Web | Any | DMZ_SDCX | HTTPS/443 | Accept | Yes |
| 104 | DNS Outbound | All_Internal | WAN | DNS/53 | Accept | Yes |
| 105 | NTP Outbound | All_Internal | WAN | NTP/123 | Accept | Yes |
| 106 | HTTPS Outbound | All_Internal | WAN | HTTPS/443 | Accept | Yes |
| 107 | SMTP Outbound | All_Internal | WAN | SMTP/587 | Accept | Yes |
| 108 | Wasabi S3 | NAS_Storage | WAN | HTTPS/443 | Accept | Yes |
| 109 | Zabbix Monitoring | Management | All_Internal | SNMP, ICMP | Accept | Yes |
| 110 | iLO Management | Management | Servers | HTTPS/443 | Accept | Yes |
| 111 | DSM Management | Management | NAS_Storage | HTTPS/5001 | Accept | Yes |
| 112 | Admin SSH | Management | All_Devices | SSH/22 | Accept | Yes |
| 113 | FortiAnalyzer Logging | All_Devices | FANALYZER-01 | SYSLOG/514 | Accept | Yes |
| 114 | Site-to-Site VPN | SiteA | SiteB | Any | Accept | Yes |
| 115 | Guest Internet | Guest | WAN | HTTP, HTTPS | Accept | Yes |
| 200 | Block Guest to Internal | Guest | Internal | Any | Deny | Yes |
| 201 | Block DMZ to Internal | DMZ | Internal | Any | Deny | Yes |
| 202 | Block Inbound SMB | WAN | Any | SMB/445 | Deny | Yes |
| 203 | Block Inbound RDP | WAN | Any | RDP/3389 | Deny | Yes |
| 204 | Block Inbound SSH | WAN | Any | SSH/22 | Deny | Yes |
| 205 | Block Known Bad IPs | Any | WAN_Bad_IPs | Any | Deny | Yes |
| 300 | Deny All | Any | Any | Any | Deny | Alert |

### 1.9 FortiGate Design Rationale ⭐ ENHANCED

#### 1.9.1 Why FortiGate 120G (Not 100F or 200F)

Performance Calculation Table:

| Metric | 100F | 120G | 200F |
| --- | --- | --- | --- |
| Firewall Throughput | 20 Gbps | 50 Gbps | 100 Gbps |
| NGFW Throughput | 8 Gbps | 15 Gbps | 25 Gbps |
| Threat Protection | 6 Gbps | 14 Gbps | 20 Gbps |
| Price (India) | ₹4.2 Lakhs | ₹7.1 Lakhs | ₹14 Lakhs |
| Concurrent Sessions | 2M | 8M | 16M |
| **Suitability for B2H** | Too Small | ✅ **Perfect** | Overkill |

Throughput Calculation for B2H Studios:

Base Traffic Requirements:
├── 25 users × 100 Mbps average = 2.5 Gbps
├── Replication traffic (site-to-site) = 1 Gbps
├── Remote ZTNA users (10 concurrent) = 500 Mbps
├── Overhead (management, monitoring) = 500 Mbps
└── Total Baseline = 4.5 Gbps

Headroom Calculation:
├── Industry best practice = 2× headroom minimum
├── Required capacity = 4.5 Gbps × 2 = 9 Gbps
├── NGFW throughput needed = 9 Gbps
└── FortiGate 120G NGFW = 15 Gbps ✓

Why Not FortiGate 100F:

NGFW throughput of 8 Gbps is below our 9 Gbps requirement

Only 2M concurrent sessions vs. 8M needed for 25 users with multiple connections

Limited interface options (no 10GbE SFP+ on 100F)

Would require replacement within 2 years as studio grows

Why Not FortiGate 200F:

2× the price (₹14L vs ₹7.1L) for capabilities we won't use

Designed for 500+ user environments

Higher power consumption (300W vs 200W) = ₹25K/year extra electricity

Design Trade-off: We chose the 120G as the "Goldilocks" solution — not underpowered like the 100F, not overpriced like the 200F. The 15 Gbps NGFW throughput provides 3.3× headroom over current needs.

#### 1.9.2 Why Active-Passive HA (Not Active-Active)

HA Mode Comparison:

| Factor | Active-Passive | Active-Active |
| --- | --- | --- |
| License Cost | 1× base license | 2× full licenses |
| Session Sync | Simple (async) | Complex (sync required) |
| Failover Time | <2 seconds | <1 second |
| Load Balancing | N/A | Both units process |
| Configuration Complexity | Low | High |
| Troubleshooting | Simple | Complex (split sessions) |
| **Best For** | Stateful apps (SMB, NFS) | Stateless web apps |

Why Active-Passive for B2H Studios:

SMB/NFS Session State: Media production relies heavily on SMB/NFS file shares. Active-active splits sessions between firewalls, causing file lock issues when failover occurs.

License Cost Savings: Active-active requires both units to have full UTP/ATP licenses = ₹4.2L extra annual cost. Active-passive only needs licenses on primary.

Operational Simplicity: With a small IT team, troubleshooting session issues in active-active is not practical.

Adequate Performance: Single FortiGate 120G provides 15 Gbps NGFW — far exceeding our 4.5 Gbps requirement. No need to load-balance.

HA Failover Decision Process:

flowchart TD
    A[HA Heartbeat Monitoring] --> B{Heartbeat Lost?}
    B -->|No| A
    B -->|Yes| C{Link Monitor OK?}
    C -->|No| D[Trigger Failover]
    C -->|Yes| E{Remote Link OK?}
    E -->|No| D
    E -->|Yes| F{Override Config?}
    F -->|Yes| D
    F -->|No| G[Continue Primary]
    D --> H[Secondary Assumes Active]
    H --> I[VRRP MAC Migration]
    I --> J[Session Pickup]
    J --> K[Traffic Resumes]
    K --> L[Alert Generated]

Design Trade-off: We sacrificed the marginal performance benefit of active-active for the operational simplicity and cost savings of active-passive. For B2H Studios' workflow, 2-second failover is acceptable.

#### 1.9.3 SD-WAN Decision Logic

Dual ISP with SD-WAN vs. Single ISP with Backup:

| Approach | Single ISP + Cold Backup | Dual ISP with SD-WAN |
| --- | --- | --- |
| Monthly Cost | ₹25K (1Gbps) | ₹45K (2× 1Gbps) |
| Failover Time | 5-10 minutes (manual) | <5 seconds (automatic) |
| Bandwidth Aggregation | No | Yes (load balancing) |
| Application Steering | No | Yes (per-app routing) |
| SLA Monitoring | No | Yes (latency, jitter, packet loss) |
| User Impact | High (interruption) | Zero (seamless) |

Why SD-WAN for B2H Studios:

Real-Time Replication: Site-to-site replication cannot tolerate 5-10 minute outages. SD-WAN provides sub-5-second failover.

Upload Bandwidth: Media files require high upload bandwidth. Two ISPs = 2 Gbps aggregate upload for large file transfers.

Quality of Service: SD-WAN can prioritize Signiant traffic over general internet, ensuring file transfers complete on time.

ISP Diversity: Airtel and Jio use different last-mile infrastructure, reducing correlated failure risk.

SD-WAN Traffic Steering Logic:

flowchart TD
    A[Traffic Generated] --> B{Traffic Type?}
    B -->|Signiant SDCX| C[Route via ISP1<br/>Lowest Cost Priority]
    B -->|Wasabi Cloud| D[Route via Best Quality<br/>Latency-based]
    B -->|Video Streaming| E[Route via Lowest Latency<br/>Real-time Priority]
    B -->|General Web| F[Route via Both ISPs<br/>Load Balanced]
    
    C --> G{ISP1 Up?}
    D --> H{SLA Met?}
    E --> I{Latency < 50ms?}
    F --> J{Both ISPs Up?}
    
    G -->|No| K[Failover to ISP2]
    H -->|No| K
    I -->|No| L[Switch to Better ISP]
    J -->|No| M[Use Available ISP]
    
    G -->|Yes| N[Continue ISP1]
    H -->|Yes| O[Continue Current]
    I -->|Yes| P[Continue Current]
    J -->|Yes| Q[Distribute Load]

Design Trade-off: We accepted the additional ₹20K/month ISP cost for automatic failover. For a post-production studio, the cost of even 5 minutes of downtime during a client deadline far exceeds the annual ISP cost.

#### 1.9.4 ZTNA vs VPN — Deep Dive

Security Comparison Matrix (6 Attack Scenarios):

| Attack Scenario | Traditional VPN | ZTNA Protection | Advantage |
| --- | --- | --- | --- |
| **Stolen Credentials** | Full network access | Blocked — no device cert | ZTNA |
| **Compromised Endpoint** | Full network access | Blocked — posture check fails | ZTNA |
| **Lateral Movement** | Easy — same subnet | Impossible — micro-segmentation | ZTNA |
| **Insider Threat** | Can scan entire network | Only sees authorized apps | ZTNA |
| **Credential Stuffing** | No protection | MFA required | ZTNA |
| **Man-in-the-Middle** | Protected via IPsec | Protected via TLS 1.3 | Equal |

Cost Comparison:

| Component | VPN (IPsec/SSL) | ZTNA (Separate Appliance) | Fortinet ZTNA (Included) |
| --- | --- | --- | --- |
| Gateway Appliance | ₹0 (built-in) | ₹15-25 Lakhs | ₹0 (FortiGate native) |
| Client Licenses | ₹0 | ₹3K/user/year | ₹0 (included in UTP) |
| MFA Solution | ₹2L/year (separate) | ₹2L/year | ₹0 (FortiAuthenticator) |
| **Total Year 1** | ₹2 Lakhs | ₹18-27 Lakhs | **₹0** |

ZTNA Authentication Flow:

sequenceDiagram
    participant User
    participant FortiClient
    participant FortiGate
    participant FortiAuth as FortiAuthenticator
    participant NAS as NAS Storage
    
    User->>FortiClient: Launch & Select NAS Access
    FortiClient->>FortiClient: Device Posture Check
    Note over FortiClient: AV Running?<br/>OS Patched?<br/>Disk Encrypted?
    
    alt Posture Check FAILS
        FortiClient->>User: Access Denied — Remediation Required
    else Posture Check PASSES
        FortiClient->>FortiGate: ZTNA Connection Request
        FortiGate->>FortiAuth: Authentication Request
        FortiAuth->>User: MFA Push Notification
        User->>FortiAuth: Approve Login
        FortiAuth->>FortiGate: Auth Success + User Attributes
        FortiGate->>NAS: Proxy Connection Established
        NAS->>User: Grant Access to Shares
    end

Critical Factor — Data Residency:

B2H Studios handles copyrighted media content. Cloud-based ZTNA (Zscaler/Netskope) would route all file access through international proxies, potentially:

Violating client data residency requirements

Exposing unreleased content to foreign jurisdictions

Adding latency to large file transfers

Fortinet's on-premise ZTNA keeps all data within India.

Design Trade-off: ZTNA requires more initial configuration than VPN, but provides dramatically improved security posture. The zero additional cost (included in FortiGate UTP) made this an easy decision over traditional VPN.

## 2. Switch Design — HPE Aruba CX 6300M

### 2.1 Hardware Specifications

| Specification | Value |
| --- | --- |
| **Model** | HPE Aruba CX 6300M (JL659A) |
| **Form Factor** | 1U Rackmount |
| **Switching Capacity** | 880 Gbps |
| **Forwarding Rate** | 655 Mpps |
| **Total Ports** | 48x 1GbE RJ45 + 4x 25GbE SFP28 |
| **PoE Budget** | 1,440W (PoE++) |
| **PoE Ports** | 48 (802.3bt ready) |
| **Management** | OOB Ethernet, USB Console |
| **Stacking** | VSX (Virtual Switching Extension) |
| **MAC Address Table** | 64,000 entries |
| **VLAN Support** | 4,094 VLANs |
| **Jumbo Frames** | MTU 9,216 bytes |
| **Power** | Dual hot-swappable PSU |
| **Cooling** | Hot-swappable fans |
| **MTBF** | 340,000 hours |

Quantity: 2 units (SW1 and SW2) for redundant core

### 2.2 VSX Stacking Configuration

| Parameter | SW1 (Primary) | SW2 (Secondary) |
| --- | --- | --- |
| **VSX Role** | Primary | Secondary |
| **VSX System MAC** | 00:01:02:03:04:05 | 00:01:02:03:04:05 (shared) |
| **Keepalive Interface** | mgmt | mgmt |
| **Keepalive IP** | 10.10.40.2 | 10.10.40.3 |
| **ISL Ports** | 1/1/51, 1/1/52 | 1/1/51, 1/1/52 |
| **ISL LAG ID** | 1 | 1 |

VSX Features Enabled:

Active-Active Gateway (AAG) for VLAN interfaces

Multi-Active Detection (MAD)

VSX Sync for MAC, ARP, and route tables

### 2.3 LACP Configuration for HD6500 Connectivity

| Parameter | Value |
| --- | --- |
| **LAG ID** | 10 |
| **LAG Name** | HD6500-LACP |
| **Mode** | LACP Active |
| **Hash Policy** | L3-L4 (src-dst-ip-port) |
| **Member Ports (SW1)** | 1/1/49, 1/1/50 |
| **Member Ports (SW2)** | 1/1/49, 1/1/50 |
| **Speed** | 10 Gbps per link |
| **Aggregate Speed** | 40 Gbps (4x 10GbE) |

### 2.4 VLAN Trunk Configuration

Trunk Port Configuration:

| Port | Connected To | Native VLAN | Allowed VLANs | Mode |
| --- | --- | --- | --- | --- |
| 1/1/1 | FortiGate-Pri | 1 | 10,20,30,40,50 | Trunk |
| 1/1/2 | FortiGate-Sec | 1 | 10,20,30,40,50 | Trunk |
| 1/1/51 | SW2 (ISL) | 1 | All | Trunk |
| 1/1/52 | SW2 (ISL) | 1 | All | Trunk |
| lag 10 | HD6500 | 1 | 30 | Trunk |

VLAN Interface Configuration (SVI):

| VLAN | Interface IP | Subnet | VRRP IP | Purpose |
| --- | --- | --- | --- | --- |
| 10 | 10.10.10.2/24 | 10.10.10.0/24 | 10.10.10.1 | DMZ |
| 20 | 10.10.20.2/24 | 10.10.20.0/24 | 10.10.20.1 | Production |
| 30 | 10.10.30.2/24 | 10.10.30.0/24 | 10.10.30.1 | Storage |
| 40 | 10.10.40.2/24 | 10.10.40.0/24 | 10.10.40.1 | Management |
| 50 | 10.10.50.2/24 | 10.10.50.0/24 | 10.10.50.1 | Guest |

### 2.5 Spanning-Tree Configuration

| Parameter | Value |
| --- | --- |
| **Protocol** | Rapid PVST+ |
| **Mode** | RPVST |
| **Bridge Priority (SW1)** | 4096 (Root) |
| **Bridge Priority (SW2)** | 8192 (Backup) |
| **PortFast** | Enabled on access ports |
| **BPDU Guard** | Enabled on access ports |
| **Root Guard** | Enabled on trunk ports |
| **Loop Guard** | Enabled globally |

### 2.6 Jumbo Frames Configuration

| VLAN | MTU Setting |
| --- | --- |
| VLAN 10 (DMZ) | 1500 |
| VLAN 20 (Production) | 1500 |
| **VLAN 30 (Storage)** | **9000** |
| VLAN 40 (Management) | 1500 |
| VLAN 50 (Guest) | 1500 |

End-to-End MTU Verification:

HD6500: MTU 9000 configured

Switch VLAN 30: MTU 9000 configured

Server NICs (VLAN 30): MTU 9000 configured

### 2.9 HPE Aruba Design Rationale ⭐ ENHANCED

#### 2.9.1 Why HPE vs. Cisco vs. Arista

Detailed Comparison Table:

| Criteria | HPE Aruba CX 6300M | Cisco Catalyst 9300 | Arista 7020SR |
| --- | --- | --- | --- |
| **List Price (per switch)** | ₹4.2 Lakhs | ₹6.5 Lakhs | ₹5.8 Lakhs |
| **5-Year TCO** | ₹6.8 Lakhs | ₹10.5 Lakhs | ₹9.2 Lakhs |
| **Stacking Technology** | VSX (hitless) | StackWise (election) | MLAG (complex) |
| **25GbE Uplinks** | 4× native SFP28 | Requires module | 4× native SFP28 |
| **PoE++ Budget** | 1,440W | 1,600W | 1,200W |
| **GUI Management** | Aruba Central (free) | DNA Center (+₹8L) | CLI only |
| **API/Automation** | REST API native | DNA Center dependent | EOS API excellent |
| **Firmware Stability** | Excellent | Good (recent issues) | Excellent |
| **Support in India** | Good | Excellent | Limited |
| **Learning Curve** | Moderate | Steep | Steep |
| **Smart Licensing** | No (traditional) | Yes (mandatory) | No |

Total Cost of Ownership (5-Year Analysis):

HPE Aruba CX 6300M (2 units):
├── Year 0 (Hardware): ₹8.4 Lakhs
├── Year 1-5 Support: ₹4.2 Lakhs (₹84K/year)
├── Management Tools: ₹0 (Aruba Central free)
├── Training: ₹1.2 Lakhs
└── 5-Year TCO: ₹13.8 Lakhs

Cisco Catalyst 9300 (2 units):
├── Year 0 (Hardware): ₹13.0 Lakhs
├── Year 1-5 Support: ₹6.5 Lakhs (₹1.3L/year)
├── DNA Center: ₹8.0 Lakhs (₹1.6L/year)
├── Smart Licensing: ₹2.0 Lakhs
├── Training: ₹2.5 Lakhs
└── 5-Year TCO: ₹32.0 Lakhs

Support Quality Comparison (India):

| Aspect | HPE | Cisco | Arista |
| --- | --- | --- | --- |
| 4-Hour Response | Available (Premium) | Standard (SmartNet) | Limited cities |
| Spare Parts Depots | 12 cities | 20+ cities | 4 cities |
| Local Engineers | Good coverage | Excellent | Sparse |
| TAC Quality | Good | Excellent | Excellent |

Why HPE Aruba for B2H Studios:

Cost Efficiency: 57% lower TCO than Cisco, 51% lower than Arista

VSX Technology: True hitless failover vs. StackWise election delay

No Forced Licensing: Cisco's Smart Licensing requires cloud connectivity; HPE uses traditional licensing

Right-Sized Features: All needed features without enterprise overhead

Design Trade-off: We sacrificed Cisco's superior support ecosystem for significant cost savings. Given the redundancy built into the design (dual switches, DR site), the risk of needing emergency support is mitigated.

#### 2.9.2 VSX Stacking Deep Dive

How VSX Differs from Traditional Stacking:

| Characteristic | Traditional Stacking (Cisco StackWise) | VSX (HPE Aruba) |
| --- | --- | --- |
| **Control Plane** | Shared (single brain) | Separate (two brains, synced) |
| **Failover Time** | 30-60 seconds (election) | <1 second (stateful) |
| **Firmware Upgrade** | Entire stack reboots | ISSU (one at a time) |
| **Distance Between Switches** | Limited (stacking cables) | Standard fiber (10km+) |
| **Scalability** | Limited members (9 max) | 2 members (always) |
| **Configuration Complexity** | Simple (one config) | Moderate (sync required) |

VSX Failure Scenario Walkthrough:

Scenario 1: SW1 Fails

Timeline of Events:
T+0ms    SW1 stops responding
T+100ms  SW2 misses 1st keepalive
T+200ms  SW2 misses 2nd keepalive
T+300ms  SW2 declares SW1 dead
T+400ms  SW2 assumes primary gateway role
T+500ms  LACP on SW2 links detects partner loss
T+600ms  Traffic reroutes through SW2
T+700ms  GARP sent to update MAC tables
T+800ms  Full convergence complete

Total Downtime: <1 second (users don't notice)

What Happens:

SW2 immediately takes over as default gateway for all VLANs (Active-Active Gateway)

LACP on the HD6500 detects that SW1 links are down

Traffic continues flowing through SW2's LACP members

No reconfiguration needed on NAS, servers, or firewall

Scenario 2: ISL (Inter-Switch Link) Fails

Timeline of Events:
T+0ms    ISL fiber cut detected
T+50ms   Both switches detect link down
T+100ms  Multi-Active Detection (MAD) engages
T+200ms  Secondary (SW2) disables all data ports
T+300ms  SW1 continues as sole active switch

Result: No split-brain, no loop, controlled degradation

Scenario 3: Firmware Upgrade

flowchart LR
    A[Normal Operation<br/>SW1=Primary, SW2=Secondary] --> B[Initiate ISSU Upgrade]
    B --> C[SW2 Upgraded First<br/>Still Secondary]
    C --> D{SW2 Upgrade OK?}
    D -->|Yes| E[SW2 Takes Over Primary]
    E --> F[SW1 Upgraded]
    F --> G{SW1 Upgrade OK?}
    G -->|Yes| H[SW1 Returns as Primary]
    G -->|No| I[SW2 Remains Primary]
    D -->|No| J[Rollback SW2<br/>Abort Upgrade]

VSX State Diagram:

stateDiagram-v2
    [*] --> Initializing: Power On
    Initializing --> InSync: ISL Up + Config Sync
    InSync --> Primary: Role Election
    InSync --> Secondary: Role Election
    
    Primary --> Secondary: Failover Triggered
    Secondary --> Primary: Takeover
    
    Primary --> OutOfSync: ISL Down
    Secondary --> OutOfSync: ISL Down
    
    OutOfSync --> InSync: ISL Restored
    OutOfSync --> StandaloneAlone: MAD Engaged
    
    StandaloneAlone --> InSync: ISL Restored + Manual Recovery
    
    Primary --> [*]: Shutdown
    Secondary --> [*]: Shutdown

Design Trade-off: VSX requires more initial configuration than traditional stacking, but provides true hitless failover and ISSU capabilities that are essential for a production environment.

#### 2.9.3 LACP Design Explanation

Why 4× 10GbE LACP (40 Gbps) for HD6500:

Bandwidth Calculation:

Current Requirements:
├── 25 users × 20 MB/s (proxy access) = 500 MB/s
├── Replication traffic = 500 MB/s
├── Backup operations = 300 MB/s
└── Total Required = 1,300 MB/s (10.4 Gbps)

With 4× 10GbE LACP:
├── Aggregate Bandwidth = 40 Gbps
├── Effective Throughput (L3-L4 hash) = ~35 Gbps
├── Headroom = 3.4×
└── Future-proof for 100+ users

Why Not 2× 25GbE Instead:

HD6500 comes with 10GbE RJ45 ports standard (25GbE requires add-on card at ₹1.8L)

Cat6a cabling already planned for 10GbE (25GbE needs fiber or Cat8)

40 Gbps aggregate exceeds our needs by 3×

LACP with 4 links provides better failure resilience (can lose 3 links, still have 10 Gbps)

Hash Algorithm Selection — L3-L4 (src-dst-ip-port):

| Hash Method | Best For | Limitation |
| --- | --- | --- |
| L2 (MAC) | Small networks | Poor distribution with single router |
| L3 (IP) | General use | Poor for same-source bulk transfers |
| **L4 (IP+Port)** | **Multi-session protocols** | **Best overall distribution** |
| L3-L4 (Enhanced) | High-variability traffic | CPU overhead (minimal) |

Why L3-L4 for HD6500:

File protocols (SMB/NFS) use multiple TCP connections

Different source ports = different hash = load distribution across all 4 links

Ensures no single link becomes bottleneck during large transfers

Failover Behavior — Link Failure Detection:

sequenceDiagram
    participant NAS as HD6500
    participant SW as Switch LACP
    
    Note over NAS,SW: Normal Operation<br/>4 Links Active
    
    SW->>NAS: LACP PDU (every 30s)
    NAS->>SW: LACP Response
    
    Note over NAS: Link 1 Failure
    
    SW->>NAS: LACP PDU (no response)
    SW->>SW: Mark Link 1 Down
    SW->>SW: Redistribute Hash Table
    
    Note over NAS,SW: Traffic Rebalanced<br/>3 Links Active (30 Gbps)
    
    NAS->>SW: Traffic Continues Seamlessly

Design Trade-off: We chose 4× 10GbE over 2× 25GbE for cost savings and better resilience. The L3-L4 hash ensures optimal distribution for multi-session file protocols.

#### 2.9.4 Jumbo Frames (MTU 9000) Justification

Standard MTU (1500) vs Jumbo (9000) Performance Comparison:

| Metric | MTU 1500 | MTU 9000 | Improvement |
| --- | --- | --- | --- |
| **Frames per 1 GB transfer** | 683,594 | 113,932 | 6× reduction |
| **Header overhead** | 4.1% | 0.7% | 5.4% more efficient |
| **CPU interrupts (per GB)** | 683,594 | 113,932 | 83% fewer |
| **Throughput (single stream)** | 850 MB/s | 1,050 MB/s | +24% |
| **Latency (per hop)** | 0.02 ms | 0.015 ms | 25% reduction |

When Jumbo Frames Help (Large Sequential Transfers):

Scenario: Exporting 50GB video project to NAS

With MTU 1500:
├── Frames required: 35,791,668
├── Header processing: Significant CPU load
├── Interrupts: High frequency
└── Effective throughput: ~700 MB/s

With MTU 9000:
├── Frames required: 5,965,278 (6× fewer)
├── Header processing: Minimal CPU load
├── Interrupts: Low frequency
└── Effective throughput: ~950 MB/s (+36%)

When They Don't Help (Small Random I/O):

Scenario: Loading 1000 small proxy files (1-5 MB each)

With MTU 1500:
├── Most packets are already <1500 bytes
├── No fragmentation occurs
└── MTU 9000 provides no benefit

Configuration Requirements — End-to-End Consistency:

flowchart TD
    A[Enable MTU 9000<br/>Storage VLAN Only] --> B{All Devices Support?}
    B -->|Yes| C[HD6500: MTU 9000]
    B -->|No| D[Identify Incompatible Device]
    C --> E[Switch VLAN 30: MTU 9000]
    E --> F[Server NICs: MTU 9000]
    F --> G[Test End-to-End]
    G --> H{Ping -s 8972 Success?}
    H -->|Yes| I[Deployment Complete]
    H -->|No| J[Troubleshoot Path]
    J --> G
    D --> K[Upgrade or Exclude from VLAN 30]

Why This Setting — MTU 9000 Only on VLAN 30 (Storage):

| VLAN | MTU | Reasoning |
| --- | --- | --- |
| VLAN 10 (DMZ) | 1500 | Internet-facing, compatibility required |
| VLAN 20 (Production) | 1500 | Mixed devices, not all support jumbo |
| **VLAN 30 (Storage)** | **9000** | **Controlled environment, all devices support** |
| VLAN 40 (Management) | 1500 | OOB management, keep simple |
| VLAN 50 (Guest) | 1500 | Unknown devices, must be compatible |

Risk Mitigation:

Misconfigured MTU causes hard-to-diagnose issues

We enable only where controlled (NAS, switches, servers)

All devices on VLAN 30 are managed by IT (no user devices)

Monitoring alert for MTU mismatches configured in Zabbix

Design Trade-off: Jumbo frames provide 20-30% performance improvement for large file transfers but require careful end-to-end configuration. We limit them to the storage VLAN where we control all endpoints.

## 3. Cabling Schedule

### 3.1 Cable Inventory

| Cable ID | From | To | Type | Length | Purpose |
| --- | --- | --- | --- | --- | --- |
| C-001 | ISP1 ONT | FG-Pri Port1 | Cat6 | 2m | WAN Primary |
| C-002 | ISP2 ONT | FG-Sec Port2 | Cat6 | 2m | WAN Secondary |
| C-003 | FG-Pri Port3 | SW1 Port 1/1/1 | Cat6 | 1m | Core Uplink Primary |
| C-004 | FG-Sec Port3 | SW2 Port 1/1/1 | Cat6 | 1m | Core Uplink Secondary |
| C-005 | FG-Pri Port7 | FG-Sec Port7 | Cat6 | 0.5m | HA Heartbeat 1 |
| C-006 | FG-Pri Port8 | FG-Sec Port8 | Cat6 | 0.5m | HA Heartbeat 2 |
| C-007 | HD6500 Port1 | SW1 Port 1/1/49 | Cat6a | 2m | NAS 10GbE Link 1 |
| C-008 | HD6500 Port2 | SW1 Port 1/1/50 | Cat6a | 2m | NAS 10GbE Link 2 |
| C-009 | HD6500 Port3 | SW2 Port 1/1/49 | Cat6a | 2m | NAS 10GbE Link 3 |
| C-010 | HD6500 Port4 | SW2 Port 1/1/50 | Cat6a | 2m | NAS 10GbE Link 4 |
| C-011 | SW1 Port 1/1/51 | SW2 Port 1/1/51 | Fiber OM4 | 5m | VSX ISL Link 1 |
| C-012 | SW1 Port 1/1/52 | SW2 Port 1/1/52 | Fiber OM4 | 5m | VSX ISL Link 2 |
| C-013 | R760 Port1 | SW1 Port 1/1/10 | Cat6a | 2m | Server 10GbE Primary |
| C-014 | R760 Port2 | SW1 Port 1/1/11 | Cat6a | 2m | Server 10GbE Secondary |
| C-015 | R760 Port3 | SW2 Port 1/1/10 | Cat6a | 2m | Server 10GbE Tertiary |
| C-016 | R760 iLO | SW2 Port 1/1/11 | Cat6 | 2m | Server OOB Management |
| C-017 | SW1 Port 1/1/20 | FortiAP-01 | Cat6 | 15m | Floor 1 AP (PoE++) |
| C-018 | SW1 Port 1/1/21 | FortiAP-02 | Cat6 | 15m | Floor 1 AP #2 (PoE++) |
| C-019 | SW1 Port 1/1/22 | FortiAP-03 | Cat6 | 20m | Floor 2 AP (PoE++) |
| C-020 | SW1 Port 1/1/23 | FortiAP-04 | Cat6 | 20m | Floor 2 AP #2 (PoE++) |
| C-021 | SW2 Port 1/1/20 | FortiAP-05 | Cat6 | 25m | Floor 3 AP (PoE++) |
| C-022 | SW2 Port 1/1/21 | FortiAP-06 | Cat6 | 10m | Edit Bay AP (PoE++) |
| C-023 | FG-Pri MGMT | Management PC | Cat6 | 3m | Firewall Console |
| C-024 | SW1 MGMT | Management PC | Cat6 | 3m | Switch Console |
| C-025 | SW2 MGMT | Management PC | Cat6 | 3m | Switch Console |
| C-026 | HD6500 MGMT | Management PC | Cat6 | 3m | NAS Console |
| C-027 | UPS 1 | Rack PDU 1 | Power C13-C14 | 2m | UPS Power Feed |
| C-028 | UPS 2 | Rack PDU 2 | Power C13-C14 | 2m | UPS Power Feed |
| C-029 | ATS | Rack PDU 3 | Power C13-C14 | 2m | ATS Power Feed |
| C-030 | ATS | Rack PDU 4 | Power C13-C14 | 2m | ATS Power Feed |

### 3.2 Patch Panel Layout

PP1 - Network Patch Panel (Rear of Rack):

| Port | Destination | Type |
| --- | --- | --- |
| 1-4 | ISP1/ISP2 Input | Cat6 |
| 5-12 | FortiGate Ports | Cat6 |
| 13-24 | SW1 Uplinks | Cat6/Cat6a |
| 25-36 | SW2 Uplinks | Cat6/Cat6a |
| 37-48 | Future Expansion | - |

PP2 - Workstation Patch Panel:

| Port | Destination | Type |
| --- | --- | --- |
| 1-12 | Floor 1 Workstations | Cat6 |
| 13-24 | Floor 2 Workstations | Cat6 |
| 25-36 | Floor 3 Workstations | Cat6 |
| 37-48 | Edit Bay Stations | Cat6 |

PP3 - Infrastructure Patch Panel:

| Port | Destination | Type |
| --- | --- | --- |
| 1-6 | Wireless APs | Cat6 |
| 7-12 | Servers/Storage | Cat6a |
| 13-16 | Management/OOB | Cat6 |
| 17-24 | Future Expansion | - |

### 3.3 Cable Labeling Scheme

Label Format: {CABLE-ID}-{FROM}-{TO}

Examples:

`C-003-FG-PRI-SW1-P1`

`C-007-HD6500-SW1-P49`

`C-017-SW1-P20-AP01`

Label Placement:

Both ends of every cable

5cm from connector

Facing outward for visibility

Color Coding:

| Cable Type | Color |
| --- | --- |
| WAN/Internet | Yellow |
| Trunk/Uplink | Red |
| Production LAN | Blue |
| Storage (10GbE) | Green |
| Management | Orange |
| Guest/WiFi | Purple |
| Power | Black |

### 3.4 Testing Procedures

Pre-Installation Testing:

| Test | Tool | Pass Criteria |
| --- | --- | --- |
| Continuity | Fluke DSX-5000 | No opens/shorts |
| Wire Map | Fluke DSX-5000 | T568B pinout correct |
| Length Verification | Fluke DSX-5000 | Within ±3m of spec |
| Return Loss | Fluke DSX-5000 | Cat6: >12dB, Cat6a: >12dB |
| NEXT | Fluke DSX-5000 | Cat6: >30dB, Cat6a: >30dB |

Post-Installation Testing:

| Test | Command/Tool | Expected Result |
| --- | --- | --- |
| LACP Status | `show lacp aggregates` | All members Active |
| VSX Status | `show vsx status` | In-Sync |
| VLAN Trunking | `show vlan trunk` | All VLANs passing |
| MTU Verification | `ping -M do -s 8972` | Success with 9000 MTU |
| Speed Test | `iperf3` | 9.5+ Gbps on 10GbE |
| Failover Test | Disconnect link | <2 sec failover |

### 3.5 Cable Plant Design Philosophy ⭐ ENHANCED

#### 3.5.1 Why Cat6a (Not Cat6 or Cat7)

Distance Limitations Analysis:

| Cable Type | Max Speed | Max Distance | 10GbE Support | PoE++ Support |
| --- | --- | --- | --- | --- |
| **Cat5e** | 1 Gbps | 100m | No | Yes (limited) |
| **Cat6** | 1 Gbps | 100m | 55m only | Yes |
| **Cat6a** | 10 Gbps | **100m** | **Yes** | **Yes (improved)** |
| **Cat7** | 10 Gbps | 100m | Yes | Yes |
| **Cat8** | 25/40 Gbps | 30m | Yes | Yes |

Cost Comparison (per 1000ft/305m box):

| Cable Type | Cost (INR) | Installation Cost | Total per Drop |
| --- | --- | --- | --- |
| Cat6 | ₹18,000 | ₹2,500 | ₹4,500 |
| **Cat6a** | **₹28,000** | **₹3,000** | **₹6,000** |
| Cat7 | ₹45,000 | ₹4,500 | ₹9,500 |
| Cat8 | ₹85,000 | ₹5,000 | ₹15,500 |

Future-Proofing Analysis:

Expected Lifecycle: 10-15 years
Network Speed Trends:
├── 2015: 1 Gbps standard
├── 2020: 1 Gbps standard, 10 Gbps emerging
├── 2025: 10 Gbps becoming standard for workstations
└── 2030: 10 Gbps expected standard, 25 Gbps emerging

Cat6 Limitations:
├── 10 Gbps only to 55 meters (not full 100m)
├── Higher error rates at 10 Gbps
├── No headroom for future speeds
└── Would require re-cabling for 10 Gbps at distance

Cat6a Advantages:
├── 10 Gbps to full 100 meters
├── Lower crosstalk, better signal integrity
├── Supports PoE++ (90W) with less heat
├── Headroom for future 25 Gbps (short distances)
└── ANSI/TIA-568.2-D standard (approved for 10GBase-T)

Why Not Cat7:

Not recognized by TIA/EIA standards (European ISO standard only)

Requires GG45 or TERA connectors (not compatible with RJ45)

70% more expensive than Cat6a

No performance benefit over Cat6a for 10 Gbps

Why Not Cat8:

Limited to 30 meters (insufficient for many building runs)

Designed for data center rack-to-rack, not horizontal distribution

2.5× cost of Cat6a

25 Gbps capability wasted on current endpoints

Design Trade-off: We chose Cat6a as the sweet spot — it supports 10 Gbps to full distance, is standards-compliant, and costs only 33% more than Cat6 while providing 3× the bandwidth headroom.

#### 3.5.2 Fiber vs. Copper Decision Matrix

When We Use Fiber:

| Scenario | Cable Type | Why Fiber |
| --- | --- | --- |
| ISL Links (SW1-SW2) | OM4 Multimode | Distance immunity, no EMI |
| Future 25GbE upgrade | OM4/OS2 | Higher bandwidth capability |
| Building-to-building | OS2 Single-mode | Long distance (up to 10km) |
| High EMI environments | OM4/OS2 | Electrical isolation |

When We Use Copper:

| Scenario | Cable Type | Why Copper |
| --- | --- | --- |
| Server connections (<10m) | Cat6a | Lower cost, easier termination |
| Workstation drops (<100m) | Cat6a | Standard RJ45 connectors |
| PoE devices (APs, cameras) | Cat6a | Power + data on same cable |
| Management ports | Cat6 | Cost-effective for 1 Gbps |

Fiber Type Selection:

flowchart TD
    A[Fiber Requirement] --> B{Distance?}
    B -->|< 100m| C{Speed?}
    B -->|> 100m| D[OS2 Single-Mode]
    
    C -->|10 Gbps| E[OM3 Multimode]
    C -->|25/40 Gbps| F[OM4 Multimode]
    C -->|100 Gbps| F
    
    D --> G[Long-Range Transceivers]
    E --> H[SR Transceivers]
    F --> I[SR/BiDi Transceivers]

Why OM4 (Not OM3) for ISL Links:

| Specification | OM3 | OM4 |
| --- | --- | --- |
| Bandwidth @ 850nm | 2,000 MHz-km | 4,700 MHz-km |
| 10GbE Distance | 300m | 550m |
| 40GbE Distance | 100m | 150m |
| 100GbE Distance | 70m | 150m |
| Price (per meter) | ₹180 | ₹220 |

OM4 provides 2.5× bandwidth headroom

Future-proof for 25/40 Gbps switch upgrades

Price difference of ₹40/meter is negligible for 10m runs

Design Trade-off: We use fiber only where necessary (ISL links for VSX) and copper everywhere else for cost-effectiveness and ease of installation.

#### 3.5.3 Cable Management Philosophy

Color Coding Scheme Explanation:

| Color | Purpose | Rationale |
| --- | --- | --- |
| **Yellow** | WAN/Internet | Caution — external connectivity |
| **Red** | Trunk/Uplink | Critical infrastructure — high visibility |
| **Blue** | Production LAN | Standard network color |
| **Green** | Storage | "Go" — high-performance data |
| **Orange** | Management | Distinct from production traffic |
| **Purple** | Guest/WiFi | Non-corporate, lower priority |
| **Black** | Power | Standard electrical color |
| **White/Grey** | Future use | Reserved for expansion |

Why This Color Scheme:

Follows ANSI/TIA-606-C standard where applicable

Matches common industry conventions (blue for LAN, yellow for WAN)

Provides immediate visual identification during troubleshooting

Reduces human error during moves/adds/changes

Labeling Convention Explanation:

Format: {CABLE-ID}-{FROM}-{TO}

Example: C-007-HD6500-P1-SW1-P49

C-007      = Cable ID (sequential numbering)
HD6500-P1  = Source: HD6500, Port 1
SW1-P49    = Destination: Switch 1, Port 49

Benefits:
├── Unique identifier for asset tracking
├── Clear source/destination at both ends
├── Sortable by cable ID in spreadsheets
├── Identifies cable type from ID range
└── Supports barcoding/QR codes

Patch Panel Layout Rationale:

PP1 - Network Patch Panel:
├── Top half (1-24): Core infrastructure
│   ├── 1-4: ISP connections (entry point)
│   ├── 5-12: Firewall ports (security boundary)
│   └── 13-24: Switch uplinks (distribution)
└── Bottom half (25-48): Future expansion

PP2 - Workstation Patch Panel:
├── Organized by floor for cable management
├── 1-12: Floor 1 (shortest runs, top of panel)
├── 13-24: Floor 2 (medium runs)
├── 25-36: Floor 3 (longest runs)
└── 37-48: Edit bay (high-density area)

PP3 - Infrastructure:
├── 1-6: Wireless APs (PoE connections)
├── 7-12: Servers/Storage (10GbE connections)
└── 13-16: Management/OOB (segregated access)

Why This Layout:

Groups related connections for easier troubleshooting

Separates infrastructure (PP1, PP3) from user access (PP2)

Physical separation reduces accidental disconnection

Top-to-bottom matches cable tray routing

Cable Management Best Practices Implemented:

Service Loop: 1 meter service loop at each end for re-termination

Strain Relief: Velcro straps (not zip ties) to prevent crushing

Bend Radius: Minimum 4× cable diameter (25mm for Cat6a)

Vertical Management: D-rings every 1U for vertical runs

Horizontal Management: 1U brush strips between patch panels

Documentation: As-built drawings updated same day as changes

Design Trade-off: We invested in comprehensive labeling and color-coding upfront to reduce operational costs over the 10-15 year cable lifecycle. A misidentified cable during an outage can cost hours of downtime.

## 4. Redundancy Scenarios

### 4.1 Scenario A: Single ISP Failure (SD-WAN Failover)

Trigger: ISP1 (Airtel) link failure detected by SD-WAN performance SLA.

Detection Time: 3-5 seconds (based on 3 consecutive ping failures)

Automatic Actions:

SD-WAN marks ISP1 member as "dead"

All existing sessions failed over to ISP2

New sessions routed via ISP2

DNS resolution continues via secondary DNS

Manual Actions Required:

Contact ISP1 for ETA

Monitor bandwidth utilization on ISP2

Consider rate-limiting non-critical traffic

Recovery:

ISP1 link restored

SD-WAN detects link up

Sessions gradually rebalanced (slow return)

Full redundancy restored

Impact: Zero downtime (session pickup enabled)

### 4.2 Scenario B: Single FortiGate Failure (HA Failover)

Trigger: Primary FortiGate hardware failure or manual failover.

Detection Time: < 1 second (heartbeat timeout)

Automatic Actions:

Secondary FortiGate detects primary failure

Secondary assumes active role

VRRP virtual MAC moves to secondary

Session table synchronized (no re-authentication)

ZTNA connections maintained

Manual Actions Required:

Investigate primary unit failure

If hardware failure, initiate RMA

Review logs on FortiAnalyzer

Recovery:

Replace/repair primary unit

Primary boots and joins HA cluster

Configuration syncs automatically

Optional manual failback

Impact: < 2 seconds (sub-second with session pickup)

### 4.3 Scenario C: Single Switch Failure (VSX/LACP Failover)

Trigger: SW1 hardware failure or maintenance.

Detection Time: < 1 second (VSX keepalive timeout)

Automatic Actions:

SW2 detects SW1 failure via keepalive

SW2 assumes primary gateway role for all VLANs

LACP on SW1 links times out

Traffic flows through SW2 only

APs with dual-home fail over to SW2

Manual Actions Required:

Replace/repair SW1

Verify all connections operational

Recovery:

SW1 replaced and powered on

VSX sync re-establishes

MAC tables synchronize

LACP members rejoin

Traffic rebalances

Impact: < 1 second for routed traffic; wireless may have brief association

### 4.4 Scenario D: HD6500 Drive Failure (RAID6 Rebuild)

Trigger: DSM alert for drive failure in HD6500.

Detection Time: Immediate (SMART monitoring)

Automatic Actions:

DSM marks drive as crashed

RAID6 continues operation (2-drive fault tolerance)

Hot spare activates (if configured)

Rebuild begins automatically

Manual Actions Required:

Order replacement drive

Schedule drive replacement during maintenance window

Monitor rebuild progress

RAID6 Rebuild Details:

| Parameter | Value |
| --- | --- |
| **RAID Type** | RAID6 (56+4) |
| **Usable Drives** | 56 |
| **Parity Drives** | 4 |
| **Fault Tolerance** | 2 drives |
| **Rebuild Speed** | ~200 MB/s |
| **56TB Drive Rebuild** | ~78 hours |
| **Impact During Rebuild** | 10-15% performance degradation |

Impact: Zero downtime; reduced performance during rebuild

### 4.5 Scenario E: Complete Site A Failure (DR Failover)

Trigger: Complete Site A loss (fire, flood, extended power outage).

Detection Time: Site B monitoring alerts within 5 minutes

Manual Failover Procedure:

| Step | Action | Owner | ETA |
| --- | --- | --- | --- |
| 1 | Confirm Site A total loss | IT Manager | T+0 |
| 2 | Initiate DR declaration | IT Manager | T+5 min |
| 3 | Promote Site B NAS via Replication Manager | SysAdmin | T+10 min |
| 4 | Update FortiGate ZTNA profiles to Site B | Network Admin | T+15 min |
| 5 | Update DNS records (if using internal DNS) | SysAdmin | T+20 min |
| 6 | Notify users of new ZTNA gateway | IT Manager | T+25 min |
| 7 | Verify user connectivity | SysAdmin | T+30 min |
| 8 | Begin recovery operations at Site A | All | T+ongoing |

Recovery Time Objective (RTO): < 30 minutes

Recovery Point Objective (RPO):

| Data Type | RPO | Achieved Via |
| --- | --- | --- |
| Active Projects | 15 minutes | Real-time replication |
| Archive Data | 4 hours | Scheduled replication |
| System Configs | 24 hours | Nightly config backup |

## 5. Wireless Infrastructure

### 5.1 FortiAP Model Recommendations

| Model | Deployment Location | Quantity | Specifications |
| --- | --- | --- | --- |
| **FortiAP 431F** | Office Floors 1-3 | 4 | Wi-Fi 6, 4x4:4, 2.97 Gbps, Dual 5GHz |
| **FortiAP 431F** | Edit Bays | 2 | Wi-Fi 6, 4x4:4, 2.97 Gbps, High Density |

FortiAP 431F Specifications:

| Specification | Value |
| --- | --- |
| **Wi-Fi Standard** | 802.11ax (Wi-Fi 6) |
| **Frequency Bands** | 2.4 GHz, 5 GHz (Dual 5GHz capable) |
| **Max Data Rate** | 2.97 Gbps |
| **MIMO** | 4x4:4 (5GHz), 2x2:2 (2.4GHz) |
| **Max Clients** | 512 per radio |
| **Ethernet Ports** | 1x 2.5GbE, 1x GE |
| **PoE Requirement** | 802.3at (PoE+) or 802.3bt (PoE++) |
| **Controller** | FortiGate integrated (no extra license) |
| **Antennas** | Internal omni-directional |

### 5.2 SSID Configuration

| SSID | VLAN | Security | Authentication | Bandwidth Limit |
| --- | --- | --- | --- | --- |
| B2H-Corporate | 20 | WPA3-Enterprise | 802.1X + RADIUS | Unlimited |
| B2H-Guest | 50 | WPA2-Personal | Captive Portal | 50 Mbps |
| B2H-IoT | 60 | WPA2-Enterprise | MAC + Certificate | 10 Mbps |

B2H-Corporate SSID Details:

| Setting | Value |
| --- | --- |
| **Broadcast SSID** | Yes |
| **Security Mode** | WPA3-Enterprise (192-bit mode) |
| **Encryption** | GCMP-256 |
| **Key Management** | 802.1X (EAP-TLS preferred) |
| **RADIUS Server** | FANALYZER-01 (FortiAuthenticator) |
| **RADIUS Accounting** | Enabled |
| **Dynamic VLAN** | Disabled (static VLAN 20) |
| **Client Isolation** | Disabled (internal access required) |
| **Airtime Fairness** | Enabled |
| **Band Steering** | Enabled (5GHz preferred) |

### 5.3 RADIUS Server Configuration

RADIUS Configuration:

| Parameter | Value |
| --- | --- |
| **Server** | FANALYZER-01 (FortiAuthenticator VM) |
| **IP Address** | 10.10.20.10 |
| **Authentication Port** | 1812 |
| **Accounting Port** | 1813 |
| **Shared Secret** | [REDACTED - stored in Vault] |
| **Timeout** | 5 seconds |
| **Retries** | 3 |
| **NAS Identifier** | B2H-WLAN |

Authentication Flow:

User connects to B2H-Corporate SSID

FortiAP forwards EAP request to FortiGate

FortiGate proxies to FortiAuthenticator (RADIUS)

FortiAuthenticator validates against AD/LDAP

MFA challenge sent via FortiToken push

Upon success, access granted to VLAN 20

### 5.6 Wireless Architecture Reasoning ⭐ ENHANCED

#### 5.6.1 Why FortiAP (Not Aruba, Cisco, Ubiquiti)

Vendor Comparison Matrix:

| Factor | FortiAP 431F | Aruba AP-535 | Cisco 9130 | Ubiquiti U6-Enterprise |
| --- | --- | --- | --- | --- |
| **AP Price** | ₹65,000 | ₹85,000 | ₹1,05,000 | ₹38,000 |
| **Controller Required** | No (FortiGate native) | Yes (₹8-15L) | Yes (₹12-20L) | Yes (Cloud Key/UDM) |
| **Total Cost (6 APs)** | ₹3.9 Lakhs | ₹13.1 Lakhs | ₹17.3 Lakhs | ₹4.8 Lakhs* |
| **Wi-Fi 6 Support** | Yes | Yes | Yes | Yes |
| **4x4 MIMO** | Yes | Yes | Yes | Yes |
| **Dual 5GHz** | Yes | Yes | Yes | No |
| **Enterprise Security** | Yes | Yes | Yes | Limited |
| **Support Quality** | Good | Excellent | Excellent | Community |

*Ubiquiti total excludes hidden costs of cloud management and limited enterprise features

Total Cost of Ownership (5-Year):

FortiAP Solution:
├── 6 APs: ₹3.9 Lakhs
├── Controller: ₹0 (built into FortiGate)
├── Licenses: ₹0 (included in UTP)
├── Support: ₹1.2 Lakhs
└── 5-Year TCO: ₹5.1 Lakhs

Aruba Solution:
├── 6 APs: ₹5.1 Lakhs
├── Controller (7205): ₹12.0 Lakhs
├── Licenses (6 APs): ₹3.6 Lakhs
├── Support: ₹4.2 Lakhs
└── 5-Year TCO: ₹24.9 Lakhs

Key Advantage — FortiGate Integration:

flowchart LR
    subgraph "Fortinet Ecosystem"
        FG[FortiGate 120G<br/>Firewall + Controller]
        FAP[FortiAP 431F<br/>Managed APs]
        FC[FortiClient<br/>Endpoint Agent]
    end
    
    subgraph "Aruba/Cisco Ecosystem"
        FW[Firewall<br/>Separate]
        AC[Controller<br/>Hardware/Virtual]
        AP[Access Points]
        EP[Endpoints<br/>Separate agents]
    end
    
    FG <-->|Single Management| FAP
    FG <-->|Unified Policy| FC
    
    FW -.->|No Integration| AC
    AC <-->|Separate| AP
    FW -.->|No Integration| EP

Why Not Ubiquiti (Despite Lower Price):

Enterprise Security Gap: No WPA3-Enterprise support, limited RADIUS attributes

No WIDS/WIPS: Rogue AP detection not enterprise-grade

Cloud Dependency: Management requires cloud connection (data residency concern)

Support Model: Community-based, no SLA for critical issues

Integration: No seamless integration with FortiGate security policies

Design Trade-off: FortiAP costs 5× less than Aruba/Cisco when controller costs are included, while providing seamless security integration. We sacrificed some advanced RF features for operational simplicity and cost savings.

#### 5.6.2 AP Placement Methodology

Coverage Calculation — Square Feet per AP:

Office Environment (Floor 1):
├── Total Area: 4,000 sq ft
├── Recommended Coverage: 1 AP per 1,500 sq ft
├── Calculation: 4,000 / 1,500 = 2.67 APs
├── Deployed: 2 APs (slightly under for cost efficiency)
└── Verification needed via site survey

Production Environment (Floor 2):
├── Total Area: 3,500 sq ft
├── Higher density required (media equipment)
├── Recommended: 1 AP per 1,200 sq ft
├── Calculation: 3,500 / 1,200 = 2.92 APs
├── Deployed: 2 APs (acceptable with good placement)
└── Edit bays may need additional coverage

Edit Bay:
├── Total Area: 2,000 sq ft
├── High-density requirement
├── Recommended: 1 AP per 1,000 sq ft
├── Deployed: 1 AP (center-mounted for coverage)
└── Critical area — site survey mandatory

Density Calculation — Users per AP:

| Area | Max Concurrent Users | FortiAP 431F Capacity | Headroom |
| --- | --- | --- | --- |
| Floor 1 | 15 | 512 | 34× |
| Floor 2 | 12 | 512 | 43× |
| Floor 3 | 8 | 512 | 64× |
| Edit Bay | 10 | 512 | 51× |

Wi-Fi 6 OFDMA handles high density efficiently

Current design has 30×+ headroom for growth

Design Trade-off: We planned for 6 APs based on coverage calculations, but strongly recommend an Ekahau site survey to validate. The cost of one survey (₹1.5L) is far less than the cost of poor coverage (productivity loss, recabling).

#### 5.6.3 WPA3-Enterprise Rationale

Security Protocol Comparison:

| Protocol | Encryption | Authentication | Security Level | Use Case |
| --- | --- | --- | --- | --- |
| WPA2-Personal | AES-CCMP | PSK (password) | Moderate | Home/Small office |
| WPA3-Personal | GCMP | SAE (improved PSK) | Good | Advanced home |
| WPA2-Enterprise | AES-CCMP | 802.1X/RADIUS | Strong | Corporate |
| **WPA3-Enterprise** | **GCMP-256** | **802.1X/RADIUS** | **Very Strong** | **High-security corporate** |

Why Not WPA2-Personal for Corporate:

WPA2-Personal Risks:
├── Single password for all users
├── Password sharing risk
├── No user accountability (logs show shared key)
├── Cannot revoke individual access
├── Offline dictionary attacks possible
└── Not compliant with ISO 27001 A.9.2

WPA3-Enterprise Benefits:
├── Individual credentials per user
├── Central authentication (RADIUS)
├── Full audit trail (who connected when)
├── Instant revocation capability
├── Mutual authentication (client verifies network)
└── ISO 27001 compliant

Why Not WPA3-Personal (SAE):

SAE improves upon WPA2-Personal but still uses shared credentials

No central authentication = no audit trail

B2H Studios needs per-user accountability for media access

Client requirement: ISO 27001 compliance mandates individual authentication

802.1X Benefits for B2H Studios:

| Feature | Benefit for B2H Studios |
| --- | --- |
| Per-user credentials | Individual accountability for media access |
| Central authentication | Manage all users from FortiAuthenticator |
| MFA integration | FortiToken push for sensitive areas |
| Dynamic VLAN assignment | Could separate editors from admin in future |
| Certificate-based auth | TPM-bound certificates prevent credential theft |

Design Trade-off: WPA3-Enterprise requires RADIUS infrastructure and certificate deployment, but provides the security and audit capabilities required for a media production environment handling sensitive content.

#### 5.6.4 RADIUS Architecture

Why FortiAuthenticator (Not Microsoft NPS, FreeRADIUS):

| Factor | FortiAuthenticator | Microsoft NPS | FreeRADIUS |
| --- | --- | --- | --- |
| **Integration** | Native FortiGate | Windows Server | Manual config |
| **MFA Support** | Built-in FortiToken | Requires Azure AD | Requires plugin |
| **Certificate Management** | Integrated PKI | Separate AD CS | Manual OpenSSL |
| **Guest Portal** | Built-in | Not available | Custom development |
| **Reporting** | Built-in dashboards | Event log only | Custom scripts |
| **Cost** | ₹1.8L (virtual) | ₹0 (if have Windows) | ₹0 |
| **Support** | Fortinet TAC | Microsoft | Community |
| **Deployment Time** | 2 hours | 8+ hours | 2-3 days |

Authentication Flow Diagram:

sequenceDiagram
    participant User as User Device
    participant AP as FortiAP
    participant FG as FortiGate
    participant FA as FortiAuthenticator
    participant AD as Active Directory
    
    Note over User,AD: WPA3-Enterprise 802.1X Authentication
    
    User->>AP: Associate with B2H-Corporate
    AP->>FG: EAPOL-Start (802.1X)
    FG->>FA: RADIUS Access-Request
    
    alt EAP-TLS (Certificate)
        FA->>User: EAP-Request/Identity
        User->>FA: Client Certificate + Identity
        FA->>FA: Validate Certificate (PKI)
    else PEAP-MSCHAPv2 (Username/Password)
        FA->>User: EAP-Request/Identity
        User->>FA: Username
        FA->>User: TLS Tunnel Setup
        User->>FA: Encrypted Password
        FA->>AD: LDAP Bind (verify credentials)
        AD->>FA: Success + Group Info
    end
    
    FA->>FA: Check MFA Requirement
    FA->>User: FortiToken Push
    User->>FA: MFA Approval
    
    FA->>FG: RADIUS Access-Accept<br/>+ VLAN 20 + ACL
    FG->>AP: EAP-Success
    AP->>User: Association Complete (VLAN 20)
    
    Note over User: Full Network Access Granted

Failover Design:

Primary RADIUS: FortiAuthenticator on R760 (Site A)
├── IP: 10.10.20.10
├── Status: Active
└── Timeout: 5 seconds

Secondary RADIUS: FortiAuthenticator on R760 (Site B DR)
├── IP: 10.10.20.10 (same, different site)
├── Status: Standby
├── Activated during Site A failure
└── Replication: Config synced every 15 minutes

Tertiary (Local Fallback): FortiGate Local Users
├── Enabled: Yes
├── Use Case: RADIUS unreachable
└── Limitation: No MFA, limited audit

Design Trade-off: FortiAuthenticator adds ₹1.8L cost vs. free Microsoft NPS, but provides integrated MFA, better reporting, and unified support. For a security-conscious media studio, this is justified.

## 6. Server Infrastructure

### 6.1 Dell PowerEdge R760 Specifications

| Component | Specification |
| --- | --- |
| **Model** | Dell PowerEdge R760 |
| **Form Factor** | 2U Rackmount |
| **CPU** | 2x Intel Xeon Silver 4410Y (12-core, 2.0GHz, 30MB Cache) |
| **Total Cores** | 24 cores / 48 threads |
| **Memory** | 128GB DDR5-4800 ECC (8x 16GB) |
| **Memory Slots** | 32 (expandable to 4TB) |
| **Storage Controller** | PERC H965i 12Gbps SAS RAID Controller |
| **Boot Drives** | 2x 480GB SATA SSD (RAID 1) |
| **Data Drives** | 8x 1.2TB 10K RPM SAS 12Gbps |
| **RAID Configuration** | RAID 10 (Striped Mirrors) |
| **Usable Storage** | 4.8TB (8x 1.2TB / 2 for RAID 10) |
| **Network** | 2x 10GbE SFP+ (Intel X710), 2x 1GbE RJ45 (Broadcom) |
| **OOB Management** | iDRAC9 Enterprise with dedicated port |
| **Power** | 2x 1100W Titanium redundant PSU |
| **Expansion** | 8x PCIe Gen5 slots |
| **Operating System** | VMware vSphere 8.0 Update 2 |

### 6.2 Virtualization Plan

Platform: VMware vSphere 8.0 Update 2

Licensing: vSphere Standard (16-core kit) + vCenter Server Foundation

Cluster Configuration:

| Parameter | Value |
| --- | --- |
| **Cluster Name** | B2H-Compute-01 |
| **ESXi Hosts** | 1 (Site A), 1 (Site B - DR) |
| **HA Enabled** | Yes |
| **DRS Enabled** | Yes (Manual mode) |
| **EVC Mode** | Intel Sapphire Rapids |

Resource Allocation:

| Resource | Total | Reserved for VMs | Overhead |
| --- | --- | --- | --- |
| **CPU Cores** | 24 | 20 | 4 (ESXi) |
| **Memory** | 128GB | 112GB | 16GB (ESXi) |
| **Storage** | 4.8TB | 4.0TB | 800GB (reservation) |

### 6.3 VM Allocation Table

| VM Name | vCPU | RAM | Storage | OS | Purpose | Network |
| --- | --- | --- | --- | --- | --- | --- |
| **SDCX-01** | 8 | 32GB | 500GB SSD | Windows Server 2022 | Signiant Jet SDCX Server | VLAN 10 (DMZ) |
| **FANALYZER-01** | 4 | 16GB | 1TB SSD | FortiAnalyzer VM | Centralized logging & SIEM | VLAN 40 (Mgmt) |
| **EMS-01** | 4 | 16GB | 200GB SSD | FortiClient EMS | Endpoint management | VLAN 40 (Mgmt) |
| **VAULT-01** | 4 | 16GB | 100GB SSD | HashiCorp Vault | Secrets management | VLAN 40 (Mgmt) |
| **KSC-01** | 4 | 16GB | 200GB SSD | Windows Server 2022 | Kaspersky Security Centre | VLAN 40 (Mgmt) |
| **RADIUS-01** | 2 | 8GB | 100GB SSD | FortiAuthenticator | 802.1X/RADIUS auth | VLAN 20 (Prod) |
| **DNS-01** | 2 | 4GB | 50GB SSD | Windows Server 2022 | Internal DNS/DHCP | VLAN 20 (Prod) |
| **MON-01** | 2 | 8GB | 500GB SSD | Ubuntu 22.04 LTS | Zabbix monitoring | VLAN 40 (Mgmt) |

Total Resource Consumption:

| Resource | Allocated | Available | Utilization |
| --- | --- | --- | --- |
| **vCPU** | 30 | 48 (with HT) | 62.5% |
| **RAM** | 116GB | 128GB | 90.6% |
| **Storage** | 2.67TB | 4.8TB | 55.6% |

### 6.6 Compute Infrastructure Reasoning ⭐ ENHANCED

#### 6.6.1 Why Dell R760 (Not HPE DL380, Lenovo SR650)

Price-Performance Comparison:

| Component | Dell R760 | HPE DL380 Gen11 | Lenovo SR650 V3 |
| --- | --- | --- | --- |
| **List Price** | ₹6.8 Lakhs | ₹7.4 Lakhs | ₹6.5 Lakhs |
| **CPU** | 2× Xeon Silver 4410Y | 2× Xeon Silver 4410Y | 2× Xeon Silver 4410Y |
| **Memory** | 128GB DDR5 | 128GB DDR5 | 128GB DDR5 |
| **RAID Controller** | PERC H965i | Smart Array P408i | ThinkSystem RAID 9350-16i |
| **Drive Bays** | 8× 2.5" + 2× M.2 | 8× 2.5" + 2× M.2 | 8× 2.5" + 2× M.2 |
| **Network** | 2× 10GbE + 2× 1GbE | 2× 1GbE (10GbE extra) | 2× 1GbE (10GbE extra) |
| **OOB Management** | iDRAC9 Enterprise | iLO 6 Advanced | XClarity Enterprise |
| **Warranty** | 3-year NBD | 3-year NBD | 3-year NBD |
| **5-Year TCO** | ₹10.2 Lakhs | ₹11.8 Lakhs | ₹10.8 Lakhs |

Service Quality in India:

| Aspect | Dell | HPE | Lenovo |
| --- | --- | --- | --- |
| Service Centers | 25+ cities | 20+ cities | 15 cities |
| 4-Hour Response | Available | Available | Limited |
| Parts Availability | Excellent | Very Good | Good |
| TAC Quality | Excellent | Excellent | Good |
| Escalation Speed | Fast | Fast | Moderate |
| Local Presence | Mumbai, Delhi, Bangalore | Mumbai, Delhi, Bangalore | Mumbai, Delhi |

iLO vs. iDRAC vs. XClarity Comparison:

| Feature | Dell iDRAC9 | HPE iLO 6 | Lenovo XClarity |
| --- | --- | --- | --- |
| **Web Interface** | Excellent | Excellent | Good |
| **Virtual Console** | HTML5 (no Java) | HTML5 (no Java) | Requires plugin |
| **Mobile App** | Yes (iDRAC Mobile) | Yes (HPE Insight) | Limited |
| **API/Automation** | Redfish + RACADM | Redfish + iLOrest | REST API |
| **License Cost** | Included (Enterprise) | Extra (₹45K) | Included |
| **Security Features** | SIEM integration, MFA | SIEM integration | Basic |
| **Remote Firmware Update** | Yes | Yes | Limited |

Why Dell for B2H Studios:

Best Value: Lowest TCO among the three major vendors

Included 10GbE: Network ports are included (HPE/Lenovo charge extra)

iDRAC Enterprise Included: No additional cost for full OOB management

Largest Service Network: 25+ cities in India for fastest response

Proven Reliability: PowerEdge series has excellent track record

Design Trade-off: Dell provides the best price-performance ratio with included enterprise features. HPE offers slightly better support quality, but the 16% cost premium is not justified for this environment.

#### 6.6.2 VM Sizing Methodology

How We Calculated vCPU/RAM for Each VM:

| VM | Base Requirements | Growth Headroom | Final Allocation |
| --- | --- | --- | --- |
| **SDCX-01** | 6 vCPU / 24GB RAM | 33% | 8 vCPU / 32GB RAM |
| **FANALYZER-01** | 3 vCPU / 12GB RAM | 33% | 4 vCPU / 16GB RAM |
| **EMS-01** | 3 vCPU / 12GB RAM | 33% | 4 vCPU / 16GB RAM |
| **VAULT-01** | 3 vCPU / 12GB RAM | 33% | 4 vCPU / 16GB RAM |
| **KSC-01** | 3 vCPU / 12GB RAM | 33% | 4 vCPU / 16GB RAM |
| **RADIUS-01** | 1.5 vCPU / 6GB RAM | 33% | 2 vCPU / 8GB RAM |
| **DNS-01** | 1.5 vCPU / 3GB RAM | 33% | 2 vCPU / 4GB RAM |
| **MON-01** | 1.5 vCPU / 6GB RAM | 33% | 2 vCPU / 8GB RAM |

Resource Contention Analysis:

CPU Overcommit Ratio:
├── Allocated vCPUs: 30
├── Physical Cores: 24
├── Threads (with HT): 48
├── Overcommit Ratio: 30/24 = 1.25:1
└── Status: ✅ Conservative (recommended < 3:1)

Memory Overcommit:
├── Allocated RAM: 116GB
├── Physical RAM: 128GB
├── Overcommit: None (reservation recommended)
└── Status: ✅ No swapping risk

Storage IOPS:
├── RAID 10 provides ~2,000 IOPS
├── Estimated VM requirement: ~1,500 IOPS
├── Headroom: 25%
└── Status: ✅ Adequate for workload

Growth Headroom Calculation:

Current Utilization (Year 1):
├── vCPU: 62.5% of available
├── RAM: 90.6% of available
└── Storage: 55.6% of available

Projected Growth (Year 3):
├── Additional users: +60%
├── Additional VMs needed: 4-6
├── RAM will be constraint (predicted 95% utilization)
└── Upgrade path: Add 128GB RAM (₹1.2L)

Projected Growth (Year 5):
├── May need second host for HA
├── Current host becomes capacity constrained
└── Planning: Budget for R760 Gen2 in Year 4

Design Trade-off: We sized VMs with 33% headroom over vendor minimums. While this increases initial cost, it prevents performance issues and reduces support tickets.

#### 6.6.3 Why VMware vSphere (Not Proxmox, Hyper-V)

Enterprise Features Comparison:

| Feature | VMware vSphere 8 | Proxmox VE 8 | Microsoft Hyper-V |
| --- | --- | --- | --- |
| **Live Migration** | vMotion (seamless) | Live Migrate (some downtime) | Live Migration (requires shared storage) |
| **High Availability** | Built-in (automatic restart) | Manual/Scripted | Built-in (Windows Server only) |
| **DRS (Load Balancing)** | Automatic | Manual | Semi-Automatic |
| **Storage vMotion** | Yes (no downtime) | No | Yes |
| **Backup APIs** | VADP (industry standard) | Proxmox Backup | VSS-based |
| **Enterprise Support** | Excellent | Community/Commercial | Good |
| **Ecosystem** | Massive (Veeam, etc.) | Growing | Windows-centric |
| **Learning Curve** | Moderate | Steep | Low (if Windows admin) |
| **Cost (25 VMs)** | ₹4.5L/year | ₹0 (or ₹1.2L support) | ₹0 (with Windows DC) |

Support Ecosystem:

VMware Ecosystem:
├── Veeam Backup (industry standard)
├── Zerto DR (enterprise DR)
├── vRealize (monitoring)
├── NSX (network virtualization)
├── Thousands of certified partners
└── Extensive documentation

Proxmox Ecosystem:
├── Proxmox Backup Server
├── Community plugins
├── Limited commercial support
├── Smaller partner network
└── Requires more self-support

Staff Skillset Considerations:

VMware is the dominant enterprise virtualization platform

Easier to hire/train staff on VMware than Proxmox

B2H Studios' IT staff likely has Windows/Linux background

Hyper-V requires Windows Server expertise which they may lack

Why Not Proxmox:

No live migration without shared storage (requires Ceph/RBD)

Limited enterprise backup integration (no Veeam support)

Support is community-based unless you pay for Enterprise

Smaller ecosystem of third-party tools

Would save ₹4.5L/year but increase operational risk

Why Not Hyper-V:

Requires Windows Server licensing (not included in our BOM)

Less mature Linux VM support (many security tools are Linux-based)

Smaller ecosystem for multi-cloud management

Limited macOS support (some creative tools may need it)

Design Trade-off: VMware costs ₹4.5L annually vs. free Proxmox, but provides enterprise-grade features, extensive ecosystem, and easier staffing. For a 24/7 production environment, this is justified.

#### 6.6.4 RAID10 for VMs Explanation

Why RAID10 (Not RAID5/6) for VM Storage:

| RAID Level | Usable Capacity | Write Performance | Read Performance | Fault Tolerance | Best For |
| --- | --- | --- | --- | --- | --- |
| **RAID 5** | 87.5% (7/8) | Poor (write penalty 4x) | Good | 1 drive | Archive data |
| **RAID 6** | 75% (6/8) | Poor (write penalty 6x) | Good | 2 drives | Large files |
| **RAID 10** | 50% (4/8) | **Excellent** (2x) | **Excellent** (2x) | 1 per mirror | **VMs/Databases** |

IOPS per VM Calculation:

VM Workload Profile:
├── SDCX-01 (Signiant): 200 IOPS (file transfer)
├── FANALYZER-01: 100 IOPS (logging)
├── EMS-01: 50 IOPS (management)
├── VAULT-01: 20 IOPS (secrets - mostly RAM)
├── KSC-01: 150 IOPS (AV scanning)
├── RADIUS-01: 30 IOPS (auth - mostly RAM)
├── DNS-01: 20 IOPS (DNS - mostly RAM)
├── MON-01 (Zabbix): 100 IOPS (database)
└── Total Required: ~670 IOPS

RAID 10 IOPS Capability:
├── 8× 10K SAS drives
├── Raw IOPS per drive: ~140
├── RAID 10 read multiplier: 2×
├── RAID 10 write multiplier: 2×
├── Total Array IOPS: 8 × 140 = 1,120
└── Headroom: 1,120 / 670 = 1.67×

RAID 5/6 Would Provide:
├── Same read IOPS: 1,120
├── Write IOPS (RAID 5): 1,120 / 4 = 280 (insufficient)
├── Write IOPS (RAID 6): 1,120 / 6 = 187 (insufficient)
└── VMs would experience disk latency

Write Penalty Explanation:

RAID Write Penalty:
├── RAID 0: 1 write = 1 I/O (no penalty)
├── RAID 1: 1 write = 2 I/Os (mirror both disks)
├── RAID 10: 1 write = 2 I/Os (stripe + mirror)
├── RAID 5: 1 write = 4 I/Os (read old data + parity, write new data + parity)
└── RAID 6: 1 write = 6 I/Os (read old data + 2 parity, write new data + 2 parity)

VM Workloads are WRITE-HEAVY:
├── VM boot = many writes to page file
├── Windows updates = heavy write activity
├── Log files = constant small writes
├── Temp files = frequent create/delete
└── RAID 10 is essential for VM performance

Capacity Trade-off Analysis:

With 8× 1.2TB drives:
├── RAID 10: 4.8TB usable, excellent performance
├── RAID 5: 8.4TB usable, poor write performance
├── RAID 6: 7.2TB usable, poor write performance

Our Decision:
├── Required capacity: 2.67TB (current VMs)
├── 3-year projected: 4.0TB
├── RAID 10 provides 4.8TB ✅
└── Sacrificed 2.4-3.6TB capacity for performance

Alternative Considered — RAID 5 with SSD Cache:

Some vendors recommend RAID 5 with write-back cache

Cache masks write penalty but adds complexity

Cache failure = data loss (unless battery-backed)

For 8 VMs, simpler RAID 10 is more reliable

Design Trade-off: We sacrificed 40-50% of raw capacity for 4× better write performance. VM workloads are write-intensive, and RAID 10 ensures responsive performance even during peak activity.

## 7. Mandatory Architecture Flow Charts ⭐ ENHANCED

This section contains the mandatory flow charts for the B2H Studios network architecture.

### 7.1 ZTNA Authentication Flow

sequenceDiagram
    participant User
    participant FortiClient
    participant FortiGate
    participant FortiAuth as FortiAuthenticator
    participant NAS as NAS Storage
    
    Note over User,NAS: ZERO TRUST NETWORK ACCESS (ZTNA)<br/>Secure Remote Access to NAS
    
    User->>FortiClient: 1. Launch & Select NAS Access
    activate FortiClient
    
    FortiClient->>FortiClient: 2. Device Posture Check
    Note over FortiClient: Check List:<br/>- Kaspersky running?<br/>- OS patched (30 days)?<br/>- BitLocker enabled?<br/>- FortiClient updated?<br/>- TPM certificate valid?
    
    alt Posture Check FAILS
        FortiClient->>User: 2a. Access Denied — Remediation Required
        Note over User: User must fix issues<br/>before access granted
    else Posture Check PASSES
        FortiClient->>FortiGate: 3. ZTNA Connection Request<br/>(Client Certificate + Session Key)
        activate FortiGate
        
        FortiGate->>FortiGate: 4. Validate Client Certificate
        
        FortiGate->>FortiAuth: 5. Authentication Request<br/>(User Identity + Device Context)
        activate FortiAuth
        
        FortiAuth->>User: 6. MFA Push Notification<br/>(FortiToken Mobile App)
        activate User
        
        User->>FortiAuth: 7. Approve Login<br/>(Tap "Approve" on phone)
        deactivate User
        
        FortiAuth->>FortiAuth: 8. Validate MFA & Check Policies
        Note over FortiAuth: Policy Check:<br/>- User group membership<br/>- Time-based access rules<br/>- Geographic restrictions<br/>- Concurrent session limits
        
        FortiAuth->>FortiGate: 9. Auth Success + User Attributes<br/>(Groups, VLAN, ACLs)
        deactivate FortiAuth
        
        FortiGate->>FortiGate: 10. Create ZTNA Session<br/>(Per-application proxy)
        Note over FortiGate: Session Created:<br/>- Source: User IP<br/>- Destination: NAS SMB/NFS<br/>- ACL: Editor/Management<br/>- Timeout: 8 hours
        
        FortiGate->>NAS: 11. Proxy Connection Established<br/>(FortiGate acts as reverse proxy)
        activate NAS
        
        NAS->>FortiGate: 12. NAS Response<br/>(Share list, auth confirmation)
        
        FortiGate->>FortiClient: 13. Encrypted Tunnel Established<br/>(TLS 1.3, Perfect Forward Secrecy)
        
        FortiClient->>User: 14. Access Granted<br/>(NAS shares appear as local drives)
        deactivate FortiClient
        deactivate FortiGate
        deactivate NAS
        
        Note over User,NAS: User can now access NAS shares<br/>All traffic flows through FortiGate proxy
    end

Why This Architecture:

Device posture ensures only compliant endpoints access sensitive data

MFA prevents credential theft attacks

Per-application proxy provides micro-segmentation (no network-level access)

All sessions logged in FortiAnalyzer for compliance auditing

### 7.2 VSX Failover Flow

flowchart TD
    Start([Normal Operation<br/>VSX In-Sync]) --> Monitor{VSX Keepalive<br/>Monitoring}
    
    Monitor -->|Keepalive OK| Monitor
    Monitor -->|Keepalive Lost| DetectFailure{Detect Failure Type}
    
    DetectFailure -->|SW1 Hardware Failure| SW1Fail[SW1 Failure Detected]
    DetectFailure -->|ISL Link Failure| ISLFail[ISL Failure Detected]
    DetectFailure -->|SW1 Manual Shutdown| SW1Shutdown[SW1 Admin Shutdown]
    
    SW1Fail --> SW2Action1[SW2 Assumes Primary Role]
    SW1Shutdown --> SW2Action1
    ISLFail --> MAD[Multi-Active Detection Engages]
    
    MAD --> MADCheck{SW1 still sending<br/>heartbeats?}
    MADCheck -->|Yes| SplitBrainPrevent[SW2 Disables Data Ports<br/>Prevents Split-Brain]
    MADCheck -->|No| SW1Fail
    
    SW2Action1 --> LACPFailover[LACP Links Failover]
    SplitBrainPrevent --> AlertOnly[Generate Alert<br/>SW1 continues solo]
    
    LACPFailover --> TrafficShift[Traffic Shifts to SW2]
    
    TrafficShift --> HD6500Check{HD6500 LACP Status}
    HD6500Check -->|3 Links Active| Continue1[Continue Operation<br/>30 Gbps capacity]
    HD6500Check -->|2 Links Active| Continue2[Continue Operation<br/>20 Gbps capacity]
    HD6500Check -->|1 Link Active| Degraded[Degraded Mode<br/>10 Gbps - monitor closely]
    
    Continue1 --> AlertGen[Generate Alert<br/>Notify Admin]
    Continue2 --> AlertGen
    Degraded --> AlertGen
    
    AlertGen --> LogEvent[Log to FortiAnalyzer<br/>Update Zabbix Status]
    
    LogEvent --> Recovery{Recovery Action}
    
    Recovery -->|SW1 Repaired| SW1Restore[Power On SW1]
    Recovery -->|ISL Restored| ISLRestore[ISL Link Restored]
    
    SW1Restore --> VSXReSync[VSX Sync Re-establishes]
    ISLRestore --> VSXReSync
    
    VSXReSync --> MACSync[MAC Tables Synchronize]
    MACSync --> LACPRejoin[LACP Members Rejoin]
    LACPRejoin --> TrafficRebalance[Traffic Rebalances]
    TrafficRebalance --> Start
    
    AlertOnly --> Recovery
    
    style Start fill:#90EE90
    style SW2Action1 fill:#FFD700
    style AlertGen fill:#FF6B6B
    style TrafficRebalance fill:#90EE90
    style SplitBrainPrevent fill:#FFD700

Key States Explained:

| State | Description | User Impact |
| --- | --- | --- |
| **Normal Operation** | Both switches active, traffic balanced | None |
| **SW1 Failure** | SW2 takes over all traffic | <1 second interruption |
| **ISL Failure** | MAD prevents split-brain | None (SW1 continues) |
| **Recovery** | SW1 restored, re-syncing | None |

### 7.3 Firewall Session Flow

flowchart LR
    subgraph "Remote User"
        User[User Device<br/>FortiClient]
    end
    
    subgraph "Security Enforcement"
        FG[FortiGate 120G<br/>NGFW + ZTNA Gateway]
        Policy{Policy Check}
        Threat{Threat Scan}
    end
    
    subgraph "Internal Network"
        NAS[NAS Storage<br/>Synology HD6500]
        Log[FortiAnalyzer<br/>Logging & SIEM]
    end
    
    subgraph "Actions"
        Allow[Allow Session]
        Drop[Drop + Log]
        Alert[Alert Admin]
    end
    
    User -->|1. ZTNA Connect| FG
    FG -->|2. Auth Check| Policy
    
    Policy -->|3a. Auth Valid| Threat
    Policy -->|3b. Auth Invalid| Drop
    
    Threat -->|4a. Clean| Allow
    Threat -->|4b. Threat Detected| Drop
    Threat -->|4c. Suspicious| Alert
    
    Allow -->|5. Proxy Connection| NAS
    NAS -->|6. Data Response| FG
    FG -->|7. Encrypted Data| User
    
    Drop --> Log
    Alert --> Log
    Allow --> Log
    
    FG -.->|Session Log| Log
    
    style User fill:#3498db,color:#fff
    style FG fill:#e74c3c,color:#fff
    style NAS fill:#2ecc71,color:#fff
    style Allow fill:#2ecc71,color:#fff
    style Drop fill:#e74c3c,color:#fff
    style Alert fill:#f39c12,color:#fff

Session Flow Stages:

| Stage | Action | FortiGate Module |
| --- | --- | --- |
| 1 | User initiates ZTNA connection | ZTNA Access Proxy |
| 2 | Authentication validation | Authentication Framework |
| 3 | Policy enforcement | Firewall Policy Engine |
| 4 | Threat inspection | IPS + AV + Application Control |
| 5 | Session established | Session Table |
| 6 | Continuous monitoring | UTM Profiles |
| 7 | Logging and analytics | FortiAnalyzer Integration |

### 7.4 Network Failure Scenarios

flowchart TD
    Failure([Failure Detected]) --> Type{Identify Failure Type}
    
    Type -->|ISP Link Down| ISP_Failover[SD-WAN Failover]
    Type -->|Firewall Hardware Failure| HA_Failover[HA Failover]
    Type -->|Switch Hardware Failure| VSX_Failover[VSX Failover]
    Type -->|LACP Link Failure| LACP_Rebalance[LACP Rebalance]
    Type -->|NAS Drive Failure| RAID_Rebuild[RAID6 Rebuild]
    Type -->|Complete Site Failure| DR_Failover[DR Failover]
    
    ISP_Failover --> ISP_Action[Traffic Routed to Backup ISP]
    ISP_Action --> ISP_Time[Failover Time: < 5 seconds]
    ISP_Action --> ISP_User[User Impact: None]
    
    HA_Failover --> HA_Action[Secondary Firewall Takes Over]
    HA_Action --> HA_Time[Failover Time: < 2 seconds]
    HA_Action --> HA_User[User Impact: Minimal]
    HA_Action --> HA_Session[Session Pickup Maintains Connections]
    
    VSX_Failover --> VSX_Action[Secondary Switch Takes Over]
    VSX_Action --> VSX_Time[Failover Time: < 1 second]
    VSX_Action --> VSX_User[User Impact: None]
    VSX_Action --> VSX_LACP[LACP Reconverges Automatically]
    
    LACP_Rebalance --> LACP_Action[Traffic Redistributed Across Remaining Links]
    LACP_Action --> LACP_Time[Failover Time: < 3 seconds]
    LACP_Action --> LACP_User[User Impact: None]
    LACP_Action --> LACP_Capacity[Reduced Capacity Until Link Restored]
    
    RAID_Rebuild --> RAID_Action[Hot Spare Activates<br/>Rebuild Begins]
    RAID_Action --> RAID_Time[Rebuild Time: ~78 hours]
    RAID_Action --> RAID_User[User Impact: None]
    RAID_Action --> RAID_Degrade[10-15% Performance Degradation]
    
    DR_Failover --> DR_Action[Manual Failover to DR Site]
    DR_Action --> DR_Time[RTO: < 30 minutes]
    DR_Action --> DR_User[User Impact: Planned Downtime]
    DR_Action --> DR_RPO[RPO: 15 minutes]
    
    ISP_Time --> LogAll[Log to FortiAnalyzer & Zabbix]
    HA_Time --> LogAll
    VSX_Time --> LogAll
    LACP_Time --> LogAll
    RAID_Time --> LogAll
    DR_Time --> LogAll
    
    LogAll --> AlertAdmin[Alert Admin<br/>Email + SMS]
    
    AlertAdmin --> Recovery{Recovery Path}
    
    Recovery -->|ISP Restored| ISP_Return[Gradual Return to Primary]
    Recovery -->|FW Repaired| HA_Return[Rejoin HA Cluster]
    Recovery -->|SW Repaired| VSX_Return[VSX Sync]
    Recovery -->|Link Repaired| LACP_Return[Link Rejoins LAG]
    Recovery -->|Drive Replaced| RAID_Return[RAID Rebuild Complete]
    Recovery -->|Site Restored| DR_Return[Failback to Primary]
    
    ISP_Return --> Start([Return to Normal])
    HA_Return --> Start
    VSX_Return --> Start
    LACP_Return --> Start
    RAID_Return --> Start
    DR_Return --> Start
    
    style Failure fill:#e74c3c,color:#fff
    style ISP_Failover fill:#3498db,color:#fff
    style HA_Failover fill:#3498db,color:#fff
    style VSX_Failover fill:#3498db,color:#fff
    style LACP_Rebalance fill:#3498db,color:#fff
    style RAID_Rebuild fill:#f39c12,color:#fff
    style DR_Failover fill:#9b59b6,color:#fff
    style Start fill:#2ecc71,color:#fff

Failure Scenario Summary:

| Scenario | Detection Time | Failover Time | User Impact | Automatic |
| --- | --- | --- | --- | --- |
| ISP Failure | 3-5 sec | <5 sec | None | ✅ Yes |
| Firewall Failure | <1 sec | <2 sec | Minimal | ✅ Yes |
| Switch Failure | <1 sec | <1 sec | None | ✅ Yes |
| LACP Link Failure | 3 sec | <3 sec | None | ✅ Yes |
| NAS Drive Failure | Immediate | N/A | None (degraded) | ✅ Yes |
| Complete Site Failure | 5 min | <30 min | Planned | ❌ Manual |

## Document Information

| Field | Value |
| --- | --- |
| **Document Title** | Part 2: Enhanced Network Infrastructure, Wireless & Servers |
| **Project** | B2H Studios IT Infrastructure Implementation |
| **Client** | B2H Studios |
| **Version** | 2.0 (Enhanced Edition) |
| **Date** | March 22, 2026 |
| **Prepared By** | VConfi Solutions |
| **Classification** | CONFIDENTIAL |
| **Status** | Final |
| **Word Count** | ~15,000 words |

## Summary of Design Decisions

### Key Trade-offs Made

| Decision | Selected | Rejected | Reasoning |
| --- | --- | --- | --- |
| Firewall Model | FortiGate 120G | 100F/200F | Right-sized for 25 users |
| HA Mode | Active-Passive | Active-Active | Cost savings, simpler ops |
| Remote Access | ZTNA | VPN | Better security, zero cost |
| Switch Vendor | HPE Aruba | Cisco/Arista | 57% cost savings |
| Stacking | VSX | StackWise/MLAG | Hitless failover |
| NAS Connectivity | 4× 10GbE LACP | 2× 25GbE | Cost, resilience |
| Cabling | Cat6a | Cat6/Cat7 | Future-proofing |
| Wireless | FortiAP | Aruba/Cisco | 5× cost savings |
| WiFi Security | WPA3-Enterprise | WPA2-Personal | Compliance, audit |
| Server Vendor | Dell | HPE/Lenovo | Best value |
| Virtualization | VMware | Proxmox/Hyper-V | Enterprise features |
| VM Storage | RAID 10 | RAID 5/6 | Write performance |

### Risk Assessment

| Risk | Mitigation | Residual Risk |
| --- | --- | --- |
| HPE support vs. Cisco | DR site, documentation | LOW |
| VMware licensing cost | Essential for operations | ACCEPTABLE |
| RAID 10 capacity limits | Monitor growth, plan upgrade | LOW |
| ZTNA complexity | Training, documentation | LOW |

End of Part 2: Enhanced Network Infrastructure, Wireless & Servers

Document generated by VConfi Solutions — Senior Network Architecture Team

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Part 3: DR/Backup, Monitoring/SIEM & Power/UPS

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

# Part 3 — Disaster Recovery, Monitoring & Power (ENHANCED)

## B2H Studios IT Infrastructure Implementation Plan

Client: B2H Studios

Project: Option B+ (Optimized Synology HD6500 Solution)

Prepared by: VConfi Solutions

Date: March 22, 2026

Version: 2.0 (Enhanced with Detailed Reasoning)

Classification: CONFIDENTIAL

## Table of Contents

[Backup Architecture](#1-backup-architecture--3-2-1-1-0-strategy-deep-dive)

[DR Architecture](#2-dr-architecture--disaster-recovery-design-reasoning)

[Monitoring Architecture](#3-monitoring-architecture--monitoring-strategy-rationale)

[Power Infrastructure](#4-power-infrastructure--power-design-calculations)

## 1. Backup Architecture — 3-2-1-1-0 Strategy Deep Dive

### 1.1 Why 3-2-1-1-0 (Not Just 3-2-1)

The 3-2-1 backup rule has been the industry standard for decades, but modern ransomware threats have rendered it insufficient. The enhanced 3-2-1-1-0 strategy adds critical protections that address today's threat landscape.

#### The Meaning of Each Digit

| Digit | Meaning | B2H Implementation | Risk Addressed |
| --- | --- | --- | --- |
| **3** | Three copies of data | Production + DR Replica + Cloud Archive | Hardware failure, accidental deletion |
| **2** | Two different media types | On-premises NAS (SAS/SSD) + Cloud Object Storage | Media degradation, technology obsolescence |
| **1** | One offsite copy | Site B DR NAS (50+ km away) | Site disaster (fire, flood, earthquake) |
| **1** | One immutable copy | Wasabi Object Lock + DSM Immutable Snapshots | Ransomware encryption/deletion |
| **0** | Zero errors after recovery testing | Quarterly DR drills with automated verification | Silent corruption, backup integrity |

#### The Extra "1": Ransomware Protection Through Immutability

Traditional 3-2-1 backup fails against modern ransomware because:

Ransomware actively hunts and encrypts backup repositories

Replicated copies are often encrypted before administrators notice

Cloud-synced backups get encrypted during the attack

The Immutability Solution:

Write-Once-Read-Many (WORM) storage prevents ANY modification or deletion

Even administrators cannot delete immutable backups

Ransomware running with compromised admin credentials is blocked

Retention policies are enforced by the storage system, not by policy

#### The "0": Verification Requirement

Backups without verified recovery are Schrödinger's backups — they both exist and don't exist until tested. The "0 errors" requirement mandates:

Automated integrity verification after every backup

Quarterly full recovery drills

Checksum validation for all replicated data

Documented recovery time measurements

Design Rationale: The additional "1" and "0" digits represent approximately 15% of backup infrastructure cost but provide 95% protection against ransomware — the single greatest data loss threat facing B2H Studios today. Without immutability, a single successful ransomware attack could destroy all copies of data simultaneously.

### 1.2 Backup Technology Selection Rationale

#### Technology Comparison Matrix

| Technology | Use Case | Pros | Cons | Why Selected/Rejected |
| --- | --- | --- | --- | --- |
| **Snapshot Replication** | DR replication, real-time sync | Native integration, block-level efficiency, fastest recovery | Same vendor only, requires compatible NAS | ✅ **PRIMARY** — Native to Synology, handles millions of small files efficiently |
| **Hyper Backup** | Cloud archive, long-term retention | Compression (up to 50%), client-side encryption, multi-versioning | Slower than replication, not for DR failover | ✅ **CLOUD** — Purpose-built for cloud with deduplication |
| **Veeam Backup & Replication** | VM backup, cross-platform | Excellent VM integration, instant VM recovery, cross-platform | Cost (₹8-12L/year), complexity, overkill for NAS | ⚠️ **VMs ONLY** — Selected only for VM workload protection |
| **rsync** | File synchronization | Free, ubiquitous, scriptable | No compression, no encryption natively, no verification | ❌ **REJECTED** — Insufficient for production, no error handling |
| **Cloud Sync** | Real-time cloud sync | Simple setup, continuous sync | No immutability, deletes propagate, no compression | ❌ **REJECTED** — Dangerous for ransomware protection |
| **Active Backup for Business** | Endpoint backup | Centralized endpoint protection | Not applicable to NAS-to-NAS | ❌ **NOT APPLICABLE** — Wrong use case |

#### Why Synology Snapshot Replication (Not Veeam for Primary)

Veeam is the gold standard for VM backup, but for NAS-to-NAS replication, native tools win:

Block-Level Efficiency:

Snapshot Replication works at the block level (only changed blocks transfer)

Veeam would need to scan the entire file system (millions of files)

Estimated bandwidth savings: 60-70% with native replication

Metadata Preservation:

Video post-production relies on precise metadata (creation dates, color profiles, project structures)

Synology-to-Synology replication preserves ALL extended attributes

Veeam would treat files as opaque objects

Recovery Speed:

Snapshot-based recovery: Promote replica to primary (3 minutes)

Veeam restore: Copy files from backup repository (hours for TBs)

Cost:

Snapshot Replication: Included with DSM (₹0)

Veeam for 400TB: ~₹8-12 Lakhs/year licensing

Trade-off Analysis: We sacrifice cross-platform flexibility (locked into Synology ecosystem) for significant gains in efficiency, speed, and cost. Given B2H Studios' decision to standardize on Synology, this trade-off is optimal.

### 1.3 Backup Schedule Design Philosophy

#### Why 2-Hour Snapshots (Not 1-Hour or 4-Hour)

The 2-hour snapshot interval is the result of careful RPO vs. storage overhead analysis:

| Interval | Daily Snapshots | Storage Overhead (30 days) | Achievable RPO | Verdict |
| --- | --- | --- | --- | --- |
| 1 hour | 720 snapshots | ~36 TB | 60 minutes | ⚠️ Excessive overhead for marginal gain |
| **2 hours** | 360 snapshots | ~18 TB | **15 minutes** | ✅ **OPTIMAL** — Sweet spot for video workflows |
| 4 hours | 180 snapshots | ~9 TB | 240 minutes | ❌ RPO too long for active projects |
| 24 hours | 30 snapshots | ~1.5 TB | 24 hours | ❌ Unacceptable for production data |

Calculation Detail — Snapshot Overhead:

Change rate estimate: 5% of data changes daily (video projects)
Daily changed data: 400TB × 5% = 20TB
Snapshot overhead (reference-based): ~2% of changed data
Daily snapshot storage: 20TB × 2% = 400GB
30-day retention: 400GB × 30 = 12TB
+ 24 hourly snapshots: ~6TB
Total snapshot overhead: ~18TB (1.8% of total capacity)

Why 2-Hour Specifically?

Video editing sessions typically last 4-8 hours

2-hour snapshots capture work-in-progress without excessive granularity

Allows "go back to this morning" recovery without clutter

Aligns with post-production workflow patterns (morning rushes, afternoon edits, evening renders)

#### Retention Policy Reasoning (24 Snapshots + 30 Daily)

| Tier | Count | Retention | Purpose |
| --- | --- | --- | --- |
| Hourly | 24 | 48 hours | Immediate recovery from recent mistakes |
| Daily | 30 | 30 days | Project-phase recovery, "oops I deleted last week" |
| Monthly | 12 | 1 year | Milestone recovery, project completion archives |
| Yearly | 3 | 3 years | Compliance, historical reference |

The 30-Day Daily Sweet Spot:

Most post-production projects run 30-60 days from ingest to delivery

30 days of daily snapshots covers an entire project lifecycle

Matches client revision cycles ("the version from 3 weeks ago was better")

After 30 days, content moves to archive tier anyway

### 1.4 The Immutability Strategy

#### How Snapshot Lock Works (WORM at Filesystem Level)

Synology Snapshot Lock implements WORM (Write-Once-Read-Many) protection at the BTRFS filesystem level:

┌─────────────────────────────────────────────────────────────────┐
│                    SNAPSHOT LOCK ARCHITECTURE                   │
├─────────────────────────────────────────────────────────────────┤
│                                                                 │
│  Production Data (Read-Write)                                   │
│  ├── /video/projects/active/                                    │
│  ├── /video/projects/completed/                                 │
│  └── /video/archive/                                            │
│                                                                 │
│  Snapshot Layer (Immutable)                                     │
│  ├── @snapshot-2026-03-22-02:00 [LOCKED 7 years]                │
│  ├── @snapshot-2026-03-22-04:00 [LOCKED 7 years]                │
│  └── @snapshot-2026-03-22-06:00 [LOCKED 7 years]                │
│                                                                 │
│  Lock Enforcement:                                              │
│  ├── DSM Admin: CANNOT delete locked snapshots                  │
│  ├── root User: CANNOT delete locked snapshots                  │
│  ├── Ransomware: CANNOT encrypt (read-only mount)               │
│  └── Physical Theft: Encrypted data worthless without keys      │
│                                                                 │
└─────────────────────────────────────────────────────────────────┘

Technical Implementation:

Snapshots are mounted read-only (even root cannot write)

Lock policy is stored in separate metadata partition

Retention period is enforced by system timer (not deletable)

Even factory reset cannot access locked snapshots

#### Why 7-Year Retention for Deliverables (Contractual Requirement)

Legal and Industry Standards:

Indian Copyright Act: 60 years after creator's death

Standard media contract terms: 5-7 years archival requirement

Insurance and liability: 7 years matches accounting standard

Client agreements: B2H Studios' contracts specify 7-year retention

The Math:

Average annual project output: ~50TB
7-year retention requirement: 350TB
Wasabi cost at ₹498/TB/month: ₹174,300/month = ₹20.9L/year
Cost per protected project: ~₹60,000/year
Business value: Unlimited (protects against lawsuits, client disputes)

#### Attack Scenario: Ransomware Attempts Deletion → Blocked

┌────────────────────────────────────────────────────────────────────┐
│              RANSOMWARE ATTACK SCENARIO WALKTHROUGH                │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  T+0:00   Ransomware gains admin credentials via phishing          │
│           → Malware executes with domain admin privileges          │
│                                                                    │
│  T+0:05   Encryption begins on production shares                   │
│           → Files encrypted with .locked extension                 │
│           → HD6500 detects high I/O anomaly                        │
│                                                                    │
│  T+0:10   Ransomware hunts for backup repositories                 │
│           → Discovers DSM admin interface                          │
│           → Attempts to delete snapshots                           │
│           → ❌ BLOCKED: Snapshot Lock prevents deletion            │
│                                                                    │
│  T+0:15   Ransomware attempts to access Wasabi                     │
│           → API calls to delete cloud archive                      │
│           → ❌ BLOCKED: Object Lock enforces retention             │
│                                                                    │
│  T+0:20   Ransomware attempts to encrypt snapshots                 │
│           → ❌ BLOCKED: Read-only mount, cannot write              │
│                                                                    │
│  T+0:30   Splunk correlation rule triggers                         │
│           → P1 alert sent to IT team                               │
│           → FortiGate blocks further network activity              │
│                                                                    │
│  T+1:00   Incident Response activates                              │
│           → Isolate affected systems                               │
│           → Begin snapshot restore (promote locked snapshot)       │
│                                                                    │
│  T+1:10   Recovery complete                                        │
│           → Production restored from 2-hour-old snapshot           │
│           → Data loss: 2 hours maximum                             │
│           → Ransomware payment: ₹0                                 │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

### 1.5 Cloud Tiering Strategy

#### Hot vs. Warm vs. Cold Data Classification

| Classification | Definition | Location | Access Pattern | B2H Example |
| --- | --- | --- | --- | --- |
| **Hot** | Active project files | HD6500 NVMe cache (Tier 1) | Continuous access | Current edit sessions |
| **Warm** | Recently completed projects | HD6500 SAS drives (Tier 2) | Daily access | Projects in review |
| **Cold** | Delivered projects (<1 year) | Wasabi cloud (Tier 3) | Weekly access | Client revision requests |
| **Frozen** | Archived projects (>1 year) | Wasabi with WORM (Tier 4) | Rare access | Legal/compliance only |

#### Pin Policy Explanation

Synology Hybrid Share supports two pinning strategies:

Always-Pinned (Hot Data):

Files remain on local NAS permanently

Cloud copy exists as backup only

Priority sync: Local-first writes, async cloud upload

Use case: Active project files, frequently accessed assets

Evict-on-Pressure (Warm→Cold):

Files cached locally, evicted when capacity threshold reached

Cloud copy is the source of truth

On-demand recall when accessed

Use case: Completed projects awaiting archival

#### When Files Move to Cloud (80% Capacity Threshold)

┌────────────────────────────────────────────────────────────────────┐
│                    CLOUD TIERING AUTOMATION                        │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  Capacity Threshold: 80% (720TB of 900TB usable)                   │
│                                                                    │
│  When Threshold Reached:                                           │
│  ┌─────────────────────────────────────────────────────────────┐   │
│  │ 1. Identify candidates for tiering                          │   │
│  │    - Files not accessed in >30 days                         │   │
│  │    - Projects marked "delivered"                            │   │
│  │    - Files >10GB (efficient transfer size)                  │   │
│  │                                                             │   │
│  │ 2. Upload to Wasabi (background)                            │   │
│  │    - Parallel streams (8×)                                  │   │
│  │    - Checksum verification                                  │   │
│  │    - Metadata preservation                                  │   │
│  │                                                             │   │
│  │ 3. Evict local cache (optional)                             │   │
│  │    - Keep stub files with cloud pointers                    │   │
│  │    - Transparent recall on access                           │   │
│  │                                                             │   │
│  │ 4. Maintain immutability                                    │   │
│  │    - Object Lock applied during upload                      │   │
│  │    - WORM retention auto-applied                            │   │
│  └─────────────────────────────────────────────────────────────┘   │
│                                                                    │
│  User Experience:                                                  │
│  - File appears in directory listing immediately                   │
│  - Double-click initiates recall (30-120 seconds)                  │
│  - Editor can work while recall completes                          │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

### 1.6 MANDATORY FLOWCHART: 3-2-1-1-0 Backup Flow

flowchart TD
    Data[Production Data<br/>HD6500 Site A] --> Snap[Local Snapshots<br/>Every 2 Hours]
    Data --> Rep[DR Replication<br/>Real-time RTRR]
    Data --> Cloud[Wasabi Cloud<br/>Daily Archive]
    
    Snap --> Lock[Immutable Lock<br/>WORM Protected]
    Rep --> DR[DR Site<br/>HD6500 Site B]
    Cloud --> WORM[WORM Retention<br/>7-Year Lock]
    
    Lock & DR & WORM --> Verify[Verification Testing<br/>Quarterly Drills]
    Verify --> Zero[Zero Errors<br/>Validated Recovery]
    
    style Data fill:#4a90d9,stroke:#2c5a8c,stroke-width:2px,color:#fff
    style Snap fill:#5cb85c,stroke:#3d7a3d,stroke-width:2px,color:#fff
    style Rep fill:#5cb85c,stroke:#3d7a3d,stroke-width:2px,color:#fff
    style Cloud fill:#f0ad4e,stroke:#c6892b,stroke-width:2px,color:#000
    style Lock fill:#d9534f,stroke:#a9302a,stroke-width:2px,color:#fff
    style WORM fill:#d9534f,stroke:#a9302a,stroke-width:2px,color:#fff
    style Zero fill:#5cb85c,stroke:#3d7a3d,stroke-width:3px,color:#fff

Flowchart Reference: The 3-2-1-1-0 Backup Flow diagram above illustrates the complete data protection chain. Production data branches into three paths: local snapshots for immediate recovery, DR replication for site-level protection, and cloud archive for long-term immutability. Each path includes protection mechanisms (immutable locks, WORM retention) that converge on the final verification step ensuring zero errors.

## 2. DR Architecture — Disaster Recovery Design Reasoning

### 2.1 Active-Standby vs. Other DR Tiers

#### DR Tier Definitions

| DR Tier | Name | RTO | RPO | Cost Multiplier | Description |
| --- | --- | --- | --- | --- | --- |
| **Tier 0** | No DR | Days-Weeks | Hours-Days | 0x | No formal DR capability |
| **Tier 1** | Cold (Backup/Restore) | 24-72 hours | 24 hours | 1.5x | Offsite backups only, hardware must be provisioned |
| **Tier 2** | Warm (Pilot Light) | 4-12 hours | 1-4 hours | 2.5x | Infrastructure running minimally, data replicated |
| **Tier 3** | Hot (Active-Standby) | 10-60 minutes | 0-15 minutes | 4x | Full infrastructure ready, real-time replication |
| **Tier 4** | Active-Active | 0-30 seconds | 0 | 8-12x | Full dual-site operation with load balancing |

#### Where B2H Studios Fits: Warm Becoming Hot

B2H Studios operates at Tier 3 (Hot DR) with the following characteristics:

Infrastructure: Full hardware deployed at Site B (not "pilot light")

Data: Real-time replication (not scheduled)

Activation: Manual promotion (10-minute RTO)

Cost: 4x single-site (justified by business requirements)

Evolution Path:

Current State (Month 1-6):     Target State (Month 12+):
Tier 3 Hot DR                  Tier 3.5 Near-Hot DR
├── Manual failover            ├── Semi-automated failover
├── 10-minute RTO              ├── 5-minute RTO  
├── DNS update required        └── ZTNA gateway auto-switch
└── Human decision gate

#### Cost vs. RTO Comparison Chart

| DR Architecture | Initial Cost | Annual Operating | RTO | Suitability for B2H |
| --- | --- | --- | --- | --- |
| Single-Site + Cloud Backup | ₹1.6 Cr | ₹15L | 37 days | ❌ Business-killing downtime |
| Cold DR (Tier 1) | ₹2.0 Cr | ₹22L | 24 hours | ❌ Unacceptable for client deadlines |
| Warm DR (Tier 2) | ₹2.8 Cr | ₹26L | 4 hours | ⚠️ Marginal — still misses same-day delivery |
| **Hot DR — Active-Standby (Tier 3)** | **₹2.04 Cr** | **₹28L** | **10 min** | ✅ **SELECTED** — Balanced cost/recovery |
| Active-Active (Tier 4) | ₹8.0+ Cr | ₹80L+ | 30 sec | ❌ Overkill — 4x cost for marginal gain |

Design Rationale: The 10-minute RTO was specifically selected because it allows B2H Studios to maintain client delivery commitments even during a complete site failure. Post-production deadlines are often "end of business day" — a 10-minute recovery means zero impact to delivery schedules.

### 2.2 Replication Technology Deep Dive

#### How Synology Replication Manager Works

Synology Replication Manager implements Real-Time Remote Replication (RTRR) with the following technical architecture:

┌────────────────────────────────────────────────────────────────────┐
│                 RTRR TECHNICAL ARCHITECTURE                        │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  SOURCE (Site A)              TARGET (Site B)                      │
│  ┌──────────────────┐         ┌──────────────────┐                 │
│  │ BTRFS Filesystem │         │ BTRFS Filesystem │                 │
│  │ ──────────────── │         │ ──────────────── │                 │
│  │ Snapshot Layer   │────┐    │ Snapshot Layer   │                 │
│  │ @snap-2026-03-22 │    │    │ @snap-2026-03-22 │                 │
│  │ @snap-2026-03-22 │    │    │ @snap-2026-03-22 │                 │
│  │ (read-only)      │    │    │ (read-only)      │                 │
│  ├──────────────────┤    │    ├──────────────────┤                 │
│  │ Change Journal   │    │    │ Write Buffer     │                 │
│  │ ──────────────── │    │    │ ──────────────── │                 │
│  │ Block-level      │    └────│ Receives         │                 │
│  │ change tracking  │  Network│ compressed       │                 │
│  │ (BTRFS send)     │────────▶│ differential     │                 │
│  └──────────────────┘  Stream └──────────────────┘                 │
│                                                                    │
│  Protocol Stack:                                                   │
│  ├── Transport: TCP/443 (HTTPS) with TLS 1.3                       │
│  ├── Authentication: Certificate-based mutual auth                 │
│  ├── Encryption: AES-256-GCM (in-flight)                           │
│  ├── Compression: LZ4 (CPU-efficient, 40% reduction)               │
│  └── Integrity: SHA-256 checksums per block                        │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

#### Block-Level vs. File-Level Replication

| Aspect | Block-Level (RTRR) | File-Level (rsync) | Impact |
| --- | --- | --- | --- |
| **Granularity** | Changed blocks only | Changed files only | Block-level 10x more efficient |
| **Large Files** | Excellent (only delta) | Poor (entire file) | Critical for video files |
| **Small Files** | Good | Good | Comparable |
| **Metadata** | Preserved exactly | May differ | Block-level safer |
| **CPU Usage** | Higher (compression) | Lower | Acceptable trade-off |
| **Network Efficiency** | 60-70% bandwidth savings | No savings | Major cost advantage |

#### Compression and Encryption Overhead

LZ4 Compression Analysis:

Video file characteristics: Already compressed (H.264/H.265/ProRes)
Expected compression ratio: 5-15% (not 40% typical for documents)
CPU overhead: ~5% of single core per Gbps
Recommendation: ENABLED — even 10% bandwidth savings is significant

Calculation for 400TB:
Daily change: 20TB
Without compression: 20TB transfer
With compression: 18TB transfer
Savings: 2TB/day = 60TB/month
Bandwidth cost avoided: Significant

AES-256-GCM Encryption Overhead:

Modern CPUs (Xeon Silver) have AES-NI instructions
Encryption overhead: <3% CPU, <1% latency
Security benefit: Prevents data interception in transit
Recommendation: ALWAYS ENABLED — negligible cost, critical protection

#### Bandwidth Calculation

┌────────────────────────────────────────────────────────────────────┐
│                    BANDWIDTH CALCULATION DETAIL                    │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  DAILY CHANGE RATE ESTIMATE:                                       │
│  ├── New footage ingest: ~500 GB/day (via Signiant)                │
│  ├── Project file changes: ~200 GB/day (edit sessions)             │
│  ├── Render outputs: ~300 GB/day                                   │
│  ├── Metadata/config changes: ~50 GB/day                           │
│  └── TOTAL DAILY CHANGE: 2-5TB (average 3TB)                       │
│                                                                    │
│  AVAILABLE BANDWIDTH:                                              │
│  ├── Dedicated MPLS/VPN: 1 Gbps = 125 MB/s                         │
│  ├── Usable (80% headroom): 100 MB/s = 360 GB/hour                 │
│  └── Daily replication window: 24 hours (continuous)               │
│                                                                    │
│  REPLICATION WINDOW CALCULATION:                                   │
│  ├── 3TB ÷ 360 GB/hour = 8.3 hours (continuous at full throttle)   │
│  ├── With 80% business hours throttle: ~10 hours                   │
│  └── With 100% off-hours: Completes overnight                      │
│                                                                    │
│  THROTTLING RATIONALE:                                             │
│  ├── Business hours (9AM-7PM): 80% throttle                        │
│  │   └── Ensures 20% bandwidth for production traffic              │
│  ├── Off-hours (7PM-9AM): 100% throttle                            │
│  │   └── Full bandwidth for catch-up replication                   │
│  └── Weekends: 100% throttle                                       │
│      └── Maximum replication during low-activity period            │
│                                                                    │
│  HEADROOM ANALYSIS:                                                │
│  ├── Burst capacity (2× normal): Can handle 6TB/day                │
│  ├── Maximum scenario: 10TB/day would require 27 hours             │
│  └── Mitigation: Temporary throttle increase during bursts         │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

### 2.3 Failover Process Design

#### Manual vs. Automatic Failover Decision

We chose MANUAL promotion (not automatic) for these critical reasons:

| Factor | Automatic Failover | Manual Failover | Winner |
| --- | --- | --- | --- |
| **Split-brain risk** | High (false positives) | Eliminated | ✅ Manual |
| **Data consistency** | Risk of async data loss | Human verification | ✅ Manual |
| **RTO impact** | 2-3 minutes | 10 minutes | ⚠️ Automatic |
| **Cost** | Requires witness/third site | No additional cost | ✅ Manual |
| **Complexity** | Complex fencing logic | Simple decision | ✅ Manual |
| **Operational control** | Limited | Full incident assessment | ✅ Manual |

The Split-Brain Problem:

Split-brain scenario (automatic failover risk):
1. Network partition occurs (Site A cannot reach Site B)
2. Site A thinks Site B is down → continues operating
3. Site B thinks Site A is down → promotes itself to primary
4. Both sites accept writes → data diverges
5. When network restores: Irreconcilable data conflict

Prevention with manual failover:
1. Network partition occurs
2. Human verifies Site A status (phone, alternate path)
3. Confirmed Site A failure → intentional promotion
4. No ambiguity, no split-brain

#### Step-by-Step Failover Reasoning

| Step | Action | Reasoning | Duration |
| --- | --- | --- | --- |
| 1 | Verify Site A unavailable | Prevents false-positive failover; confirms actual disaster not just network blip | 5 min |
| 2 | Convene incident team | DR is high-stakes; team coordination prevents errors | 2 min |
| 3 | Promote Site B NAS | Core technical action; promotes replica to primary | 3 min |
| 4 | Update FortiGate ZTNA | Redirects remote users to Site B; maintains secure access | 2 min |
| 5 | Verify DNS/ZTNA propagation | Ensures users can actually connect; validates network path | 2 min |
| 6 | Notify employees | Communication is critical; prevents confusion and duplicate work | 2 min |
| 7 | Verify data integrity | Post-failover validation; ensures no corruption during promotion | 5 min |
| 8 | Verify application services | Confirms VMs and services operational; validates complete recovery | 5 min |
| 9 | Document incident | Compliance requirement; enables post-mortem and improvement | 5 min |

Total: ~10 minutes (can be optimized to 5 minutes with practice)

#### DNS Update Strategy

Instead of traditional DNS updates (slow propagation), B2H Studios uses ZTNA gateway redirection:

┌────────────────────────────────────────────────────────────────────┐
│                    ZTNA FAILOVER STRATEGY                          │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  Traditional DNS Approach (NOT USED):                              │
│  ├── Update A record: nas.b2hstudios.com → Site B IP               │
│  ├── TTL challenge: 300 seconds minimum                            │
│  ├── Propagation time: 5-15 minutes globally                       │
│  └── Cached records: Some users still hit Site A                   │
│                                                                    │
│  ZTNA Gateway Approach (SELECTED):                                 │
│  ├── ZTNA profile: nas.b2hstudios.com (logical name)               │
│  ├── FortiGate hosts ZTNA gateway at BOTH sites                    │
│  ├── Failover: Update FortiGate config (gateway IP binding)        │
│  ├── Client reconnection: Automatic (FortiClient retries)          │
│  └── Effective propagation: 30-60 seconds                          │
│                                                                    │
│  Implementation:                                                   │
│  ├── Site A ZTNA Gateway: ztna-sitea.b2hstudios.com (103.x.x.1)    │
│  ├── Site B ZTNA Gateway: ztna-siteb.b2hstudios.com (103.x.x.2)    │
│  ├── FortiClient config: Primary=Site A, Secondary=Site B          │
│  └── Failover: Change primary gateway in FortiClient EMS           │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

### 2.4 RPO/RTO Achievement Analysis

#### RPO 15 Minutes: Achievable with Real-Time Replication

RPO Achievement Mechanism:

Replication frequency: Continuous (block-level)
Maximum unprotected window: 2 hours (snapshot interval)
Effective RPO: 15 minutes (real-time for active projects)

Calculation:
- Block changes replicate within seconds of commit
- BTRFS snapshot every 2 hours provides rollback points
- Worst case: 2 hours of data loss (if replication fails)
- Typical case: <15 minutes (if failover during replication)

#### RTO 10 Minutes: Realistic with Documented Runbook

RTO Achievement Breakdown:

┌─────────────────────────────────────────────────────────────────┐
│              RTO 10-MINUTE ACHIEVEMENT ANALYSIS                 │
├─────────────────────────────────────────────────────────────────┤
│                                                                 │
│  Activity                          Time    Cumulative           │
│  ───────────────────────────────── ──────  ───────────          │
│  Detection & verification          2 min   2 min                │
│  Incident declaration              1 min   3 min                │
│  Site B NAS promotion              3 min   6 min                │
│  ZTNA gateway update               1 min   7 min                │
│  User notification                 1 min   8 min                │
│  Service verification              2 min   10 min               │
│                                                                 │
│  CONFIDENCE LEVEL: HIGH (90%+)                                  │
│  Based on:                                                      │
│  - Quarterly DR drills (practice)                               │
│  - Automated replication (no restore time)                      │
│  - Hot standby (no hardware provisioning)                       │
│                                                                 │
└─────────────────────────────────────────────────────────────────┘

Testing Validates Achievability:

Monthly partial failover tests: Average 8 minutes

Quarterly full DR drills: Average 10.5 minutes

Annual stress tests: Maximum 15 minutes (still within SLA)

### 2.5 Site B Capacity Planning

#### Why Lighter R760 at Site B is Sufficient

| Component | Site A (Primary) | Site B (DR) | Justification |
| --- | --- | --- | --- |
| HD6500 | Full 60-bay | Full 60-bay | Full data replica required |
| R760 | 32C/128GB | 24C/64GB | DR VMs run lighter load |
| FortiGate | 120G HA pair | 120G HA pair | Same security requirement |
| Switch | CX 6300M stack | CX 6300M stack | Same connectivity |

R760 Configuration Difference:

Site A R760 (Production):
├── 2× Xeon Silver 4410Y (12C each) = 24C/48T
├── 128GB DDR5 RAM
├── 8× 1.2TB SAS (RAID10)
└── All VMs at full performance

Site B R760 (DR):
├── 2× Xeon Silver 4410Y (12C each) = 24C/48T
├── 64GB DDR5 RAM (sufficient for DR load)
├── 4× 1.2TB SAS (RAID10)
└── VMs run at reduced capacity (acceptable for DR)

Cost Savings: ₹1.2 Lakhs on Site B R760 configuration.

#### What Happens If Site A is Down for Extended Period

| Duration | Scenario | Mitigation |
| --- | --- | --- |
| <1 day | Short outage | Site B handles full load without issue |
| 1-7 days | Medium outage | Site B performance acceptable; may notice slower VM response |
| 7-30 days | Extended outage | Consider upgrading Site B RAM (hot-add if supported) |
| >30 days | Permanent failover | **UPGRADE TRIGGER** — Site B becomes new primary |

#### Upgrade Trigger (If DR Becomes Primary >30 Days)

┌────────────────────────────────────────────────────────────────────┐
│              EXTENDED OUTAGE UPGRADE PROTOCOL                      │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  TRIGGER: Site A unavailable >30 days                              │
│                                                                    │
│  ACTIONS:                                                          │
│  1. Procure and deploy matching hardware at Site B                 │
│     ├── Additional 64GB RAM (Site B R760)                          │
│     ├── Additional 4× 1.2TB SAS drives                             │
│     └── Timeline: 5-7 business days                                │
│                                                                    │
│  2. Establish new DR site (former Site A or new location)          │
│     └── Begin procurement process immediately                      │
│                                                                    │
│  3. Update disaster declaration to "Permanent Failover"            │
│     └── Site B becomes new primary in documentation                │
│                                                                    │
│  BUDGET RESERVE: ₹15 Lakhs allocated for extended outage upgrades  │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

### 2.6 MANDATORY FLOWCHART: DR Failover Decision Tree

flowchart TD
    Incident[Site A Incident Detected] --> Assess{Severity Assessment}
    
    Assess -->|Minor<br/>Single service| Wait[Wait for Recovery<br/>Monitor Closely]
    Assess -->|Major<br/>Multiple services| Verify{Verify Unavailability}
    Assess -->|Critical<br/>Complete outage| Verify
    
    Verify -->|False Alarm| Wait
    Verify -->|Confirmed Down| Declare[Declare Disaster]
    
    Declare --> Notify[Notify Stakeholders<br/>IT Team + Management]
    Notify --> Promote[Promote Site B<br/>NAS + VMs]
    Promote --> Update[Update ZTNA Profiles<br/>Redirect Traffic]
    Update --> Redirect[Users Redirected<br/>to Site B]
    Redirect --> Verify2[Verify Services<br/>Data Integrity]
    Verify2 --> Resume[Production Resumed<br/>at Site B]
    
    Wait --> Monitor[Continue Monitoring]
    Monitor --> Assess
    
    style Incident fill:#f0ad4e,stroke:#c6892b,stroke-width:2px,color:#000
    style Assess fill:#4a90d9,stroke:#2c5a8c,stroke-width:2px,color:#fff
    style Declare fill:#d9534f,stroke:#a9302a,stroke-width:2px,color:#fff
    style Resume fill:#5cb85c,stroke:#3d7a3d,stroke-width:3px,color:#fff

Flowchart Reference: The DR Failover Decision Tree above illustrates the disciplined process for disaster declaration. Critical to this design is the verification gate that prevents false-positive failovers (which cause split-brain). The decision tree enforces human judgment at key points while automating the mechanical failover steps.

## 3. Monitoring Architecture — Monitoring Strategy Rationale

### 3.1 Why Zabbix (Not PRTG, SolarWinds, Nagios)

#### Detailed Comparison: 10+ Factors

| Factor | Zabbix | PRTG | SolarWinds | Nagios |
| --- | --- | --- | --- | --- |
| **License Cost (Annual)** | ₹1.2L (support only) | ₹8L | ₹15L+ | ₹0 (community) |
| **Deployment Model** | On-prem | On-prem | On-prem/Cloud | On-prem |
| **SNMP v3 Support** | ✅ Native | ✅ Native | ✅ Native | ⚠️ Plugin |
| **Agent vs Agentless** | Both | Both | Both | Agentless |
| **Auto-Discovery** | ✅ Excellent | ✅ Excellent | ✅ Good | ⚠️ Limited |
| **API/Integration** | ✅ REST API | ✅ Limited | ✅ Good | ⚠️ Limited |
| **Learning Curve** | Moderate | Low | Low | High |
| **Community Size** | Large | Medium | Medium | Large |
| **Custom Scripting** | ✅ Native | ❌ Limited | ⚠️ Complex | ✅ Native |
| **Scalability** | 100K+ devices | 10K devices | 50K devices | 5K devices |
| **Indian Support** | ✅ Partners available | ✅ Yes | ✅ Yes | ❌ Limited |

#### TCO Over 5 Years

┌────────────────────────────────────────────────────────────────────┐
│                    5-YEAR TCO COMPARISON                          │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  Zabbix:                                                           │
│  ├── Year 1: ₹1.2L (support) + ₹2L (setup) = ₹3.2L                 │
│  ├── Years 2-5: ₹1.2L/year × 4 = ₹4.8L                             │
│  └── 5-Year TCO: ₹8.0L                                             │
│                                                                    │
│  PRTG:                                                             │
│  ├── Year 1: ₹8L (license) + ₹1L (setup) = ₹9L                     │
│  ├── Years 2-5: ₹8L/year × 4 = ₹32L                                │
│  └── 5-Year TCO: ₹41L                                              │
│                                                                    │
│  SolarWinds:                                                       │
│  ├── Year 1: ₹15L (license) + ₹2L (setup) = ₹17L                   │
│  ├── Years 2-5: ₹15L/year × 4 = ₹60L                               │
│  └── 5-Year TCO: ₹77L                                              │
│                                                                    │
│  SAVINGS WITH ZABBIX: ₹33L-₹69L over 5 years                       │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

#### Agent vs Agentless Monitoring Decision

Hybrid Approach Selected:

| Device Type | Method | Reasoning |
| --- | --- | --- |
| **Network gear** (FortiGate, HPE switches) | Agentless (SNMP) | No agent installation possible on appliances |
| **Servers** (R760 VMs) | Zabbix Agent | Detailed OS metrics, log monitoring |
| **Storage** (HD6500) | Agentless (SNMP + API) | Native DSM integration, no agent needed |
| **UPS** | Agentless (SNMP) | Standard SNMP MIB support |

Agent Advantages:

Can monitor internal metrics (processes, logs, custom scripts)

Works behind NAT/firewall (active connection from agent to server)

Lower network overhead (pushes vs polls)

Agentless Advantages:

No software installation required

Works with any SNMP-enabled device

Simpler management (no agent updates)

#### SNMP v3 Security Requirements

┌────────────────────────────────────────────────────────────────────┐
│                    SNMP v3 SECURITY CONFIGURATION                  │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  Security Level: authPriv (Authentication + Encryption)            │
│                                                                    │
│  Authentication:                                                   │
│  ├── Protocol: SHA-256 (not MD5/SHA1)                              │
│  └── Passphrase: 16+ characters, complex                           │
│                                                                    │
│  Privacy (Encryption):                                             │
│  ├── Protocol: AES-256 (not DES)                                   │
│  └── Passphrase: Unique per device, rotated quarterly              │
│                                                                    │
│  User Configuration:                                               │
│  ├── Username: zabbix-monitor (unique per device recommended)      │
│  ├── Context: Device-specific (where supported)                    │
│  └── Access: Read-only (noWrite, noNotify for strictest)           │
│                                                                    │
│  Network:                                                          │
│  └── SNMP traffic restricted to Management VLAN (VLAN 40)          │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

Design Rationale: Zabbix was selected because it provides enterprise-grade monitoring capabilities at a fraction of the cost of commercial alternatives. For B2H Studios' scale (~50 monitored devices), the feature gap between Zabbix and PRTG/SolarWinds is negligible, while the cost savings (₹33-69 Lakhs over 5 years) are substantial.

### 3.2 Monitoring Coverage Design

#### What We Monitor (The "Four Pillars")

| Pillar | Metrics | Business Impact |
| --- | --- | --- |
| **Availability** | Uptime, ping, service status | Revenue protection |
| **Performance** | CPU, memory, disk I/O, latency | User experience |
| **Capacity** | Disk usage, bandwidth, licensing | Growth planning |
| **Security** | Failed logins, threats, anomalies | Breach prevention |

Detailed Coverage Matrix:

| Device | Availability | Performance | Capacity | Security |
| --- | --- | --- | --- | --- |
| FortiGate | ✅ Ping, HA status | ✅ CPU, memory, sessions | ✅ Bandwidth | ✅ Threats, VPN |
| HD6500 | ✅ Ping, RAID status | ✅ IOPS, latency | ✅ Volume usage | ✅ Snapshots, access |
| HPE Switches | ✅ Ping, VSX status | ✅ CPU, port utilization | ✅ Port counters | ✅ MAC anomalies |
| R760 VMs | ✅ Ping, service status | ✅ CPU, memory, disk | ✅ Disk usage | ✅ Logins, processes |
| UPS | ✅ Status | ✅ Load % | ✅ Battery | N/A |

#### What We Don't Monitor (and Why)

| Not Monitored | Reason | Risk Assessment |
| --- | --- | --- |
| Individual workstation health | Too many endpoints, low criticality | Low — users report issues |
| Printer status | Not business-critical | Low — facilities handle |
| Environmental (detailed) | Separate BMS system | Medium — integrate if budget allows |
| Application performance (deep) | Requires APM tools (extra cost) | Medium — consider AppDynamics/Dynatrace later |
| User behavior analytics | Requires UEBA/SIEM correlation | Covered by Splunk correlation rules |

#### Threshold Setting Methodology (Baseline + 20%)

┌────────────────────────────────────────────────────────────────────┐
│              THRESHOLD SETTING METHODOLOGY                         │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  PHASE 1: BASELINE COLLECTION (Weeks 1-2)                          │
│  ├── Collect metrics without alerts                               │
│  ├── Identify normal operating ranges                              │
│  ├── Note peak usage periods                                       │
│  └── Document business hours patterns                              │
│                                                                    │
│  PHASE 2: THRESHOLD CALCULATION                                    │
│  ├── Warning threshold: Baseline average + 20%                     │
│  ├── High threshold: Baseline peak + 10%                           │
│  └── Critical threshold: Baseline peak + 20%                       │
│                                                                    │
│  EXAMPLE: CPU Utilization on R760                                  │
│  ├── Baseline average: 35%                                         │
│  ├── Baseline peak (observed): 65%                                 │
│  ├── Warning: 35% × 1.2 = 42% → rounded to 45%                     │
│  ├── High: 65% × 1.1 = 71.5% → rounded to 70%                      │
│  └── Critical: 65% × 1.2 = 78% → rounded to 80%                    │
│                                                                    │
│  PHASE 3: VALIDATION (Weeks 3-4)                                   │
│  ├── Enable alerts with low-noise channels                         │
│  ├── Tune thresholds based on false positives                      │
│  └── Document final thresholds                                     │
│                                                                    │
│  REVIEW CYCLE: Quarterly threshold review                          │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

### 3.3 Alert Escalation Design

#### Why P1/P2/P3/P4 Classification

ITIL-Aligned Severity Levels:

| Severity | Definition | Examples | Business Impact |
| --- | --- | --- | --- |
| **P1 — Critical** | Complete service outage | Site down, NAS failure, ransomware | Production stopped |
| **P2 — High** | Major functionality impaired | Replication lag >1hr, VM crash | Significant degradation |
| **P3 — Medium** | Minor functionality affected | Single AP down, disk predictive fail | Workaround available |
| **P4 — Low** | Cosmetic issues | Non-critical service restart | No business impact |
| **P5 — Info** | Informational only | Successful backup completed | Logging only |

Why This Classification Works:

Industry standard (ITIL v4)

Clear priority for on-call engineers

Maps directly to SLA commitments

Enables meaningful reporting (MTTR by severity)

#### Response Time Targets (SLOs)

| Severity | Response Time | Resolution Target | Escalation Timeline |
| --- | --- | --- | --- |
| P1 — Critical | 15 minutes | 2 hours | 15 min → IT Manager → 30 min → CTO |
| P2 — High | 1 hour | 4 hours | 2 hr → Senior Admin → 4 hr → IT Manager |
| P3 — Medium | 4 hours | 24 hours | Next business day → Senior Admin |
| P4 — Low | 24 hours | 72 hours | Weekly review |

#### Who Gets Alerted When (On-Call Rotation)

┌────────────────────────────────────────────────────────────────────┐
│              ON-CALL ROTATION SCHEDULE                             │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  PRIMARY ON-CALL:                                                  │
│  ├── Rotation: Weekly (Monday 00:00 - Sunday 23:59)                │
│  ├── Coverage: 24×7                                                │
│  ├── Notification: SMS + Mobile App + Email                        │
│  └── Response obligation: 15 minutes (P1)                          │
│                                                                    │
│  SECONDARY ON-CALL (Escalation):                                   │
│  ├── Same rotation as primary (different person)                   │
│  ├── Activated if primary doesn't acknowledge in 15 minutes        │
│  └── Notification: SMS + Phone call                                │
│                                                                    │
│  MANAGEMENT ESCALATION:                                            │
│  ├── IT Manager: After 30 minutes (P1)                             │
│  └── CTO: After 1 hour (P1 unresolved)                             │
│                                                                    │
│  ROTATION EXAMPLE:                                                 │
│  ├── Week 1: Rahul (Primary), Priya (Secondary)                    │
│  ├── Week 2: Priya (Primary), Arun (Secondary)                     │
│  └── Week 3: Arun (Primary), Rahul (Secondary)                     │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

#### Alert Fatigue Prevention (Correlation, Deduplication)

Alert Fatigue Mitigation Strategies:

┌────────────────────────────────────────────────────────────────────┐
│              ALERT FATIGUE PREVENTION MEASURES                     │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  1. CORRELATION (Zabbix Dependency Configuration):                 │
│     ├── Parent: Core switch down                                   │
│     ├── Children: All connected devices "unreachable"              │
│     └── Result: ONE alert (switch), not 50 (all devices)           │
│                                                                    │
│  2. DEDUPLICATION:                                                 │
│     ├── Same problem within 1 hour = suppress duplicate            │
│     ├── Flapping detection: 3+ state changes = maintenance mode    │
│     └── Acknowledgment stops escalation                            │
│                                                                    │
│  3. MAINTENANCE WINDOWS:                                           │
│     ├── Scheduled: Change windows pre-defined                      │
│     ├── Ad-hoc: One-click maintenance mode in Zabbix               │
│     └── Automatic: Backup windows (no alerts for expected I/O)     │
│                                                                    │
│  4. SEVERITY-BASED CHANNELS:                                       │
│     ├── P1: SMS + Phone + Slack + Email                            │
│     ├── P2: Slack + Email                                          │
│     ├── P3: Email only                                             │
│     └── P4: Dashboard only (no notification)                       │
│                                                                    │
│  5. SHIFT HANDOFF:                                                 │
│     └── Automated digest of active alerts at shift change          │
│                                                                    │
│  TARGET: <5 actionable alerts per day per on-call engineer         │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

### 3.4 Dashboard Design Philosophy

#### NOC Dashboard Layout (What Goes Where)

┌────────────────────────────────────────────────────────────────────┐
│  NOC DASHBOARD — NETWORK OPERATIONS CENTER                         │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  ┌─────────────────────────────────────────────────────────────┐   │
│  │ TOP ROW — Executive Summary (Always Visible)                │   │
│  │ [Health Score] [Uptime %] [Active Alerts P1/P2/P3] [SLA]    │   │
│  └─────────────────────────────────────────────────────────────┘   │
│                                                                    │
│  ┌──────────────────────┐  ┌──────────────────────────────────┐   │
│  │ LEFT COLUMN          │  │ RIGHT COLUMN                     │   │
│  │ ─────────────        │  │ ────────────                     │   │
│  │                      │  │                                  │   │
│  │ Network Health       │  │ Storage Health                   │   │
│  │ ┌────────────────┐   │  │ ┌────────────────────────────┐   │   │
│  │ │ FortiGate CPU  │   │  │ │ HD6500 Capacity Trend      │   │   │
│  │ │ Bandwidth Graph│   │  │ │ Replication Lag            │   │   │
│  │ │ VPN Sessions   │   │  │ │ RAID Status                │   │   │
│  │ └────────────────┘   │  │ └────────────────────────────┘   │   │
│  │                      │  │                                  │   │
│  │ Switch Status        │  │ Compute Health                   │   │
│  │ ┌────────────────┐   │  │ ┌────────────────────────────┐   │   │
│  │ │ VSX Stack      │   │  │ │ VM Resource Usage          │   │   │
│  │ │ Port Utilization│   │  │ │ Service Status Grid        │   │   │
│  │ └────────────────┘   │  │ └────────────────────────────┘   │   │
│  │                      │  │                                  │   │
│  │ Security Overview    │  │ Power & Environment              │   │
│  │ ┌────────────────┐   │  │ ┌────────────────────────────┐   │   │
│  │ │ Failed Logins  │   │  │ │ UPS Status                 │   │   │
│  │ │ Blocked Threats│   │  │ │ Rack Temperature           │   │   │
│  │ └────────────────┘   │  │ └────────────────────────────┘   │   │
│  │                      │  │                                  │   │
│  └──────────────────────┘  └──────────────────────────────────┘   │
│                                                                    │
│  REFRESH RATE: 1 minute (NOC), 5 minutes (Executive)               │
│  COLOR CODING: Green/Yellow/Red status indicators                  │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

#### Executive Dashboard (High-Level Health)

Audience: IT Manager, CTO, Business Stakeholders

| Widget | Metric | Visual |
| --- | --- | --- |
| Overall Health Score | 0-100 composite | Large gauge |
| SLA Compliance | % of time within SLA | Trend line |
| Incident Count | P1/P2/P3 this month | Bar chart |
| Capacity Forecast | Days until capacity limit | Warning indicator |
| DR Status | Last test date, sync status | Green/Yellow/Red |
| Security Posture | Open threats, blocked attacks | Summary count |

#### Technical Dashboard (Detailed Metrics)

Audience: Network Admin, System Admin, Security Admin

Network Admin View: FortiGate deep dive, routing tables, VPN tunnels, interface errors

System Admin View: VM performance, disk I/O, memory pressure, process lists

Security Admin View: Splunk integration, threat feeds, correlation alerts, honeypot status

### 3.5 Splunk SIEM Design

#### Why Splunk (Not ELK, QRadar, Sentinel)

| Factor | Splunk | ELK Stack | QRadar | Azure Sentinel |
| --- | --- | --- | --- | --- |
| **Search Language** | SPL (excellent) | KQL/Lucene (good) | AQL (good) | KQL (good) |
| **Learning Curve** | Moderate | High | High | Moderate |
| **Correlation Rules** | Excellent | Build yourself | Excellent | Good |
| **Compliance Reports** | Pre-built | Custom build | Pre-built | Some |
| **Vendor Support** | Excellent | Community/Elastic | Good | Microsoft |
| **On-prem Option** | ✅ Yes | ✅ Yes | ✅ Yes | ❌ Cloud only |
| **Cost (50GB/day)** | ₹6.5L/year | ₹2L/year (support) | ₹25L+/year | ₹4L/year |
| **Data Residency** | ✅ India possible | ✅ Self-controlled | ✅ India possible | ❌ Global cloud |

Why Splunk Was Selected:

Time-to-Value: Pre-built correlation rules for security use cases

Staffing: B2H Studios lacks specialists to maintain ELK

Compliance: ISO 27001 reports out-of-the-box

Data Residency: Can be deployed entirely on-premises in India

Trade-off Analysis: Splunk costs 3× ELK but delivers 5× faster deployment and requires 0.5× staff time. For B2H Studios' resource constraints, this trade-off favors Splunk.

#### Log Source Prioritization

| Priority | Source | Volume/Day | Why Critical |
| --- | --- | --- | --- |
| **P1 — Critical** | FortiGate | 10 GB | Perimeter security, all traffic visibility |
| **P1 — Critical** | HD6500 DSM | 5 GB | Data integrity, access audit |
| **P2 — High** | Windows Servers | 5 GB | VM security, authentication |
| **P2 — High** | Kaspersky | 3 GB | Endpoint protection status |
| **P3 — Medium** | FortiAnalyzer | 3 GB | Aggregated FortiGate logs |
| **P3 — Medium** | HPE Switches | 1 GB | Network security |
| **P4 — Low** | FortiAuthenticator | 1 GB | Authentication logs |
| **P4 — Low** | HashiCorp Vault | 500 MB | Secrets access audit |

#### Correlation Rule Design

Brute Force Detection Logic:

| tstats `summariesonly` count from datamodel=Authentication 
  where action=failure by src_ip, user, _time 
| bucket _time span=5m 
| stats count by src_ip, user, _time 
| where count > 5 
| eval severity="high" 
| table src_ip, user, count, severity

Honeypot Trigger Logic:

| index=dms source="/var/log/samba/honeypot_access.log" 
| stats count by src_ip, file_accessed 
| where count > 0 
| lookup honeypot_files.csv file_accessed 
| eval alert_type="HONEYPOT_BREACH", severity="critical" 
| table _time, src_ip, file_accessed, severity

Data Exfiltration Detection:

| tstats `summariesonly` sum(bytes_out) as total_bytes 
  from datamodel=Network_Traffic.All_Traffic 
  where dest_ip!=10.0.0.0/8 AND dest_ip!=172.16.0.0/12 
  by src_ip, _time 
| bucket _time span=1h 
| stats sum(total_bytes) as hourly_bytes by src_ip, _time 
| eval hourly_gb = hourly_bytes/1024/1024/1024 
| where hourly_gb > 100 
| eval severity=if(hourly_gb>500, "critical", "high")

#### Retention Tiering Rationale (Hot/Warm/Cold)

┌────────────────────────────────────────────────────────────────────┐
│                    SPLUNK RETENTION TIERING                        │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  HOT TIER (90 days on SSD):                                        │
│  ├── Storage: Splunk indexers with NVMe/SSD                        │
│  ├── Performance: Sub-second search                                │
│  ├── Cost: High (₹25/TB/day)                                       │
│  └── Use Case: Security investigations, operational troubleshooting│
│                                                                    │
│  WARM TIER (91 days — 1 year on HDD):                              │
│  ├── Storage: Splunk indexers with SAS HDD                         │
│  ├── Performance: 2-5 second search                                │
│  ├── Cost: Medium (₹8/TB/day)                                      │
│  └── Use Case: Compliance queries, trend analysis                  │
│                                                                    │
│  COLD TIER (1 year — 3 years on Wasabi):                           │
│  ├── Storage: Wasabi S3 object storage                             │
│  ├── Performance: Restore required (minutes)                       │
│  ├── Cost: Low (₹16.5/TB/month = ₹0.55/TB/day)                     │
│  └── Use Case: Long-term compliance, forensic preservation         │
│                                                                    │
│  RATIONALE FOR 90-DAY HOT:                                         │
│  ├── Most security incidents detected within 30 days               │
│  ├── Quarterly audits need 90-day window                           │
│  ├── Diminishing returns after 90 days                             │
│  └── Cost optimization for high-performance storage                │
│                                                                    │
│  RATIONALE FOR 3-YEAR TOTAL:                                       │
│  ├── ISO 27001 requires 3-year log retention                       │
│  ├── Legal hold requirements typically 3-7 years                   │
│  └── Beyond 3 years: Frozen tier (tape, optional)                  │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

### 3.6 MANDATORY FLOWCHART: Monitoring Alert Flow

flowchart LR
    Issue[Issue Detected<br/>Infrastructure] --> Zabbix[Zabbix Agent/SNMP]
    
    Zabbix --> Classify{Classify Severity}
    
    Classify -->|P1 Critical| Page[Page On-Call<br/>SMS + Phone]
    Classify -->|P2 High| Email[Email Team<br/>+ Slack Alert]
    Classify -->|P3 Medium| Ticket[Create Ticket<br/>ServiceNow]
    Classify -->|P4 Low| Log[Log Only<br/>Dashboard Update]
    
    Page --> Response[15min Response<br/>Required]
    Response --> Ack{Acknowledged?}
    
    Ack -->|Yes| Resolve[Work to Resolve]
    Ack -->|No| Escalate[Escalate to Manager<br/>+30min]
    
    Resolve --> Fixed{Resolved?}
    Fixed -->|Yes| Close[Close Incident<br/>Document]
    Fixed -->|No| Escalate
    
    Email --> Response2[1hr Response]
    Ticket --> Response3[4hr Response]
    
    style Issue fill:#f0ad4e,stroke:#c6892b,stroke-width:2px,color:#000
    style Classify fill:#4a90d9,stroke:#2c5a8c,stroke-width:2px,color:#fff
    style Page fill:#d9534f,stroke:#a9302a,stroke-width:2px,color:#fff
    style Close fill:#5cb85c,stroke:#3d7a3d,stroke-width:2px,color:#fff
    style Escalate fill:#d9534f,stroke:#a9302a,stroke-width:2px,color:#fff

Flowchart Reference: The Monitoring Alert Flow diagram illustrates the complete alert lifecycle from detection through resolution. The classification gate ensures appropriate response resources are allocated based on severity, while the escalation paths guarantee no critical alert goes unaddressed.

### 3.7 MANDATORY FLOWCHART: Splunk Log Flow

flowchart LR
    Sources[Log Sources<br/>FortiGate, DSM, Windows] --> Forwarders[Universal Forwarders]
    
    Forwarders --> Indexers[Indexers<br/>2× Clustered]
    
    Indexers --> Hot[Hot 90d<br/>SSD Storage]
    Indexers --> Warm[Warm 1yr<br/>HDD Storage]
    Indexers --> Cold[Cold 3yr<br/>Wasabi Archive]
    
    Indexers --> Search[Search Head]
    Search --> Alerts[Alert Engine<br/>Correlation Rules]
    Search --> Dashboards[Dashboards<br/>Executive + Technical]
    
    Alerts --> SOC[SOC Team<br/>Email, SMS, Slack]
    Dashboards --> Users[Analysts, Admin]
    
    style Sources fill:#f0ad4e,stroke:#c6892b,stroke-width:2px,color:#000
    style Indexers fill:#4a90d9,stroke:#2c5a8c,stroke-width:2px,color:#fff
    style Search fill:#5cb85c,stroke:#3d7a3d,stroke-width:2px,color:#fff
    style Alerts fill:#d9534f,stroke:#a9302a,stroke-width:2px,color:#fff

Flowchart Reference: The Splunk Log Flow diagram shows how log data flows from sources through forwarders to clustered indexers, where it's tiered by age and searchable via the search head. This architecture ensures both high availability (clustered indexers) and cost-effective long-term storage (Wasabi cold tier).

## 4. Power Infrastructure — Power Design Calculations

### 4.1 Load Calculation Detail

#### Every Device's Power Draw (Idle, Typical, Peak)

| Device | Qty | Idle Watts | Typical Watts | Peak Watts | Duty Cycle | Weighted Avg |
| --- | --- | --- | --- | --- | --- | --- |
| HD6500 | 2 | 800W | 1,200W | 1,400W | 95% | 1,140W × 2 = 2,280W |
| Dell R760 | 2 | 400W | 800W | 1,100W | 80% | 640W × 2 = 1,280W |
| FortiGate 120G | 4 | 120W | 180W | 200W | 100% | 180W × 4 = 720W |
| HPE CX 6300M | 4 | 80W | 130W | 150W | 100% | 130W × 4 = 520W |
| FortiAP 431F | 8 | 8W | 18W | 25W | 100% | 18W × 8 = 144W |
| PDUs/KVM/Fans | — | 100W | 200W | 300W | 100% | 200W |
| **TOTALS** | **1,588W** | **3,728W** | **5,175W** | **5,144W** |  |  |

Calculation Detail — Weighted Average Formula:

Weighted Average = (Idle × 0.2) + (Typical × 0.6) + (Peak × 0.2)

HD6500 Example:
= (800W × 0.2) + (1200W × 0.6) + (1400W × 0.2)
= 160W + 720W + 280W
= 1,160W (rounded to 1,140W for conservative estimate)

#### Power Factor Explanation

Apparent vs. Real Power:

┌────────────────────────────────────────────────────────────────────┐
│                    POWER FACTOR EXPLANATION                        │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  Real Power (Watts):                                               │
│  ├── The actual work being done                                    │
│  ├── What devices consume and convert to heat/light/processing     │
│  └── B2H Studios load: 5,144W                                      │
│                                                                    │
│  Apparent Power (VA):                                              │
│  ├── What the UPS must supply                                      │
│  ├── Includes reactive power (inductance/capacitance)              │
│  └── Formula: Watts ÷ Power Factor                                 │
│                                                                    │
│  Power Factor (PF):                                                │
│  ├── Ratio of real power to apparent power (0.0 to 1.0)            │
│  ├── Modern servers: 0.9 to 0.99                                   │
│  ├── Legacy equipment: 0.7 to 0.85                                 │
│  └── B2H Studios (modern gear): 0.95 average                       │
│                                                                    │
│  CALCULATION:                                                      │
│  ├── Real Power: 5,144W                                            │
│  ├── Power Factor: 0.95                                            │
│  ├── Apparent Power: 5,144 ÷ 0.95 = 5,415 VA                       │
│  └── With 20% headroom: 5,415 × 1.2 = 6,498 VA                     │
│                                                                    │
│  UPS SELECTION: 10,000 VA (provides 54% headroom)                  │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

#### Diversity Factor (Not Everything Peaks Simultaneously)

Diversity Factor Application:

Sum of individual peaks: 5,175W × 1.2 (PF) = 6,210 VA
Diversity factor: 0.85 (not all devices peak at same time)
Diversified load: 6,210 VA × 0.85 = 5,279 VA

Why 0.85 Diversity Factor?
- HD6500 and R760 rarely peak simultaneously
- Network gear has constant draw
- Statistical probability of simultaneous peak: <15%

Conservative UPS sizing uses 0.85; aggressive could use 0.75
We use 0.85 for safety margin

### 4.2 UPS Sizing Math

#### Step-by-Step Calculation

┌────────────────────────────────────────────────────────────────────┐
│                    UPS SIZING CALCULATION                          │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  STEP 1: Calculate Real Power Load                                 │
│  ├── HD6500 (2×): 2,280W                                           │
│  ├── R760 (2×): 1,280W                                             │
│  ├── FortiGate (4×): 720W                                          │
│  ├── HPE Switches (4×): 520W                                       │
│  ├── FortiAP (8×): 144W                                            │
│  ├── Miscellaneous: 200W                                           │
│  └── TOTAL REAL POWER: 5,144W                                      │
│                                                                    │
│  STEP 2: Convert to Apparent Power                                 │
│  ├── Power Factor: 0.95                                            │
│  ├── Apparent Power: 5,144W ÷ 0.95 = 5,415 VA                      │
│  └── Note: UPS ratings are in VA (apparent power)                  │
│                                                                    │
│  STEP 3: Apply Diversity Factor                                    │
│  ├── Diversity Factor: 0.85                                        │
│  ├── Diversified Load: 5,415 VA × 0.85 = 4,603 VA                  │
│  └── This is the "realistic" maximum load                          │
│                                                                    │
│  STEP 4: Apply Headroom                                            │
│  ├── Headroom Required: 20% (industry standard)                    │
│  ├── UPS Size Needed: 4,603 VA × 1.2 = 5,524 VA                    │
│  └── Allows for future growth and UPS aging                        │
│                                                                    │
│  STEP 5: Select Standard Size                                      │
│  ├── Calculated Need: 5,524 VA                                     │
│  ├── Standard Sizes Available: 3kVA, 5kVA, 6kVA, 8kVA, 10kVA       │
│  ├── 5kVA/6kVA: Insufficient headroom                              │
│  └── SELECTED: 10kVA (provides 82% headroom = excellent)           │
│                                                                    │
│  STEP 6: N+1 Redundancy                                            │
│  ├── Each 10kVA UPS can handle full load alone                     │
│  ├── Two UPS units provide redundancy                              │
│  └── If one fails, other carries 55% load (well within capacity)   │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

#### Headroom Justification (20%)

Why 20% Headroom (Not 10% or 30%):

| Headroom | Pros | Cons | Verdict |
| --- | --- | --- | --- |
| 10% | Lower upfront cost | No room for growth; UPS runs hot | ❌ Too tight |
| **20%** | Balanced; industry standard | Slightly higher cost | ✅ **OPTIMAL** |
| 30% | Maximum flexibility | Oversized, inefficient at low load | ❌ Unnecessary |

20% Headroom Covers:

Battery aging (capacity decreases 2-3% per year)

Ambient temperature variations (higher temp = lower capacity)

Short-term overloads (startup surges)

Future equipment additions (10-15% growth)

#### Runtime Calculation at Various Loads

APC Smart-UPS SRT 10kVA Runtime:

| Load % | Load Watts | Runtime | Use Case |
| --- | --- | --- | --- |
| 50% | 5,000W | ~75 minutes | Extended generator startup |
| 70% | 7,000W | ~45 minutes | Full load with safety margin |
| 90% | 9,000W | ~20 minutes | Peak load, brief duration only |
| 100% | 10,000W | ~12 minutes | Emergency shutdown only |

Runtime Calculation Detail:

Battery Specifications:
├── Battery Type: Maintenance-free sealed lead-acid
├── Voltage: 192V (16× 12V batteries)
├── Capacity: 9Ah per string
├── Energy: 192V × 9Ah = 1,728 Wh
├── Usable (80% depth of discharge): 1,382 Wh
└── Efficiency (online UPS): 95%

Runtime Formula:
Runtime = (Battery Energy × Efficiency) ÷ Load

At 70% load (7,000W):
Runtime = (1,382 Wh × 0.95) ÷ 7,000W
Runtime = 1,313 Wh ÷ 7,000W
Runtime = 0.188 hours = 11.3 minutes (per UPS)

With 2× UPS (N+1):
Runtime remains ~45 minutes (parallel operation)

#### Why 45 Minutes is Sufficient (Generator/Transfer Time)

┌────────────────────────────────────────────────────────────────────┐
│              POWER FAILURE RESPONSE TIMELINE                       │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  T+0:00    Utility Power Fails                                     │
│            ├── UPS detects outage (<4ms for online UPS)            │
│            ├── UPS switches to battery (zero transfer time)        │
│            └── Equipment continues operating uninterrupted         │
│                                                                    │
│  T+0:10    Generator Auto-Start Signal Sent                        │
│            ├── AMF panel detects power loss                        │
│            └── Generator starter motor engages                     │
│                                                                    │
│  T+0:30    Generator Cranking                                      │
│            └── Diesel engine starts, reaches idle speed            │
│                                                                    │
│  T+0:45    Generator At Operating Speed                            │
│            └── Output voltage and frequency stabilizing            │
│                                                                    │
│  T+1:00    Generator Stable                                        │
│            ├── Voltage: 230V ±5%                                   │
│            ├── Frequency: 50Hz ±0.5%                               │
│            └── AMF prepares to transfer load                       │
│                                                                    │
│  T+1:10    ATS Transfer to Generator                               │
│            └── Load switches from UPS to generator                 │
│                                                                    │
│  T+1:15    UPS Returns to Normal Mode                              │
│            ├── UPS input now from generator                        │
│            ├── Battery charging begins                             │
│            └── System stable on generator power                    │
│                                                                    │
│  TOTAL TIME ON BATTERY: ~75 seconds                                │
│                                                                    │
│  UPS RUNTIME AVAILABLE: 45 minutes                                 │
│  SAFETY MARGIN: 44+ minutes (99.9% buffer)                         │
│                                                                    │
│  NO GENERATOR SCENARIO:                                            │
│  ├── UPS provides 45 minutes runtime                               │
│  ├── Graceful shutdown initiated at 30 minutes                     │
│  └── All systems shut down cleanly with 15 minutes spare           │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

### 4.3 Online vs. Line-Interactive Deep Dive

#### Topology Differences (Double-Conversion vs. Standby)

┌────────────────────────────────────────────────────────────────────┐
│              UPS TOPOLOGY COMPARISON                               │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  ONLINE (DOUBLE-CONVERSION) — SELECTED                             │
│  ┌─────────────────────────────────────────────────────────────┐   │
│  │  AC Input ──► Rectifier ──► DC Bus ──► Inverter ──► AC Out  │   │
│  │                  │              ▲                           │   │
│  │                  ▼              │                           │   │
│  │               Battery (always connected)                    │   │
│  └─────────────────────────────────────────────────────────────┘   │
│                                                                    │
│  • Power always flows through rectifier/inverter                   │
│  • Battery always in circuit (zero transfer time)                  │
│  • Complete isolation from grid (voltage, frequency, noise)        │
│  • Efficiency: 92-96% (some loss to heat)                          │
│                                                                    │
│  LINE-INTERACTIVE (NOT SELECTED)                                   │
│  ┌─────────────────────────────────────────────────────────────┐   │
│  │         ┌──────────────────────────────────────────┐        │   │
│  │         ▼                                          │        │   │
│  │  AC Input ──► AVR ──► AC Out (normal operation)    │        │   │
│  │         │                                          │        │   │
│  │         ▼ (on outage)                              │        │   │
│  │      Inverter ◄── Battery                         │        │   │
│  │         │                                          │        │   │
│  │         └──────────────────────────────────────────┘        │   │
│  └─────────────────────────────────────────────────────────────┘   │
│                                                                    │
│  • Power bypasses inverter during normal operation                 │
│  • Transfer time: 4-8 milliseconds                                 │
│  • AVR (Automatic Voltage Regulation) handles small sags/swells    │
│  • Efficiency: 97-99% (more efficient)                             │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

#### Power Quality Comparison

| Power Issue | Online UPS Protection | Line-Interactive Protection | Impact if Unprotected |
| --- | --- | --- | --- |
| Outage | ✅ Zero transfer | ⚠️ 4-8ms transfer | Server crash, data corruption |
| Voltage sag | ✅ Full correction | ✅ AVR correction | Equipment shutdown |
| Voltage swell | ✅ Full isolation | ✅ AVR correction | Equipment damage |
| Frequency variation | ✅ Full regeneration | ❌ Passes through | Clock drift, sync issues |
| Electrical noise | ✅ Complete filtering | ⚠️ Partial filtering | Data errors, hardware damage |
| Harmonic distortion | ✅ Sine wave output | ⚠️ Some distortion | Power supply stress |

#### Transfer Time Implications

The 4-8ms Problem:

Modern server power supplies have hold-up time of:
├── Typical: 16-20 milliseconds at full load
├── Aged power supply: 10-12 milliseconds
└── Worst case: 8-10 milliseconds

Line-interactive transfer: 4-8ms
Safety margin: 8ms - 4ms = 4ms (TOO TIGHT)

With aged power supplies or marginal conditions:
Transfer time + power supply degradation = CRASH

Online UPS transfer: 0ms (always on inverter)
Safety margin: Unlimited
Verdict: No risk of transfer-related outages

#### When Line-Interactive is Acceptable (and Why Not Here)

Line-Interactive IS Acceptable For:

Desktop workstations (PSU hold-up sufficient)

Network printers (non-critical)

Small office servers (1-2 units, non-critical)

Environments with stable power (low outage frequency)

Why NOT Here:

Data center with 50+ devices (cascade failure risk)

Video editing workstations (data loss = hours of work)

NAS storage (corruption affects all users)

Post-production deadlines (downtime = contract breach)

Design Rationale: The ₹3 Lakh savings from line-interactive UPS is insignificant compared to the risk of a 10-minute outage costing ₹5+ Lakhs in missed deadlines and reputation damage. Online UPS is non-negotiable for this environment.

### 4.4 Dual UPS with ATS Design

#### Single Points of Failure Eliminated

┌────────────────────────────────────────────────────────────────────┐
│              SINGLE POINT OF FAILURE ANALYSIS                      │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  SINGLE UPS CONFIGURATION (❌ NOT USED):                           │
│  ┌─────────┐                                                       │
│  │  UPS A  │──► Load                                               │
│  └─────────┘                                                       │
│  ├── SPOF: UPS itself                                              │
│  ├── SPOF: Battery system                                          │
│  ├── SPOF: Internal inverter                                       │
│  └── Maintenance = DOWNTIME                                        │
│                                                                    │
│  DUAL UPS WITH ATS CONFIGURATION (✅ SELECTED):                    │
│  ┌─────────┐      ┌─────────┐                                      │
│  │  UPS A  │◄────►│  UPS B  │                                      │
│  └────┬────┘  ATS └────┬────┘                                      │
│       └────────────────┘                                           │
│              │                                                     │
│              ▼                                                     │
│            Load                                                    │
│                                                                    │
│  SINGLE POINTS OF FAILURE ELIMINATED:                              │
│  ├── Individual UPS failure: Covered by parallel unit              │
│  ├── Battery failure: Each UPS has independent batteries           │
│  ├── Inverter failure: ATS switches to other UPS                   │
│  └── Maintenance: One UPS serviced while other carries load        │
│                                                                    │
│  REMAINING SPOF (Mitigated):                                       │
│  ├── ATS itself: Manual bypass available                           │
│  ├── Output distribution: Dual PDU paths                           │
│  └── Generator: Not required for 45-min runtime                    │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

#### Maintenance Window Creation

With Dual UPS, Maintenance is Non-Disruptive:

| Maintenance Activity | Single UPS | Dual UPS with ATS |
| --- | --- | --- |
| Battery replacement | 2-4 hour downtime | Zero downtime (transfer to UPS B) |
| Firmware update | 15-min downtime | Zero downtime (rolling update) |
| Capacity testing | Weekend required | Any time (load transfer) |
| Fan replacement | 1-hour downtime | Zero downtime |
| Annual PM | Scheduled outage | Online maintenance |

#### Failure Scenario Walkthrough

Scenario 1: UPS A Fails

T+0:00    UPS A internal fault detected
          ├── UPS A signals fault to ATS
          ├── ATS switches load to UPS B (<15ms)
          └── Users experience zero interruption

T+0:01    Zabbix alert triggered
          └── IT team notified of UPS A failure

T+0:30    IT team acknowledges alert
          └── Begins isolation of UPS A

T+1:00    UPS A safely isolated
          ├── UPS B carrying 100% load
          └── UPS A ready for service

Result: Zero downtime, UPS A repaired/replaced

Scenario 2: ATS Fails

T+0:00    ATS fails to switch or shows fault
          └── Manual bypass procedure initiated

T+0:05    IT team engages manual bypass
          └── Load connected directly to UPS A

T+0:10    ATS replaced or repaired
          └── Normal operation restored

Result: 10-minute manual intervention required
Mitigation: ATS is simple electro-mechanical device (rare failure)

Scenario 3: Both UPS Fail

T+0:00    UPS A fails
          └── ATS transfers to UPS B

T+0:30    UPS B fails (cascade failure)
          └── ATS has no power source

T+0:31    Load loses power (CRITICAL EVENT)
          └── Generator starts (if installed)

T+1:00    Generator at speed, ATS transfers
          └── Load restored on generator

Mitigation: Dual UPS failure probability <0.001%
           Generator provides third layer of protection

### 4.5 Generator Integration

#### ATS Transfer Timing

┌────────────────────────────────────────────────────────────────────┐
│              GENERATOR ATS TRANSFER SEQUENCE                       │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  AUTOMATIC MAINS FAILURE (AMF) PANEL LOGIC:                        │
│                                                                    │
│  1. Mains Voltage Monitoring                                       │
│     ├── Undervoltage threshold: 207V (90% of 230V)                 │
│     ├── Overvoltage threshold: 253V (110% of 230V)                 │
│     ├── Undervoltage duration: 2 seconds (prevents nuisance starts)│
│     └── Frequency tolerance: 47-53 Hz                              │
│                                                                    │
│  2. Generator Start Sequence                                       │
│     ├── Start signal sent to generator controller                  │
│     ├── Starter motor cranks (max 10 seconds)                      │
│     ├── Engine reaches idle speed (800 RPM)                        │
│     ├── Warm-up period: 30 seconds                                 │
│     └── Engine reaches rated speed (1500 RPM)                      │
│                                                                    │
│  3. Voltage Stabilization                                          │
│     ├── Alternator output monitored                                │
│     ├── Voltage regulator stabilizes output                        │
│     ├── Frequency locked to 50Hz                                   │
│     └── Stabilization time: 15-30 seconds                          │
│                                                                    │
│  4. Load Transfer                                                  │
│     ├── AMF confirms stable generator power                        │
│     ├── Break-before-make transfer (prevents backfeed)             │
│     ├── Load transferred to generator                              │
│     └── Total transfer time: <10 seconds from mains failure        │
│                                                                    │
│  5. Return to Mains                                                │
│     ├── Mains stable for 30 seconds                                │
│     ├── Cool-down period: 2 minutes (generator running unloaded)   │
│     ├── Transfer back to mains                                     │
│     └── Generator shutdown                                         │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

#### UPS Role During Generator Startup

The UPS as a Bridge:

┌────────────────────────────────────────────────────────────────────┐
│              UPS BRIDGE FUNCTION                                   │
├────────────────────────────────────────────────────────────────────┤
│                                                                    │
│  Timeline:                                                         │
│                                                                    │
│  Mains    ████████████████████████████████████████                 │
│  Power    ▲ Failure                                                │
│           │                                                        │
│  UPS      ▼░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░▼                 │
│  Battery    Battery Discharge (75 seconds)                         │
│                                                                    │
│  Gen      ░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░▲                │
│  Power                                              Generator      │
│                                                     Stable         │
│                                                                    │
│  Load     ████████████████████████████████████████████             │
│           ↑ Uninterrupted throughout                               │
│                                                                    │
│  UPS ACTIONS:                                                      │
│  ├── T+0: Mains fails, UPS takes over instantly                    │
│  ├── T+0-75s: UPS provides power from battery                      │
│  ├── T+75s: Generator stable, UPS returns to normal mode           │
│  └── UPS battery begins recharging                                 │
│                                                                    │
│  CRITICAL REQUIREMENT:                                             │
│  UPS runtime must exceed generator start time                      │
│  45 minutes >> 75 seconds ✓                                        │
│                                                                    │
└────────────────────────────────────────────────────────────────────┘

#### Frequency/Voltage Regulation

Generator Output Quality vs. UPS Tolerance:

| Parameter | Generator Output | UPS Tolerance | Pass/Fail |
| --- | --- | --- | --- |
| Voltage | 230V ±5% (218-242V) | ±10% (207-253V) | ✅ Pass |
| Frequency | 50Hz ±0.5% (49.75-50.25Hz) | ±5% (47.5-52.5Hz) | ✅ Pass |
| THD (Harmonics) | <5% | <10% | ✅ Pass |
| Transient Response | ±10% for 2 sec | ±15% for 10 sec | ✅ Pass |

UPS Acceptance of Generator Power:

Online UPS regenerates output (generator quality less critical)

Voltage/frequency variations isolated by double-conversion

Generator only needs to be "good enough" for UPS input

UPS provides "perfect" power to load regardless of generator quality

### 4.6 MANDATORY FLOWCHART: Power Failure Response

flowchart TD
    Power[Power Failure<br/>Utility Outage] --> UPS[UPS Battery<br/>Takes Over]
    
    UPS --> GenCheck{Generator<br/>Installed?}
    
    GenCheck -->|Yes| GenStart[Generator Starts<br/>~60 seconds]
    GenStart --> GenStable{Generator<br/>Stable?}
    GenStable -->|Yes| Transfer[ATS Transfer<br/>Load to Generator]
    Transfer --> Stable[Stable Power<br/>UPS Recharges]
    
    GenCheck -->|No| Runtime[UPS Runtime<br/>45 Minutes]
    Runtime --> Shutdown[Graceful Shutdown<br/>@ 30 Minutes]
    
    GenStable -->|No| Runtime
    
    Power --> MainsCheck{Mains<br/>Returns?}
    MainsCheck -->|Before Gen| UPS
    MainsCheck -->|After Transfer| Return[Return to Mains<br/>2-min Cooldown]
    
    style Power fill:#f0ad4e,stroke:#c6892b,stroke-width:2px,color:#000
    style UPS fill:#4a90d9,stroke:#2c5a8c,stroke-width:2px,color:#fff
    style Stable fill:#5cb85c,stroke:#3d7a3d,stroke-width:3px,color:#fff
    style Shutdown fill:#d9534f,stroke:#a9302a,stroke-width:2px,color:#fff

Flowchart Reference: The Power Failure Response flowchart demonstrates the layered protection strategy. UPS provides immediate protection, generator provides extended runtime, and graceful shutdown protects data if both fail. The decision points ensure optimal response for each scenario.

## Appendix: Summary of Design Rationale

### Backup Architecture Key Decisions

| Decision | Selection | Reasoning |
| --- | --- | --- |
| Backup strategy | 3-2-1-1-0 | Ransomware protection requires immutability |
| Primary replication | Snapshot Replication | Native, efficient, preserves metadata |
| Cloud archive | Hyper Backup + Wasabi | Compression, encryption, zero egress |
| Snapshot interval | 2 hours | RPO vs. overhead sweet spot |
| Retention | 24hr + 30day + 12mo + 3yr | Matches post-production workflow |
| Immutability | 7-year WORM | Contractual requirement |

### DR Architecture Key Decisions

| Decision | Selection | Reasoning |
| --- | --- | --- |
| DR tier | Hot (Tier 3) | 10-min RTO meets business needs |
| Failover type | Manual | Prevents split-brain, allows verification |
| Replication | Real-time RTRR | Block-level efficiency |
| Bandwidth throttle | 80% business hours | Protects production traffic |
| Site B spec | Lighter R760 | Cost optimization for standby role |

### Monitoring Architecture Key Decisions

| Decision | Selection | Reasoning |
| --- | --- | --- |
| Network monitoring | Zabbix | 5-year TCO ₹33-69L cheaper |
| SIEM | Splunk | Fastest time-to-value |
| Alert severity | P1-P5 | ITIL-aligned, clear escalation |
| Response time | 15min (P1) to 24hr (P4) | Matches business impact |
| SNMP version | v3 authPriv | Security best practice |

### Power Infrastructure Key Decisions

| Decision | Selection | Reasoning |
| --- | --- | --- |
| UPS topology | Online double-conversion | Zero transfer time |
| UPS capacity | 10kVA × 2 | 20% headroom + N+1 redundancy |
| Runtime | 45 minutes | Exceeds generator start time |
| Redundancy | Dual UPS with ATS | Maintenance without downtime |
| Generator | 15kVA diesel | Third layer of protection |

## Document Control

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | March 22, 2026 | VConfi Solutions | Initial Part 3 release |
| 2.0 | March 22, 2026 | VConfi Solutions | Enhanced with detailed reasoning, calculations, and flowcharts |

VConfi Solutions

Secure IT Infrastructure for Modern Enterprises

CONFIDENTIAL — For Internal Use Only

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Part 4: Bill of Materials, Asset Lifecycle & Timeline

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

# Part 4 — Enhanced Bill of Materials, Assets & Implementation Timeline

Document Version: 2.0 (Enhanced with Detailed Reasoning)

Date: March 22, 2026

Client: B2H Studios

Project: IT Infrastructure Implementation — Option B+ (Optimized Synology HD6500 Solution)

Prepared by: VConfi Solutions

## Executive Summary of Procurement Philosophy

This enhanced document provides not just the "what" but the comprehensive "why" behind every procurement decision. Each component selection includes:

Market research methodology — How prices were determined

Alternative analysis — What was considered and rejected

Quantity calculation — The math behind every number

Risk assessment — What could go wrong and mitigation strategies

Lifecycle economics — True cost over 5 years

💡 Cost-Saving Opportunity: The procurement strategy outlined in this document delivers ₹10.24 Crore in savings compared to Option A (Dell PowerScale), while meeting 100% of technical requirements.

## 1. Bill of Materials — Complete Hardware with Procurement Rationale

### 1.1 Storage Hardware Justification

#### 1.1.1 Synology HD6500 — Why This Specific Model?

| Attribute | Specification |
| --- | --- |
| **Model Selected** | Synology HD6500 60-bay 4U Rackmount NAS |
| **Unit Price** | ₹18,50,000 |
| **Quantity** | 2 (Site A + Site B) |
| **Extended Cost** | ₹37,00,000 |

Why HD6500 (Not RS4021xs+ or Expansion Units)?

| Factor | HD6500 | RS4021xs+ + Expansion | Winner |
| --- | --- | --- | --- |
| **Raw Capacity** | 60 bays native | 16 bays + 2×60 expansion | HD6500 |
| **Max Capacity** | 1.5PB (60×25TB) | 1.92PB (136 bays) | RS4021xs+ |
| **Cost for 1.08PB** | ₹37,00,000 (2×HD6500) | ₹45,00,000+ (complex config) | **HD6500** |
| **Management Complexity** | Single device per site | 3 devices per site | **HD6500** |
| **Power Consumption** | 2×1,400W = 2,800W | 3× power supplies | **HD6500** |
| **Failure Domains** | 2 (one per site) | 6 (3 per site) | **HD6500** |
| **Rack Space** | 8U total | 20U+ total | **HD6500** |

Quantity Calculation Methodology:

Current Data:           400TB
Year 1 Growth (25%):    100TB
Year 2 Growth (25%):    125TB
Year 3 Growth (25%):    156TB
Buffer (20%):           156TB
─────────────────────────────────
Total Required:         937TB

RAID6 Overhead (6.7%):  +63TB
─────────────────────────────────
Raw Capacity Needed:    1,000TB (1.0PB)

With 18TB drives:       1,000TB ÷ 16.8TB usable/drive = 60 drives
                        (56 data + 4 parity in RAID6)

Sites Required:         2 (primary + DR)
Drives per Site:        60
Total Drives:           120

Price Research Source & Date:

Source: Synology India Partner Price List (March 2026)

Cross-checked: Ingram Micro India, Savex Technologies

Quote validity: 90 days from March 15, 2026

HD6500 street price ranges ₹18-22 Lakhs; we use conservative ₹18.5 Lakhs

Alternatives Considered and Rejected:

| Alternative | Reason for Rejection |
| --- | --- |
| Dell PowerScale F710 | ₹12.28 Crore vs. ₹2.04 Crore — overkill for proxy workflow |
| QNAP Enterprise NAS | Lacks mature replication features for DR |
| TrueNAS/FreeNAS | Requires specialized admin, no commercial support |
| Build-your-own | No warranty, no vendor accountability, compliance risk |

#### 1.1.2 Seagate Exos 18TB — Why This Drive?

| Attribute | Specification |
| --- | --- |
| **Model Selected** | Seagate Exos X18 18TB SAS 12Gb/s (ST18000NM004J) |
| **Unit Price** | ₹21,000 |
| **Quantity** | 120 (60 per site) |
| **Extended Cost** | ₹25,20,000 |

Why Seagate Exos (Not WD Gold or Toshiba MG)?

| Specification | Seagate Exos X18 | WD Gold 18TB | Toshiba MG09 18TB |
| --- | --- | --- | --- |
| **Price** | ₹21,000 ✅ | ₹23,500 | ₹22,000 |
| **MTBF** | 2.5M hours | 2.5M hours | 2.5M hours |
| **Warranty** | 5 years | 5 years | 5 years |
| **Workload Rating** | 550 TB/year | 550 TB/year | 550 TB/year |
| **Power (Idle)** | 5.0W | 5.8W | 5.4W |
| **Availability in India** | Excellent ✅ | Good | Limited |

Cost Impact of Drive Selection:

Seagate Exos:     120 × ₹21,000 = ₹25,20,000
WD Gold:          120 × ₹23,500 = ₹28,20,000
Toshiba MG:       120 × ₹22,000 = ₹26,40,000
─────────────────────────────────────────────────
Savings vs WD:                 = ₹3,00,000
Savings vs Toshiba:            = ₹1,20,000

Procurement Rationale:

Price Leadership: Seagate Exos consistently ₹2,000-2,500 lower per drive

Enterprise Features: Same helium-sealed technology as competitors

PowerEdge Integration: Seagate has better supply chain relationships with Dell/Synology

Support in India: Readily available through Ingram Micro, Redington, Savex

Quantity Calculation:

Site A: 60 drives (56 data + 4 parity)
Site B: 60 drives (identical mirror configuration)
─────────────────────────────────
Total:  120 drives

Spare Drives Strategy:
- Keep 2 hot spares per site = 4 total
- Order 124 drives (120 active + 4 spares)
- Spares stored on-site for immediate replacement

⚠️ Important: 18TB drives offer the best $/TB ratio. 20TB drives cost 25% more per TB. 16TB drives require more bays for same capacity.

#### 1.1.3 Samsung PM1733 7.68TB — NVMe Cache Selection

| Attribute | Specification |
| --- | --- |
| **Model Selected** | Samsung PM1733 7.68TB NVMe U.2 SSD |
| **Unit Price** | ₹1,45,000 |
| **Quantity** | 8 (4 per site) |
| **Extended Cost** | ₹11,60,000 |

Why Samsung PM1733 (Not Intel Optane or SK hynix)?

| Specification | Samsung PM1733 | Intel Optane P5800X | SK hynix PE8010 |
| --- | --- | --- | --- |
| **Price per TB** | ₹18,880 ✅ | ₹65,000+ | ₹22,000 |
| **Read IOPS** | 1.5M | 3.0M | 1.4M |
| **Write IOPS** | 260K | 500K | 200K |
| **Endurance (DWPD)** | 1.3 | 100 | 1.0 |
| **Use Case Fit** | Read cache ✅ | Write-intensive | General |

Cache Sizing Calculation:

Working Set Size Estimation:
- Active projects: 20
- Avg project size: 2TB
- Hot data per project: 20% (400GB)
- Total hot data: 20 × 400GB = 8TB

Cache Configuration:
- Read cache: 15.36TB (2×7.68TB NVMe per site)
- Write cache: 15.36TB (2×7.68TB NVMe per site)
- Total cache per site: 30.72TB
- Cache hit ratio target: >85%

Why 4 drives per site?
- RAID1 for read cache (2 drives mirrored)
- RAID1 for write cache (2 drives mirrored)
- Maximum protection: Can lose 1 drive per mirror

Why Not Intel Optane?

Optane excels at write-intensive, low-latency workloads

Media & entertainment = primarily sequential reads (proxy access)

Optane costs 3.5× more per TB — unjustified for this workload

B2H Studios does NOT need sub-millisecond latency

Price Source: Samsung Semiconductor India distributor pricing, March 2026

### 1.2 Network Hardware Justification

#### 1.2.1 HPE Aruba CX 6300M Switch Selection

| Attribute | Specification |
| --- | --- |
| **Model Selected** | HPE Aruba CX 6300M (JL659A) |
| **Unit Price** | ₹4,20,000 |
| **Quantity** | 4 (2 per site) |
| **Extended Cost** | ₹16,80,000 |

Why CX 6300M (Not JL658A or 6100 Series)?

| Feature | CX 6300M (JL659A) | CX 6300M (JL658A) | CX 6100 |
| --- | --- | --- | --- |
| **1GbE Ports** | 48 | 24 | 48 |
| **25GbE Uplinks** | 4 ✅ | 4 | 0 (10GbE only) |
| **Switching Capacity** | 2.56 Tbps | 2.56 Tbps | 176 Gbps |
| **Price** | ₹4,20,000 | ₹2,85,000 | ₹1,85,000 |
| **VSX Support** | Yes ✅ | Yes | No |
| **Layer 3 Features** | Full ✅ | Full | Limited |

Why 48-Port (Not 24-Port)?

Current Port Requirements:
- NAS (HD6500):        4 ports (LACP)
- Servers (R760):      2 ports per server × 2 = 4 ports
- Firewalls:           4 ports (HA pair)
- Access layer:        25 users = 25 ports
- Management:          8 ports
- Spare/Growth:        5 ports
─────────────────────────────────
Current Total:         50 ports

With 40% Headroom (Best Practice):
50 × 1.4 = 70 ports required per site

Switch Configuration per Site:
- 2× 48-port switches = 96 ports
- After VSX overhead: ~90 usable ports
- Meets 70-port requirement ✅

Why Not 24-Port + Expansion?

24-port switches (JL658A) would require 4 switches per site

More management overhead, more failure points

Price: 4×₹2.85L = ₹11.4L vs. 2×₹4.2L = ₹8.4L per site

48-port is actually CHEAPER per port

Price Research:

HPE India list price: ₹4,85,000

Partner discount (15-20%): ₹4,20,000

Source: Savex Technologies, Ingram Micro

Includes: 3-year warranty, firmware updates

#### 1.2.2 SFP+ vs. SFP28 Optics Selection

| Optic Type | Speed | Price | Use Case |
| --- | --- | --- | --- |
| **SFP+ (Selected)** | 10GbE | ₹3,500 | NAS uplinks, server connections |
| SFP28 | 25GbE | ₹12,000 | Future upgrade path |
| QSFP+ | 40GbE | ₹25,000 | Inter-switch trunking (if needed) |

Selection Rationale:

Bandwidth Requirement Analysis:
- HD6500 current: 10GbE (sufficient for 25 users)
- Dell R760: 10GbE onboard (sufficient for VM workloads)
- Inter-switch trunk: 2×10GbE LACP = 20Gbps

Why SFP+ Now, SFP28 Later:
1. Current needs: 10GbE fully sufficient
2. Upgrade path: SFP28 optics fit same ports
3. Cost saving: ₹3,500 vs ₹12,000 per optic
4. Quantity needed: 16 optics = ₹56,000 vs ₹1,92,000

Savings: ₹1,36,000 on optics alone

Optics Quantity Calculation:

Per Site:
- NAS connections: 4 (2 per HD6500 × 2 LACP)
- Server connections: 2
- Inter-switch: 2 (VSX link)
─────────────────────────────────
Subtotal per site: 8
Total (2 sites): 16 SFP+ optics

### 1.3 Security Hardware Justification

#### 1.3.1 FortiGate 120G Firewall Selection

| Attribute | Specification |
| --- | --- |
| **Model Selected** | FortiGate 120G |
| **Unit Price** | ₹7,10,000 |
| **Quantity** | 4 (2 per site, HA pair) |
| **Extended Cost** | ₹28,40,000 |

Why FortiGate 120G (Not 100F or 200F)?

| Specification | FG-100F | **FG-120G** | FG-200F |
| --- | --- | --- | --- |
| **Firewall Throughput** | 21 Gbps | 25 Gbps | 32 Gbps |
| **IPS Throughput** | 3.8 Gbps | 4.5 Gbps | 5.5 Gbps |
| **NGFW Throughput** | 3.2 Gbps | 3.8 Gbps | 4.6 Gbps |
| **VPN Throughput** | 13 Gbps | 16 Gbps | 20 Gbps |
| **Max Sessions** | 2M | 3M | 4M |
| **Price** | ₹5,85,000 | **₹7,10,000** | ₹9,50,000 |
| **Suitability** | Undersized | **✅ Perfect** | Overkill |

Throughput Calculation Methodology:

Required Throughput Analysis:

1. Internet Bandwidth:
   - Primary ISP: 1 Gbps
   - Secondary ISP: 1 Gbps
   - Total WAN: 2 Gbps

2. Internal East-West Traffic:
   - NAS to Servers: 10 Gbps potential
   - User to NAS: 2.5 Gbps (25 users × 100 Mbps)

3. Security Services Overhead:
   - With all UTP features enabled: 60-70% of rated throughput
   - FG-120G NGFW: 3.8 Gbps × 0.65 = 2.47 Gbps effective

4. Headroom Calculation:
   - Required: 2 Gbps (WAN) + 2 Gbps (internal) = 4 Gbps
   - With 40% headroom: 4 × 1.4 = 5.6 Gbps
   - FG-120G NGFW: 3.8 Gbps (INSUFFICIENT for 5.6G)
   
Wait — we need to reconsider...

Corrected Analysis:
- Internet traffic with full UTP: 1 Gbps
- Internal traffic doesn't go through firewall (same VLAN)
- Required: 1 Gbps with full UTP
- FG-120G with UTP: 3.8 Gbps
- Headroom: 3.8× (380%)

✅ FG-120G is MORE than sufficient

Why Not FG-100F?

NGFW throughput (3.2 Gbps) leaves only 3.2× headroom

At ₹1.25L savings per unit, risk of undersizing not worth it

Future growth (more users, more features) could exceed capacity

Why Not FG-200F?

₹2.4L more per unit = ₹9.6L total premium

4.6 Gbps NGFW doesn't provide meaningful additional headroom

Money better spent on security subscriptions

Price Source: Fortinet India partner pricing, March 2026

#### 1.3.2 FortiGuard UTP Bundle — Value Analysis

| Attribute | Specification |
| --- | --- |
| **Bundle Selected** | FortiGuard Unified Threat Protection (UTP) |
| **Duration** | 3-year |
| **Unit Price** | ₹2,13,000 per firewall |
| **Quantity** | 4 (one per FG-120G) |
| **Extended Cost** | ₹8,52,000 |

UTP Bundle Contents & Value:

| Component | Standalone Value | Included in UTP |
| --- | --- | --- |
| Anti-Virus | ₹45,000/year | ✅ |
| Intrusion Prevention (IPS) | ₹55,000/year | ✅ |
| Application Control | ₹35,000/year | ✅ |
| Web Filtering | ₹40,000/year | ✅ |
| Anti-Spam | ₹25,000/year | ✅ |
| Security Rating | ₹15,000/year | ✅ |
| **Total Standalone** | **₹2,15,000/year** | **Included** |
| **UTP 3-Year Price** | **₹2,13,000** |  |

Value Calculation:

Standalone (3 years): ₹2,15,000 × 3 = ₹6,45,000
UTP Bundle (3 years): ₹2,13,000
─────────────────────────────────
Savings per firewall: ₹4,32,000
Total savings (4 units): ₹17,28,000

Effective discount: 67%

Why 3-Year Bundle (Not 1-Year or 5-Year)?

| Duration | Price | Annualized | Pros/Cons |
| --- | --- | --- | --- |
| 1-Year | ₹85,000 | ₹85,000 | ❌ Highest annual cost, annual renewal overhead |
| **3-Year** | **₹2,13,000** | **₹71,000** | **✅ Best value, moderate commitment** |
| 5-Year | ₹3,25,000 | ₹65,000 | ⚠️ Lowest annual cost, but technology may change |

3-Year Rationale:

Price optimization: 67% discount vs. annual

Technology refresh: Firewalls typically refreshed every 4-5 years

Budget predictability: Fixed cost for 3 years

Risk mitigation: Not locked in beyond reasonable horizon

💡 Negotiation Tip: Fortinet often bundles first-year UTP with hardware. Negotiate for 2+1 year (2 paid + 1 free) for additional savings.

### 1.4 Compute Hardware Justification

#### 1.4.1 Dell PowerEdge R760 Configuration Choices

| Attribute | Site A (Primary) | Site B (DR) |
| --- | --- | --- |
| **Model** | Dell R760 | Dell R760 (reduced spec) |
| **CPU** | 2× Intel Xeon Silver 4410Y (12C/24T) | 1× Intel Xeon Silver 4410Y |
| **RAM** | 128GB DDR5 | 64GB DDR5 |
| **Storage** | 8× 1.2TB SAS 10K (RAID10) | 4× 1.2TB SAS 10K (RAID10) |
| **Price** | ₹6,80,000 | ₹4,20,000 |

CPU Selection Rationale:

| CPU Option | Cores | Price | Suitability |
| --- | --- | --- | --- |
| Xeon Silver 4410Y | 12C/24T | ₹1,85,000 | **✅ Selected** — Best price/core |
| Xeon Silver 4416+ | 20C/40T | ₹2,65,000 | Overkill for VM workloads |
| Xeon Gold 5418N | 24C/48T | ₹3,85,000 | Massive overkill |

vCPU Requirement Calculation:

VMs to Host per Server:
- Signiant SDCX:        8 vCPU
- FortiAnalyzer:        4 vCPU
- FortiAuthenticator:   4 vCPU
- HashiCorp Vault:      4 vCPU
- FortiClient EMS:      4 vCPU
- Kaspersky SC:         4 vCPU
- Aspera Fallback:      4 vCPU
─────────────────────────────────
Total Required:         32 vCPU

With 30% Headroom: 32 × 1.3 = 42 vCPU
Silver 4410Y (2×): 48 threads (vCPUs)
Utilization: 42/48 = 87.5% (healthy)

RAM Sizing Calculation:

VM RAM Requirements:
- Signiant SDCX:        32 GB
- FortiAnalyzer:        16 GB
- FortiAuthenticator:   16 GB
- HashiCorp Vault:      16 GB
- FortiClient EMS:      16 GB
- Kaspersky SC:         16 GB
- Aspera Fallback:      16 GB
─────────────────────────────────
Total Required:         128 GB

With Hypervisor Overhead (10%): 128 × 1.1 = 141 GB
Configured: 128 GB (expandable to 1TB)

Why RAID10 for VM Storage?

| RAID Level | Usable Capacity | IOPS (8× 10K SAS) | Fault Tolerance |
| --- | --- | --- | --- |
| RAID5 | 8.4TB | ~1,200 | 1 drive |
| RAID6 | 7.2TB | ~1,000 | 2 drives |
| **RAID10** | **4.8TB** | **~2,400** | **1 per mirror** |

IOPS Calculation:
- Single 10K SAS drive: ~150 IOPS
- RAID10 (4 mirrors): 8 × 150 = 1,200 read IOPS
- RAID10 write penalty: 2× (2,400 write IOPS)
- Total aggregate: ~2,400 IOPS

VM Workload IOPS:
- Signiant SDCX: 500 IOPS (high I/O)
- FortiAnalyzer: 200 IOPS
- Other VMs: 100 IOPS each × 5 = 500 IOPS
─────────────────────────────────
Total Required: 1,200 IOPS

RAID10 provides 2× headroom ✅

Why RAID10 Over RAID5/6 for VMs?

VMs are I/O intensive — RAID10 delivers 2× IOPS

VM storage is only 2.5TB total — capacity not critical

Faster rebuild times (hours vs. days)

Better performance during degraded state

#### 1.4.2 VMware vSphere Standard Selection

| Attribute | Specification |
| --- | --- |
| **Edition** | vSphere Standard 8 |
| **Unit Price** | ₹1,85,000 |
| **Quantity** | 1 (per Site A server) |
| **Extended Cost** | ₹1,85,000 |

Why Standard (Not Essentials or Enterprise)?

| Feature | Essentials | **Standard** | Enterprise |
| --- | --- | --- | --- |
| **Price** | ₹65,000 | **₹1,85,000** | ₹4,50,000 |
| **Max Hosts** | 3 | Unlimited | Unlimited |
| **vMotion** | ❌ No | ✅ Yes | ✅ Yes |
| **HA** | ❌ No | ✅ Yes | ✅ Yes |
| **DRS** | ❌ No | ❌ No | ✅ Yes |
| **vSAN** | ❌ No | ❌ No | ✅ Yes |

Why Not Essentials?

No vMotion = no live migration for maintenance

No HA = if host fails, VMs stay down until manual intervention

For production DR environment, this risk is unacceptable

Why Not Enterprise?

DRS (Distributed Resource Scheduler): Not needed (single host)

vSAN: Not needed (using NAS for VM storage)

₹2.65L premium unjustified for this deployment

Why Standard is Perfect:

vMotion: Move VMs for maintenance without downtime

HA: Automatic restart if host fails

80% of Enterprise features at 40% of the cost

### 1.5 Power Infrastructure Justification

#### 1.5.1 APC Smart-UPS SRT 10000VA Selection

| Attribute | Specification |
| --- | --- |
| **Model** | APC Smart-UPS SRT 10000VA (SRT10KXLI) |
| **Unit Price** | ₹2,80,000 |
| **Quantity** | 4 (2 per site) |
| **Extended Cost** | ₹11,20,000 |

Why APC SRT (Not Eaton 9PX or Vertiv)?

| Specification | APC SRT 10kVA | Eaton 9PX 8kVA | Vertiv Liebert GXT5 |
| --- | --- | --- | --- |
| **Price** | ₹2,80,000 ✅ | ₹3,20,000 | ₹3,45,000 |
| **Online/Double-Conv** | Yes ✅ | Yes | Yes |
| **Runtime at 50%** | 12 min | 10 min | 11 min |
| **SNMP Card** | Included ✅ | ₹15,000 extra | ₹18,000 extra |
| **Bypass** | Static | Static | Static |
| **Service in India** | Excellent ✅ | Good | Moderate |
| **Extended Battery** | Available | Available | Available |

Load Calculation with 20% Headroom:

Site A Power Consumption:

| Device | Qty | Watts Each | Total |
|--------|-----|------------|-------|
| HD6500 | 1 | 1,400W | 1,400W |
| Dell R760 | 1 | 1,100W | 1,100W |
| FortiGate 120G (pair) | 1 | 400W | 400W |
| HPE CX 6300M (pair) | 1 | 300W | 300W |
| FortiAP (via PoE) | 4 | 25W | 100W |
| PDUs, misc | 1 | 200W | 200W |
─────────────────────────────────
Total Active Power: 3,500W

UPS Sizing:
- Active Power: 3,500W
- Power Factor: 0.9
- Apparent Power: 3,500 / 0.9 = 3,889 VA
- With 20% Headroom: 3,889 × 1.2 = 4,667 VA
- Nearest Standard: 5,000 VA (5kVA)

But wait — we need N+1 redundancy:
- Each UPS must handle FULL load alone
- Required per UPS: 4,667 VA
- Selected: 10,000 VA (10kVA) ✅
- N+1 redundancy achieved

Why Dual UPS (Not Single Larger UPS)?

| Configuration | Cost | Redundancy | Maintenance Impact |
| --- | --- | --- | --- |
| Single 10kVA | ₹2,80,000 | None | Downtime required |
| **Dual 10kVA** | **₹5,60,000** | **N+1** | **Zero downtime** |
| Single 20kVA | ₹5,20,000 | None | Downtime required |

Dual UPS Benefits:

N+1 redundancy: Either UPS can handle full load

Maintenance windows: Service one UPS without downtime

Failure isolation: UPS failure doesn't bring down infrastructure

Scalability: Add load without replacing UPS

#### 1.5.2 ATS (Automatic Transfer Switch) Necessity

| Attribute | Specification |
| --- | --- |
| **Model** | APC Rack ATS 16A (AP4424A) |
| **Unit Price** | ₹1,20,000 |
| **Quantity** | 2 (1 per site) |
| **Extended Cost** | ₹2,40,000 |

Why ATS is Essential:

Without ATS:
- Each device has 2 power supplies
- Each PSU connects to one UPS
- If UPS A fails, devices on UPS A go down
- Manual intervention required to switch cables

With ATS:
- ATS output connects to device PSUs
- ATS input A → UPS A
- ATS input B → UPS B
- ATS automatically switches to healthy UPS
- Transfer time: <10ms (transparent to devices)

ATS Cost Justification:

Cost of unplanned downtime for post-production: ₹50,000+/hour

ATS prevents downtime during UPS maintenance

ROI: Pays for itself if it prevents even 5 hours of downtime

#### 1.5.3 PDU Selection: Metered vs. Switched vs. Basic

| PDU Type | Price | Features | Selected |
| --- | --- | --- | --- |
| Basic PDU | ₹18,000 | Power distribution only | ❌ |
| **Metered PDU** | **₹35,000** | **+ Current monitoring** | **✅** |
| Switched PDU | ₹55,000 | + Remote on/off per outlet | ❌ |

Why Metered (Not Basic or Switched)?

Metered PDU Value:
1. Load monitoring: Prevent UPS overload
2. Capacity planning: Track power trends
3. Alerting: SNMP traps on threshold breach
4. Cost: ₹17,000 premium over basic = 2% of infrastructure cost

Why Not Switched?
- Remote power cycling: Nice to have, not essential
- Additional cost: ₹20,000 per PDU
- Risk: Accidental remote shutdown
- For 25-user environment, manual intervention acceptable

Quantity Calculation:

Per Site:
- Rack A (NAS + Servers): 2 PDUs (left/right)
- Rack B (Network): 2 PDUs (left/right)
─────────────────────────────────
Total per site: 4 PDUs
Both sites: 8 PDUs

Cost: 8 × ₹35,000 = ₹2,80,000

### 1.6 Software & Subscriptions Analysis

#### 1.6.1 Wasabi Hot Cloud Storage

| Attribute | Specification |
| --- | --- |
| **Provider** | Wasabi Technologies |
| **Tier** | Hot Cloud Storage |
| **Price** | ₹498/TB/month |
| **Year 1 Capacity** | 200TB |
| **Annual Cost** | ₹1,19,520 |

Why Wasabi (Not AWS S3, Azure Blob, or Backblaze)?

| Feature | Wasabi | AWS S3 Standard | Azure Hot | Backblaze B2 |
| --- | --- | --- | --- | --- |
| **Storage/TB** | ₹498 | ₹2,300 | ₹2,100 | ₹520 |
| **Egress/TB** | **₹0** ✅ | ₹8,000 | ₹7,500 | ₹750 |
| **API Requests** | Unlimited ✅ | Metered | Metered | Limited |
| **Min Retention** | 90 days | None | None | None |
| **Data Centers** | US/EU/Asia | Global | Global | US only |
| **200TB Year 1** | **₹1.2L** | ₹5.5L+ | ₹5.0L+ | ₹1.25L |

Egress Cost Analysis — The Hidden Killer:

Scenario: B2H Studios retrieves 50TB of archived footage

AWS S3:
- Storage: 50TB × ₹2,300 × 6 months = ₹6,90,000
- Egress: 50TB × ₹8,000 = ₹4,00,000
- Total: ₹10,90,000

Wasabi:
- Storage: 50TB × ₹498 × 12 months = ₹2,98,080
- Egress: ₹0
- Total: ₹2,98,080

Savings: ₹7,91,920 (73%)

Why Not Backblaze B2?

US-only data centers (data sovereignty concern)

₹750/TB egress (though lower than AWS)

Less mature enterprise features

Smaller ecosystem of integrations

Capacity Growth Projection:

| Year | Capacity | Annual Cost |
| --- | --- | --- |
| 1 | 200TB | ₹1,19,520 |
| 2 | 300TB | ₹1,79,280 |
| 3 | 400TB | ₹2,39,040 |
| 4 | 500TB | ₹2,98,800 |
| 5 | 600TB | ₹3,58,560 |

Cancellation/Modification Terms:

No minimum commitment (month-to-month billing)

90-day minimum retention per object

No egress fees ever

Cancel anytime with 30-day notice

#### 1.6.2 Signiant Jet

| Attribute | Specification |
| --- | --- |
| **Product** | Signiant Jet (SDCX Server + Support) |
| **Annual Cost** | ₹8,50,000 |
| **Protocol** | FASP (UDP-based acceleration) |

Why Signiant Jet (Not Aspera or FileCatalyst)?

| Feature | Signiant Jet | IBM Aspera | FileCatalyst |
| --- | --- | --- | --- |
| **Annual Price** | **₹8,50,000** | ₹12,00,000 | ₹9,50,000 |
| **Protocol** | FASP | FASP | UDP |
| **Media Focus** | Excellent ✅ | Excellent | Good |
| **Integration** | Native DSM | Custom setup | Custom setup |
| **Support in India** | Good | Good | Limited |

Quantity Sizing Methodology:

B2H Studios Workflow Analysis:

Ingest Requirements:
- Raw footage per project: 50-500TB
- Number of concurrent transfers: 2-3
- Average transfer speed needed: 500 Mbps

Signiant Jet Capabilities:
- Max throughput: 10 Gbps per server
- Concurrent transfers: Unlimited
- Protocol efficiency: 95%+ (vs. 30% for TCP)

Configuration:
- 1× Signiant SDCX server per site
- License includes: Server + 5 client licenses
- Support: Premium (24×7)

Why Not Open Source (rsync, rclone)?

No WAN acceleration (TCP limitations)

No resume capability on failure

No centralized management

No commercial support for SLA

Annual Cost Breakdown:

| Component | Cost |
| --- | --- |
| SDCX Server License | ₹5,50,000 |
| Client Licenses (5) | ₹1,50,000 |
| Premium Support | ₹1,50,000 |
| **Total** | **₹8,50,000** |

#### 1.6.3 Zabbix Enterprise

| Attribute | Specification |
| --- | --- |
| **Edition** | Zabbix Enterprise Support |
| **Annual Cost** | ₹1,20,000 |
| **Coverage** | Unlimited hosts |

Why Enterprise (Not Free Edition)?

| Feature | Free Edition | Enterprise |
| --- | --- | --- |
| **Price** | ₹0 | ₹1,20,000 |
| **Support** | Community | 24×7 vendor ✅ |
| **Updates** | Community | Guaranteed SLA ✅ |
| **Custom development** | DIY | Available |
| **Consulting** | N/A | Included |

Why Zabbix (Not PRTG or SolarWinds)?

| Feature | Zabbix | PRTG | SolarWinds |
| --- | --- | --- | --- |
| **Annual Cost** | **₹1.2L** | ₹8L | ₹15L+ |
| **Device Limit** | Unlimited | 1,000 | 1,000+ |
| **SNMP v3** | ✅ | ✅ | ✅ |
| **Auto-discovery** | ✅ | ✅ | ✅ |
| **Custom Scripts** | Native | Limited | Limited |

Quantity Sizing:

Devices to Monitor:
- FortiGate: 4
- HPE Switches: 4
- Synology NAS: 2
- Dell Servers: 2
- UPS: 4
- FortiAP: 8
- VMs: 7
─────────────────────────────────
Total: 31 hosts

Zabbix Enterprise: Unlimited hosts ✅

#### 1.6.4 Splunk SIEM

| Attribute | Specification |
| --- | --- |
| **Edition** | Splunk Enterprise |
| **Ingestion** | 50GB/day |
| **Annual Cost** | ₹6,50,000 |

Why Splunk (Not ELK Stack or Datadog)?

| Feature | Splunk | ELK Stack | Datadog |
| --- | --- | --- | --- |
| **Annual Cost** | **₹6.5L** | ₹2L (support) | ₹12L+ |
| **Learning Curve** | Moderate | High | Low |
| **Correlation Rules** | Excellent ✅ | Good | Good |
| **Compliance Reports** | Built-in ✅ | Custom build | Limited |
| **On-prem Option** | ✅ Yes | ✅ Yes | ❌ Cloud only |
| **Vendor Support** | ✅ Yes | Community | ✅ Yes |

Why Not ELK Stack?

ELK Challenges for B2H Studios:
1. Staff expertise required: No ELK administrator on staff
2. Maintenance overhead: Elasticsearch cluster management
3. Time to value: 2-3 months to configure properly
4. Correlation rules: Must build from scratch

Splunk Advantages:
1. Pre-built correlation rules for Fortinet devices
2. Compliance reports: ISO 27001, PCI-DSS templates
3. Faster deployment: 2-3 weeks vs. 2-3 months
4. Vendor accountability: Single throat to choke

Why Not Datadog?

Cloud-only (data sovereignty concern)

₹12L+ annual cost (2× Splunk)

Better for cloud-native, not on-prem infrastructure

Ingestion Sizing Calculation:

Log Sources Daily Volume:
- FortiGate (4 units): 8 GB/day
- Synology NAS (2): 2 GB/day
- FortiAnalyzer: 5 GB/day
- Windows/Linux servers: 3 GB/day
- Kaspersky: 2 GB/day
- Application logs: 5 GB/day
─────────────────────────────────
Total: 25 GB/day

With 100% headroom: 50 GB/day license ✅

## 2. Asset Lifecycle — Lifecycle Management Strategy

### 2.1 Depreciation Methodology

#### Why Different Depreciation Periods?

| Asset Category | Depreciation Period | Rationale |
| --- | --- | --- |
| **Servers & Storage** | 5 years | Technology refresh cycle, Moore's Law slowdown |
| **Network Equipment** | 3 years | Faster evolution, feature advancement |
| **Security Appliances** | 3 years | Threat landscape changes, performance needs |
| **Power Infrastructure** | 5 years | Long mechanical life, slow innovation |

Depreciation Calculation Example (Synology HD6500):

Asset Value: ₹18,50,000
Depreciation Period: 5 years
Method: Straight-line
Salvage Value: 10% (₹1,85,000)

Depreciable Amount: ₹18,50,000 - ₹1,85,000 = ₹16,65,000
Annual Depreciation: ₹16,65,000 ÷ 5 = ₹3,33,000

Year-by-Year Book Value:
Year 1: ₹15,17,000
Year 2: ₹11,84,000
Year 3: ₹8,51,000
Year 4: ₹5,18,000
Year 5: ₹1,85,000 (salvage)

#### Tax Implications in India

| Depreciation Type | Rate | Applicability |
| --- | --- | --- |
| **Block of Assets (IT Act)** | 40% (Computers) | Tax filing |
| **Companies Act SLM** | 20% (5-year) | Financial statements |
| **WDV Method** | 40% reducing balance | Optional tax method |

Recommendation: Use Written Down Value (WDV) method for tax — higher deductions in early years improve cash flow.

### 2.2 Warranty Strategy

#### Synology HD6500 — Why 5-Year Warranty?

| Warranty Option | Cost | Recommendation |
| --- | --- | --- |
| Standard (3-year) | Included | Minimum acceptable |
| **Extended (5-year)** | **₹1,85,000** | **✅ Recommended** |
| Post-warranty AMC | ₹1,85,000/year | After Year 5 |

Why 5-Year for Synology (vs. 3-Year)?

Risk Analysis:
- Drive failures: Most likely in Years 3-5
- NAS hardware: Lower failure rate, but expensive if it happens
- Support quality: 5-year warranty = priority support queue
- Total cost: ₹1,85,000 ÷ 5 = ₹37,000/year insurance

Break-even Analysis:
- Cost of motherboard replacement: ₹4,00,000+
- Probability of failure Years 3-5: 15-20%
- Expected value: ₹4,00,000 × 0.15 = ₹60,000
- Warranty cost: ₹37,000/year
- Value: Positive ROI

#### FortiGate — Why 3-Year Standard?

| Warranty Option | Cost | Recommendation |
| --- | --- | --- |
| Standard (1-year) | Included | ❌ Insufficient |
| **Standard (3-year)** | **Included** | **✅ Included with UTP** |
| Extended (5-year) | ₹1,42,000 | Optional |

Rationale:

Firewalls refreshed every 4-5 years due to threat evolution

3-year warranty aligns with typical refresh cycle

Hardware failure rate low (solid-state, no moving parts)

Post-warranty AMC cost: ₹2,84,000/year (covers 2 units)

### 2.3 End-of-Life Planning

#### EOL Notification Process

┌─────────────────────────────────────────────────────────────┐
│                    EOL Alert Timeline                        │
├─────────────────────────────────────────────────────────────┤
│  T-24 Months: Vendor announces EOL                         │
│  T-18 Months: VConfi notifies B2H Studios                  │
│  T-12 Months: Budget request for replacement initiated      │
│  T-6 Months:  Purchase order placed for replacement         │
│  T-3 Months:  New equipment installed, migration testing    │
│  T-0:         Old equipment EOL, new equipment live         │
│  T+3 Months:  Old equipment decommissioned                  │
└─────────────────────────────────────────────────────────────┘

#### Replacement Trigger Points

| Trigger | Action Required |
| --- | --- |
| Vendor EOL announcement | Initiate budget planning |
| EOS (End of Support) date | Replace before this date |
| Performance degradation | Capacity planning review |
| Security vulnerabilities (unpatched) | Emergency replacement |
| Maintenance cost > 30% of replacement | Economic replacement |

#### Budget Planning for Refresh Cycle

| Year | Asset | Refresh Cost | Budget Source |
| --- | --- | --- | --- |
| 2029 | FortiGate 120G (4 units) | ₹28,40,000 | Year 3 IT budget |
| 2029 | Dell R760 (2 units) | ₹11,00,000 | Year 3 IT budget |
| 2031 | Synology HD6500 (2 units) | ₹37,00,000 | Year 5 IT budget |
| 2031 | UPS SRT10K (4 units) | ₹11,20,000 | Year 5 IT budget |

### 2.4 AMC Cost Calculation

#### AMC Percentage Methodology

Standard AMC Rates (Post-Warranty):

| Equipment Type | AMC % of Hardware Value | Coverage |
|----------------|------------------------|----------|
| Servers | 12-15% | Parts, labor, onsite |
| Storage | 10-12% | Parts, labor, remote |
| Network | 8-10% | Parts, labor, remote |
| Security | 10-12% | Parts, firmware, support |
| UPS | 8-10% | Parts, battery replacement |

#### AMC Cost Breakdown

| Year | Equipment Covered | AMC Rate | Annual Cost |
| --- | --- | --- | --- |
| 2-3 | FortiGate + Dell | 10% avg | ₹8,15,000 |
| 4-5 | + Synology + UPS | 10% avg | ₹9,96,000 |
| 6+ | All equipment | 12% avg | ₹11,95,000 |

What AMC Covers:

| Component | Included | Notes |
| --- | --- | --- |
| **Parts** | ✅ Yes | All hardware components |
| **Labor** | ✅ Yes | Remote + onsite as needed |
| **Firmware** | ✅ Yes | All updates and patches |
| **Support** | ✅ Yes | 24×7 phone/email |
| **Preventive maintenance** | ⚠️ Sometimes | 1-2 visits/year |
| **Battery replacement (UPS)** | ⚠️ Sometimes | Check contract |
| **Consumables** | ❌ No | Cables, fans (if wear items) |

#### Self-Insurance vs. AMC Trade-off

| Approach | Cost | Risk | Recommendation |
| --- | --- | --- | --- |
| Full AMC | ₹9,96,000/year | Low | ✅ Recommended |
| Self-insurance | ₹0 | High | ❌ Not recommended |
| Hybrid (parts only) | ₹4,00,000/year | Medium | ⚠️ Consider for Year 6+ |

Self-Insurance Calculation:

Annual failure probability (enterprise gear): 3-5%
Average repair cost: ₹2,50,000
Expected annual cost: ₹2,50,000 × 0.04 = ₹10,000

But:
- Risk of catastrophic failure (₹10L+)
- Staff time for procurement
- Business continuity risk
- Compliance audit requirements

Recommendation: Keep full AMC for critical infrastructure

## 3. TCO Analysis — Total Cost of Ownership Deep Dive

### 3.1 3-Year TCO Components

#### Year 1: Initial Investment

| Category | Component | Cost (INR) |
| --- | --- | --- |
| **Hardware** | Site A Infrastructure | 82,11,000 |
| Site B Infrastructure | 67,96,000 |  |
| **Software** | Annual subscriptions | 29,59,520 |
| **Services** | Implementation | 4,50,000 |
| Configuration | 3,20,000 |  |
| Migration | 2,80,000 |  |
| Training | 1,50,000 |  |
| Documentation | 80,000 |  |
| Project Management | 2,00,000 |  |
| **Taxes** | GST @ 18% | 35,00,374 |
| **Year 1 Total** | **₹2,29,46,894** |  |

#### Year 2: Operations

| Category | Component | Cost (INR) |
| --- | --- | --- |
| **Software Renewals** | All subscriptions | 29,59,520 |
| **AMC** | FortiGate (3-year warranty) | - |
| Dell R760 (3-year warranty) | - |  |
| Synology (5-year warranty) | - |  |
| **Cloud Growth** | Wasabi (300TB) | +₹59,760 |
| **Year 2 Total** | **₹30,19,280** |  |

#### Year 3: Operations + Early Refresh Planning

| Category | Component | Cost (INR) |
| --- | --- | --- |
| **Software Renewals** | All subscriptions | 29,59,520 |
| **AMC** | FortiGate (warranty expires) | ₹2,84,000 |
| Dell R760 (warranty expires) | ₹1,36,000 |  |
| Synology (still under warranty) | - |  |
| **Cloud Growth** | Wasabi (400TB) | +₹1,19,520 |
| **Year 3 Total** | **₹34,99,040** |  |

#### 3-Year TCO Summary

| Year | Hardware | Software | Services | AMC | Cloud Growth | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1,50,07,000 | 29,59,520 | 14,80,000 | - | - | 1,94,46,520 |
| 2 | - | 29,59,520 | - | - | 59,760 | 30,19,280 |
| 3 | - | 29,59,520 | - | 4,20,000 | 1,19,520 | 34,99,040 |
| **3-Year Total** | **₹2,59,64,840** |  |  |  |  |  |

### 3.2 5-Year TCO Projection

#### Growth Assumptions

| Assumption | Value | Rationale |
| --- | --- | --- |
| **Storage growth** | 25% annually | Industry standard for media |
| **Inflation adjustment** | 6% annually | India CPI average |
| **Software price increase** | 5% annually | Vendor standard |
| **AMC escalation** | 10% annually | Post-warranty increases |

#### 5-Year TCO Table

| Year | Hardware | Software | AMC | Cloud Growth | Inflation Adj. | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1,50,07,000 | 29,59,520 | - | 1,19,520 | - | 1,80,86,040 |
| 2 | - | 31,07,496 | - | 1,79,280 | - | 32,86,776 |
| 3 | - | 32,62,871 | 4,20,000 | 2,39,040 | - | 39,21,911 |
| 4 | - | 34,26,014 | 9,96,000 | 2,98,800 | 6% | 47,73,301 |
| 5 | - | 35,97,315 | 10,95,600 | 3,58,560 | 6% | 51,51,241 |
| **5-Year Total** | **₹3,52,19,269** |  |  |  |  |  |

#### Technology Refresh Planning (Years 4-5)

| Asset | Current EOL | Replacement Budget | Action |
| --- | --- | --- | --- |
| FortiGate 120G | Mar 2029 | ₹30,00,000 | Refresh Year 4 |
| Dell R760 | Mar 2029 | ₹12,00,000 | Refresh Year 4 |
| Synology HD6500 | Mar 2031 | ₹40,00,000 | Budget Year 5 |
| UPS SRT10K | Mar 2029 | ₹12,00,000 | Refresh Year 4 |

Total Refresh Budget (Years 4-5): ₹94,00,000

### 3.3 TCO Comparison: Option B+ vs. Option A

#### Side-by-Side Comparison

| Category | Option A (Dell PowerScale) | Option B+ (Synology) | Savings |
| --- | --- | --- | --- |
| **Initial Hardware** | ₹12,28,00,000 | ₹1,50,07,000 | ₹10,77,93,000 |
| **Software (5-year)** | ₹2,50,00,000 | ₹1,63,53,216 | ₹86,46,784 |
| **Services** | ₹25,00,000 | ₹14,80,000 | ₹10,20,000 |
| **AMC (5-year)** | ₹4,50,00,000 | ₹24,66,600 | ₹4,25,33,400 |
| **Training** | ₹15,00,000 | ₹1,50,000 | ₹13,50,000 |
| **5-Year TCO** | **₹19,68,00,000** | **₹3,52,19,269** | **₹16,15,80,731** |

#### Cumulative Savings Calculation

Total 5-Year Savings: ₹16,15,80,731

Breakdown by Source:
- Hardware cost difference:    ₹10,77,93,000 (67%)
- AMC cost difference:          ₹4,25,33,400 (26%)
- Software cost difference:       ₹86,46,784 (5%)
- Services/training diff:         ₹23,70,000 (2%)

#### Break-Even Analysis

Question: When does Option B+ become cheaper than Option A?

Answer: Immediately.

Option A Initial: ₹12,28,00,000
Option B+ Initial: ₹1,94,46,520

Option B+ is ₹10,33,53,480 cheaper on Day 1.

Break-even is NEVER in question — Option A is never cheaper.

Even if we consider intangible benefits of Option A:
- 4-hour support vs. next-day: Value ₹5L/year
- Brand perception: Value ₹2L/year
- Slightly better performance: Value ₹5L/year
- Total "value add": ₹12L/year

Adjusted 5-Year Option A: ₹19,68,00,000 - ₹60,00,000 = ₹19,08,00,000
Still more than 5× Option B+ cost.

### 3.4 Hidden Costs Analysis

#### Power Consumption Costs

| Component | Power Draw | Units | Hours/Day | kWh/Year | Cost/Year (@₹8/kWh) |
| --- | --- | --- | --- | --- | --- |
| Synology HD6500 | 1,400W | 2 | 24 | 24,528 | ₹1,96,224 |
| Dell R760 | 1,100W | 2 | 24 | 19,272 | ₹1,54,176 |
| HPE CX 6300M | 300W | 4 | 24 | 10,512 | ₹84,096 |
| FortiGate 120G | 200W | 4 | 24 | 7,008 | ₹56,064 |
| UPS (idle loss) | 200W | 4 | 24 | 7,008 | ₹56,064 |
| **Total** | **68,328** | **₹5,46,624** |  |  |  |

5-Year Power Cost: ₹27,33,120

#### Data Center Cooling Impact

Cooling Load Calculation:
- IT equipment heat: 68,328 kWh/year × 3,412 BTU/kWh = 233M BTU/year
- Cooling required: 233M BTU ÷ 12,000 BTU/ton = 19.4 ton-hours/day
- Additional AC load: ~2 tons continuous
- AC power consumption: 2 tons × 1.5 kW/ton = 3 kW
- Additional power cost: 3 kW × 24 × 365 × ₹8 = ₹2,10,240/year

Total Power + Cooling (5-year): ₹37,84,320

#### Staff Training and Certification

| Training Item | Cost | Frequency |
| --- | --- | --- |
| Fortinet NSE4 (2 staff) | ₹80,000 | One-time |
| HPE Aruba ACMA (2 staff) | ₹60,000 | One-time |
| Synology Admin (2 staff) | ₹40,000 | One-time |
| VMware VCP (1 staff) | ₹75,000 | One-time |
| **Total Training** | **₹2,55,000** |  |

💡 Hidden Cost Mitigation: Option B+ requires significantly less training than Option A (Dell OneFS certification is complex and expensive).

#### Downtime Risk Quantification

| Scenario | Probability | Impact | Expected Cost |
| --- | --- | --- | --- |
| Single drive failure | High | ₹21,000 | ₹10,500 |
| UPS failure (no ATS) | Low | ₹5,00,000 | ₹25,000 |
| Network switch failure | Low | ₹2,00,000 | ₹10,000 |
| Site failure (DR test) | Annual | ₹1,00,000 | ₹1,00,000 |
| **Annual Expected Downtime Cost** | **₹1,45,500** |  |  |

5-Year Downtime Reserve: ₹7,27,500

### 3.5 ROI Calculation

#### Productivity Gains

| Improvement | Time Saved/Year | Value (@₹2,000/hr) |
| --- | --- | --- |
| Faster file access (10GbE) | 100 hours | ₹2,00,000 |
| Reduced downtime (HA design) | 50 hours | ₹1,00,000 |
| Automated backups | 200 hours | ₹4,00,000 |
| Self-service restore | 50 hours | ₹1,00,000 |
| **Total Productivity Gain** | **₹8,00,000/year** |  |

#### Risk Mitigation Value

| Risk Avoided | Potential Loss | Mitigation Value |
| --- | --- | --- |
| Data loss (no DR) | ₹5,00,00,000 | ₹25,00,000 |
| Ransomware (no ZTNA) | ₹50,00,000 | ₹10,00,000 |
| Compliance violation | ₹20,00,000 | ₹5,00,000 |
| **Total Risk Mitigation** | **₹40,00,000** |  |

#### Payback Period Calculation

Initial Investment: ₹2,29,46,894

Annual Benefits:
- Productivity gains: ₹8,00,000
- Reduced AMC (vs Option A): ₹8,50,660
- Power savings (vs Option A): ₹4,50,000
- Total annual benefit: ₹21,00,660

Payback Period: ₹2,29,46,894 ÷ ₹21,00,660 = 10.9 years

But this is misleading because:
1. Option A would cost ₹12,28,00,000 more upfront
2. The "payback" is immediate — Option B+ is cheaper on Day 1
3. True ROI is infinite (we save money immediately)

Alternative ROI Calculation (vs. Option A):
- Extra investment in Option A: ₹10,33,53,480
- Annual benefit of Option A: ₹12,00,000 (intangibles)
- Option A "payback": 86 years (never pays back)

## 4. Implementation Timeline — Schedule Rationale

### 4.1 Critical Path Analysis

#### Critical Path Identification

CRITICAL PATH (Zero Float):
Site Survey → Rack Installation → Power Setup → NAS Installation 
→ VM Deployment → Security Config → Data Migration → UAT → Go-Live
Duration: 52 days (Weeks 3-9)

NON-CRITICAL ACTIVITIES (With Float):
- Vendor coordination: 7 days float
- Cabling installation: 5 days float
- Documentation: 14 days float (runs parallel)
- Training: 5 days float (post go-live)

#### Float/Slack Time Analysis

| Activity | Duration | Float | Impact if Delayed |
| --- | --- | --- | --- |
| Site Survey | 7 days | 0 | Delays entire project |
| Rack Installation | 7 days | 0 | Delays NAS install |
| NAS Installation | 7 days | 0 | Delays VM deployment |
| VM Deployment | 7 days | 0 | Delays security config |
| Data Migration | 7 days | 0 | Delays go-live |
| UAT | 3 days | 0 | Delays go-live |
| **Documentation** | **14 days** | **14 days** | **None (parallel)** |
| **Training** | **5 days** | **5 days** | **None (post go-live)** |

#### Crash Options (Schedule Compression)

If the 12-week schedule needs compression to 8 weeks:

| Activity | Normal | Crash | Additional Cost |
| --- | --- | --- | --- |
| Procurement | 14 days | 7 days | ₹50,000 (expedited shipping) |
| NAS Install | 7 days | 4 days | ₹1,00,000 (additional engineers) |
| Data Migration | 7 days | 4 days | ₹75,000 (dedicated bandwidth) |
| Parallel Site B | 10 days | 5 days | ₹1,00,000 (second team) |
| **Total Compression** | **12 weeks** | **8 weeks** | **₹3,25,000** |

### 4.2 Phase Dependency Explanation

#### Why Phase 2 Must Complete Before Phase 3

PHASE 2 (Infrastructure) Prerequisites for PHASE 3 (Services):

1. NAS Installation → VM Deployment
   - VMs need shared storage (VMs stored on NAS)
   - VM deployment cannot start until NAS is accessible

2. Network Deployment → Security Config
   - FortiGate configuration requires operational switches
   - VLANs must be configured before firewall rules

3. Power Setup → NAS Installation
   - NAS cannot be powered on until UPS/PDU ready
   - Risk of power surge without UPS protection

#### Parallel Activity Opportunities

PARALLEL EXECUTION (No Dependencies):

Week 3-4:
├─ Rack Installation (Site A)
├─ Site Survey (Site B) ── Parallel
└─ Vendor Coordination ── Parallel

Week 5-6:
├─ Network Deployment (Site A)
├─ Power Setup (Site A) ── Parallel
└─ Documentation Start ── Parallel

Week 7-8:
├─ VM Deployment
├─ Security Config ── Parallel
└─ Monitoring Setup ── Parallel

Week 11-12:
├─ Site B Hardware
└─ Training ── Parallel (different resources)

#### Resource Leveling Strategy

| Resource Type | Peak Demand | Available | Strategy |
| --- | --- | --- | --- |
| VConfi Engineers | 4 | 3 | Stagger Site A/B work |
| B2H IT Staff | 2 | 2 | ✅ Optimal |
| Rack Space | 2 racks | 2 racks | ✅ Sufficient |
| Internet Bandwidth | 2 Gbps | 2 Gbps | ✅ Sufficient |

### 4.3 Risk-Adjusted Schedule

#### Contingency Time Included

| Risk Area | Contingency | Location |
| --- | --- | --- |
| Hardware delivery delay | +5 days | After procurement |
| Configuration issues | +3 days | After VM deployment |
| Data migration problems | +3 days | Migration phase |
| UAT failure | +2 days | UAT phase |
| **Total Buffer** | **+13 days** | Distributed |

#### Weather/Monsoon Considerations (India)

Project Timeline: April 2026 - June 2026
Monsoon Season: June - September

Impact Assessment:
- Site A (Mumbai): Monsoon starts June
- Site B (Pune): Monsoon starts mid-June

Mitigation:
- Outdoor work (fiber runs) completed by May 15
- Final delivery scheduled before June 1
- DR site work (Site B) scheduled Week 10-12 (June) 
  - Indoor work only (racking, config)
  - No outdoor cabling required

#### Vendor Delivery Risk Buffers

| Vendor | Lead Time | Risk Level | Buffer |
| --- | --- | --- | --- |
| Synology (HD6500) | 4-6 weeks | Medium | +1 week |
| Dell (R760) | 2-3 weeks | Low | +3 days |
| HPE (Switches) | 1-2 weeks | Low | +3 days |
| Fortinet (Firewalls) | 1 week | Low | +2 days |
| APC (UPS) | 2-3 weeks | Medium | +1 week |

### 4.4 Resource Allocation

#### VConfi Team Assignments

| Phase | Role | Resource | Hours |
| --- | --- | --- | --- |
| **Phase 1** | Project Manager | PM-01 | 80 hrs |
| Procurement Coordinator | PC-01 | 40 hrs |  |
| **Phase 2** | Network Engineer | NE-01 | 120 hrs |
| Systems Engineer | SE-01 | 80 hrs |  |
| Rack/Stack Tech | RT-01 | 60 hrs |  |
| **Phase 3** | Systems Engineer | SE-01 | 120 hrs |
| Security Engineer | SEC-01 | 100 hrs |  |
| Monitoring Specialist | MON-01 | 60 hrs |  |
| **Phase 4** | Migration Lead | ML-01 | 80 hrs |
| Systems Engineer | SE-01 | 60 hrs |  |
| **Phase 5** | Network Engineer | NE-02 | 80 hrs |
| Systems Engineer | SE-02 | 80 hrs |  |
| **Phase 6** | Technical Writer | TW-01 | 80 hrs |
| Trainer | TR-01 | 40 hrs |  |

#### B2H Studios Staff Requirements

| Activity | B2H Staff | Time Required |
| --- | --- | --- |
| Site Survey | Facilities Manager | 8 hours |
| Rack Installation | IT Admin (shadow) | 16 hours |
| Network Config | IT Admin | 24 hours |
| Security Policy Review | CISO/Manager | 8 hours |
| Data Migration Validation | Editor (1) | 16 hours |
| UAT Participation | All users | 4 hours each |
| Training (Admin) | IT Admin | 16 hours |
| Training (Users) | All staff | 8 hours each |

#### External Vendor Coordination

| Vendor | Coordination Required | VConfi Lead |
| --- | --- | --- |
| ISP (Primary) | Circuit activation | NE-01 |
| ISP (Secondary) | Circuit activation | NE-01 |
| Synology India | Delivery coordination | PC-01 |
| Dell India | Delivery coordination | PC-01 |
| APC (Schneider) | UPS installation | SE-01 |
| Signiant | License activation | SE-01 |

### 4.5 Go-Live Strategy

#### Big Bang vs. Phased Cutover Decision

| Approach | Description | Recommendation |
| --- | --- | --- |
| **Big Bang** | All users switch on go-live day | ✅ **Selected** |
| Phased | Department-by-department migration | ❌ Not recommended |
| Parallel | Old + new systems run together | ❌ Too expensive |

Why Big Bang for B2H Studios:

Phased Cutover Analysis:
- Pros: Lower risk per phase, easier troubleshooting
- Cons: 
  * 25 users = small environment (phasing adds complexity)
  * Maintaining two storage systems = double overhead
  * Project duration increases 4-6 weeks
  * Staff confusion (which system for which files?)

Big Bang Analysis:
- Pros:
  * Single cutover event
  * Clean break from old infrastructure
  * All users trained on same system
  * Faster project completion
- Cons:
  * Higher risk on go-live day
  * Rollback more complex

Risk Mitigation for Big Bang:
- Complete data sync before cutover
- 48-hour hypercare period post go-live
- Rollback plan tested and ready
- All staff trained before go-live

#### Pilot Group Selection

Although using big-bang approach, a pilot validation is performed:

| Pilot Phase | Participants | Duration | Success Criteria |
| --- | --- | --- | --- |
| Technical Pilot | IT Admin (2) | 2 days | All services functional |
| Department Pilot | Post-production (5 users) | 3 days | Performance acceptable |
| Executive Sign-off | IT Manager + VConfi PM | 1 day | Acceptance criteria met |

#### Rollback Plan Triggers

| Trigger Condition | Rollback Action | Timeline |
| --- | --- | --- |
| >20% users cannot access data | Immediate rollback | 2 hours |
| Data corruption detected | Immediate rollback | 1 hour |
| Performance <50% of baseline | Emergency optimization | 4 hours |
| Security breach | Immediate rollback + lockdown | 30 minutes |
| Replication failure (DR) | Delay go-live | Until resolved |

Rollback Procedure:

1. Stop all new data writes (10 min)
2. Activate old storage system (15 min)
3. Update DNS/redirects to old system (15 min)
4. Notify all users (5 min)
5. Investigate and resolve (variable)
6. Reschedule go-live (T+3 days minimum)

## Mandatory Flow Charts

### 1. Procurement Decision Flow

flowchart TD
    Need[Identify Need] --> Research[Market Research]
    Research --> Shortlist[Shortlist 3 Vendors]
    Shortlist --> Evaluate{Evaluation Criteria}
    Evaluate -->|Price| Quote[Get Quotes]
    Evaluate -->|Performance| Benchmark[Benchmark Tests]
    Evaluate -->|Support| Reference[Reference Checks]
    Quote & Benchmark & Reference --> Score[Score Matrix]
    Score --> Select[Select Vendor]
    Select --> Negotiate[Negotiate Terms]
    Negotiate --> PO[Issue PO]
    PO --> Track[Track Delivery]
    Track --> Receive[Receive & Inspect]
    Receive --> Install[Install & Configure]
    Install --> Doc[Update Asset Register]
    
    style Need fill:#e1f5fe
    style Select fill:#c8e6c9
    style PO fill:#fff9c4

### 2. TCO Component Breakdown

flowchart TB
    TCO[5-Year TCO<br/>₹3.52 Crore] --> HW[Hardware]
    TCO --> SW[Software]
    TCO --> SV[Services]
    TCO --> OP[Operating]
    
    HW --> Initial[Initial Purchase<br/>₹1.50 Cr]
    HW --> Refresh[Year 4 Refresh<br/>₹0.94 Cr]
    
    SW --> Annual[Annual Subscriptions<br/>₹1.64 Cr]
    SW --> Growth[Capacity Growth<br/>₹0.40 Cr]
    
    SV --> Impl[Implementation<br/>₹0.15 Cr]
    SV --> Train[Training<br/>₹0.03 Cr]
    
    OP --> Power[Power & Cooling<br/>₹0.38 Cr]
    OP --> AMC[Support Contracts<br/>₹0.25 Cr]
    
    style TCO fill:#ffccbc
    style HW fill:#c8e6c9
    style SW fill:#bbdefb
    style SV fill:#fff9c4
    style OP fill:#e1bee7

### 3. Implementation Critical Path

flowchart LR
    A[Week 1-2<br/>Procurement] --> B[Week 3-4<br/>Site A Infrastructure]
    B --> C[Week 5-6<br/>Services Deployment]
    C --> D[Week 7-8<br/>Data Migration]
    D --> E[Week 9<br/>Go-Live]
    E --> F[Week 10-12<br/>Site B DR]
    
    B -.->|Parallel| B2[Documentation]
    C -.->|Parallel| C2[Monitoring Setup]
    E -.->|Parallel| E2[Training]
    
    style A fill:#bbdefb
    style B fill:#c8e6c9
    style C fill:#fff9c4
    style D fill:#ffccbc
    style E fill:#e1bee7
    style F fill:#d7ccc8

### 4. Asset Lifecycle Flow

flowchart LR
    Purchase[Purchase<br/>Year 0] --> Deploy[Deploy<br/>Month 1-2]
    Deploy --> Operate[Operate<br/>Years 1-3]
    Operate --> Maintain[Maintain<br/>AMC/Years 4-5]
    Maintain --> Decision{Asset Status}
    
    Decision -->|Healthy| Refresh[Refresh<br/>Year 5-6]
    Decision -->|EOL/EOS| Replace[Replace<br/>Budget Approved]
    Decision -->|Obsolete| Dispose[Dispose<br/>Secure Wipe]
    
    Refresh --> Purchase
    Replace --> Purchase
    Dispose --> Purchase
    
    style Purchase fill:#c8e6c9
    style Operate fill:#bbdefb
    style Maintain fill:#fff9c4
    style Refresh fill:#e1bee7
    style Dispose fill:#ffccbc

## Vendor Evaluation Scorecard Template

┌─────────────────────────────────────────────────────────────────────┐
│                    VENDOR EVALUATION SCORECARD                      │
├─────────────────────────────────────────────────────────────────────┤
│ Vendor: _______________________  Date: _______________________     │
│ Product: ______________________  Evaluator: __________________     │
├─────────────────────────────────────────────────────────────────────┤
│ CRITERIA          │ WEIGHT │ SCORE (1-10) │ WEIGHTED │ COMMENTS   │
├───────────────────┼────────┼──────────────┼──────────┼────────────┤
│ Technical Fit     │  25%   │              │          │            │
│ Price             │  20%   │              │          │            │
│ Support Quality   │  20%   │              │          │            │
│ Delivery Time     │  15%   │              │          │            │
│ References        │  10%   │              │          │            │
│ Financial Stable  │  10%   │              │          │            │
├───────────────────┼────────┼──────────────┼──────────┼────────────┤
│ TOTAL             │ 100%   │              │          │            │
└─────────────────────────────────────────────────────────────────────┘

Minimum passing score: 7.0 weighted average

## Summary: Key Financial Decisions

| Decision | Selected Option | Savings vs. Alternative | Justification |
| --- | --- | --- | --- |
| Storage Platform | Synology HD6500 | ₹10.24 Cr | Proxy workflow doesn't need all-flash |
| Network Speed | 10GbE (SFP+) | ₹1.36 L | Sufficient bandwidth, easy upgrade path |
| Firewall | FortiGate 120G | ₹9.6 L | Right-sized for throughput needs |
| Cloud Storage | Wasabi | ₹17.5 L/yr | Zero egress fees |
| Monitoring | Zabbix | ₹6.8 L/yr | Feature-complete at lower cost |
| UPS | Dual 10kVA | N/A | N+1 redundancy essential |
| **Total 5-Year Savings** | **₹16.16 Cr** |  |  |

Document Version 2.0 — Enhanced with Detailed Procurement Reasoning

Prepared by: VConfi Solutions

Date: March 22, 2026

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Part 5: Security Stress Test Results

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

# Part 5 — ENHANCED Security Stress Test & Hardening

## B2H Studios IT Infrastructure Implementation Plan

Client: B2H Studios

Project: Media & Entertainment Infrastructure — Option B+ (Optimized Synology HD6500)

Document Version: 2.0 (Enhanced Edition with Detailed Reasoning)

Date: March 22, 2026

Prepared by: VConfi Solutions

Classification: CONFIDENTIAL

## Table of Contents

[Security Assessment Methodology](#1-security-assessment-methodology-new-section)

[Attack Surface Analysis](#2-attack-surface-analysis--enhanced)

[Attack Scenarios with Kill Chain Analysis](#3-attack-scenarios--enhanced-with-kill-chain-analysis)

[Vulnerability Report](#4-vulnerability-report--enhanced)

[Hardening Recommendations](#5-hardening-recommendations--enhanced)

[Security Metrics & KPIs](#6-security-metrics--kpis--new-section)

[Cost of Breach Analysis](#7-cost-of-breach-analysis--new-section)

[Security Testing Plan](#8-security-testing-plan--new-section)

[Remediation Timeline](#9-remediation-timeline)

[Sign-Off](#10-sign-off)

## 1. Security Assessment Methodology (NEW SECTION)

### 1.1 Threat Modeling Approach

#### Why STRIDE Methodology for B2H Studios?

STRIDE (Spoofing, Tampering, Repudiation, Information Disclosure, Denial of Service, Elevation of Privilege) was selected as the primary threat modeling framework for the following reasons:

| Factor | Rationale |
| --- | --- |
| **Industry Alignment** | STRIDE is the de facto standard for enterprise threat modeling; auditors expect this framework |
| **Comprehensive Coverage** | Covers all six fundamental attack categories applicable to media/entertainment infrastructure |
| **Tool Support** | Microsoft Threat Modeling Tool and OWASP Threat Dragon provide native STRIDE support |
| **Team Familiarity** | Most security professionals trained on STRIDE, enabling peer review and validation |

Detailed STRIDE Application to B2H Infrastructure:

| STRIDE Category | B2H Asset | Threat Example | Control Implemented |
| --- | --- | --- | --- |
| **Spoofing** | ZTNA Portal | Attacker impersonates legitimate user | MFA via FortiToken, device certificates |
| **Tampering** | NAS Project Files | Modification of project deliverables | Snapshot replication, integrity verification |
| **Repudiation** | Admin Actions | Admin denies deleting files | FortiAnalyzer audit logging, immutable logs |
| **Information Disclosure** | Client Content | Leak of unreleased media | Encryption at rest (AES-256), ZTNA access controls |
| **Denial of Service** | Signiant SDCX | Attack prevents file transfers | DDoS protection, redundant ISPs |
| **Elevation of Privilege** | DSM Admin | Guest user gains admin rights | Role-based access, least privilege |

#### Attack Surface Identification Process

flowchart TD
    A[Attack Surface Discovery] --> B{Data Source}
    B -->|Network Diagrams| C[Document Review]
    B -->|Asset Inventory| D[CMDB Extraction]
    B -->|Scan Results| E[Vulnerability Scans]
    B -->|Interviews| F[Stakeholder Input]
    
    C & D & E & F --> G[Attack Surface Catalog]
    G --> H{Classification}
    H -->|External| I[Internet-Facing Assets]
    H -->|Internal| J[Internal Network Assets]
    H -->|Data| K[Data Stores & Flows]
    H -->|Human| L[Personnel & Processes]
    
    I & J & K & L --> M[Risk Scoring]
    M --> N[Prioritized Attack Surface Map]

Attack Surface Discovery Sources Used:

Design_Decisions_Detailed.md — Architecture decisions and technology selections

Network Topology Diagrams — VLAN segmentation and traffic flows

BOM (Bill of Materials) — All hardware and software components

Vendor Documentation — FortiGate, Synology, Signiant security guides

Stakeholder Interviews — B2H operational requirements and workflows

#### Threat Actor Profiling

Threat Actor Categories Relevant to B2H Studios:

| Actor Type | Capability | Motivation | Likelihood | Impact |
| --- | --- | --- | --- | --- |
| **Script Kiddies** | Low | Fame/Notoriety | Medium | Low |
| **Cybercriminals (Ransomware)** | Medium-High | Financial | HIGH | HIGH |
| **Competitors** | Medium | Competitive advantage | Low | Medium |
| **APTs (Nation-State)** | Very High | Economic espionage | Low | Very High |
| **Insider Threats** | High | Financial/Grievance | Medium | Very High |
| **Hacktivists** | Medium | Ideological | Low | Medium |

Why These Actors Matter for B2H Studios:

Ransomware Groups: Media companies are prime targets due to time-sensitive deliverables and high willingness to pay. The Maze, REvil, and BlackCat groups have specifically targeted post-production studios.

Competitors: Unreleased project files have significant commercial value; insider knowledge of client lists can be exploited.

Insider Threats: High-value media files can be easily exfiltrated; disgruntled employees have caused significant breaches in the industry.

### 1.2 Risk Assessment Framework

#### Likelihood × Impact Calculation

Risk Formula Used:

Risk Score = Likelihood (1-5) × Impact (1-5) × Control Effectiveness Modifier (0.5-1.5)

Likelihood Scale:

| Rating | Description | Occurrence Frequency |
| --- | --- | --- |
| 1 - Rare | Unlikely to occur | >10 years |
| 2 - Unlikely | May occur in exceptional circumstances | 5-10 years |
| 3 - Possible | Might occur at some time | 1-5 years |
| 4 - Likely | Will probably occur in most circumstances | <1 year |
| 5 - Almost Certain | Expected to occur in most circumstances | Multiple times/year |

Impact Scale:

| Rating | Description | Financial Impact | Business Impact |
| --- | --- | --- | --- |
| 1 - Negligible | Minor inconvenience | <₹5 Lakhs | No disruption |
| 2 - Minor | Limited damage | ₹5-25 Lakhs | Minor delays |
| 3 - Moderate | Significant damage | ₹25-75 Lakhs | Project delays |
| 4 - Major | Severe damage | ₹75-200 Lakhs | Client loss |
| 5 - Catastrophic | Business-threatening | >₹200 Lakhs | Business failure |

Control Effectiveness Modifier:

0.5 — Excellent controls (multiple redundant protections)

0.75 — Good controls (protection in place, minor gaps)

1.0 — Adequate controls (standard protection)

1.25 — Weak controls (significant gaps)

1.5 — Inadequate controls (little/no protection)

Risk Scoring Matrix (Visual):

IMPACT
           1      2      3      4      5
        ┌──────┬──────┬──────┬──────┬──────┐
    5   │  5   │  10  │  15  │  20  │  25  │ ← CRITICAL
        ├──────┼──────┼──────┼──────┼──────┤
L   4   │  4   │  8   │  12  │  16  │  20  │ ← HIGH
        ├──────┼──────┼──────┼──────┼──────┤
I   3   │  3   │  6   │  9   │  12  │  15  │ ← MEDIUM
        ├──────┼──────┼──────┼──────┼──────┤
K   2   │  2   │  4   │  6   │  8   │  10  │ ← LOW
        ├──────┼──────┼──────┼──────┼──────┤
H   1   │  1   │  2   │  3   │  4   │  5   │ ← MINIMAL
        └──────┴──────┴──────┴──────┴──────┘
        
        Risk Score Interpretation:
        20-25: CRITICAL — Immediate remediation required
        15-19: HIGH — Remediate before go-live
        9-14:  MEDIUM — Remediate within 30 days
        4-8:   LOW — Remediate next maintenance window
        1-3:   MINIMAL — Monitor and document

#### Risk Appetite Definition for B2H Studios

Organizational Risk Appetite Statement:

"B2H Studios operates in the media and entertainment industry where intellectual property protection is paramount. The organization has a LOW risk appetite for data breaches and a MEDIUM risk appetite for operational disruption. Financial losses exceeding ₹1 Crore from a single security incident are unacceptable."

Risk Tolerance by Category:

| Risk Category | Appetite | Justification | Escalation Threshold |
| --- | --- | --- | --- |
| **Data Breach** | VERY LOW | Client content is core asset | ANY incident |
| **Ransomware** | LOW | Cannot afford project delays | >₹50 Lakhs impact |
| **Downtime** | MEDIUM | 10-minute RTO is acceptable | >4 hours downtime |
| **Compliance** | LOW | ISO 27001 certification required | ANY non-compliance |
| **Insider Threat** | LOW | High-value IP at risk | ANY confirmed incident |
| **Third-Party** | MEDIUM | Vendors necessary for business | >₹25 Lakhs impact |

### 1.3 Testing Methodology

#### Black Box vs. Gray Box vs. White Box

Testing Approach Selected: Gray Box with White Box Components

| Testing Type | Rationale for B2H | Scope |
| --- | --- | --- |
| **Gray Box (Primary)** | Simulates realistic attacker with limited insider knowledge (e.g., compromised employee account) | External perimeter, ZTNA portal, wireless networks |
| **White Box (Supplemental)** | Validates internal control effectiveness; required for compliance | Internal network segmentation, configuration review |
| **Black Box (Limited)** | Validates exposed attack surface; useful for DDoS resilience | Internet-facing services enumeration |

Why Not Full Black Box?

Limited time and budget constraints

Gray box provides better ROI for security assessment

B2H's primary threat model assumes authenticated attackers (ransomware, insider threats)

Why Include White Box?

ISO 27001 requires configuration reviews

Internal segmentation validation is critical for this architecture

Allows identification of misconfigurations invisible to external testing

#### Automated Scanning Tools Used

| Tool Category | Tool | Version | Purpose | Coverage |
| --- | --- | --- | --- | --- |
| **Network Scanner** | Nmap | 7.94 | Port scanning, service discovery | Perimeter, internal |
| **Vulnerability Scanner** | Nessus | 10.7 | CVE identification, configuration audit | All hosts |
| **Web Scanner** | Burp Suite Pro | 2023.12 | Web application testing | ZTNA portal, DSM |
| **Wireless Scanner** | Aircrack-ng | 1.7 | Wireless security assessment | FortiAP |
| **SSL/TLS Scanner** | SSLyze | 5.2 | TLS configuration analysis | All HTTPS services |
| **Configuration Auditor** | CIS-CAT Pro | 4.0 | Benchmark compliance | FortiGate, DSM |

#### Manual Penetration Testing Approach

Phased Testing Methodology:

flowchart LR
    subgraph Phase1["Phase 1: Reconnaissance"]
        P1A[OSINT Gathering]
        P1B[Infrastructure Mapping]
        P1C[Employee Enumeration]
    end
    
    subgraph Phase2["Phase 2: Scanning"]
        P2A[Port Scanning]
        P2B[Vulnerability Scanning]
        P2C[Configuration Review]
    end
    
    subgraph Phase3["Phase 3: Exploitation"]
        P3A[Credential Attacks]
        P3B[Service Exploitation]
        P3C[Lateral Movement]
    end
    
    subgraph Phase4["Phase 4: Post-Exploitation"]
        P4A[Privilege Escalation]
        P4B[Data Exfiltration Test]
        P4C[Persistence Testing]
    end
    
    subgraph Phase5["Phase 5: Reporting"]
        P5A[Findings Analysis]
        P5B[Risk Scoring]
        P5C[Remediation Plan]
    end
    
    Phase1 --> Phase2 --> Phase3 --> Phase4 --> Phase5

Manual Testing Scenarios:

ZTNA Bypass Attempts: Testing for authentication bypasses, session hijacking

VLAN Hopping: Attempting to bypass network segmentation

DSM Exploitation: Testing for default credentials, API vulnerabilities

File Upload Attacks: Testing Signiant SDCX for malicious file handling

Social Engineering: Phishing simulation (coordinated with B2H management)

#### Social Engineering Test Design

Testing Framework:

| Test Type | Method | Target | Success Metric | Frequency |
| --- | --- | --- | --- | --- |
| **Phishing Email** | Simulated credential harvest | All employees | Click rate <5% | Quarterly |
| **Pretexting Call** | Fake IT support | IT staff | Disclosure rate 0% | Bi-annual |
| **USB Drop** | Infected USB in parking lot | Found devices | Execution rate <10% | Annual |
| **Physical Tailgating** | Unauthorized facility access | Security staff | Success rate 0% | Annual |

Phishing Test Scenarios for B2H:

"New Project Assignment" — Fake SharePoint link to "new client project"

"FortiClient Update Required" — Fake IT notification with malicious attachment

"Invoice Payment Issue" — Fake vendor email targeting finance team

"Client Feedback" — Fake client portal login page

## 2. Attack Surface Analysis — Enhanced

### 2.1 Perimeter Attack Surface

#### 2.1.1 ZTNA Gateway (HTTPS/443)

Service Overview:

| Attribute | Detail |
| --- | --- |
| **Function** | Zero Trust Network Access portal for remote employee authentication |
| **Technology** | FortiGate ZTNA with FortiClient |
| **Exposure** | Internet-facing, TCP/443 |
| **User Base** | 25 remote employees |
| **Authentication** | FortiToken push MFA + device certificate |

Why It Must Be Exposed:

Remote workforce requires secure access to internal resources

VPN replacement for Zero Trust architecture

Must be accessible from any internet location (employees work remotely)

Attack Vectors Specific to This Service:

| Attack Vector | Description | Current Control | Residual Risk |
| --- | --- | --- | --- |
| **Credential Stuffing** | Automated login with breached credentials | MFA blocks successful auth | Account enumeration possible |
| **Session Hijacking** | Theft of valid session token | TLS 1.3, secure cookies | XSS or malware could steal tokens |
| **Device Certificate Theft** | Steal valid device cert from compromised endpoint | Certificate tied to hardware | Possible with admin access to endpoint |
| **Brute Force** | Dictionary attack against weak passwords | No rate limiting configured | Resource exhaustion, MFA fatigue |
| **Zero-Day Exploit** | Unpatched FortiGate vulnerability | Auto-update enabled | Window of exposure between disclosure and patch |

Compensating Controls:

Geo-filtering to India + operational countries only

Device posture validation (Kaspersky, patches, encryption)

FortiAnalyzer logging all authentication attempts

Account lockout after failed attempts (to be implemented)

Residual Risk Rating: MEDIUM (Score: 9)

Likelihood: 3 (Possible)

Impact: 4 (Major — full network access)

Control Modifier: 0.75 (MFA provides strong protection)

Risk Score: 3 × 4 × 0.75 = 9

#### 2.1.2 Signiant SDCX (UDP/33001)

Service Overview:

| Attribute | Detail |
| --- | --- |
| **Function** | High-speed file transfer for client content ingest/delivery |
| **Technology** | Signiant SDCX with FASP protocol |
| **Exposure** | Internet-facing, UDP/33001 (FASP) + TCP/443 (Management) |
| **User Base** | External clients, B2H operations team |
| **Data Flow** | Client uploads → Signiant → HD6500 NAS |

Why It Must Be Exposed:

External clients must upload large media files (100GB+ per project)

Traditional protocols (FTP, SFTP) too slow for 4K/8K media

FASP acceleration requires direct UDP communication

Attack Vectors Specific to This Service:

| Attack Vector | Description | Current Control | Residual Risk |
| --- | --- | --- | --- |
| **FASP Protocol Exploit** | Buffer overflow or state machine attack | Proprietary protocol (less research available) | No IPS on DMZ to detect anomalies |
| **DoS via UDP Flood** | Flood UDP/33001 to disrupt transfers | FortiGate DDoS protection | Could overwhelm link bandwidth |
| **Management Interface Compromise** | Attack TCP/443 management console | ZTNA required for admin access | Weak admin password could be guessed |
| **File Upload Malware** | Malicious file upload to compromise NAS | File type validation | Zero-day in file parser possible |
| **Client Account Compromise** | Stolen client credentials used for access | Per-client isolated directories | Lateral movement possible |

Compensating Controls:

Geo-filtering to operational countries only

Client-specific directories with strict permissions

Signiant's built-in AES-256 encryption

ZTNA required for management access

Residual Risk Rating: MEDIUM (Score: 12)

Likelihood: 4 (Likely — high-value target)

Impact: 3 (Moderate — service disruption)

Control Modifier: 1.0 (Standard protection)

Risk Score: 4 × 3 × 1.0 = 12

#### 2.1.3 DNS (External Resolution)

Service Overview:

| Attribute | Detail |
| --- | --- |
| **Function** | Domain name resolution for B2H infrastructure |
| **Technology** | ISP-provided DNS or public resolver (Quad9/Cloudflare) |
| **Exposure** | Internal DNS queries to external resolvers |
| **User Base** | All internal systems |

Why DNS Configuration Matters:

DNS is often overlooked attack vector

DNS hijacking can redirect traffic to malicious sites

DNS tunneling can exfiltrate data

Attack Vectors Specific to DNS:

| Attack Vector | Description | Current Control | Residual Risk |
| --- | --- | --- | --- |
| **DNS Hijacking** | Redirect traffic to malicious site | ISP DNSSEC | No internal DNS filtering configured |
| **DNS Tunneling** | Exfiltrate data via DNS queries | Standard DNS | No DNS monitoring for tunneling |
| **Cache Poisoning** | Inject false records into resolver | External resolvers | Low (external resolvers hardened) |

Recommended DNS Security:

# FortiGate DNS Configuration
config system dns
    set primary 9.9.9.9    # Quad9 (security-focused)
    set secondary 1.1.1.2  # Cloudflare for Families (malware blocking)
    set dnsfilter-profile "B2H-DNS-Filter"
end

# DNS Filter Profile
config dnsfilter profile
    edit "B2H-DNS-Filter"
        config ftgd-dns
            set options error-allow
            config filters
                edit 1
                    set category 2  # Botnet
                    set action block
                next
                edit 2
                    set category 3  # Hacking
                    set action block
                next
                edit 3
                    set category 4  # Phishing
                    set action block
                next
            end
        end
        set log-all-domain enable
        set sdns-ftgd-err-log enable
    next
end

Residual Risk Rating: LOW (Score: 4)

Likelihood: 2 (Unlikely)

Impact: 3 (Moderate)

Control Modifier: 0.75

Risk Score: 2 × 3 × 0.75 = 4.5

### 2.2 Internal Attack Surface

#### 2.2.1 Lateral Movement Pathways

flowchart TB
    subgraph VLAN20["VLAN 20: Production"]
        WS[Workstations<br/>ZTNA Clients]
    end
    
    subgraph VLAN30["VLAN 30: Storage"]
        NAS[Synology HD6500<br/>Project Files]
    end
    
    subgraph VLAN40["VLAN 40: Management"]
        MGMT[Management VMs<br/>FortiAnalyzer, DSM]
        ILO[iLO Interface<br/>R760 Server]
    end
    
    subgraph VLAN10["VLAN 10: DMZ"]
        SDCX[Signiant SDCX]
    end
    
    subgraph VLAN50["VLAN 50: Guest"]
        GUEST[Guest Wi-Fi]
    end
    
    WS -->|Allowed| NAS
    WS -.->|Blocked| MGMT
    WS -.->|Blocked| ILO
    WS -.->|Blocked| SDCX
    
    SDCX -->|Allowed| NAS
    
    GUEST -.->|Blocked| NAS
    GUEST -.->|Blocked| MGMT
    GUEST -.->|Blocked| WS
    
    MGMT -->|Allowed| NAS
    MGMT -->|Allowed| ILO

Lateral Movement Path Analysis:

| Source VLAN | Target VLAN | Path Exists | Control | Risk |
| --- | --- | --- | --- | --- |
| Production (20) | Storage (30) | ✅ Yes | Firewall rules | Low (required for work) |
| Production (20) | Management (40) | ❌ No | Firewall deny | Controlled |
| DMZ (10) | Storage (30) | ✅ Yes | Firewall rules | Medium (if DMZ compromised) |
| Guest (50) | Any Internal | ❌ No | Firewall deny | Controlled |
| Management (40) | Any | ✅ Yes | Admin access | Requires strict monitoring |

Critical Lateral Movement Risk:

DMZ → Storage (VLAN 10 → VLAN 30)

If Signiant SDCX is compromised, attacker has direct access to NAS

Mitigation: Strict firewall rules, IPS on DMZ, regular SDCX patching

#### 2.2.2 Privilege Escalation Opportunities

| Initial Access | Privilege Target | Method | Current Control |
| --- | --- | --- | --- |
| Regular Domain User | Domain Admin | Kerberoasting, DCSync | No AD in scope (workgroup only) |
| DSM User | DSM Admin | Privilege escalation bug | DSM auto-update, 2FA |
| FortiAnalyzer User | Super Admin | RBAC bypass | RBAC configured, MFA |
| iLO Operator | iLO Admin | Password brute force | Network isolation (planned) |
| VM User | Hypervisor Access | VM escape | VMware hardening |

Why Workgroup (Not Domain) Reduces Privilege Escalation Risk:

No Active Directory = no Kerberos attacks

No domain trust relationships to exploit

Local privilege escalation only (limited impact per host)

Trade-off: More management overhead, but lower attack surface

#### 2.2.3 Trust Boundary Analysis

flowchart TB
    subgraph Internet["Internet (Untrusted)"]
        direction TB
        EXT[External Actors<br/>Risk: HIGH]
    end
    
    subgraph Perimeter["Perimeter (Semi-Trusted)"]
        direction TB
        PER[ZTNA Gateway<br/>Signiant SDCX<br/>Risk: MEDIUM]
    end
    
    subgraph Internal["Internal (Trusted with Verification)"]
        direction TB
        INT[Internal Network<br/>Risk: MEDIUM]
    end
    
    subgraph Critical["Critical Assets (High Trust)"]
        direction TB
        CRIT[NAS Data<br/>Backup Systems<br/>Risk: LOW]
    end
    
    Internet -->|ZTNA Auth| Perimeter
    Perimeter -->|Firewall Rules| Internal
    Internal -->|Privileged Access| Critical
    
    style Internet fill:#ffcccc
    style Perimeter fill:#ffffcc
    style Internal fill:#ccffcc
    style Critical fill:#ccffff

Trust Boundaries:

| Boundary | Verification Mechanism | Risk |
| --- | --- | --- |
| Internet → Perimeter | ZTNA authentication, device posture | Medium |
| Perimeter → Internal | Firewall rules, VLAN segmentation | Low |
| Internal → Critical | Admin authentication, 2FA | Low |
| Guest → Internal | Complete isolation | Controlled |

### 2.3 Data Flow Analysis

#### 2.3.1 Sensitive Data Inventory

| Data Category | Location | Sensitivity | Volume | Retention |
| --- | --- | --- | --- | --- |
| **Active Project Files** | HD6500 Primary (VLAN 30) | CRITICAL | 400TB | Project duration |
| **Archived Projects** | Wasabi Cloud + HD6500 DR | HIGH | 200TB+ | 7 years |
| **Client Contact Data** | HD6500, FortiAuthenticator | MEDIUM | ~500 records | Business need |
| **Financial Records** | HD6500 (restricted share) | HIGH | ~10GB | 7 years |
| **Employee PII** | HR system (future) | MEDIUM | ~25 records | Employment + 7 years |
| **System Credentials** | HashiCorp Vault | CRITICAL | ~100 secrets | Rotated quarterly |

#### 2.3.2 Data Flow Diagrams with Security Controls

Data Flow 1: Client Upload via Signiant

flowchart LR
    CLIENT[External Client] -->|FASP UDP/33001| SDCX[Signiant SDCX]
    SDCX -->|SMB 10GbE| NAS[Synology HD6500]
    NAS -->|Snapshot| LOCK[Immutable Snapshots]
    NAS -->|Replication| DR[DR Site NAS]
    NAS -->|Hybrid Share| CLOUD[Wasabi Cloud]
    
    SDCX -.->|Geo-filter| GF[Country Whitelist]
    SDCX -.->|Encryption| ENC[AES-256 FASP]
    NAS -.->|Access Control| AC[Per-Client Folders]

Security Controls per Stage:

| Stage | Control | Implementation |
| --- | --- | --- |
| Upload | Geo-filtering | FortiGate country whitelist |
| Upload | Encryption | FASP AES-256 |
| Upload | Authentication | Per-client credentials |
| Storage | Access Control | SMB share permissions |
| Storage | Encryption at Rest | AES-256 volume encryption |
| Backup | Immutability | Snapshot Lock (7 days) |
| Archive | WORM | Wasabi compliance mode |

Data Flow 2: Remote Employee Access via ZTNA

flowchart LR
    REMOTE[Remote Employee] -->|HTTPS/443| FG[FortiGate ZTNA]
    FG -->|Posture Check| PC[Device Validation]
    PC -->|Auth| FA[FortiAuthenticator]
    FA -->|MFA| FT[FortiToken Push]
    FT -->|Allow| ACCESS[NAS Access Granted]
    
    FG -.->|Geo-filter| GEO[Country Check]
    FG -.->|Rate Limit| RL[Brute Force Protection]
    ACCESS -.->|Micro-segment| SEG[Only NAS Shares]

Data Flow 3: Replication to DR Site

flowchart LR
    PRIMARY[Site A HD6500] -->|HTTPS/5001| INTERNET[Internet/WAN]
    INTERNET -->|HTTPS/5001| DR[Site B HD6500]
    
    PRIMARY -.->|Encryption| ENC[AES-256]
    DR -.->|Certificate| CERT[Pinning Validation]
    DR -.->|Integrity| INT[Hash Verification]

#### 2.3.3 Encryption in Transit Analysis

| Communication Path | Protocol | Encryption | Cipher Suite | Key Length | Status |
| --- | --- | --- | --- | --- | --- |
| Client → Signiant | FASP | AES-256-GCM | Proprietary | 256-bit | ✅ Secure |
| Client → ZTNA | HTTPS | TLS 1.3 | TLS_AES_256_GCM_SHA384 | 256-bit | ✅ Secure |
| ZTNA → NAS | SMB 3.1.1 | AES-128-GCM | SMB Encryption | 128-bit | ✅ Secure |
| NAS → Wasabi | HTTPS | TLS 1.2+ | ECDHE-RSA-AES256-GCM | 256-bit | ✅ Secure |
| NAS → DR NAS | HTTPS | AES-256 | Synology Encryption | 256-bit | ✅ Secure |
| Admin → FortiGate | HTTPS | TLS 1.3 | TLS_AES_256_GCM_SHA384 | 256-bit | ✅ Secure |
| Admin → DSM | HTTPS | TLS 1.2 | Configurable | 256-bit | ⚠️ Verify config |

Gap Identified: DSM TLS configuration must be verified to ensure TLS 1.0/1.1 are disabled.

#### 2.3.4 Encryption at Rest Analysis

| Storage Location | Encryption Type | Key Management | Algorithm | Status |
| --- | --- | --- | --- | --- |
| HD6500 Primary | Volume Encryption | DSM Key Manager | AES-256-XTS | ✅ Implemented |
| HD6500 DR | Volume Encryption | DSM Key Manager | AES-256-XTS | ✅ Implemented |
| Wasabi Cloud | Server-Side Encryption | Wasabi Managed | AES-256 | ✅ Automatic |
| VM Disks (R760) | VMware vSAN encryption | vCenter KMS | AES-256 | ⚠️ Verify config |
| Workstations | BitLocker/FileVault | TPM/Password | AES-256-XTS | ✅ FortiClient policy |
| Backup Tapes | N/A (not used) | N/A | N/A | N/A |

## 3. Attack Scenarios — Enhanced with Kill Chain Analysis

### Kill Chain Framework Applied

All attack scenarios follow the MITRE ATT&CK kill chain stages:

Reconnaissance — Information gathering

Weaponization — Payload creation

Delivery — Payload transmission

Exploitation — Vulnerability exploitation

Installation — Malware/persistence installation

Command & Control (C2) — Remote control establishment

Actions on Objective — Goal achievement

### Scenario 1: Ransomware Attack (Enhanced)

#### Threat Actor Profile

| Attribute | Detail |
| --- | --- |
| **Actor Type** | Cybercriminal (Ransomware-as-a-Service) |
| **Capability** | Medium-High (automated tools, affiliate model) |
| **Motivation** | Financial (ransom payment in cryptocurrency) |
| **Target Value** | HIGH (media companies pay ransoms to meet deadlines) |
| **Examples** | LockBit, BlackCat (ALPHV), Play, Akira |

Why B2H Studios Is a Ransomware Target:

Time-Sensitive Deliverables: Post-production deadlines create ransom pressure

High-Value Data: Unreleased media content is irreplaceable

Insurance Coverage: Many media companies have cyber insurance that covers ransoms

SMB Profile: 25-employee company = potentially weaker security than major studios

#### Kill Chain Analysis

flowchart LR
    subgraph KillChain["Ransomware Kill Chain"]
        direction LR
        R[Reconnaissance] --> W[Weaponization]
        W --> D[Delivery]
        D --> E[Exploitation]
        E --> I[Installation]
        I --> C2[C2 Channel]
        C2 --> A[Actions on Obj]
    end
    
    subgraph Controls["B2H Controls"]
        direction TB
        C1[Email Filter]
        C2[EDR/FortiClient]
        C3[ZTNA Segmentation]
        C4[Immutable Snapshots]
        C5[Immutable Snapshots]
    end
    
    R -->|Email harvest| R1[LinkedIn scraping]
    W -->|Payload creation| W1[Encryptor + Stealer]
    D -->|Phishing email| D1[C1<br/>⚠️ Gap: No email security]
    E -->|Macro execution| E1[C2<br/>✅ EDR Detects]
    I -->|Persistence via registry| I1[C3<br/>⚠️ Local admin possible]
    C2 -->|HTTPS beacon| C2a[C2<br/>⚠️ ZTNA may block]
    A -->|File encryption| A1[C4/C5<br/>✅ Immutable backups protect]

Detailed Kill Chain Walkthrough:

| Stage | TTP (Tactics, Techniques, Procedures) | B2H Control | Effectiveness |
| --- | --- | --- | --- |
| **Reconnaissance** | Harvest emails from B2H website, LinkedIn; identify ZTNA portal URL | None (public info) | Attackers gain target list |
| **Weaponization** | Create malicious Office doc with macro; embed ransomware payload | Email gateway (to be verified) | Depends on email security |
| **Delivery** | Spear-phishing email to project manager: "New client brief attached" | Employee training (VULN-009 gap) | High risk without training |
| **Exploitation** | User enables macro; VBA downloads ransomware loader | FortiClient EDR real-time protection | EDR should detect and block |
| **Installation** | Registry Run key persistence; disable Windows Defender | Admin rights required | Limited if standard user |
| **C2** | HTTPS beacon to attacker server (often compromised legitimate site) | FortiGate web filtering | May block known C2 |
| **Actions** | Encrypt files on accessible shares; delete shadow copies; ransom note | **IMMUTABLE SNAPSHOTS** | ✅ Data recoverable |

#### Why Immutable Snapshots Stop Each Stage

| Attack Stage | Ransomware Action | Immutable Snapshot Protection |
| --- | --- | --- |
| **Encryption** | Encrypt NAS files | Snapshots contain pre-encryption versions |
| **Deletion** | Delete snapshots | Lock prevents deletion for 7 days minimum |
| **Replication** | Corrupt DR site | Replication is one-way; DR snapshots also locked |
| **Cloud Tiering** | Delete Wasabi data | WORM compliance mode prevents deletion |

Recovery Time Calculation:

Scenario: Ransomware encrypts 400TB on primary NAS

Without Immutable Snapshots:
├─ Restore from DR site: 10 minutes failover
├─ Data loss since last snapshot: Up to 2 hours
└─ Total RTO: 10 minutes (but data integrity questionable)

With Immutable Snapshots:
├─ Identify last clean snapshot: 15 minutes
├─ Clone snapshot to new volume: 30 minutes
├─ Redirect users to recovered data: 10 minutes
└─ Total Recovery Time: ~1 hour

Cost Comparison:
├─ Ransom demand (typical): ₹3-8 Crores
├─ Recovery with immutable backups: ₹0
└─ ROI of snapshot immutability: INFINITE

#### CVSS Calculation

VULN-RAN-001: Ransomware Vulnerability (Pre-Remediation)

| Metric | Value | Explanation |
| --- | --- | --- |
| **Attack Vector (AV)** | Network | Can be delivered remotely |
| **Attack Complexity (AC)** | Low | Phishing requires minimal skill |
| **Privileges Required (PR)** | None | Targets regular users |
| **User Interaction (UI)** | Required | Must click/open file |
| **Scope (S)** | Changed | Can affect NAS from workstation |
| **Confidentiality (C)** | High | All files encrypted |
| **Integrity (I)** | High | Data modified (encrypted) |
| **Availability (A)** | High | Data unavailable until recovered |

CVSS v3.1 Vector: CVSS:3.1/AV:N/AC:L/PR:N/UI:R/S:C/C:H/I:H/A:H

Base Score Calculation:

Exploitability Score: 2.8

Impact Score: 6.0

Base Score: 10.0 (CRITICAL)

Temporal Score (with controls):

Exploit Code Maturity: Functional (1.0)

Remediation Level: Official fix (0.95)

Report Confidence: Confirmed (1.0)

Temporal Score: 9.5

Environmental Score (B2H-specific):

Confidentiality Requirement: High (1.5)

Integrity Requirement: High (1.5)

Availability Requirement: High (1.5)

Modified Attack Vector: Network (1.0)

Modified Privileges Required: None (1.0)

Environmental Score: 9.8

Overall Risk Rating: CRITICAL (9.8)

#### Current Controls Gap Analysis

| Gap | Risk | Mitigation Status |
| --- | --- | --- |
| No email security gateway | HIGH | ⚠️ Not yet implemented |
| Security awareness training missing | HIGH | ⚠️ Planned (VULN-009) |
| Snapshot lock verification manual | MEDIUM | ⚠️ Planned (VULN-004) |
| No application whitelisting | MEDIUM | ⚠️ Future enhancement |

#### Remediation with Specific Configuration

Immediate Actions (Pre-Go-Live):

Deploy Email Security (if not configured):

# If using FortiMail or external gateway
# Configure anti-phishing rules:
- Block executable attachments
- Sandbox Office documents
- URL rewriting for email links

Verify FortiClient EDR Configuration:

# FortiClient EMS Policy
config endpoint-control profile
    edit "B2H-Workstation-Profile"
        set forticlient-win-ver 7.0.0
        set forticlient-mac-ver 7.0.0
        config forticlient-threat-protection
            set forticlient-av-signature enable
            set forticlient-av-realtime enable
            set forticlient-behavior enable  # Behavioral detection
            set forticlient-ransomware enable  # Ransomware-specific protection
        end
    next
end

Implement Automated Snapshot Lock Verification:

#!/bin/bash
# /usr/local/bin/ransomware_protection_verify.sh
# Run hourly via DSM Task Scheduler

LOG_FILE="/var/log/ransomware_protection.log"
ALERT_EMAIL="security@b2hstudios.com"

# Check snapshot lock status
LOCK_STATUS=$(synosharesnapshot --list | grep -c "unlocked")

if [ "$LOCK_STATUS" -gt 5 ]; then
    echo "$(date): ALERT - $LOCK_STATUS unlocked snapshots detected" >> $LOG_FILE
    
    # Lock any unlocked snapshots older than 1 hour
    synosharesnapshot --list | while read line; do
        status=$(echo $line | awk '{print $7}')
        if [ "$status" == "unlocked" ]; then
            id=$(echo $line | awk '{print $1}')
            share=$(echo $line | awk '{print $2}')
            synosharesnapshot --lock "$share@$id"
            echo "$(date): Auto-locked snapshot $id" >> $LOG_FILE
        fi
    done
    
    # Send alert
    echo "Ransomware protection auto-locked snapshots" | mail -s "B2H Security Alert" $ALERT_EMAIL
fi

# Check for mass file modification (ransomware indicator)
# Alert if >1000 files modified in last 10 minutes
RECENT_CHANGES=$(find /volume1/projects -mmin -10 -type f | wc -l)
if [ "$RECENT_CHANGES" -gt 1000 ]; then
    echo "$(date): CRITICAL - Mass file modification detected ($RECENT_CHANGES files)" >> $LOG_FILE
    synonotify -c potential_ransomware_detected
fi

#### Verification — How to Test the Fix

| Test | Method | Expected Result |
| --- | --- | --- |
| Snapshot Lock Verification | Manually unlock a test snapshot; wait 1 hour | Auto-lock script re-locks snapshot |
| Ransomware Simulation | Use legitimate ransomware simulator (e.g., KnowBe4 RanSim) | FortiClient blocks/quarantines |
| Recovery Drill | Simulate encrypted share; restore from snapshot | Recovery within 1 hour |
| Alert Testing | Trigger mass file creation | Alert received by security team |

### Scenario 2: Insider Threat (Enhanced)

#### Threat Actor Profile

| Attribute | Detail |
| --- | --- |
| **Actor Type** | Malicious Insider, Negligent Insider, Compromised Insider |
| **Capability** | HIGH (has legitimate access) |
| **Motivation** | Financial, grievance, espionage, negligence |
| **Detection Difficulty** | Very High (authorized behavior) |
| **Examples** | Employee selling client lists, accidental data sharing |

Insider Threat Categories:

| Type | Description | Example for B2H | Likelihood |
| --- | --- | --- | --- |
| **Malicious** | Intentional harm | Editor copies client project for competitor | Low |
| **Negligent** | Careless actions | PM emails files to personal Gmail for "easy access" | Medium |
| **Compromised** | Credentials stolen | Employee workstation infected; attacker uses valid login | Medium |
| **Third-Party** | Contractor/vendor threat | Freelance editor retains project files | Medium |

Why Insiders Are Dangerous for B2H:

Legitimate Access: Employees need access to sensitive project files

Knowledge of Controls: Insiders know where security gaps exist

No Technical Barriers: No firewall or antivirus blocks authorized users

High-Value Targets: Individual projects worth ₹10-50 Lakhs

#### Kill Chain Analysis

flowchart LR
    subgraph KillChain["Insider Threat Kill Chain"]
        direction LR
        R[Identification] --> W[Planning]
        W --> D[Access]
        D --> E[Collection]
        E --> I[Concealment]
        I --> C2[Exfiltration]
        C2 --> A[Monetization]
    end
    
    subgraph Controls["B2H Controls"]
        direction TB
        C1[Access Controls]
        C2[DLP Gap]
        C3[ZTNA Logging]
        C4[No UBA]
        C5[DLP Gap]
    end
    
    R -->|Target selection| R1[High-value project]
    W -->|Method planning| W1[USB vs Cloud vs Email]
    D -->|Legitimate login| D1[C1<br/>✅ Normal access]
    E -->|File copying| E1[C3<br/>⚠️ Logged but not alerted]
    I -->|Compress/encrypt| I1[C4<br/>⚠️ No UBA to detect anomaly]
    C2 -->|Upload to Drive| C2a[C2/C5<br/>❌ No DLP blocking]
    A -->|Sell to competitor| A1[Financial gain]

Detailed Kill Chain Walkthrough:

| Stage | Insider Action | Detection Opportunity | Control Gap |
| --- | --- | --- | --- |
| **Identification** | Identify valuable project; check access permissions | None (internal knowledge) | Impossible to prevent |
| **Planning** | Decide exfiltration method; check monitoring | DLP policy would block planning | No DLP configured |
| **Access** | Log in via ZTNA with valid credentials | FortiAnalyzer logs authentication | Legitimate access |
| **Collection** | Copy files to local device during ZTNA session | Large file access logged | No anomaly detection |
| **Concealment** | Compress, encrypt, rename files to avoid detection | File type change visible | Manual review only |
| **Exfiltration** | Upload to personal cloud (Google Drive, Dropbox) | HTTPS traffic allowed | No egress DLP |
| **Monetization** | Sell to competitor; use for personal gain | External intelligence | Post-facto investigation |

#### Data Exfiltration Pathways

| Pathway | Method | Current Control | Gap |
| --- | --- | --- | --- |
| **Cloud Upload** | Google Drive, Dropbox, OneDrive | None | No DLP on egress |
| **Email Attachment** | Large ZIP to personal email | 25MB limit | Split archives bypass |
| **USB Device** | Copy to external drive | Endpoint policy | Physical access hard to control |
| **Print/Fax** | Print sensitive documents | No print monitoring | No control |
| **Screenshots** | Screen capture of confidential content | None | Impossible to prevent |
| **ZTNA Download** | Download during remote session; transfer later | Session logging | Cannot prevent download |

#### DLP Strategy Gaps

Current State: No DLP solution deployed

Required DLP Coverage:

flowchart TB
    subgraph DLPCoverage["DLP Coverage Required"]
        direction TB
        
        subgraph DataAtRest["Data at Rest"]
            DAR1[File classification]
            DAR2[Sensitive data scanning]
        end
        
        subgraph DataInMotion["Data in Motion"]
            DIM1[Email DLP]
            DIM2[Web upload blocking]
            DIM3[Cloud access control]
        end
        
        subgraph DataInUse["Data in Use"]
            DIU1[USB control]
            DIU2[Print monitoring]
            DIU3[Clipboard control]
        end
    end
    
    DAR1 & DAR2 --> Classification
    DIM1 & DIM2 & DIM3 --> Network
    DIU1 & DIU2 & DIU3 --> Endpoint

#### User Behavior Analytics (UBA) Recommendations

UBA Use Cases for B2H:

| Anomaly | Detection Logic | Alert Priority |
| --- | --- | --- |
| **Off-Hours Access** | Login outside 8 AM - 10 PM IST | Medium |
| **Mass Download** | >50GB downloaded in 1 hour | High |
| **Unusual File Types** | Access to financial docs by creative staff | Medium |
| **Terminated Employee** | Access attempt by disabled account | Critical |
| **External Sharing** | Document shared outside organization | High |
| **Geographic Impossible** | Login from India and US within 1 hour | Critical |

UBA Implementation Options:

| Solution | Cost (25 users) | Integration | Recommendation |
| --- | --- | --- | --- |
| Splunk UBA | ₹8-10 Lakhs/year | Native with Splunk SIEM | Best integration |
| FortiInsight | ₹2-3 Lakhs/year | Native to Fortinet | Cost-effective |
| Microsoft Defender for Endpoint | ₹500/user/year | Windows only | Good for Windows shops |
| Proofpoint Insider Threat | ₹4-5 Lakhs/year | Email integration | Good for email focus |

Recommended: FortiInsight for seamless Fortinet integration and cost-effectiveness.

#### CVSS Calculation

VULN-INS-001: Insider Data Exfiltration

| Metric | Value | Explanation |
| --- | --- | --- |
| **Attack Vector (AV)** | Local | Requires internal access |
| **Attack Complexity (AC)** | Low | Legitimate access makes exploitation easy |
| **Privileges Required (PR)** | Low | Standard employee access |
| **User Interaction (UI)** | None | Insider acts deliberately |
| **Scope (S)** | Changed | Can exfiltrate to external systems |
| **Confidentiality (C)** | High | Sensitive data stolen |
| **Integrity (I)** | None | No modification |
| **Availability (A)** | None | No disruption |

CVSS v3.1 Vector: CVSS:3.1/AV:L/AC:L/PR:L/UI:N/S:C/C:H/I:N/A:N

Base Score: 6.7 (MEDIUM)

Environmental Score (B2H-specific):

High value of IP increases business impact

Adjusted Score: 7.5 (HIGH)

#### Remediation with Specific Configuration

Phase 1: Immediate (FortiGate DLP):

# FortiGate DLP Configuration
config dlp sensor
    edit "B2H-Data-Protection"
        config filter
            # Block video file uploads to personal cloud
            edit 1
                set name "Block-Video-Cloud"
                set type file-type
                set file-type 15  # Video files
                set filter-by all
                set action block
                set log enable
                set severity high
            next
            # Alert on large transfers
            edit 2
                set name "Alert-Large-Transfer"
                set type file-size
                set file-size 1024  # 1GB
                set filter-by all
                set action log-only
                set severity medium
            next
            # Block personal cloud storage
            edit 3
                set name "Block-Personal-Cloud"
                set type url
                set url-pattern-type wildcard
                set url "*.googleusercontent.com" "*.dropboxapi.com" "*.1drv.com"
                set action block
                set log enable
            next
        end
    next
end

# Apply to ZTNA egress policy
config firewall policy
    edit 105
        set name "ZTNA-Egress-DLP"
        set dlp-sensor "B2H-Data-Protection"
        set logtraffic all
    next
end

Phase 2: Endpoint DLP (FortiClient):

# FortiClient EMS - Endpoint DLP Policy
config endpoint-control profile
    edit "B2H-Endpoint-DLP"
        config forticlient-data-loss-prevention
            set forticlient-dlp enable
            set forticlient-dlp-sensitivity-level high
            set forticlient-dlp-block-usb enable
            set forticlient-dlp-block-print enable
            set forticlient-dlp-block-clipboard enable
        end
    next
end

Phase 3: Access Logging and Review:

# Splunk query for insider threat detection
# Run daily and alert on matches

# Off-hours access
index=fortigate eventtype=ztna_login 
| eval hour=strftime(_time, "%H") 
| where hour < 8 OR hour > 22 
| stats count by user, srcip 
| where count > 3

# Mass download
index=fortigate eventtype=nas_access action=download 
| stats sum(bytes) as total_bytes by user 
| where total_bytes > 50000000000 
| eval gb=round(total_bytes/1024/1024/1024,2)

# Access to sensitive shares
index=fortigate eventtype=nas_access share="finance" OR share="contracts" 
| lookup user_role.csv user OUTPUT role 
| where role="creative" OR role="editor"

#### Verification — How to Test the Fix

| Test | Method | Expected Result |
| --- | --- | --- |
| Cloud Upload Block | Attempt to upload video to Google Drive | Upload blocked; alert generated |
| Large Transfer Alert | Download 2GB project folder | Alert sent to security team |
| USB Block | Plug in USB drive; attempt copy | Copy blocked by FortiClient |
| Off-Hours Alert | Log in at midnight | Alert generated for off-hours access |

### Scenario 3: Supply Chain Attack

#### Threat Actor Profile

| Attribute | Detail |
| --- | --- |
| **Actor Type** | Nation-State APT, Cybercriminal, Compromised Vendor |
| **Capability** | Medium-High (depends on vendor security) |
| **Motivation** | Espionage, financial, disruption |
| **Examples** | SolarWinds Orion, Kaseya VSA, 3CX, MOVEit |

Why Supply Chain Attacks Threaten B2H:

Trust Relationship: Vendors have privileged access

Software Dependencies: Multiple vendors supply critical software

Hardware Provenance: Equipment sourced from global supply chain

Third-Party Access: MSPs and integrators need administrative access

#### Vendor Risk Assessment

| Vendor | Product/Service | Risk Level | Mitigation Status |
| --- | --- | --- | --- |
| **Fortinet** | FortiGate, FortiClient, FortiAnalyzer | Medium | Auto-update enabled |
| **Synology** | HD6500, DSM | Medium | Auto-update enabled |
| **Signiant** | SDCX Server | Medium | Quarterly security reviews |
| **Microsoft** | Windows, Office | Medium | WSUS patching |
| **HPE** | Aruba switches, R760 server | Low | Firmware verification |
| **Wasabi** | Cloud storage | Low | SOC 2 certified |
| **Kaspersky** | Endpoint protection | Low | Centralized management |
| **HashiCorp** | Vault | Low | Open source, auditable |

Vendor Risk Scoring Formula:

Vendor Risk = (Data Access × Criticality) / (Security Posture + Monitoring)

Fortinet Example:
- Data Access: 5 (full network visibility)
- Criticality: 5 (security infrastructure)
- Security Posture: 4 (enterprise vendor, bug bounty)
- Monitoring: 3 (logs monitored)
- Risk Score: (5 × 5) / (4 + 3) = 25 / 7 = 3.6 (Medium)

#### Software Update Integrity

Update Verification Requirements:

| Software | Verification Method | Automation |
| --- | --- | --- |
| FortiGate | Fortinet digital signature | Auto-verify |
| DSM | Synology signature + checksum | Auto-verify |
| Windows | Microsoft catalog signing | WSUS + verification |
| Signiant SDCX | Manual checksum verification | Manual |

Supply Chain Attack Mitigation:

flowchart TB
    subgraph Prevention["Prevention Controls"]
        P1[Vendor Security Assessment]
        P2[Code Signing Verification]
        P3[Integrity Checks]
    end
    
    subgraph Detection["Detection Controls"]
        D1[Update Monitoring]
        D2[Behavioral Analysis]
        D3[Network Anomaly Detection]
    end
    
    subgraph Response["Response Controls"]
        R1[Rollback Capability]
        R2[Incident Response Plan]
        R3[Vendor Communication]
    end
    
    Prevention --> Detection --> Response

#### Hardware Tampering Risks

| Component | Risk | Mitigation |
| --- | --- | --- |
| **FortiGate appliances** | Implanted backdoor | Purchase from authorized distributor; verify serial numbers |
| **Synology HD6500** | Modified firmware | Check firmware signature on first boot |
| **HPE Switches** | Compromised bootloader | HPE secure boot verification |
| **Hard Drives** | Pre-installed malware | Secure erase before use; verify SMART data |

#### Third-Party Access Controls

VConfi Solutions Access (Implementation Partner):

| Access Type | Duration | Controls |
| --- | --- | --- |
| **Initial Setup** | 4-6 weeks | Named accounts, MFA, session logging |
| **Remote Support** | As needed | Time-limited credentials, supervisor approval |
| **Emergency Access** | Break-glass | Dual authorization, immediate revocation |

Third-Party Access Policy:

1. All vendor access requires written authorization from B2H IT Manager
2. Named accounts only (no shared credentials)
3. MFA mandatory for all remote access
4. Session recording enabled for privileged access
5. Access automatically revoked after project completion
6. Quarterly access review to remove orphaned accounts

#### CVSS Calculation

VULN-SUP-001: Compromised Vendor Update

| Metric | Value | Explanation |
| --- | --- | --- |
| **Attack Vector (AV)** | Network | Delivered via update channel |
| **Attack Complexity (AC)** | High | Requires compromise of vendor infrastructure |
| **Privileges Required (PR)** | None | Executes with system privileges |
| **User Interaction (UI)** | None | Automatic update installation |
| **Scope (S)** | Changed | Can affect entire network |
| **Confidentiality (C)** | High | Full access if compromised |
| **Integrity (I)** | High | Can modify any data |
| **Availability (A)** | High | Can disrupt operations |

CVSS v3.1 Vector: CVSS:3.1/AV:N/AC:H/PR:N/UI:N/S:C/C:H/I:H/A:H

Base Score: 9.0 (CRITICAL)

Note: While impact is critical, likelihood is LOW due to vendor security practices. Risk = Critical × Low = Medium overall.

#### Remediation with Specific Configuration

1. Vendor Security Verification:

# Firmware integrity check script
# Run after every update

#!/bin/bash
# verify_firmware.sh

VENDOR=$1
VERSION=$2

# FortiGate firmware verification
if [ "$VENDOR" == "fortigate" ]; then
    # Get current firmware signature
    CURRENT_SIG=$(diagnose sys flash list | grep checksum)
    
    # Compare with Fortinet published signature
    OFFICIAL_SIG=$(curl -s "https://support.fortinet.com/verify?version=$VERSION")
    
    if [ "$CURRENT_SIG" != "$OFFICIAL_SIG" ]; then
        echo "ALERT: Firmware signature mismatch!"
        echo "Current: $CURRENT_SIG"
        echo "Official: $OFFICIAL_SIG"
        # Rollback to previous version
        execute update-rollback
    fi
fi

# Synology DSM verification
if [ "$VENDOR" == "synology" ]; then
    # Check update signature
    synopkg verify --all
fi

2. Network Segmentation for Vendor Access:

# Create dedicated vendor management VLAN
VLAN 99: Vendor Access (10.10.99.0/24)

# FortiGate policy for vendor access
config firewall policy
    edit 200
        set name "Vendor-Support-Access"
        set srcintf "wan1"
        set dstintf "vendor-vlan"
        set srcaddr "VConfi-Support-IP"
        set dstaddr "Managed-Systems"
        set action accept
        set schedule "always"
        set service "SSH" "HTTPS"
        set nat enable
        set logtraffic all
        set session-ttl 3600  # 1 hour max session
    next
end

3. Vendor Access Monitoring:

# Splunk alert for vendor access anomalies
index=fortigate vendor_access=true
| eval session_duration=duration/60  # Convert to minutes
| where session_duration > 120 OR src_country!="IN"
| table _time, vendor, user, srcip, destip, session_duration
| sort -session_duration

#### Verification — How to Test the Fix

| Test | Method | Expected Result |
| --- | --- | --- |
| Firmware Signature | Attempt to install unsigned firmware | Installation blocked |
| Vendor Access Limit | Vendor tries to access unauthorized system | Access denied |
| Session Timeout | Leave vendor session idle for 2 hours | Session terminated |
| Geo Restriction | Vendor connects from non-India IP | Connection blocked or requires approval |

### Scenario 4: APT Attack

#### Threat Actor Profile

| Attribute | Detail |
| --- | --- |
| **Actor Type** | Nation-State APT (e.g., Lazarus, APT41, Charming Kitten) |
| **Capability** | Very High (zero-days, custom tools, significant resources) |
| **Motivation** | Economic espionage, political, preparation for future operations |
| **Persistence** | Months to years |
| **Examples** | Sony Pictures hack (2014), HBO leak (2017) |

Why Nation-States Target Media Companies:

Content Theft: Pre-release movies/shows for piracy or propaganda

Extortion: Political pressure through embarrassing content

Supply Chain: Use media company to reach larger targets

Disruption: Destabilize media narratives

#### Advanced Persistent Threat Characteristics

flowchart TB
    subgraph APTCharacteristics["APT Attack Characteristics"]
        direction TB
        
        C1[Long-term Persistence]
        C2[Stealthy Operations]
        C3[Custom Malware]
        C4[Multiple Entry Points]
        C5[Intelligence Gathering]
        C6[Slow and Low]
    end
    
    C1 --> P1[Living off the land]
    C2 --> P2[Encrypted C2 channels]
    C3 --> P3[Zero-day exploits]
    C4 --> P4[Supply chain + phishing]
    C5 --> P5[Reconnaissance for months]
    C6 --> P6[Minimal daily activity]

APT vs. Opportunistic Attack Comparison:

| Attribute | Opportunistic Attack | APT Attack |
| --- | --- | --- |
| **Target Selection** | Random, spray-and-pray | Specific, targeted |
| **Entry Method** | Phishing, known exploits | Zero-days, supply chain |
| **Persistence** | Hours to days | Months to years |
| **Detection Difficulty** | Medium ( noisy ) | High (stealthy) |
| **Goal** | Immediate financial gain | Intelligence gathering |
| **Resources** | Limited | Significant (state-funded) |

#### Lateral Movement Techniques

| Technique | MITRE ATT&CK ID | Detection Method |
| --- | --- | --- |
| **Pass the Hash** | T1550.002 | Monitor for NTLM authentication anomalies |
| **Kerberoasting** | T1558.003 | Alert on excessive Kerberos ticket requests |
| **Remote Services** | T1021 | Monitor for unusual remote desktop/SSH connections |
| **Internal Spear Phishing** | T1534 | Email gateway logs for internal-to-internal phishing |
| **Valid Accounts** | T1078 | UBA for account usage pattern changes |

B2H-Specific Lateral Movement Risk:

Workgroup (not domain) architecture limits some lateral movement

However, credential reuse across systems remains a risk

ZTNA segmentation limits blast radius if one workstation compromised

#### Long-Term Persistence Mechanisms

| Persistence Method | Location | Detection Difficulty |
| --- | --- | --- |
| **Registry Run Keys** | Windows Registry | Medium |
| **Scheduled Tasks** | Windows Task Scheduler | Medium |
| **WMI Event Subscription** | Windows Management Instrumentation | High |
| **Firmware Rootkit** | BIOS/UEFI | Very High |
| **Hypervisor Rootkit** | Below OS | Very High |
| **Cloud Account Compromise** | Wasabi, FortiCloud | Medium |

#### Detection Strategies

1. Network-Based Detection:

# FortiGate IPS signatures for APT detection
config ips sensor
    edit "APT-Detection"
        config entries
            edit 1
                set rule "CobaltStrike.Beacon"
                set action block
                set log enable
            next
            edit 2
                set rule "Metasploit.Traffic"
                set action block
                set log enable
            next
            edit 3
                set rule "Empire.Framework"
                set action block
                set log enable
            next
        end
    next
end

2. Behavioral Detection (Splunk):

# Detect beaconing behavior (APT C2 indicator)
index=firewall sourcetype=fortigate_traffic
| stats count, values(dest_ip) as dest_ips, earliest(_time) as first_seen, latest(_time) as last_seen by src_ip
| eval duration = last_seen - first_seen
| eval frequency = count / (duration / 3600)  # Events per hour
| where frequency > 10 AND frequency < 60  # Regular beaconing pattern
| table src_ip, dest_ips, frequency, count

# Detect unusual admin activity
index=fortigate eventtype=admin_login
| lookup admin_baseline user OUTPUT avg_login_hour, typical_src_ip
| eval current_hour=strftime(_time, "%H")
| eval hour_diff = abs(current_hour - avg_login_hour)
| where hour_diff > 4 OR srcip!=typical_src_ip
| table _time, user, srcip, action, hour_diff

3. Deception Technology (Honeypots):

# Deploy decoy credentials and files
# Alert if accessed

# Fake admin credentials in password manager
Username: honeypot_admin
Password: [fake_password]
Alert: Immediate if used

# Honeypot files on NAS
/volume1/projects/HONEYPOT_CLIENT/CONFIDENTIAL_DO_NOT_SHARE.txt
Content: "This is a honeypot file. If you're reading this, you're being monitored."
Alert: Immediate if accessed

#### CVSS Calculation

VULN-APT-001: APT Compromise

| Metric | Value | Explanation |
| --- | --- | --- |
| **Attack Vector (AV)** | Network | Multiple entry points possible |
| **Attack Complexity (AC)** | High | Requires significant resources |
| **Privileges Required (PR)** | None | Starts from unprivileged |
| **User Interaction (UI)** | Required | Initial compromise vector |
| **Scope (S)** | Changed | Full network compromise possible |
| **Confidentiality (C)** | High | Complete data access |
| **Integrity (I)** | High | Can modify all systems |
| **Availability (A)** | High | Can destroy all data |

CVSS v3.1 Vector: CVSS:3.1/AV:N/AC:H/PR:N/UI:R/S:C/C:H/I:H/A:H

Base Score: 8.9 (HIGH)

Note: While severity is high, likelihood for B2H Studios (small post-production house) is LOW unless working on politically sensitive content.

#### Remediation with Specific Configuration

1. Enhanced Logging:

# FortiGate full logging configuration
config log fortiguard setting
    set status enable
    set source-ip interface
    set upload-option realtime
    set reliable enable
end

config system fortiguard
    set analytics-log-period 180  # 180 days retention
    set sandbox-region india
end

2. File Integrity Monitoring:

# AIDE (Advanced Intrusion Detection Environment) on R760
# Install and configure

yum install aide
aide --init
mv /var/lib/aide/aide.db.new.gz /var/lib/aide/aide.db.gz

# Create daily check script
#!/bin/bash
# /etc/cron.daily/aide-check

aide --check | mail -s "AIDE Check $(hostname)" security@b2hstudios.com

3. Threat Intelligence Integration:

# FortiGate threat feed integration
config system external-resource
    edit "APT-Indicators"
        set type ip-address
        set resource "https://threat-intel.b2h.local/apt-ips.txt"
        set refresh-rate 60
    next
end

# Block known APT infrastructure
config firewall policy
    edit 1
        set name "Block-APT-IPs"
        set srcintf "any"
        set dstintf "any"
        set dstaddr "APT-Indicators"
        set action deny
        set logtraffic all
    next
end

#### Verification — How to Test the Fix

| Test | Method | Expected Result |
| --- | --- | --- |
| Beaconing Detection | Simulate regular HTTPS callbacks | Alert generated for beaconing pattern |
| Honeypot Access | Access decoy file | Immediate alert to SOC |
| FIM Alert | Modify critical system file | AIDE alert within 24 hours |
| Threat Intel | Attempt connection to known bad IP | Connection blocked |

## 4. Vulnerability Report — Enhanced

### 4.1 Vulnerability Scoring Detail

#### CVSS v3.1 Scoring Methodology

Scoring Components:

CVSS Base Score (0-10)
├── Exploitability Metrics
│   ├── Attack Vector (AV): N/A/L/P
│   ├── Attack Complexity (AC): L/H
│   ├── Privileges Required (PR): N/L/H
│   └── User Interaction (UI): N/R
├── Impact Metrics
│   ├── Scope (S): U/C
│   ├── Confidentiality (C): N/L/H
│   ├── Integrity (I): N/L/H
│   └── Availability (A): N/L/H
└── Qualitative Rating
    ├── 0.0: None
    ├── 0.1-3.9: Low
    ├── 4.0-6.9: Medium
    ├── 7.0-8.9: High
    └── 9.0-10.0: Critical

### 4.2 Comprehensive Vulnerability Table with Detailed Reasoning

| ID | Finding | Severity | CVSS Vector | Base Score | Environmental Score | Reasoning |
| --- | --- | --- | --- | --- | --- | --- |
| **VULN-001** | Brute-force protection not enabled on ZTNA | **HIGH** | `CVSS:3.1/AV:N/AC:L/PR:N/UI:N/S:U/C:L/I:N/A:L` | **5.3** | **6.5** | MFA prevents successful auth, but lack of rate limiting allows account enumeration and MFA fatigue attacks. MFA fatigue is a known attack vector where attackers spam push notifications until user approves. Without rate limiting, attackers can systematically test usernames and trigger MFA requests. |
| **VULN-002** | IPS not enabled on DMZ segment | **HIGH** | `CVSS:3.1/AV:N/AC:L/PR:N/UI:N/S:U/C:L/I:L/A:L` | **7.3** | **7.5** | Signiant SDCX exposes proprietary FASP protocol on UDP/33001. Without IPS, protocol anomalies and known vulnerability exploits go undetected. While geo-filtering reduces exposure, sophisticated attackers using compromised infrastructure in allowed countries could exploit FASP vulnerabilities without detection. |
| **VULN-003** | TLS 1.0/1.1 potentially enabled | **HIGH** | `CVSS:3.1/AV:N/AC:H/PR:N/UI:N/S:U/C:H/I:N/A:N` | **5.9** | **6.8** | Downgrade attacks (BEAST, POODLE, CRIME) are possible if legacy TLS versions accepted. Default FortiGate configurations often enable TLS 1.0/1.1 for compatibility. For a media company handling sensitive client content, weak encryption is unacceptable. |
| **VULN-004** | Snapshot lock not automated | **HIGH** | `CVSS:3.1/AV:L/AC:L/PR:H/UI:N/S:U/C:N/I:H/A:H` | **6.0** | **7.0** | If admin credentials compromised, ransomware can delete unlocked snapshots. Manual lock process creates window of vulnerability. Automation ensures snapshots are locked immediately after creation, eliminating the window. Without verification, a compromised DSM admin could disable locking entirely. |
| **VULN-005** | No DLP on egress | **MEDIUM** | `CVSS:3.1/AV:N/AC:L/PR:L/UI:N/S:U/C:H/I:N/A:N` | **6.5** | **6.0** | Malicious insider or compromised account can exfiltrate project files to personal cloud storage. ZTNA limits access to approved shares, but within those shares, no controls prevent bulk download and exfiltration. High-value IP makes this significant, but requires insider access. |
| **VULN-006** | iLO not segmented | **MEDIUM** | `CVSS:3.1/AV:A/AC:L/PR:L/UI:N/S:U/C:H/I:H/A:H` | **7.7** | **6.5** | iLO provides out-of-band server control. If VLAN 40 compromised, attacker can access iLO and take complete control of R760 server, bypassing all VM-level security. Dedicated iLO VLAN limits blast radius. |
| **VULN-007** | Rogue AP containment not automated | **MEDIUM** | `CVSS:3.1/AV:A/AC:H/PR:N/UI:R/S:U/C:L/I:L/A:N` | **4.0** | **4.5** | Fake APs can trick employees into connecting, enabling credential capture and traffic interception. FortiAP detects rogues but requires manual containment, creating exposure window. Auto-containment immediately deauthenticates clients from rogue APs. |
| **VULN-008** | ISP DDoS protection unconfirmed | **MEDIUM** | `CVSS:3.1/AV:N/AC:L/PR:N/UI:N/S:U/C:N/I:N/A:H` | **7.5** | **6.0** | Volumetric DDoS attacks exceeding ISP link capacity cannot be mitigated at FortiGate. Without upstream scrubbing, attack saturates links before reaching firewall. For a business dependent on file transfers, extended outage is significant. |
| **VULN-009** | Security awareness training missing | **HIGH** | `CVSS:3.1/AV:N/AC:L/PR:N/UI:R/S:U/C:H/I:H/A:N` | **7.1** | **7.5** | Phishing is the #1 attack vector for ransomware. Without training, users are likely to fall for well-crafted phishing emails. For B2H Studios with 25 employees, a single successful phish can compromise the entire network. |
| **VULN-010** | Physical security unverified | **MEDIUM** | `CVSS:3.1/AV:P/AC:L/PR:N/UI:N/S:U/C:H/I:H/A:H` | **6.8** | **5.0** | Physical access allows equipment tampering, drive theft, and direct network connection. Co-location facility security not verified. For a media company, physical theft of drives containing unreleased content is a significant risk. |

### 4.3 Vulnerability Categories

#### Network Security

| ID | Finding | CVSS | Priority |
| --- | --- | --- | --- |
| VULN-002 | IPS not enabled on DMZ | 7.3 | Pre-go-live |
| VULN-003 | TLS 1.0/1.1 enabled | 5.9 | Pre-go-live |
| VULN-007 | Rogue AP containment manual | 4.0 | Post-deployment |
| VULN-008 | DDoS protection unconfirmed | 7.5 | Post-deployment |

#### Access Control

| ID | Finding | CVSS | Priority |
| --- | --- | --- | --- |
| VULN-001 | No brute-force protection | 5.3 | Pre-go-live |
| VULN-006 | iLO not segmented | 7.7 | Post-deployment |

#### Data Protection

| ID | Finding | CVSS | Priority |
| --- | --- | --- | --- |
| VULN-004 | Snapshot lock not automated | 6.0 | Pre-go-live |
| VULN-005 | No DLP on egress | 6.5 | Post-deployment |

#### Logging & Monitoring

| ID | Finding | CVSS | Priority |
| --- | --- | --- | --- |
| *Covered in other categories* |  |  |  |

#### Configuration Management

| ID | Finding | CVSS | Priority |
| --- | --- | --- | --- |
| VULN-009 | No security training | 7.1 | Pre-go-live |
| VULN-010 | Physical security unverified | 6.8 | Post-deployment |

### 4.4 Remediation Priority Matrix

flowchart TB
    subgraph PreGoLive["Pre-Go-Live (Must Fix)"]
        P1[VULN-001: Brute-force protection]
        P2[VULN-002: IPS on DMZ]
        P3[VULN-003: TLS hardening]
        P4[VULN-004: Snapshot automation]
        P5[VULN-009: Security training]
    end
    
    subgraph PostDeployment["Post-Deployment (30 Days)"]
        D1[VULN-005: DLP deployment]
        D2[VULN-006: iLO segmentation]
        D3[VULN-007: Rogue AP auto-containment]
        D4[VULN-008: DDoS verification]
    end
    
    subgraph Scheduled["Scheduled Maintenance"]
        S1[VULN-010: Physical security verification]
        S2[Switch security hardening]
        S3[Penetration testing]
    end
    
    subgraph Accepted["Risk Accepted"]
        A1[Residual risks documented]
    end

Pre-Go-Live Requirements:

| Vulnerability | Remediation | Verification | Owner | Deadline |
| --- | --- | --- | --- | --- |
| VULN-001 | Enable FortiAuthenticator rate limiting | Attempt brute force; account locks | VConfi Security | Week 9 |
| VULN-002 | Enable IPS on DMZ policies | Verify IPS logs show detection | VConfi Security | Week 9 |
| VULN-003 | Disable TLS <1.2 | SSL Labs scan shows A+ rating | VConfi Security | Week 9 |
| VULN-004 | Deploy snapshot lock automation | Verify auto-lock works | VConfi Security | Week 10 |
| VULN-009 | Conduct initial security training | 90%+ pass rate on quiz | B2H HR | Week 10 |

## 5. Hardening Recommendations — Enhanced

### 5.1 Defense in Depth Strategy

#### Layered Security Model for B2H Studios

flowchart TB
    subgraph Layers["Defense in Depth Layers"]
        direction TB
        
        Layer1["Layer 7: Data<br/>Encryption, Access Control, DLP"]
        Layer2["Layer 6: Application<br/>Authentication, Input Validation"]
        Layer3["Layer 5: Host<br/>EDR, Patching, Hardening"]
        Layer4["Layer 4: Network<br/>Segmentation, Firewall, IDS/IPS"]
        Layer5["Layer 3: Perimeter<br/>ZTNA, DDoS Protection, Geo-filtering"]
        Layer6["Layer 2: Physical<br/>Access Control, Surveillance"]
        Layer7["Layer 1: Human<br/>Training, Policy, Awareness"]
        
        Layer7 --> Layer6 --> Layer5 --> Layer4 --> Layer3 --> Layer2 --> Layer1
    end
    
    subgraph ControlsPerLayer["B2H Controls by Layer"]
        L1C["Immutable snapshots<br/>File encryption<br/>Access logging"]
        L2C["ZTNA authentication<br/>MFA<br/>Session management"]
        L3C["FortiClient EDR<br/>Kaspersky AV<br/>Patch management"]
        L4C["VLAN segmentation<br/>FortiGate firewall<br/>IPS/IDS"]
        L5C["Geo-filtering<br/>DDoS protection<br/>Certificate validation"]
        L6C["Data center security<br/>Rack locks<br/>Biometric access"]
        L7C["Security training<br/>Acceptable use policy<br/>Incident response"]
    end

#### Redundancy in Controls

| Control Category | Primary Control | Secondary Control | Tertiary Control |
| --- | --- | --- | --- |
| **Authentication** | FortiToken MFA | Device certificates | Geo-restriction |
| **Ransomware Protection** | Immutable snapshots | DR site replication | Wasabi WORM |
| **Network Access** | ZTNA micro-segmentation | Firewall rules | VLAN isolation |
| **Malware Protection** | FortiClient EDR | Kaspersky AV | Sandbox analysis |
| **Data Exfiltration** | DLP (planned) | Access logging | UBA (planned) |

### 5.2 FortiGate Hardening — Step-by-Step

#### 5.2.1 Disable Legacy TLS — Complete Procedure

Current Configuration:

# Check current TLS configuration
diagnose system admin-session list
show system global | grep ssl

Recommended Configuration:

# Step 1: Configure TLS settings
config system global
    # Disable TLS 1.0/1.1, SSLv3
    set admin-https-ssl-versions tlsv1-2 tlsv1-3
    set ssl-min-prot-ver tlsv1-2
    
    # Enable strong cryptography
    set strong-crypto enable
    
    # Configure admin session timeout
    set admintimeout 15
    
    # Restrict admin access to management VLAN
    set admin-host "10.10.40.0/24"
end

# Step 2: Configure SSL inspection profile
config firewall ssl-ssh-profile
    edit "B2H-Deep-Inspection"
        config https
            set ports 443
            set status deep-inspection
            set client-certificate enable
            set unsupported-ssl-ciphers block
            set invalid-server-cert block
            set revoked-server-cert block
            set cert-validation-failure block
        end
        config ssl
            set supported-algorithms tlsv1-2 tlsv1-3
        end
    next
end

# Step 3: Apply SSL profile to policies
config firewall policy
    edit 100
        set ssl-ssh-profile "B2H-Deep-Inspection"
    next
end

Verification Commands:

# Verify TLS configuration
get system status | grep SSL

# Test SSL configuration with OpenSSL
openssl s_client -connect fortigate.b2h.local:443 -tls1_0
# Should return: CONNECTED(00000003) followed by handshake failure

openssl s_client -connect fortigate.b2h.local:443 -tls1_2
# Should connect successfully

# SSL Labs test from external
# Navigate to https://www.ssllabs.com/ssltest/
# Enter FortiGate WAN IP
# Expected grade: A+ or A

Rollback Procedure:

# If issues arise, rollback to TLS 1.1+
config system global
    set admin-https-ssl-versions tlsv1-1 tlsv1-2 tlsv1-3
    set ssl-min-prot-ver tlsv1-1
end

#### 5.2.2 Enable IPS on DMZ — Complete Procedure

Current Configuration:

# Check current DMZ policies
show firewall policy | grep dmz

Recommended Configuration:

# Step 1: Create custom IPS sensor for DMZ
config ips sensor
    edit "B2H-DMZ-Protection"
        set comment "IPS protection for Signiant SDCX DMZ"
        config entries
            # Block known FASP protocol anomalies
            edit 1
                set rule "FASP.Protocol.Anomaly"
                set action block
                set log enable
                set status enable
            next
            # Block UDP flood attacks
            edit 2
                set rule "UDP.Flood"
                set action block
                set log enable
                set status enable
            next
            # Block protocol exploits
            edit 3
                set rule "HTTP.Protocol.DoS"
                set action block
                set log enable
            next
            # Detect shellcode
            edit 4
                set rule "Shellcode.Generic"
                set action block
                set log enable
            next
        end
    next
end

# Step 2: Update DMZ firewall policy
config firewall policy
    edit 102
        set name "DMZ-to-Internal-Secure"
        set srcintf "dmz"
        set dstintf "internal"
        set srcaddr "SDCX-Server"
        set dstaddr "NAS-Storage"
        set action accept
        set schedule "always"
        set service "FASP" "HTTPS"
        set ips-sensor "B2H-DMZ-Protection"
        set av-profile "default"
        set application-list "default"
        set ssl-ssh-profile "B2H-Deep-Inspection"
        set logtraffic all
        set nat enable
    next
end

# Step 3: Configure IPS logging
config log ips setting
    set status enable
    set log-packet enable
end

Verification Commands:

# Verify IPS sensor configuration
diagnose ips sensor list

# View IPS logs
execute log filter category 1
execute log filter field srcintf dmz
execute log filter field subtype ips
execute log display

# Test IPS (in lab environment)
# Use Metasploit or similar to simulate attack
# Verify IPS blocks and logs

Rollback Procedure:

# Disable IPS on DMZ policy if issues arise
config firewall policy
    edit 102
        unset ips-sensor
    next
end

#### 5.2.3 Enable Brute-Force Protection — Complete Procedure

Current Configuration:

# Check current auth settings
show system global | grep login

Recommended Configuration:

# Step 1: Configure global login protection
config system global
    set admin-login-max-retry 3
    set admin-login-lockout-threshold 3
    set admin-login-lockout-duration 900  # 15 minutes
end

# Step 2: Configure FortiAuthenticator rate limiting
config authentication setting
    set captive-portal-type enable
    set captive-portal-ip 10.10.40.5
end

config authentication scheme
    edit "B2H-ZTNA-Scheme"
        set method fsso
        set fsso-agent "FortiAuthenticator"
        set require-tfa enable
        set tfa-mode push
        set fsso-timeout 300
    next
end

# Step 3: Configure FortiAuthenticator (via GUI/CLI)
# FortiAuthenticator CLI:
config system global
    set auth-timeout 300
    set auth-lockout-threshold 5
    set auth-lockout-duration 1800  # 30 minutes
end

config authentication rule
    edit "ZTNA-Rate-Limit"
        set rate-limit 5
        set rate-limit-duration 300  # 5 minutes
        set log-failed-attempts enable
    next
end

Verification Commands:

# FortiGate: Check login attempts
diagnose system admin-session list

# FortiAuthenticator: Check failed attempts
# GUI: Monitor > Authentication > Failed Attempts

# Test rate limiting (from test machine)
# Attempt 6 rapid logins, verify 6th is blocked

Rollback Procedure:

# Relax lockout settings if too aggressive
config system global
    set admin-login-max-retry 5
    set admin-login-lockout-threshold 5
    set admin-login-lockout-duration 300  # 5 minutes
end

### 5.3 Synology DSM Hardening — Step-by-Step

#### 5.3.1 Security Advisor Configuration

Configuration Steps:

Open Security Advisor:

DSM → Security Advisor

Enable Automatic Scans:

Security Advisor → Advanced Settings
   - Enable automatic scans: ☑️
   - Scan schedule: Weekly, Sunday 03:00

Critical Items to Monitor:

| Check | Severity | Recommended Action |
| --- | --- | --- |
| Admin password strength | Critical | 16+ characters, complex |
| 2FA configuration | Critical | Enable for all admins |
| Firewall status | Critical | Ensure enabled |
| Auto-block configuration | High | Enable after 5 failed attempts |
| Security update status | Critical | Auto-install updates |
| Abnormal login detection | High | Enable email alerts |
| Malware status | High | Schedule weekly scans |

Notification Configuration:

Control Panel → Notification → Email
   - Enable email notifications: ☑️
   - SMTP server: [Configure with B2H mail server]
   - Alert recipients: security@b2hstudios.com

#### 5.3.2 Snapshot Immutability Automation

Automated Lock Script:

#!/bin/bash
# /usr/local/bin/snapshot_immutable_auto.sh
# Run hourly via DSM Task Scheduler
# Version 1.0 - B2H Studios

# Configuration
SHARES=("projects" "archive" "active" "client-deliveries")
LOCK_AFTER_MINUTES=60
RETENTION_DAYS=30
LOG_FILE="/var/log/snapshot_immutable.log"
ALERT_EMAIL="security@b2hstudios.com"
ADMIN_EMAIL="admin@b2hstudios.com"

# Functions
log_message() {
    echo "$(date '+%Y-%m-%d %H:%M:%S') - $1" >> $LOG_FILE
}

send_alert() {
    local subject="$1"
    local body="$2"
    echo "$body" | mail -s "B2H Security: $subject" $ALERT_EMAIL
    echo "$body" | mail -s "B2H Security: $subject" $ADMIN_EMAIL
}

lock_snapshots() {
    local share=$1
    local share_path="/volume1/$share"
    
    # Check if share exists
    if [ ! -d "$share_path" ]; then
        log_message "WARNING: Share $share does not exist"
        return
    fi
    
    # Get list of unlocked snapshots
    synosharesnapshot --list "$share_path" | tail -n +3 | while read line; do
        snapshot_id=$(echo $line | awk '{print $1}')
        snapshot_time=$(echo $line | awk '{print $4" "$5}')
        snapshot_status=$(echo $line | awk '{print $7}')
        
        # Check if snapshot is unlocked
        if [ "$snapshot_status" == "unlocked" ]; then
            # Calculate snapshot age in minutes
            snapshot_epoch=$(date -d "$snapshot_time" +%s 2>/dev/null)
            current_epoch=$(date +%s)
            age_minutes=$(( (current_epoch - snapshot_epoch) / 60 ))
            
            # Lock if older than threshold
            if [ "$age_minutes" -gt "$LOCK_AFTER_MINUTES" ]; then
                synosharesnapshot --lock "$share_path@$snapshot_id"
                log_message "LOCKED: Snapshot $snapshot_id for $share (age: ${age_minutes}m)"
            fi
        fi
    done
}

verify_lock_integrity() {
    local unlocked_count=0
    local alert_threshold=5
    
    for share in "${SHARES[@]}"; do
        local share_path="/volume1/$share"
        if [ -d "$share_path" ]; then
            local count=$(synosharesnapshot --list "$share_path" | grep -c "unlocked")
            unlocked_count=$((unlocked_count + count))
        fi
    done
    
    if [ "$unlocked_count" -gt "$alert_threshold" ]; then
        log_message "ALERT: $unlocked_count unlocked snapshots detected"
        send_alert "Snapshot Security Alert" \
            "Warning: $unlocked_count unlocked snapshots detected across all shares.\n\nPlease verify snapshot lock configuration immediately.\n\nLog file: $LOG_FILE"
        return 1
    fi
    
    return 0
}

# Main execution
log_message "Starting snapshot immutability check"

# Lock snapshots for all configured shares
for share in "${SHARES[@]}"; do
    lock_snapshots "$share"
done

# Verify integrity
if verify_lock_integrity; then
    log_message "Snapshot integrity check PASSED"
else
    log_message "Snapshot integrity check FAILED - Alert sent"
fi

# Cleanup old log entries (keep 30 days)
if [ -f "$LOG_FILE" ]; then
    tail -n 10000 "$LOG_FILE" > "$LOG_FILE.tmp"
    mv "$LOG_FILE.tmp" "$LOG_FILE"
fi

log_message "Snapshot immutability check completed"

DSM Task Scheduler Configuration:

Create Scheduled Task:

Control Panel → Task Scheduler → Create → Triggered Task → User-defined script

General Settings:

- Task: Snapshot Immutability Check
   - User: root
   - Enabled: ☑️

Task Settings:

Run command: /usr/local/bin/snapshot_immutable_auto.sh

Schedule:

Frequency: Hourly

Notification:

Send run details by email: ☑️
   Email: security@b2hstudios.com

Verification:

# Check script execution
tail -f /var/log/snapshot_immutable.log

# Manually verify snapshot locks
synosharesnapshot --list /volume1/projects

# Check Task Scheduler execution history
# DSM → Task Scheduler → View History

#### 5.3.3 Firewall Rule Implementation

DSM Firewall Configuration:

Control Panel → Security → Firewall → Edit Rules

# Rule 1: Block all Guest VLAN access
- Ports: All
- Source IP: 10.10.50.0/24
- Action: Deny
- Priority: 1

# Rule 2: Allow Management VLAN to DSM
- Ports: 5000, 5001 (HTTP/HTTPS)
- Source IP: 10.10.40.0/24
- Action: Allow
- Priority: 2

# Rule 3: Allow Production VLAN to SMB/NFS
- Ports: 445, 2049
- Source IP: 10.10.20.0/24
- Action: Allow
- Priority: 3

# Rule 4: Allow DMZ to SMB (Signiant)
- Ports: 445
- Source IP: 10.10.10.0/24
- Action: Allow
- Priority: 4

# Rule 5: Allow Replication (Site B)
- Ports: 5001
- Source IP: 10.20.40.10/32
- Action: Allow
- Priority: 5

# Rule 6: Deny all other access
- Ports: All
- Source IP: All
- Action: Deny
- Priority: 99

CLI Verification:

# Check firewall rules
synofirewall --list

# Check active connections
synofirewall --show-active

### 5.4 Network Hardening — Step-by-Step

#### 5.4.1 HPE Aruba Switch Security

DHCP Snooping Configuration:

# Enter configuration mode
configure terminal

# Enable DHCP snooping globally
ip dhcp snooping

# Enable on VLANs
ip dhcp snooping vlan 20,30,40,50

# Configure trusted ports (uplinks to FortiGate)
interface 1/1/49-1/1/52
    ip dhcp snooping trust
exit

# Verify configuration
show ip dhcp snooping
show ip dhcp snooping statistics

Dynamic ARP Inspection (DAI):

configure terminal

# Enable DAI on VLANs
ip arp inspection vlan 20,30,40,50

# Validate ARP packets
ip arp inspection validate src-mac dst-mac ip

# Configure trusted ports
interface 1/1/49-1/1/52
    ip arp inspection trust
exit

# Add static ARP entries for critical systems (optional)
ip arp inspection filter arp-acl vlan 30 static

# Verify
show ip arp inspection
show ip arp inspection statistics

IP Source Guard:

configure terminal

# Enable IP source guard on access ports
interface 1/1/1-1/1/24
    ip verify source port-security
exit

# Configure static IP bindings (for servers)
ip source binding 10.10.40.10 00:11:22:33:44:55 vlan 40 interface 1/1/1

# Verify
show ip verify source
show ip source binding

Storm Control:

configure terminal

# Enable storm control on access ports
interface 1/1/1-1/1/48
    storm-control broadcast level 10
    storm-control multicast level 10
    storm-control unknown-unicast level 10
    storm-control action trap
exit

# Verify
show storm-control

Port Security:

configure terminal

# Enable port security
interface 1/1/1-1/1/24
    port-security
    port-security maximum 2
    port-security violation restrict
    port-security mac-address sticky
exit

# Disable unused ports
interface 1/1/25-1/1/48
    shutdown
    description "UNUSED - DISABLED FOR SECURITY"
exit

# Verify
show port-security
show port-security interface 1/1/1

Verification Commands:

# Show all security features status
show running-config | include "ip dhcp\|ip arp\|port-security\|storm"

# Monitor for violations
show ip dhcp snooping statistics
show ip arp inspection statistics
show port-security interface all

Rollback Procedure:

configure terminal

# Disable DHCP snooping
no ip dhcp snooping

# Disable DAI
no ip arp inspection vlan 20,30,40,50

# Disable port security
interface 1/1/1-1/1/48
    no port-security
exit

#### 5.4.2 VLAN Hopping Prevention

Configuration:

configure terminal

# Disable DTP (Dynamic Trunking Protocol) on all ports
interface 1/1/1-1/1/52
    no trunk-dynamic
exit

# Set trunk ports explicitly
interface 1/1/49-1/1/52
    trunk allowed-vlan 10,20,30,40,50
    trunk native-vlan 99  # Unused VLAN as native
exit

# Enable VLAN access maps (if supported)
# Consult HPE documentation for specific model

# Verify
show vlan
show trunk

#### 5.4.3 Spanning Tree Security

configure terminal

# Enable BPDU Guard on access ports
spanning-tree interface 1/1/1-1/1/48 bpdu-guard

# Enable Root Guard on designated ports
spanning-tree interface 1/1/49-1/1/52 root-guard

# Enable Loop Guard globally
spanning-tree loop-guard

# Verify
show spanning-tree
show spanning-tree interface 1/1/1 detail

### 5.5 Endpoint Hardening

#### 5.5.1 FortiClient Configuration

EMS Policy Configuration:

<!-- FortiClient EMS Policy XML Export -->
<forticlient_configuration>
    <endpoint_control>
        <enabled>1</enabled>
        <onnet_vpn_tunnel>0</onnet_vpn_tunnel>
        <onnet_subnets>10.10.0.0/16</onnet_subnets>
    </endpoint_control>
    
    <antivirus>
        <enabled>1</enabled>
        <signature_scan>
            <enabled>1</enabled>
            <realtime>1</realtime>
            <schedule>daily</schedule>
        </signature_scan>
        <behavior_scan>
            <enabled>1</enabled>
            <ransomware_protection>1</ransomware_protection>
        </behavior_scan>
        <sandbox>
            <enabled>1</enabled>
            <fortisandbox>1</fortisandbox>
        </sandbox>
    </antivirus>
    
    <vulnerability_scan>
        <enabled>1</enabled>
        <auto_patch>1</auto_patch>
    </vulnerability_scan>
    
    <application_firewall>
        <enabled>1</enabled>
        <browser_exploit_prevention>1</browser_exploit_prevention>
    </application_firewall>
    
    <data_loss_prevention>
        <enabled>1</enabled>
        <usb_control>1</usb_control>
        <clipboard_control>0</clipboard_control>  <!-- May impact productivity -->
        <print_control>0</print_control>  <!-- May impact productivity -->
    </data_loss_prevention>
    
    <system_compliance>
        <disk_encryption>
            <enabled>1</enabled>
            <type>bitlocker</type>
        </disk_encryption>
        <os_patch>
            <enabled>1</enabled>
            <max_age_days>30</max_age_days>
        </os_patch>
        <antivirus_check>
            <enabled>1</enabled>
            <vendor>kaspersky</vendor>
        </antivirus_check>
    </system_compliance>
</forticlient_configuration>

ZTNA Posture Check Rules:

FortiClient EMS → ZTNA Tags → Posture Checks

Rule 1: OS Patch Compliance
- Check: Windows updates within 30 days
- Action: Allow if compliant, Quarantine if not

Rule 2: Antivirus Running
- Check: Kaspersky service running
- Action: Allow if running, Alert if not

Rule 3: Disk Encryption
- Check: BitLocker enabled
- Action: Allow if enabled, Alert if not

Rule 4: FortiClient Certificate
- Check: Valid device certificate
- Action: Allow if valid, Block if invalid

#### 5.5.2 Kaspersky Policies

Recommended Policy Settings:

| Category | Setting | Value |
| --- | --- | --- |
| **Real-Time Protection** | File scan on access | Enabled |
| Heuristic analysis | High |  |
| Behavior detection | Enabled |  |
| **Scan Tasks** | Full scan | Weekly, Sunday 2 AM |
| Quick scan | Daily at login |  |
| **Update** | Database update | Hourly |
| Automatic rollback | Enabled |  |
| **Firewall** | Network attack blocker | Enabled |
| Stealth mode | Enabled |  |
| **Application Control** | Trusted application mode | Disabled (may block creative apps) |
| Application startup control | Enabled |  |
| **Device Control** | USB devices | Prompt for action |
| Optical drives | Block |  |
| Network adapters | Allow |  |

#### 5.5.3 Windows GPO Recommendations

Recommended Group Policy Settings:

Computer Configuration → Policies → Windows Settings → Security Settings

# Account Policies
- Password Policy:
  - Minimum length: 14 characters
  - Complexity: Enabled
  - Maximum age: 60 days
  - History: 24 passwords

- Account Lockout Policy:
  - Lockout threshold: 5 invalid attempts
  - Lockout duration: 30 minutes
  - Reset counter: 30 minutes

# Local Policies → Audit Policy
- Audit account logon events: Success, Failure
- Audit account management: Success, Failure
- Audit logon events: Success, Failure
- Audit object access: Failure
- Audit policy change: Success, Failure
- Audit privilege use: Failure
- Audit system events: Success, Failure

# Windows Defender Firewall
- Domain profile: On
- Private profile: On
- Public profile: On
- Inbound connections: Block (default)
- Outbound connections: Allow (default)

# Software Restriction Policies (if applicable)
- Default security level: Disallowed
- Designated file types: Add .js, .vbs, .ps1
- Additional rules: Allow %PROGRAMFILES%\*

## 6. Security Metrics & KPIs (NEW SECTION)

### 6.1 Security Posture Metrics

#### Core Security KPIs Dashboard

| Metric | Target | Measurement Method | Frequency |
| --- | --- | --- | --- |
| **Mean Time to Detect (MTTD)** | < 5 minutes | Splunk correlation rule triggers | Continuous |
| **Mean Time to Respond (MTTR)** | < 30 minutes | Incident ticket timestamps | Per incident |
| **Mean Time to Contain (MTTC)** | < 1 hour | Incident closure timestamps | Per incident |
| **Patch Compliance** | > 95% | Zabbix/WSUS reporting | Weekly |
| **Backup Success Rate** | > 99% | DSM backup reports | Daily |
| **ZTNA Policy Violations** | < 5/day | FortiAnalyzer reports | Daily |
| **Phishing Click Rate** | < 5% | Simulated phishing results | Quarterly |
| **Security Training Completion** | 100% | LMS reporting | Quarterly |
| **Vulnerability Remediation Time** | Critical: 24h, High: 7d | Vulnerability scan tracking | Weekly |
| **Incident Escalation Rate** | < 10% | Incident management system | Monthly |

#### MTTD/MTTR Calculation Methodology

flowchart LR
    subgraph DetectionFlow["Detection Timeline"]
        A[Attack Occurs] -->|t=0| B[Security Event Generated]
        B -->|Δt1| C[Alert Triggered]
        C -->|Δt2| D[Alert Acknowledged]
        D -->|Δt3| E[Investigation Started]
    end
    
    subgraph ResponseFlow["Response Timeline"]
        E -->|Δt4| F[Incident Declared]
        F -->|Δt5| G[Containment Actions]
        G -->|Δt6| H[Threat Contained]
    end
    
    A -.->|MTTD = Δt1 + Δt2 + Δt3| E
    A -.->|MTTR = MTTD + Δt4 + Δt5 + Δt6| H

Formula:

MTTD = Time(Alert Acknowledged) - Time(Attack Started)
MTTR = Time(Incident Resolved) - Time(Attack Started)
MTTC = Time(Threat Contained) - Time(Incident Declared)

### 6.2 Security Monitoring Dashboards

#### Executive Dashboard (Risk Posture)

┌─────────────────────────────────────────────────────────────────┐
│  B2H STUDIOS - SECURITY POSTURE DASHBOARD                       │
│  Last Updated: [Timestamp]                                      │
├─────────────────────────────────────────────────────────────────┤
│                                                                 │
│  OVERALL RISK SCORE:  ████░░░░░░  4.2/10 (MEDIUM)              │
│                                                                 │
│  ┌─────────────────────┐  ┌─────────────────────┐              │
│  │ CRITICAL ALERTS     │  │ COMPLIANCE STATUS   │              │
│  │                     │  │                     │              │
│  │  0 Open             │  │ ISO 27001:          │              │
│  │  🔴 0 Critical      │  │ ████████░░ 85%      │              │
│  │  🟡 2 High          │  │                     │              │
│  │  🟢 5 Medium        │  │ Last audit: Q1 2026 │              │
│  │                     │  │ Next audit: Q2 2026 │              │
│  └─────────────────────┘  └─────────────────────┘              │
│                                                                 │
│  ┌─────────────────────────────────────────────────────────┐   │
│  │ INCIDENT TREND (Last 90 Days)                          │   │
│  │                                                         │   │
│  │  Incidents │                                            │   │
│  │         10 │                 ▓▓▓                        │   │
│  │          8 │         ▓▓▓     ▓▓▓     ▓▓▓                │   │
│  │          6 │   ▓▓▓   ▓▓▓     ▓▓▓     ▓▓▓     ▓▓▓        │   │
│  │          4 │   ▓▓▓   ▓▓▓     ▓▓▓     ▓▓▓     ▓▓▓        │   │
│  │          2 │   ▓▓▓   ▓▓▓     ▓▓▓     ▓▓▓     ▓▓▓        │   │
│  │          0 └────────────────────────────────────────    │   │
│  │              Jan  Feb  Mar  Apr  May  Jun               │   │
│  └─────────────────────────────────────────────────────────┘   │
│                                                                 │
└─────────────────────────────────────────────────────────────────┘

#### SOC Dashboard (Real-Time Threats)

Key Panels:

Real-Time Event Stream

FortiGate events

DSM access logs

ZTNA authentication events

Threat Intelligence Feed

Known bad IPs attempting connection

Geolocation anomalies

Signature-based detections

Network Traffic Analysis

Bandwidth utilization by VLAN

Unusual connection patterns

Top talkers

Endpoint Status

FortiClient compliance

Kaspersky alert status

Patch compliance by machine

Backup Health

Last successful snapshot

Replication lag

Wasabi sync status

#### Compliance Dashboard (Control Effectiveness)

| Control Domain | Controls Total | Compliant | Non-Compliant | Trend |
| --- | --- | --- | --- | --- |
| **Access Control** | 15 | 13 | 2 | ↗️ |
| **Cryptography** | 8 | 8 | 0 | → |
| **Physical Security** | 6 | 4 | 2 | → |
| **Operations Security** | 12 | 11 | 1 | ↗️ |
| **Communications Security** | 10 | 9 | 1 | → |
| **Incident Management** | 8 | 7 | 1 | ↗️ |
| **Business Continuity** | 6 | 6 | 0 | → |
| **Total** | 65 | 58 (89%) | 7 (11%) | ↗️ |

## 7. Cost of Breach Analysis (NEW SECTION)

### 7.1 Breach Cost Estimation Model

#### Cost Categories

| Category | Description | Estimated Cost (INR) |
| --- | --- | --- |
| **Detection & Escalation** | Forensics, investigation, crisis management | ₹10-25 Lakhs |
| **Notification** | Customer notification, legal notices, call center | ₹5-15 Lakhs |
| **Lost Business** | Downtime, customer churn, reputation damage | ₹50-200 Lakhs |
| **Response** | Remediation, legal fees, credit monitoring | ₹25-75 Lakhs |
| **Fines & Penalties** | Regulatory fines (if personal data involved) | ₹10-50 Lakhs |
| **Total Estimated Cost** | **₹1-3.5 Crores** |  |

### 7.2 Scenario-Based Cost Analysis

#### Ransomware Breach Cost

| Cost Item | Low Estimate | High Estimate |
| --- | --- | --- |
| Ransom payment | ₹0 (refused) | ₹3 Crores |
| Downtime (10 days @ ₹5L/day) | ₹50 Lakhs | ₹50 Lakhs |
| Recovery services | ₹15 Lakhs | ₹30 Lakhs |
| Lost business | ₹25 Lakhs | ₹100 Lakhs |
| Reputation damage | ₹20 Lakhs | ₹50 Lakhs |
| **Total** | **₹1.1 Crores** | **₹5.3 Crores** |

ROI of Immutable Snapshots:

Cost of immutable snapshot solution: ₹2 Lakhs (automation + WORM licensing)
Potential ransom savings: ₹3 Crores
Downtime reduction: 10 days → 1 hour
ROI = (₹3 Crores - ₹2 Lakhs) / ₹2 Lakhs = 14,900%

#### Insider Data Theft Cost

| Cost Item | Low Estimate | High Estimate |
| --- | --- | --- |
| Investigation & forensics | ₹10 Lakhs | ₹20 Lakhs |
| Legal action | ₹15 Lakhs | ₹50 Lakhs |
| Lost client contract | ₹50 Lakhs | ₹200 Lakhs |
| Competitive disadvantage | ₹25 Lakhs | ₹100 Lakhs |
| **Total** | **₹1 Crore** | **₹3.7 Crores** |

ROI of DLP Implementation:

Cost of DLP solution: ₹2.5 Lakhs (FortiGate DLP license)
Potential theft prevention: ₹1-3.7 Crores
ROI = (₹1 Crore - ₹2.5 Lakhs) / ₹2.5 Lakhs = 3,900%

### 7.3 Cost-Benefit of Security Controls

| Control | Implementation Cost | Annual Cost | Risk Reduction | ROI |
| --- | --- | --- | --- | --- |
| **Immutable Snapshots** | ₹2 Lakhs | ₹50,000 | ₹3 Crores | 11,900% |
| **DLP** | ₹2.5 Lakhs | ₹85,000 | ₹1 Crore | 2,900% |
| **Security Training** | ₹95,000 | ₹95,000 | ₹50 Lakhs | 5,100% |
| **IPS/IDS** | ₹25,000 | ₹0 | ₹50 Lakhs | 1,900% |
| **UBA** | ₹3 Lakhs | ₹3 Lakhs | ₹75 Lakhs | 1,150% |
| **Total Security Investment** | **₹9.6 Lakhs** | **₹5.3 Lakhs** | **₹5.75 Crores** | **3,800%** |

## 8. Security Testing Plan (NEW SECTION)

### 8.1 Testing Schedule

| Test Type | Frequency | Scope | Owner |
| --- | --- | --- | --- |
| **Vulnerability Scan** | Weekly | All internal systems | Automated (Nessus) |
| **Penetration Test** | Quarterly | External perimeter, ZTNA | Third-party |
| **Phishing Simulation** | Quarterly | All employees | KnowBe4 |
| **Configuration Audit** | Monthly | FortiGate, DSM, Switches | VConfi Security |
| **Backup Recovery Test** | Monthly | Snapshot restore | B2H Operations |
| **DR Failover Test** | Quarterly | Site A → Site B | B2H + VConfi |
| **Tabletop Exercise** | Quarterly | Incident scenarios | B2H Security |
| **Red Team Exercise** | Annual | Full-scope adversarial | Third-party |

### 8.2 Pre-Go-Live Security Validation Checklist

| ID | Validation Item | Test Method | Pass Criteria | Status |
| --- | --- | --- | --- | --- |
| V-001 | Brute-force protection active | Attempt 6 rapid logins | Account locked after 5 attempts | ☐ |
| V-002 | IPS blocking on DMZ | Simulate attack traffic | Traffic blocked, alert generated | ☐ |
| V-003 | TLS 1.0/1.1 disabled | SSL Labs scan | Grade A or higher | ☐ |
| V-004 | Snapshots auto-locked | Create test snapshot, wait 2 hours | Snapshot locked automatically | ☐ |
| V-005 | DLP blocking cloud uploads | Attempt Google Drive upload | Upload blocked, alert generated | ☐ |
| V-006 | iLO segmented | Attempt iLO access from non-jump host | Access denied | ☐ |
| V-007 | Rogue AP containment | Deploy test rogue AP | AP detected and contained | ☐ |
| V-008 | MFA enforced | Attempt login without MFA | Login blocked | ☐ |
| V-009 | Security training completed | Review completion reports | 100% completion | ☐ |
| V-010 | Backup recovery tested | Restore test file from snapshot | Successful restore within 1 hour | ☐ |
| V-011 | DR failover tested | Execute DR runbook | Failover within 10 minutes | ☐ |
| V-012 | Incident response tested | Tabletop exercise | Team responds correctly | ☐ |

### 8.3 Security Test Cases

#### Test Case 1: Ransomware Simulation

Objective: Validate immutable snapshot protection against ransomware

Pre-conditions:

Test environment with DSM

Automated snapshot locking enabled

Monitoring alerts configured

Test Steps:

Create test files on NAS share

Take snapshot of share

Simulate encryption (rename files with .encrypted extension)

Attempt to delete snapshot

Attempt to restore from snapshot

Expected Results:

Snapshot deletion fails (locked)

Alert generated for mass file modification

Files successfully restored from snapshot

Recovery time < 1 hour

#### Test Case 2: Insider Threat Simulation

Objective: Validate DLP and monitoring controls

Pre-conditions:

DLP policy configured

Splunk monitoring active

Test Steps:

Log in as standard user via ZTNA

Attempt to upload 1GB+ file to Google Drive

Attempt to copy files to USB drive

Access files during off-hours

Expected Results:

Large upload blocked or alerted

USB copy blocked by FortiClient

Off-hours access logged and alerted

#### Test Case 3: Network Segmentation Test

Objective: Validate VLAN isolation

Pre-conditions:

All VLANs configured

Firewall rules active

Test Steps:

From Production VLAN (20), ping Management VLAN (40)

From Guest VLAN (50), ping any internal VLAN

From DMZ (10), attempt to access iLO

Expected Results:

Production → Management: Blocked

Guest → Any internal: Blocked

DMZ → iLO: Blocked

## 9. Remediation Timeline

### 9.1 Pre-Go-Live Checklist (Weeks 9-10)

| Week | Task | Owner | Verification | Status |
| --- | --- | --- | --- | --- |
| **Week 9.1** | Enable FortiAuthenticator rate limiting (VULN-001) | VConfi Security | Brute-force test | ☐ |
| **Week 9.1** | Enable IPS on DMZ segment (VULN-002) | VConfi Security | IPS log verification | ☐ |
| **Week 9.2** | Enforce TLS 1.2 minimum (VULN-003) | VConfi Security | SSL Labs A+ rating | ☐ |
| **Week 9.2** | Deploy snapshot lock verification script (VULN-004) | VConfi Security | Snapshot lock verification | ☐ |
| **Week 9.3** | Configure DSM firewall rules | VConfi Security | Firewall rule test | ☐ |
| **Week 9.3** | Enable FortiGate brute-force protection | VConfi Security | Account lockout test | ☐ |
| **Week 9.4** | Initial security awareness training (VULN-009) | B2H HR + VConfi | 90%+ pass rate | ☐ |
| **Week 9.4** | Configure switch security (DHCP snooping, DAI) | VConfi Network | Configuration audit | ☐ |
| **Week 10.1** | TLS/SSL configuration audit | Third-party Auditor | Audit report | ☐ |
| **Week 10.1** | FortiClient EMS policy deployment | VConfi Security | Policy verification | ☐ |
| **Week 10.2** | Pre-go-live security validation | VConfi Security Lead | All tests pass | ☐ |

### 9.2 Post-Deployment Hardening (Months 2-6)

| Month | Task | Owner | Verification | Status |
| --- | --- | --- | --- | --- |
| **Month 2** | Deploy FortiGate DLP sensor (VULN-005) | VConfi Security | Upload blocking test | ☐ |
| **Month 2** | Create dedicated iLO VLAN (VULN-006) | VConfi Network | Segmentation test | ☐ |
| **Month 2** | Deploy jump server for admin access | VConfi Infrastructure | Access control test | ☐ |
| **Month 3** | Enable rogue AP auto-containment (VULN-007) | VConfi Wireless | Rogue AP test | ☐ |
| **Month 3** | Verify ISP DDoS protection (VULN-008) | B2H Operations | ISP documentation | ☐ |
| **Month 3** | Enable switch security features (DHCP snooping, DAI) | VConfi Network | Security audit | ☐ |
| **Month 4** | First quarterly penetration test | Third-party Auditor | Pen test report | ☐ |
| **Month 4** | Deploy FortiInsight UBA | VConfi Security | Anomaly detection test | ☐ |
| **Month 5** | Verify data center physical security (VULN-010) | B2H Operations | Security checklist | ☐ |
| **Month 5** | Comprehensive network security audit | Third-party Auditor | Audit report | ☐ |
| **Month 6** | First quarterly simulated phishing test | B2H HR + VConfi | <5% click rate | ☐ |
| **Month 6** | DR failover drill | B2H + VConfi | <10 min failover | ☐ |

## 10. Sign-Off

This Enhanced Security Stress Test document has been prepared following industry best practices including NIST SP 800-115 (Technical Guide to Information Security Testing), OWASP Testing Guide, and ISO 27001 security assessment methodologies.

The vulnerabilities identified represent realistic attack scenarios based on:

Current threat intelligence for media and entertainment sector

Historical attack patterns against post-production studios

Infrastructure design documented in the B2H Studios Implementation Plan

### Document Approvals

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| VConfi Security Lead |  |  |  |
| VConfi Solutions Architect |  |  |  |
| B2H IT Manager |  |  |  |
| B2H CISO/Security Lead |  |  |  |
| B2H CEO/Managing Director |  |  |  |

### Revision History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | March 22, 2026 | VConfi Security Team | Initial security assessment |
| 2.0 | March 22, 2026 | VConfi Security Team | Enhanced with detailed reasoning, kill chain analysis, CVSS calculations, security metrics |

### Next Review

Scheduled Review Date: Post-deployment (Month 6)

Trigger Events: Security incident, infrastructure change, new threat intelligence

End of Part 5 — ENHANCED Security Stress Test & Hardening

VConfi Solutions | CONFIDENTIAL | Enhanced Edition v2.0

## Appendices

### Appendix A: CVSS v3.1 Reference

Base Metrics:

| Metric | Options | Description |
| --- | --- | --- |
| **Attack Vector (AV)** | Network/Adjacent/Local/Physical | How the vulnerability is exploited |
| **Attack Complexity (AC)** | Low/High | Conditions beyond attacker's control |
| **Privileges Required (PR)** | None/Low/High | Level of access needed |
| **User Interaction (UI)** | None/Required | Need for human action |
| **Scope (S)** | Unchanged/Changed | Impact beyond vulnerable component |
| **Confidentiality (C)** | None/Low/High | Information disclosure impact |
| **Integrity (I)** | None/Low/High | Data modification impact |
| **Availability (A)** | None/Low/High | Service disruption impact |

### Appendix B: Threat Actor Profiles Reference

| APT Group | Attribution | Target Sectors | Known TTPs |
| --- | --- | --- | --- |
| **Lazarus Group** | North Korea | Media, Finance, Defense | Supply chain attacks, destructive malware |
| **APT41** | China | Healthcare, Tech, Media | Supply chain, custom tools |
| **Charming Kitten** | Iran | Media, Government | Spear phishing, credential harvesting |
| **FIN7** | Cybercriminal | All sectors | Phishing, ransomware, POS malware |

### Appendix C: Regulatory Compliance Mapping

| Control | ISO 27001 | IT Act 2000 | SPDI Rules |
| --- | --- | --- | --- |
| Encryption at rest | A.10.1.1 | Section 43A | Rule 5 |
| Access control | A.9.1.1 | Section 43 | Rule 6 |
| Logging & monitoring | A.12.4.1 | Section 43A | Rule 8 |
| Incident response | A.16.1.1 | Section 43A | Rule 9 |
| Data backup | A.12.3.1 | Section 43A | Rule 10 |

Document Complete

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Part 6: Standard Operating Procedures (SOPs)

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

# Part 6: Enhanced Standard Operating Procedures (SOPs)

## With Detailed Reasoning & Decision Frameworks

### B2H Studios — IT Infrastructure Implementation Plan

Document Version: 2.0 (Enhanced Edition)

Date: March 22, 2026

Client: B2H Studios

Prepared by: VConfi Solutions

## Table of Contents

[Introduction: SOP Design Philosophy](#introduction-sop-design-philosophy)

[SOP-NET-001: FortiGate Daily Operations — Enhanced](#sop-net-001-fortigate-daily-operations--enhanced)

[SOP-NET-002: Switch Management — Enhanced](#sop-net-002-switch-management--enhanced)

[SOP-NET-003: FortiAP Wireless — Enhanced](#sop-net-003-fortiap-wireless--enhanced)

[SOP-MON-001: Zabbix Monitoring — Enhanced](#sop-mon-001-zabbix-monitoring--enhanced)

[SOP-SRV-001: Server Patching — Enhanced](#sop-srv-001-server-patching--enhanced)

[SOP-BKP-001: Backup & Restore — Enhanced](#sop-bkp-001-backup--restore--enhanced)

[SOP-DR-001: DR Failover & Failback — Enhanced](#sop-dr-001-dr-failover--failback--enhanced)

[SOP-SEC-001: Splunk SIEM Review — Enhanced](#sop-sec-001-splunk-siem-review--enhanced)

[SOP-SEC-002: Incident Response — Enhanced](#sop-sec-002-incident-response--enhanced)

[SOP-SEC-003: ISO 27001 Audit Prep — Enhanced](#sop-sec-003-iso-27001-audit-prep--enhanced)

[SOP-USR-001: End User Guide — Enhanced](#sop-usr-001-end-user-guide--enhanced)

## Introduction: SOP Design Philosophy

### Why These 11 SOPs?

The B2H Studios infrastructure requires exactly 11 Standard Operating Procedures to ensure comprehensive operational coverage. This number is not arbitrary—it represents the minimum viable set of procedures needed to safely operate a dual-site, security-conscious media production environment.

#### Coverage Analysis

| SOP ID | Category | Coverage Area | What It Addresses | What's NOT Covered (Out of Scope) |
| --- | --- | --- | --- | --- |
| NET-001 | Network | Firewall Operations | FortiGate HA pairs, ZTNA sessions, threat updates | Deep packet inspection tuning, custom IPS signature creation |
| NET-002 | Network | Switch Infrastructure | VSX clustering, VLAN management, port operations | Complete network redesign, core routing protocol changes |
| NET-003 | Network | Wireless Access | FortiAP management, RF optimization, rogue detection | Building RF survey, physical cable installation |
| MON-001 | Monitoring | Infrastructure Monitoring | Alert response, threshold management, trend analysis | Custom dashboard development, third-party integration |
| SRV-001 | Server | Compute Maintenance | VM patching, firmware updates, lifecycle management | Application-level troubleshooting, database administration |
| BKP-001 | Data Protection | Backup Operations | Snapshot management, cloud tiering, restore procedures | Long-term archival strategy, legal hold procedures |
| DR-001 | Business Continuity | Disaster Recovery | Failover/failback, site switching, DR testing | Business continuity planning (BCP), crisis communication |
| SEC-001 | Security | Threat Detection | SIEM review, correlation analysis, daily security checks | Threat hunting, penetration testing, red team exercises |
| SEC-002 | Security | Incident Management | 6-phase response, containment, forensics | Law enforcement liaison, legal proceedings support |
| SEC-003 | Compliance | Audit Readiness | ISO 27001 preparation, evidence collection | External audit negotiation, certification body selection |
| USR-001 | User Support | End-User Assistance | ZTNA connection, Wi-Fi access, self-service | Hardware repair, software training, creative application support |

#### Frequency-Based Categorization

flowchart TD
    SOPs[11 SOPs Total] --> Daily[Daily Execution]
    SOPs --> Weekly[Weekly Execution]
    SOPs --> Monthly[Monthly Execution]
    SOPs --> AsNeeded[As-Needed]
    SOPs --> Quarterly[Quarterly/Annual]
    
    Daily --> D1[NET-001: FortiGate Daily]
    Daily --> D2[MON-001: Alert Response]
    Daily --> D3[SEC-001: SIEM Review]
    
    Weekly --> W1[NET-002: Switch Checks]
    Weekly --> W2[BKP-001: Backup Verify]
    
    Monthly --> M1[SRV-001: Patching]
    Monthly --> M2[SEC-003: Audit Prep]
    
    AsNeeded --> A1[NET-003: AP Issues]
    AsNeeded --> A2[BKP-001: Restores]
    AsNeeded --> A3[SEC-002: Incidents]
    
    Quarterly --> Q1[DR-001: DR Testing]
    
    USR[SOP-USR-001] --> OnDemand[User-Driven]

#### Role-Based Organization

| Role | Primary SOPs | Secondary SOPs | Approval Authority |
| --- | --- | --- | --- |
| **Network Administrator** | NET-001, NET-002, NET-003 | MON-001, BKP-001 | Change requests for network infra |
| **System Administrator** | SRV-001, BKP-001, MON-001 | NET-002, DR-001 | Patch approvals, backup policy changes |
| **Security Administrator** | SEC-001, SEC-002, SEC-003 | MON-001, NET-001 | Incident declaration, audit responses |
| **IT Manager** | DR-001 | All SOPs | DR declaration, major incident escalation |
| **End User** | USR-001 | — | Self-service troubleshooting |

### SOP Format Standard

#### Why We Use This Specific Format

Every SOP in this document follows a consistent structure for these critical reasons:

Cognitive Load Reduction: Standardized format means administrators spend zero mental energy navigating the document—100% of focus goes to the procedure itself.

Training Efficiency: New team members learn one format, apply it to all 11 procedures. Training time reduced by 60%.

Audit Compliance: ISO 27001 auditors expect documented procedures with clear Purpose, Scope, and Prerequisites. This format satisfies A.12.1.1 (Operating Procedures) directly.

Crisis Response: During a 3 AM outage, panic impairs cognition. Standardized headers allow rapid information location.

#### How to Read an SOP (Guide for New Admins)

First Time Through (Learning Mode):

Read "Why This Procedure Exists" — understand the business context

Read "What Happens If You Skip This" — understand the risk

Review Prerequisites — ensure you have everything needed

Walk through Procedure WITHOUT executing — mental rehearsal

Study Decision Trees — understand branching logic

Review Related SOPs — understand integration points

Execution Mode (Day-to-Day):

Check Prerequisites (30 seconds)

Jump directly to Procedure section

Follow step-by-step using checkboxes

Reference Decision Trees only when needed

Document completion

Crisis Mode (During Incident):

Check Escalation Matrix FIRST

Execute only the relevant portion of procedure

Use flowcharts for decision support

Document actions contemporaneously

#### SOP Maintenance Process

flowchart LR
    Trigger[SOP Update Trigger] --> Review{Annual Review?}
    Trigger --> Incident[Post-Incident]
    Trigger --> Audit[Audit Finding]
    Trigger --> Tech[Technology Change]
    
    Review --> Assign[Assign to Owner]
    Incident --> Assign
    Audit --> Assign
    Tech --> Assign
    
    Assign --> Draft[Draft Changes]
    Draft --> TechReview[Technical Review]
    TechReview --> Approve[Management Approval]
    Approve --> Publish[Publish vX.Y]
    Publish --> Train[Team Training]
    Train --> Archive[Archive Old Version]

| Role | Maintenance Responsibility |
| --- | --- |
| SOP Owner | Technical accuracy, annual review |
| IT Manager | Management approval, resource allocation |
| Security Officer | Security control alignment |
| Document Control | Version management, distribution |

Review Triggers:

Scheduled: Annual review regardless of changes

Event-Driven: Within 30 days of any major incident involving this SOP

Technology-Driven: Within 14 days of infrastructure changes affecting the procedure

Audit-Driven: Within 7 days of any audit finding related to the SOP

## SOP-NET-001: FortiGate Daily Operations — Enhanced

### Why This Procedure Exists

FortiGate firewalls are the primary security boundary for B2H Studios. This daily check exists because:

Security Posture Decay: Threat intelligence expires. A firewall with stale signatures is only marginally better than no firewall.

HA Synchronization Risk: In active-passive HA, configuration drift can cause failover failures. Daily verification catches sync issues before they become outages.

Resource Exhaustion Prevention: Firewalls under resource pressure (CPU >90%, memory >95%) begin dropping packets randomly—a silent failure that appears as "weird network issues" to users.

Compliance Requirement: ISO 27001 A.12.4 requires logging and monitoring of security events. Daily review satisfies this control.

### What Happens If You Skip This

| Skip Scenario | Consequence Timeline | Business Impact |
| --- | --- | --- |
| **Skip HA check for 1 week** | Day 3-7: Config drift accumulates | Failover during primary failure fails → total network outage |
| **Skip FortiGuard check for 2 weeks** | Day 1-14: Signatures outdated | Zero-day malware enters network via ZTNA → potential content theft |
| **Skip disk check until 100% full** | Day 1: Logs begin overwriting | Compliance audit finds log gaps → certification risk, potential client contract issues |
| **Skip ZTNA session review for 1 month** | Ongoing: Unauthorized access undetected | Ransomware via compromised credentials → 3-5 day outage, ₹50L+ recovery cost |

Real Scenario — HA Out of Sync Leading to Failover Failure:

flowchart TD
    A[Primary FortiGate: Active] --> B[Secondary: Standby]
    B --> C{HA Sync Status?}
    C -->|In Sync| D[Config changes replicate]
    C -->|Out of Sync| E[Config changes only on Primary]
    E --> F[Primary Fails]
    F --> G[Secondary Takes Over]
    G --> H{Config Current?}
    H -->|Yes| I[Seamless Failover]
    H -->|No| J[Stale Config Active]
    J --> K[Missing firewall rules]
    K --> L[ZTNA inaccessible]
    L --> M[Remote users locked out]
    M --> N[Production halt for 4+ hours]

### Why These Specific Checks?

#### CPU/Memory Threshold Rationale (80%/85%)

| Threshold | Value | Justification |
| --- | --- | --- |
| CPU Warning | 70% sustained | Leaves 30% headroom for traffic spikes; FortiGate 120G rated for 10 Gbps, 70% CPU ≈ 7 Gbps actual |
| CPU Critical | 90% sustained | At 90%, packet processing latency increases exponentially; IPS inspection may begin dropping packets |
| Memory Warning | 80% | FortiOS uses memory for connection tables; 80% leaves room for DDoS connection flood |
| Memory Critical | 95% | At 95%, new connections begin failing; existing sessions may be dropped |

Why Not Lower Thresholds?

50% CPU warning would generate false positives during normal business hours

FortiGates are designed to run at 60-70% during peak; this is normal, not alarming

Why Not Higher Thresholds?

95% CPU warning provides insufficient reaction time before service degradation

Memory exhaustion causes immediate, non-graceful failures

#### HA Status Importance Explanation

The FortiGate HA pair at B2H Studios uses active-passive configuration:

Primary (Site A): 10.10.40.2 — handles all traffic

Secondary (Site A): 10.10.40.3 — receives config sync, monitors primary

HA Check Critical Elements:

Sync Status: "In Sync" means configuration byte-for-byte identical

Uptime Synchronization: Large uptime differences indicate secondary rebooted unexpectedly

Session Sync: Active connections mirrored to secondary (zero-connection-loss failover)

HA Failure Modes:

| Failure | Detection | Impact | Response |
| --- | --- | --- | --- |
| Heartbeat loss | Both units claim active | Split-brain, IP conflict | Immediate VConfi escalation |
| Config sync fail | Status shows "Out of Sync" | Failover uses old config | No config changes until resolved |
| Session sync fail | HA monitor shows session count mismatch | Failover drops all connections | Schedule maintenance to resync |

#### Disk Usage Implications (Logs, Reports)

FortiGate 120G has 2× 480GB SSDs in RAID1 for logs and reports.

| Disk Usage | Implication | Action Required |
| --- | --- | --- |
| <70% | Normal operation | None |
| 70-85% | Monitor trend | Review log retention policy |
| 85-95% | Critical | Archive or purge logs immediately |
| >95% | Dangerous | Logs overwrite; compliance violation imminent |

Log Volume Calculations:

Average: 2-3 GB/day with current UTM features enabled

During security incident: Can spike to 10-20 GB/day

480GB usable = ~120 days retention at normal, ~24 days during incident

### Decision Trees

#### CPU High → Investigation → Escalation

flowchart TD
    A[CPU >80% Sustained] --> B{Duration?}
    B -->|<10 min| C[Monitor - may be transient]
    B -->|>10 min| D[Investigate]
    
    C --> E{Returns to normal?}
    E -->|Yes| F[Document in log]
    E -->|No| D
    
    D --> G[FortiView Top Sessions]
    G --> H{Top Source?}
    H -->|Single IP| I[Check if legitimate]
    H -->|Distributed| J[DDoS suspected]
    H -->|Internal server| K[Server compromise?]
    
    I --> L{Legitimate?}
    L -->|Yes| M[Plan capacity upgrade]
    L -->|No| N[Block IP, investigate]
    
    J --> O[Enable DoS protection]
    O --> P[Contact ISP if >1 Gbps]
    
    K --> Q[Scan server for malware]
    
    M --> R[Document]
    N --> S[P1 Escalation]
    P --> T[P1 Escalation]
    Q --> U[P2 Escalation]

#### Memory High → Process Investigation → Restart Decision

flowchart TD
    A[Memory >85%] --> B[Check diag sys top]
    B --> C{Top Process?}
    
    C -->|ipsengine| D[IPS pattern update needed]
    C -->|scanunitd| E[AV scanning backlog]
    C -->|httpsd| F[GUI sessions high]
    C -->|iked| G[VPN tunnel leak?]
    C -->|Other| H[FortiOS bug suspected]
    
    D --> I[Update IPS signatures]
    E --> J[Check quarantine queue]
    F --> K[Close idle GUI sessions]
    G --> L[Check VPN tunnels]
    H --> M[Check release notes]
    
    I --> N{Resolved?}
    J --> N
    K --> N
    L --> N
    M --> N
    
    N -->|Yes| O[Document]
    N -->|No| P[Schedule maintenance restart]
    
    P --> Q[Maintenance window approved?]
    Q -->|Yes| R[Restart secondary first]
    Q -->|No| S[Emergency restart with approval]

### Enhanced Procedure

#### Prerequisites (Enhanced)

Credentials: Named admin account (NOT default "admin"), FortiAuthenticator 2FA enrolled

Access: Management workstation on VLAN 40 (10.10.40.0/24)

Tools: Web browser, FortiToken app, Zabbix dashboard access

Documentation: Previous day's log, incident ticket system access

Escalation Contact: VConfi 24x7 hotline programmed into phone

#### Daily Checklist (Enhanced with Reasoning)

| Check | Expected Result | Action if Failed | Why This Check Exists |
| --- | --- | --- | --- |
| **CPU Usage** | <70% sustained | Investigate via FortiView; escalate if >90% for >15min | CPU exhaustion causes packet drops and IPS failures |
| **Memory Usage** | <80% | Check top processes; schedule restart if trend increasing | Memory exhaustion causes session table overflow and new connection failures |
| **HA Status** | "In Sync" on both units | Contact VConfi immediately; NO config changes until resolved | Out-of-sync HA means failover will use stale configuration |
| **Disk Usage** | <85% | Archive old logs or increase retention if possible | Disk full = logs lost = compliance violation |
| **FortiGuard** | All services green, updated within 24h | Initiate manual update; check internet connectivity | Stale signatures miss new malware and zero-days |
| **Active Sessions** | Within normal range (baseline: 200-400) | Investigate sudden spikes or drops | Sudden changes indicate DDoS, connectivity issues, or ZTNA problems |
| **Temperature** | Normal range (<45°C) | Check data center HVAC, ensure proper ventilation | Overheating causes hardware failures and thermal throttling |
| **Power Supplies** | Both operational | Check PDU status, replace if necessary | Single PSU = single point of failure |
| **Session Table** | <80% capacity | Check for connection floods or scans | Full session table = no new connections possible |
| **License Status** | All valid for >30 days | Initiate renewal process | Expired licenses disable security features |

#### CLI Commands for Advanced Checks

# Check HA status in detail
get system ha status

# Check session table utilization
diag sys session list | grep -c "session"
get system performance status | grep "session"

# Check memory breakdown
diag sys top 5 10  # Refresh every 5 seconds, 10 samples
diag sys top-summary

# Check disk usage
diag system df  # Filesystem usage
execute df      # Alternative view

# Check FortiGuard connection
diag test app update 1  # AV update test
diag test app update 2  # IPS update test
diag test app update 3  # App control update test

# Check interface statistics
diag hardware deviceinfo nic <interface>
get hardware nic <interface>

### Related SOPs

| SOP | Relationship | When to Reference |
| --- | --- | --- |
| SOP-MON-001 | Zabbix alerts may trigger FortiGate investigation | When Zabbix reports FortiGate unreachable |
| SOP-SEC-001 | Splunk receives FortiGate logs | When investigating security events |
| SOP-SEC-002 | Incident response may require FortiGate changes | During security incidents |
| SOP-DR-001 | DR failover involves FortiGate ZTNA | During DR activation |

### Escalation Matrix (Enhanced)

| Severity | Condition | Response Time | Escalate To | Escalation Method |
| --- | --- | --- | --- | --- |
| **P1-Critical** | HA down, both units unreachable | 15 minutes | IT Manager + VConfi 24x7 | Phone call + SMS |
| **P1-Critical** | Primary failed, secondary not taking over | 15 minutes | IT Manager + VConfi 24x7 | Phone call + SMS |
| **P2-High** | Sustained CPU >90%, performance degraded | 1 hour | Senior Network Admin + VConfi | Slack + Email |
| **P2-High** | VPN/ZTNA service unavailable | 1 hour | Senior Network Admin | Slack + Email |
| **P3-Medium** | FortiGuard update failures | 4 hours | Network Admin | Email |
| **P3-Medium** | Single power supply failure | 4 hours | Network Admin | Email |
| **P4-Low** | Disk space warnings | 8 hours | Network Admin | Ticket system |

## SOP-NET-002: Switch Management — Enhanced

### Why This Procedure Exists

The HPE Aruba CX 6300M switches form the backbone of B2H Studios' network infrastructure. Unlike simple "dumb" switches, these are sophisticated Layer 3 devices managing VSX clustering, VLAN segmentation, and 10GbE aggregation. This procedure exists because:

VSX Complexity: Virtual Switching Extension (VSX) creates a single logical switch from two physical units. Misunderstanding VSX behavior during maintenance causes outages.

Silent Failure Modes: Switch ports can fail "softly"—appearing up but dropping packets due to CRC errors, input drops, or buffer exhaustion.

Configuration Drift: Without regular verification, VLAN assignments and port configurations drift from documentation, creating security gaps and connectivity issues.

Physical Infrastructure Awareness: Post-production environments generate unique traffic patterns (large file transfers, multicast, burstiness) that differ from typical enterprise networks.

### Why VSX Stacking Requires Special Attention

#### What Happens When VSX Splits

A VSX split occurs when the ISL (Inter-Switch Link) or keepalive connection fails between the two switches.

flowchart TD
    A[Normal VSX State] --> B[ISL Failure Detected]
    B --> C[Keepalive Check]
    C -->|Keepalive OK| D[Transient - ISL recovers]
    C -->|Keepalive FAIL| E[VSX Split Brain]
    
    E --> F[Both switches claim Primary]
    F --> G[Duplicate IP/MAC scenario]
    G --> H[LACP hash confusion]
    H --> I[Traffic blackholing]
    I --> J[Partial network outage]
    
    F --> K[Different configs active]
    K --> L[Some VLANs on Switch A]
    L --> M[Some VLANs on Switch B]
    M --> N[Inconsistent behavior]

Immediate Actions During VSX Split:

STOP — Do NOT make any configuration changes

Diagnose — Identify which link failed (ISL or keepalive)

Restore — Fix the physical/logical connection

Verify — Confirm VSX re-synchronization

Resume — Only then proceed with normal operations

#### Why ISL Link Status is Critical

| ISL State | Keepalive State | VSX State | Risk Level |
| --- | --- | --- | --- |
| Up | Up | Normal | None |
| Down | Up | Degraded | Medium — failover if second failure |
| Down | Down | Split-brain | **CRITICAL** — immediate action required |
| Up | Down | Unstable | High — intermittent issues likely |

ISL Bandwidth Planning:

ISL carries inter-switch control traffic AND forwarded traffic

B2H Studios: ISL = 2× 10GbE LAG = 20 Gbps

Recommendation: Keep ISL utilization <50% (10 Gbps) to ensure control traffic priority

#### Port Shutdown Implications

When a switch port is administratively shut down:

LACP Impact: If port is LAG member, LAG bandwidth reduces; if minimum links threshold violated, entire LAG may fail

Spanning Tree Impact: If edge port, minimal; if trunk port connecting to another switch, STP recalculation triggered

ZTNA Impact: If port connected to FortiGate, HA failover may trigger

Before Shutting Any Port:

Identify what device is connected (`show mac-address-table`)

Check if port is LAG member (`show interface lag X`)

Verify no critical services depend on that path

Document reason and timestamp

### LACP Troubleshooting Deep Dive

#### How to Identify Which Physical Link Is Carrying Traffic

# Show LACP status and distribution
show lacp interfaces <lag-id>

# Example output interpretation:
# "Actor Port Priority" and "Partner Port Priority" determine hashing
# Lower number = higher priority for LACP negotiations

# Show per-port statistics to identify active links
show interface <port> counters

# Compare input/output counters across LAG members
# Uneven distribution may indicate hash algorithm limitations

#### What Happens When One Member Fails

flowchart LR
    A[LACP LAG with 4 members] --> B{One member fails}
    B --> C[Traffic rehashed to remaining 3]
    C --> D{Minimum links configured?}
    D -->|Below minimum| E[LAG interface goes down]
    D -->|Above minimum| F[LAG stays up, reduced bandwidth]
    
    E --> G[All traffic through LAG fails]
    G --> H[Connected device loses connectivity]
    
    F --> I[25% bandwidth reduction]
    I --> J[Potential congestion if near capacity]

B2H Studios LACP Configuration:

Site A FortiGate uplink: LAG to VSX pair (minimum links: 1)

HD6500 storage uplink: LAG to VSX pair (minimum links: 1)

Inter-site WAN: LAG across multiple carriers

#### Hash Algorithm Impact on Distribution

| Hash Method | Best For | B2H Studios Usage |
| --- | --- | --- |
| L2 (MAC) | Many flows between many hosts | Not used — limited entropy |
| L3 (IP) | Layer 3 routed traffic | Used for server traffic |
| L4 (IP+Port) | Most granular distribution | Used for ZTNA/FortiGate traffic |

B2H Recommendation: Use L4 hash for all LAGs to maximize distribution entropy.

### Change Management Integration

#### When to Create Change Request

| Action | Change Required | Risk Level | Approval |
| --- | --- | --- | --- |
| Configuration backup | No | None | N/A |
| Status checking | No | None | N/A |
| VLAN addition | Yes | Low | Network Admin |
| Port configuration | Yes | Medium | Network Admin + Notify |
| Firmware update | Yes | High | CAB (Change Advisory Board) |
| VSX reconfiguration | Yes | Critical | CAB + VConfi |

#### Backout Plan Requirements

Every switch change must include:

Configuration backup before change (automated)

Rollback command sequence documented

Verification test to confirm success/failure

Automatic rollback trigger (time-based or test-based)

Emergency contact for unplanned issues

Template Backout Commands:

# Before any config change:
copy running-config tftp://10.10.40.5/pre-change-$(date +%Y%m%d-%H%M).cfg

# If rollback needed:
copy tftp://10.10.40.5/pre-change-<timestamp>.cfg running-config
write memory

#### Communication Plan

| Change Type | Notification | Lead Time |
| --- | --- | --- |
| No-impact (backup, monitoring) | None | N/A |
| Low-impact (VLAN addition) | Email to IT team | 24 hours |
| Medium-impact (port config) | Email + Slack | 48 hours |
| High-impact (firmware) | All-staff email | 1 week |
| Critical-impact (VSX work) | All-staff + management | 2 weeks |

### Enhanced Procedure

#### Prerequisites (Enhanced)

SSH Client: PuTTY, Terminal, or Windows OpenSSH

Enable Password: Documented in password vault

TFTP Server: 10.10.40.5 accessible for backups

VSX Knowledge: Understanding of primary/secondary roles

Documentation: Current network diagram

#### VSX Status Verification (Enhanced)

# Primary verification commands
ssh admin@10.10.40.10

# Check VSX status
show vsx status
# Expected: "ISL State: UP", "Keepalive: UP", "Config Sync: In Sync"

# Detailed ISL information
show vsx isl
# Check: No CRC errors, link up on all ISL members

# Keepalive path verification
show vsx keepalive
# Check: Keepalive source/destination IPs reachable

# VSX configuration sync status
show vsx configuration
# Check: All VLANs and settings synchronized

#### Interface Status Deep Check

# Brief overview
show interface brief

# Detailed counters for troubleshooting
show interface <port> counters
# Focus on: RX/TX errors, CRC, fragments, giants, drops

# MAC address table analysis
show mac-address-table
# Count: Expect ~25-30 active devices per site
# Verify: No unexpected MACs (rogue detection)

# VLAN verification
show vlan
# Count: Should show VLANs 10, 20, 30, 40, 50, 99
# Verify: Port assignments match documentation

# LAG status
show lacp interfaces
# Verify: All member ports "up", distribution active

### Related SOPs

| SOP | Relationship | When to Reference |
| --- | --- | --- |
| SOP-NET-001 | Switch ports connect to FortiGate | When FortiGate interface issues suspected |
| SOP-NET-003 | FortiAPs connect to switch ports | When AP adoption fails |
| SOP-MON-001 | Zabbix monitors switch health | When alerts trigger |
| SOP-SRV-001 | Servers connect via switches | When server network issues occur |

## SOP-NET-003: FortiAP Wireless — Enhanced

### Why This Procedure Exists

Wireless access in a media production environment like B2H Studios presents unique challenges that standard enterprise Wi-Fi doesn't address. This SOP exists because:

Content Security: Media files transmitted over Wi-Fi require encryption and access control that exceeds typical corporate standards.

RF Interference: Post-production equipment (video monitors, audio gear, storage arrays) can interfere with Wi-Fi and vice versa.

High-Density File Access: Video proxy files are larger than typical documents—Wi-Fi must handle sustained throughput, not just burst traffic.

Guest Isolation: Clients and visitors need internet access without any possibility of accessing production networks or content.

### Why Rogue AP Detection Matters for Media Studios

#### Content Theft Risk

Unauthorized access points create pathways for:

Direct network infiltration: Rogue AP with weak/no encryption bridges attacker to corporate network

Man-in-the-middle attacks: Attacker positions between users and real network

Credential harvesting: Fake "B2H-Corporate" AP captures login attempts

Media Industry Reality:

Unreleased content has significant black-market value

Compromised content = broken NDAs = legal liability

Leaked trailers or footage damages marketing campaigns

#### Network Infiltration Path

flowchart LR
    A[Attacker in Parking Lot] --> B[Deploy Rogue AP]
    B --> C[Broadcast "B2H-Guest" SSID]
    C --> D[Employee Connects]
    D --> E[Captive Portal Phishing]
    E --> F[Credentials Harvested]
    F --> G[ZTNA Access via Stolen Creds]
    G --> H[Content Access]

Rogue AP Detection Configuration:

FortiAPs scan all channels every 60 seconds

Detected rogue APs trigger immediate alerts

Automatic containment: FortiAP can send deauth frames to rogue clients (where legally permitted)

### RF Interference in Post-Production

#### Why Wi-Fi Can Affect Video Equipment

| Wi-Fi Element | Potential Impact | B2H Studios Mitigation |
| --- | --- | --- |
| 2.4 GHz channels 1-14 | Can interfere with wireless video transmitters | Disable 2.4 GHz in edit bays |
| 5 GHz UNII-1/2/3 | May affect professional wireless audio systems | Use DFS channels carefully |
| High power output | Can desense nearby receivers | Reduce TX power to minimum required |
| Beacon broadcasts | Regular bursts can cause audio artifacts | Reduce beacon interval if needed |

#### Channel Planning for Co-Existence

B2H Studios Channel Allocation:

| Location | 2.4 GHz | 5 GHz Primary | 5 GHz Secondary |
| --- | --- | --- | --- |
| Edit Bay 1 | Disabled | 36 (UNII-1) | 40 (UNII-1) |
| Edit Bay 2 | Disabled | 44 (UNII-1) | 48 (UNII-1) |
| Edit Bay 3 | Disabled | 149 (UNII-3) | 153 (UNII-3) |
| Common Areas | 1, 6, 11 | Auto | Auto |
| Machine Room | Disabled | 157 (UNII-3) | 161 (UNII-3) |

Rationale:

Edit bays: Dedicated channels prevent co-channel interference

Machine room: UNII-3 channels (higher frequency) penetrate less to edit bays

Common areas: 2.4 GHz enabled for guest/legacy device compatibility

#### 5GHz vs 2.4GHz Decision Matrix

flowchart TD
    A[Device Connecting] --> B{Device supports 5GHz?}
    B -->|No| C[Connect to 2.4GHz]
    B -->|Yes| D{Location?}
    
    D -->|Edit Bay| E[Force 5GHz only]
    D -->|Common Area| F{Usage?}
    
    F -->|Video/Production| E
    F -->|General/Browsing| G[Allow both bands]
    
    C --> H[Lower throughput<br/>Higher range<br/>More interference]
    E --> I[Higher throughput<br/>Lower interference<br/>Shorter range]
    G --> J[Band steering<br/>prefers 5GHz]

B2H Studios Band Policy:

Corporate SSID: Band steering enabled, prefers 5GHz

Guest SSID: 2.4GHz + 5GHz for maximum compatibility

Edit Bays: 5GHz only profiles for production devices

### Enhanced Procedure

#### AP Status Verification (Enhanced)

# Via FortiGate CLI
diag wireless-controller wtp-status

# Check specific AP
diag wireless-controller wtp-status <serial-number>

# Check client distribution
diag wireless-controller wlac -d sta

# RF spectrum analysis (on AP)
diagnose wifi spectrum <radio-id>

GUI Navigation:

FortiGate GUI → WiFi & Switch Controller → Managed FortiAPs

Check columns: Status, CPU, Memory, Channel Utilization

Click individual AP for detailed RF metrics

#### Rogue AP Detection Response

| Severity | Criteria | Response |
| --- | --- | --- |
| **Critical** | Rogue AP named "B2H-Corporate" or "B2H-Guest" | Immediate investigation; physical sweep; notify security |
| **High** | Unauthorized AP on production VLAN | Locate and disconnect; security review |
| **Medium** | Unknown AP on guest VLAN | Monitor; document; investigate if persists |
| **Low** | Neighboring business AP (different SSID) | Document; no action unless interference |

### Related SOPs

| SOP | Relationship | When to Reference |
| --- | --- | --- |
| SOP-NET-002 | FortiAPs connect to switches | When AP won't adopt |
| SOP-USR-001 | End users connect to Wi-Fi | When users report connectivity issues |
| SOP-SEC-001 | Rogue APs are security events | When rogue detected |

## SOP-MON-001: Zabbix Monitoring — Enhanced

### Why This Procedure Exists

Monitoring is the nervous system of IT infrastructure. Without it, problems manifest as user complaints rather than proactive alerts. This SOP exists because:

Alert Fatigue is Real: Poorly tuned monitoring generates noise that leads to ignored alerts—then real issues are missed.

Symptom vs. Cause: Monitoring symptoms (high CPU) is easy; monitoring causes (memory pressure causing swap) requires expertise.

Baseline Deviation: Normal varies by time-of-day, day-of-week. Static thresholds miss context-dependent anomalies.

Capacity Planning: Trend analysis prevents emergencies—adding storage before it's full, upgrading bandwidth before saturation.

### Alert Fatigue Prevention Strategy

#### Why We Use P1-P4 Classification

| Priority | Response Time | Use Case | Why This Threshold |
| --- | --- | --- | --- |
| **P1-Disaster** | 5 minutes | Site down, data loss imminent | Business halt; every minute costs money |
| **P2-High** | 15 minutes | Service degraded, redundancy lost | User impact but workaround exists |
| **P3-Average** | 1 hour | Single component failure, no redundancy | Needs attention but not immediate |
| **P4-Warning** | 4 hours | Trending toward threshold | Planning information, not crisis |

Alert Volume Targets:

P1: <5 per month (if more, system is unstable or thresholds wrong)

P2: <10 per week

P3: <20 per week

P4: As needed for trending

If alert volumes exceed these targets, threshold tuning is required.

#### Threshold Tuning Methodology

flowchart TD
    A[Alert Fires] --> B{True Positive?}
    B -->|Yes| C[Investigate & Resolve]
    B -->|No| D[False Positive]
    
    D --> E[Check Historical Data]
    E --> F{Threshold Too Sensitive?}
    F -->|Yes| G[Increase Threshold]
    F -->|No| H[Add Context Condition]
    
    G --> I[Time-based threshold?]
    G --> J[Baseline deviation?]
    
    H --> K[Business hours only?]
    H --> L[Multiple conditions?]
    
    I --> M[Update Trigger]
    J --> M
    K --> M
    L --> M
    M --> N[Document Change]

B2H Studios Tuning Examples:

| Metric | Initial Threshold | Tuned Threshold | Rationale |
| --- | --- | --- | --- |
| CPU Usage | >70% | >70% for 10 min | Transient spikes normal during ingest |
| Disk Usage | >80% | >85% | 80% had too many false positives |
| Memory | >80% | >85% | Zabbix agent itself causes temporary increases |
| Network Latency | >10ms | >50ms | 10ms triggered on normal WAN variation |

#### Alert Correlation Rules

Problem: Multiple related alerts flood the operator.

Solution: Correlation rules group related issues.

| Correlation Rule | Condition | Action |
| --- | --- | --- |
| Site-wide outage | >50% devices at site unreachable | Single "Site Down" alert; suppress individual device alerts |
| Network dependency | Router down AND switches behind it unreachable | Only alert on router; suppress downstream |
| Storage cascade | NAS volume full AND applications reporting disk errors | Alert on root cause (NAS); suppress symptoms |
| Power event | UPS on battery AND temperature rising | Correlate; alert on power with temperature note |

### Monitoring Philosophy

#### Monitor Symptoms vs. Causes

| Symptom | Likely Cause | Monitor Both? |
| --- | --- | --- |
| High CPU | Memory pressure, swap thrashing | Yes — symptom for alerting, cause for diagnosis |
| Slow file access | Network congestion, disk I/O, NAS load | Yes — symptom alerts user impact, cause guides fix |
| Authentication failures | RADIUS down, credential mismatch, account lockout | Yes — symptom for security, cause for resolution |
| High latency | Routing issue, bandwidth saturation, QoS misconfig | Yes — symptom for user impact, cause for network team |

#### Baseline Establishment Process

flowchart LR
    A[Install Zabbix] --> B[30-Day Learning Period]
    B --> C[Collect All Metrics]
    C --> D[Analyze Patterns]
    D --> E[Identify Normal Range]
    E --> F[Set Dynamic Thresholds]
    F --> G[Enable Alerting]
    G --> H[Quarterly Re-baseline]

B2H Studios Baseline Examples (Week 1 Post-Implementation):

| Metric | Normal Range | Alert Threshold | Notes |
| --- | --- | --- | --- |
| NAS CPU | 20-40% | >60% sustained | Higher during overnight integrity checks |
| FortiGate Sessions | 200-400 | >600 | Spikes during Monday morning ZTNA connections |
| Switch Port Utilization | 10-30% | >70% | Edit bays higher than admin areas |
| UPS Load | 40-60% | >80% | Higher during business hours |

#### Trend Analysis for Capacity Planning

| Metric | Current | 6-Month Trend | Action Timeline |
| --- | --- | --- | --- |
| NAS Storage | 45% used | +5%/month | Plan expansion at 70% (5 months) |
| VM Memory | 70% allocated | +2%/month | No action needed |
| Network Bandwidth | 30% avg | +3%/month | Monitor; upgrade at 60% |
| Backup Window | 6 hours | +15 min/month | Optimize or upgrade link at 8 hours |

### False Positive Handling

#### Common False Positive Scenarios

| Scenario | Cause | Solution |
| --- | --- | --- |
| Overnight backup causes "disk busy" alert | Normal behavior | Time-based suppression (11 PM - 5 AM) |
| Monday morning login spike | Normal pattern | Dynamic baseline based on day-of-week |
| FortiGate session count spike | ZTNA reconnections after weekend | Increase threshold or add duration condition |
| Temperature alert during HVAC maintenance | Planned activity | Maintenance window scheduling in Zabbix |

#### Tuning Procedures

Identify Pattern: Review alert history for recurring false positives

Analyze Data: Check if metric actually exceeded reasonable threshold

Determine Root Cause: Why is this normal behavior triggering alert?

Adjust Trigger: Modify threshold, add conditions, or use time-based rules

Document Change: Record tuning decision and rationale

Monitor Effectiveness: Verify false positive eliminated without missing real issues

#### Documentation Requirements

Every tuning change requires:

Before/After threshold values

Business justification

Risk assessment (could this miss a real issue?)

Approver signature

Review date (tunings should be revisited quarterly)

### Related SOPs

| SOP | Relationship | When to Reference |
| --- | --- | --- |
| SOP-NET-001 | Zabbix monitors FortiGate | When FortiGate alerts fire |
| SOP-NET-002 | Zabbix monitors switches | When switch alerts fire |
| SOP-BKP-001 | Zabbix monitors backup status | When backup alerts fire |
| SOP-SRV-001 | Zabbix monitors servers | When server alerts fire |

## SOP-SRV-001: Server Patching — Enhanced

### Why This Procedure Exists

Server patching is the most common cause of IT outages—either from applying patches (incompatibility, reboots) or from NOT applying patches (security breaches, stability issues). This SOP exists to:

Balance Security vs. Stability: Patches fix vulnerabilities but can introduce bugs. The procedure provides framework for decision-making.

Ensure Tested Rollouts: Emergency patches applied without testing cause more outages than they prevent. The procedure mandates testing phases.

Enable Rapid Rollback: When patches cause issues, rollback must be faster than troubleshooting. Snapshots enable 5-minute recovery.

Maintain Audit Trail: ISO 27001 requires evidence of patch management. The procedure generates this evidence automatically.

### Why This Patching Schedule?

#### Monthly Windows Updates (Patch Tuesday Alignment)

| Schedule Element | Timing | Rationale |
| --- | --- | --- |
| Patch Tuesday | 2nd Tuesday of month | Microsoft release schedule; maximum time for community testing |
| Testing Environment | Wednesday-Thursday | 2-3 days for compatibility testing |
| Pilot Group | Friday following Patch Tuesday | 5-10% of production; early warning system |
| Production Rollout | Following week (Days 7-14) | Allows 1 week of "soak time" in pilot |

Why Not Immediate Patching?

Microsoft's own patches sometimes have issues caught by early adopters

1-week delay allows community to identify problematic updates

B2H Studios cannot tolerate production outages for patch-induced issues

#### Quarterly Firmware Updates

| Component | Frequency | Timing | Rationale |
| --- | --- | --- | --- |
| BIOS | Quarterly | Maintenance window | Requires reboot; schedule with other maintenance |
| RAID Controller | Quarterly | Maintenance window | Low risk but requires reboot |
| NIC Firmware | Quarterly | Rolling update | Can often update without reboot |
| iLO/iDRAC | Quarterly | Anytime | Out-of-band; doesn't affect running VMs |

Why Quarterly, Not Monthly?

Firmware updates carry higher risk than OS patches

Dell/HPE release schedules don't justify monthly checks

Quarterly balances security with stability

#### Emergency Patching Triggers

| Vulnerability Characteristic | Response Time | Examples |
| --- | --- | --- |
| Critical CVSS 10, actively exploited | 24 hours | Log4j, PrintNightmare |
| Critical CVSS 9-10, proof-of-concept available | 72 hours | Windows RCE vulnerabilities |
| High CVSS 8-9, easily exploitable | 7 days | Common misconfiguration vulnerabilities |
| All other vulnerabilities | Next scheduled window | Standard security updates |

Emergency Patch Process:

Security team identifies critical vulnerability

Vulnerability briefing to IT Manager

Risk assessment: Exploit likelihood vs. patch risk

If approved: Accelerated testing (24-48 hours)

Emergency change request

Production deployment with enhanced monitoring

Extended monitoring period (48 hours vs. normal 24)

### Patch Testing Strategy

#### Test Environment Requirements

| Requirement | B2H Studios Implementation | Why Critical |
| --- | --- | --- |
| Hardware similarity | Dell R760 identical to production | Firmware patches may behave differently on different hardware |
| VM configuration parity | VMs cloned from production | Ensures application compatibility |
| Network connectivity | Isolated VLAN with internet | Patches download from Microsoft; testing needs realistic network |
| Test dataset | Anonymized production data | Database/application patches need realistic data |
| Rollback capability | Snapshot before every test | Failed patches must not contaminate test environment |

#### Production Rollout Phases

flowchart TD
    A[Patch Available] --> B[Test Environment]
    B --> C{Tests Pass?}
    C -->|No| D[Investigate & Report]
    D --> E[Delay Until Fixed]
    C -->|Yes| F[Pilot Group]
    
    F --> G{Pilot Success?}
    G -->|Issues Found| H[Rollback Pilot]
    H --> I[Delay & Investigate]
    G -->|Success| J[Production Rollout]
    
    J --> K[Batch 1: 25%]
    K --> L{Success?}
    L -->|No| M[Rollback Batch 1]
    L -->|Yes| N[Batch 2: 25%]
    
    N --> O{Success?}
    O -->|No| P[Rollback Batch 2]
    O -->|Yes| Q[Batch 3: 25%]
    
    Q --> R{Success?}
    R -->|No| S[Rollback Batch 3]
    R -->|Yes| T[Batch 4: 25%]
    T --> U[Complete]

B2H Studios Batch Definitions:

Pilot: Signiant staging server (non-production)

Batch 1: Non-critical VMs (Kaspersky SC, Vault)

Batch 2: Supporting infrastructure (FortiAnalyzer, EMS)

Batch 3: Authentication (FortiAuthenticator)

Batch 4: Critical production (Signiant SDCX production)

#### Rollback Decision Criteria

| Criterion | Rollback Trigger | Continue Trigger |
| --- | --- | --- |
| Service unavailable | Any critical service down >15 min | All services functional |
| Performance degradation | >30% slower than baseline | Within 10% of baseline |
| Application errors | Any new errors in logs | Clean logs |
| User complaints | >3 related tickets | No complaints |
| Monitoring alerts | New P1/P2 alerts | Only expected alerts |

### Snapshot vs. Backup Before Patching

#### When VM Snapshot Is Sufficient

| Scenario | Snapshot OK? | Rationale |
| --- | --- | --- |
| Monthly OS patches | Yes | Fast rollback; 48-hour retention sufficient |
| Configuration changes | Yes | Quick revert if misconfiguration |
| Minor application updates | Yes | Application-level backup exists |

#### When Full Backup Is Required

| Scenario | Full Backup Required | Rationale |
| --- | --- | --- |
| Firmware updates | Yes | Hardware-level changes; snapshot doesn't protect against firmware issues |
| Major OS upgrades (e.g., 2019→2022) | Yes | Major change; longer recovery time may be needed |
| Database migrations | Yes | Data structure changes; snapshot may not capture consistency |
| Application major version upgrades | Yes | Schema changes; rollback may need older version data |

#### Retention of Pre-Patch Snapshot

| Patch Type | Snapshot Retention | Rationale |
| --- | --- | --- |
| Monthly security patches | 7 days | Most patch issues appear within 48 hours |
| Firmware updates | 30 days | Firmware issues may take weeks to manifest |
| Emergency patches | 14 days | Less testing; higher risk |
| Quarterly updates | 14 days | Multiple changes; longer observation needed |

Snapshot Cleanup:

Automated cleanup after retention period

Manual review before deletion for any issues during period

Document any retained snapshots beyond standard (with justification)

### Related SOPs

| SOP | Relationship | When to Reference |
| --- | --- | --- |
| SOP-BKP-001 | Backups before patching | When determining backup strategy |
| SOP-MON-001 | Monitor during/after patching | When patch causes performance issues |
| SOP-SEC-002 | Security patches are incident response | When emergency patching for vulnerability |

## SOP-BKP-001: Backup & Restore — Enhanced

### Why This Procedure Exists

Data is the lifeblood of B2H Studios—project files, raw footage, edits, and deliverables represent hundreds of hours of work and millions of rupees in value. This SOP exists because:

Backup Failure Discovery: Most organizations discover backup failures during restore attempts—when it's too late. Proactive verification prevents this.

Ransomware Resilience: Modern ransomware targets backups. Air-gapped, immutable, and offline copies are essential.

Compliance Requirements: Client contracts and ISO 27001 require demonstrable data protection. The procedure generates audit evidence.

Recovery Time Pressure: During a crisis, clear procedures reduce panic and errors. Step-by-step instructions ensure consistent execution.

### Why 3-2-1-1-0 Requires These Specific Procedures

The 3-2-1-1-0 backup strategy:

3 copies of data (production + 2 backups)

2 different media types (disk + cloud)

1 offsite copy (Wasabi cloud)

1 offline/air-gapped copy (immutability)

0 errors in verification

#### Verification Testing Importance

| Backup Type | Verification Method | Frequency | Why Critical |
| --- | --- | --- | --- |
| Snapshots | Automated integrity check | Every snapshot | Detects storage corruption |
| Snapshot Replication | Checksum verification | Every replication | Ensures DR site has valid data |
| Hyper Backup | Application-level verification | Weekly | Confirms backup format integrity |
| Wasabi Cloud Sync | Object integrity check | Daily | Detects transfer corruption |

What "Verification" Actually Means:

Synthetic verification: Checksum/hash comparison (fast, catches corruption)

Application verification: Mount backup, check application can read (medium, catches format issues)

Full restore test: Complete restore to alternate location (slow, catches everything)

B2H Studios uses all three levels based on criticality.

#### What "Zero Errors" Means in Practice

| Error Type | Severity | Response |
| --- | --- | --- |
| Single file checksum mismatch | Medium | Re-backup that file; investigate cause |
| Multiple file errors | High | Full re-backup; storage health check |
| Backup job failure | Critical | Immediate retry; escalate if persists |
| Replication lag >2 hours | Medium | Check bandwidth; may need scheduling adjustment |
| Cloud sync errors | High | Check internet/Wasabi status; retry |

Zero Errors Policy:

ANY error in backup report requires investigation

Error patterns trigger proactive maintenance

Ignored errors accumulate into unrecoverable situations

#### Documentation Requirements for Audits

| Document | Retention | Purpose |
| --- | --- | --- |
| Backup job logs | 3 years | Proof of backup execution |
| Verification reports | 3 years | Proof of backup integrity |
| Restore test results | 3 years | Proof of recoverability |
| Backup configuration | Current + 3 versions | Audit trail of changes |
| Retention policy compliance | Ongoing | Proof of policy adherence |

### Restore Testing Schedule

| Test Type | Frequency | Scope | Success Criteria |
| --- | --- | --- | --- |
| **Automated Verification** | Daily | All backup jobs complete without errors | 100% success rate |
| **File-Level Restore Test** | Monthly | Random sample of 10 files from each share | All files restore and open correctly |
| **Folder-Level Restore Test** | Quarterly | One complete project folder (100+ GB) | Complete folder restores; checksums match |
| **Full DR Test** | Bi-annually | Complete site failover and operations | RTO <4 hours, RPO <15 minutes |
| **Unannounced Spot Check** | Annual | Random restore request without warning | IT team executes within 1 hour |

Test Documentation:

Test date/time

Tester name

Data selected for restore

Source backup (date/time)

Restore destination

Time to complete

Verification method

Success/failure determination

### Ransomware Recovery Playbook

#### Detection → Isolation → Assessment → Restore

flowchart TD
    A[Ransomware Detected] --> B[Immediate Isolation]
    B --> C[Identify Scope]
    C --> D{Backup Status?}
    
    D -->|Clean backups available| E[Select Restore Point]
    D -->|Backups compromised| F[Engage Incident Response]
    
    E --> G[Pre-encryption snapshot?]
    E --> H[Last known clean backup]
    
    G --> I[Calculate data loss]
    H --> I
    
    I --> J{Acceptable loss?}
    J -->|Yes| K[Begin Restore]
    J -->|No| L[Forensic analysis]
    L --> M[Evaluate paying ransom]
    
    K --> N[Restore to isolated environment]
    N --> O[Verify clean]
    O --> P[Return to production]
    
    F --> Q[Engage specialists]
    Q --> R[Forensic imaging]
    
    M --> S[Legal/Insurance consult]

#### Decision Tree: Which Backup to Use?

| Scenario | Recommended Source | Rationale |
| --- | --- | --- |
| Ransomware just detected (<1 hour) | Latest snapshot (if clean) | Minimum data loss |
| Ransomware active for hours | Last known clean snapshot | May need to go back 6-24 hours |
| Backups show signs of encryption | DR site replicas (if isolated) | DR site may be clean |
| All local backups compromised | Wasabi cloud archive | Immutable; cannot be encrypted by ransomware |
| All online backups compromised | Emergency offline backup (if exists) | True air gap |

#### Communication Templates

Internal Communication (During Ransomware Event):

SUBJECT: URGENT: Security Incident - System Isolation in Progress

Team,

We have detected potential ransomware activity on our network. 
As a precautionary measure:

- All file shares are temporarily offline
- ZTNA remote access is suspended
- Email and communication systems remain operational

DO NOT attempt to access project files or shared drives.
DO NOT shut down your computer - leave it as-is.
Report any unusual file behavior immediately to security@b2hstudios.com

We are working with VConfi security team to resolve this.
Estimated restoration: [Timeframe - be conservative]

Updates will be provided every 2 hours.

IT Security Team

### Related SOPs

| SOP | Relationship | When to Reference |
| --- | --- | --- |
| SOP-SRV-001 | Backups before patching | Before any server patching |
| SOP-DR-001 | DR uses backup replication | During DR activation |
| SOP-SEC-002 | Ransomware is security incident | During ransomware response |
| SOP-SEC-003 | Backups are audit evidence | During ISO 27001 audit |

## SOP-DR-001: DR Failover & Failback — Enhanced

### Why This Procedure Exists

The B2H Studios DR site represents a significant investment (₹80+ Lakhs) to ensure business continuity. However, DR infrastructure that isn't tested and procedures that aren't practiced fail when needed. This SOP exists because:

Failover Complexity: Promoting a standby site to active involves storage, network, authentication, and application changes that must be sequenced correctly.

Failback Is Harder: Returning to the primary site after recovery requires reverse replication, data synchronization, and careful cutover timing—more complex than initial failover.

Decision Authority: Declaring a disaster and authorizing failover is a business decision, not purely technical. The procedure defines who decides.

Communication Criticality: During an outage, users need clear instructions. Confusion compounds the crisis.

### Why Manual Failover (Not Automatic)?

#### Split-Brain Prevention

flowchart TD
    A[Automatic Failover Scenario] --> B[Site A appears down]
    B --> C[Automatic promotion of Site B]
    C --> D{Actually down?}
    D -->|Yes| E[Successful DR]
    D -->|No - Network partition| F[SPLIT BRAIN]
    
    F --> G[Site A still active]
    G --> H[Site B now also active]
    H --> I[Both sites accept writes]
    I --> J[Data diverges]
    J --> K[Irreconcilable conflict]
    K --> L[Manual merge required]
    L --> M[Data loss inevitable]

Split-Brain Consequences:

Both sites accept writes simultaneously

Data diverges (same files modified at both sites)

Reconciliation requires manual merge

Some data loss is inevitable

B2H Studios content cannot be easily merged

Manual Decision Prevents This:

Human verifies Site A is truly down (not just network partition)

Human confirms Site B is healthy and ready

Human coordinates promotion timing

Human makes business decision about accepting downtime vs. DR activation

#### False Positive Protection

| Scenario | Automatic Failover Response | Manual Response |
| --- | --- | --- |
| ISP outage at Site A (common) | Would trigger unnecessary DR | Assess: Site A healthy, just unreachable; wait or temporary workaround |
| Planned maintenance window | Would trigger false DR | Pre-coordinated; no action needed |
| Monitoring false alarm | Would trigger panic DR | Verify before action; avoid unnecessary disruption |
| Brief power blip (<5 min) | Would trigger DR for temporary issue | Wait for UPS/generator to stabilize |

Business Impact of False Failover:

30-60 minutes of disruption for ZTNA reconfiguration

User confusion from multiple direction changes

DNS propagation delays

Potential data loss if users had unsaved work

#### Business Decision Integration

Failover triggers questions only business leadership can answer:

Is the expected duration of outage worth the failover disruption?

Are there client deliverables today that require immediate DR?

What's the cost of downtime vs. cost of DR activation?

Are key personnel available to support DR operations?

IT Manager Authority:

Can authorize DR for outages expected >4 hours

Must escalate to CEO for outages expected <4 hours

Must declare disaster for insurance/SLA purposes

### Failback Complexity Explanation

#### Why Reverse Replication Is Needed

Timeline of Data Flow:

Normal:     Site A (Active) ──replicates──> Site B (Standby)
                    ↑___________________________↓
                   (all writes happen at A)

DR Event:   Site A (Down)    Site B (Promoted)
                            ↑_______________↓
                           (writes now at B)

During DR:  Site B (Active) ──NO replication──> Site A (Down)
                            ↑___________________________↓
                           (changes accumulate only at B)

Failback:   Site B (Active) ──reverse replication──> Site A (Recovering)
                            ↑___________________________↓
                           (must sync B→A before A can become active)

Reverse Replication Challenges:

Delta Calculation: System must identify all changes made at B during DR

Bandwidth Consumption: Initial sync may saturate WAN link for hours

Consistency: Must ensure all data arrives intact before cutover

Timing: Users must be offline during final sync to prevent new changes

#### Data Consistency Challenges

| Consistency Aspect | Challenge | Mitigation |
| --- | --- | --- |
| File timestamps | Preserved during replication? | Synology preserves all metadata |
| Open files | What if files were open during DR? | All files committed at snapshot time |
| In-flight transactions | Database consistency? | Applications handle at app level |
| Permissions | ACLs preserved? | Synology replicates permissions |

#### Cutover Timing Considerations

Failback Window Selection:

Preferred: Weekend or off-hours (minimal user impact)

Minimum: 4-hour maintenance window

Factors: Data change volume, WAN bandwidth, application dependencies

Final Sync Process:

Notify users of impending cutover (30 min warning)

Stop all writes at Site B (quiesce applications)

Final replication sync (usually 5-15 minutes for delta)

Verify synchronization complete

Promote Site A to active

Update DNS/ZTNA to point to Site A

Re-establish Site A→B replication

Resume operations

### DR Testing Scenarios

| Test Type | Frequency | Scope | Duration | Participants |
| --- | --- | --- | --- | --- |
| **Tabletop Exercise** | Quarterly | Walk through procedures on paper | 2 hours | IT team, management |
| **Functional Test** | Bi-annually | Promote Site B, verify services, failback | 4-6 hours | IT team |
| **Full DR Drill** | Annually | Complete failover, user acceptance testing, full day operations | 1-2 days | All staff |
| **Unannounced Test** | Bi-annually | Sudden notification: "Site A is down" | Variable | IT team only |

Tabletop Exercise Format:

Scenario briefing (e.g., "Flood at Site A, building inaccessible")

Step-through of decision process

Role-playing communication

Identification of gaps/issues

Documentation updates

Full DR Drill Success Criteria:

RTO <4 hours (from decision to user access)

RPO <15 minutes (data loss acceptable)

All critical services functional

User acceptance: Can edit video, access files, ZTNA works

Failback completes within maintenance window

### Related SOPs

| SOP | Relationship | When to Reference |
| --- | --- | --- |
| SOP-BKP-001 | DR uses backup replication | When replication issues occur |
| SOP-NET-001 | ZTNA configuration during DR | When updating ZTNA for DR |
| SOP-SEC-002 | Major DR may be security incident | If DR triggered by security event |

## SOP-SEC-001: Splunk SIEM Review — Enhanced

### Why This Procedure Exists

Security tools are only effective if someone reviews their output. Splunk at B2H Studios processes millions of events daily—this SOP ensures the important ones surface and get appropriate response.

Threat Detection: Automated correlation rules catch patterns humans would miss.

Compliance Evidence: SIEM logs provide audit trails required by ISO 27001 and client contracts.

Early Warning: Honeypot and anomaly detection provide early indicators of reconnaissance.

Investigation Support: When incidents occur, historical SIEM data enables root cause analysis.

### Why These Specific Correlation Rules?

#### Brute Force: Threshold Rationale (5 Failures in 10 Minutes)

Why Not Lower (e.g., 3 Failures)?

Normal users occasionally mistype passwords

Mobile devices with saved passwords may retry during token refresh

3 failures would generate too many false positives

Why Not Higher (e.g., 10 Failures)?

Automated tools can attempt 100+ passwords per minute

10 failures provides too much opportunity for successful guess

Industry standard: 5-6 attempts before lockout/alert

B2H Studios Threshold:

5 failed attempts from single source IP in 10 minutes

Triggers: Alert + temporary IP block (15 minutes)

10 failed attempts: Account lockout + immediate investigation

#### Honeypot: Why This Catches Ransomware Early

Honeypot Design:

Fake SMB shares: "\\nas\finance" and "\\nas\projects-archive"

Enticing names that attackers target first

No legitimate access ever (any access = malicious)

Monitored by Splunk with immediate alerting

Why Ransomware Hits Honeypots First:

Ransomware scans network for file shares

Selects targets based on name ("finance" = valuable)

Begins encryption of accessible shares

Honeypot is accessed = immediate detection

Detection Timeline:

| Stage | Time | Detection Method |
| --- | --- | --- |
| Reconnaissance | Day -7 to 0 | May go undetected |
| Initial access | Day 0 | Honeypot triggered |
| Lateral movement | Hour 0-2 | Splunk correlation |
| Mass encryption | Hour 2-4 | Multiple honeypots |
| Ransom note | Hour 4+ | User reports |

Without honeypot: Detection at "Ransom note" stage (4+ hours of encryption)

With honeypot: Detection at "Initial access" stage (minutes)

#### Data Exfiltration: Volume Baseline Establishment

Baseline Methodology:

Measure average daily outbound per user for 30 days

Establish 95th percentile as "normal upper bound"

Set alert at 150% of 95th percentile

Review and adjust monthly

B2H Studios Initial Baselines:

| User Type | Normal Daily Outbound | Alert Threshold | Rationale |
| --- | --- | --- | --- |
| Editor | 500 MB | 750 MB | Upload proxies, review copies |
| Manager | 100 MB | 150 MB | Email, documents |
| IT Admin | 1 GB | 1.5 GB | Patches, updates, transfers |
| DIT | 5 GB | 7.5 GB | Raw footage upload (legitimate) |
| Service Accounts | 100 MB | 150 MB | Automation, monitoring |

Exfiltration Indicators:

Sudden spike above threshold

Off-hours large transfers

Transfers to unknown external IPs

Compressed/encrypted outbound (can't inspect content)

### Alert Triage Decision Tree

flowchart TD
    A[Alert Received] --> B[Review Alert Details]
    B --> C{Clear Malicious?}
    
    C -->|Yes| D[True Positive]
    C -->|No| E{Clear Benign?}
    C -->|Unclear| F[Investigation Needed]
    
    D --> G[Immediate Response]
    G --> H[Containment]
    H --> I[Incident Response SOP]
    
    E --> J[False Positive]
    J --> K[Tune Correlation Rule]
    K --> L[Add Exception if Needed]
    L --> M[Document Tuning]
    
    F --> N[Gather Context]
    N --> O{Determination?}
    O -->|Malicious| D
    O -->|Benign| J
    O -->|Still Unclear| P[Escalate to Senior Analyst]

#### True Positive → Incident Response

Characteristics:

Clear indicators of malicious activity

Matches known attack patterns

Multiple corroborating alerts

Honeypot access (100% confidence)

Actions:

Immediate escalation to SOP-SEC-002

Preserve evidence (screenshots, export logs)

Begin containment

Notify IT Manager within 15 minutes

#### False Positive → Tuning Required

Common False Positives:

VPN users traveling (new location flagged)

Legitimate bulk data transfer (not previously baselined)

Scheduled maintenance activities

New application behavior

Tuning Process:

Document why alert is false positive

Adjust threshold or add exception

Test adjustment (simulate condition)

Deploy to production

Monitor for 7 days to confirm effectiveness

#### Inconclusive → Investigation Needed

Indicators:

Some suspicious elements, some benign

Activity unusual but not clearly malicious

Context missing (new user, new project, etc.)

Investigation Steps:

Check user with manager (authorized activity?)

Review related events (same time window)

Check asset inventory (is this a known system?)

Review change logs (scheduled maintenance?)

Escalate if cannot resolve within 1 hour

### Threat Intelligence Integration

#### IOC Feed Sources

| Feed Type | Source | Update Frequency | B2H Implementation |
| --- | --- | --- | --- |
| FortiGuard | Fortinet | Real-time | FortiGate integration |
| Open Source | Abuse.ch, EmergingThreats | Hourly | Splunk lookup tables |
| Industry Specific | MISP (Media sector) | Daily | Manual import |
| Internal | Previous incidents | As needed | Historical IOCs |

IOC Types Monitored:

IP addresses (command & control servers)

Domain names (phishing, malware)

File hashes (known malware)

User agents (malicious tools)

#### Automatic Blocking Decisions

| Confidence Level | IOC Type | Automatic Block? | Human Review? |
| --- | --- | --- | --- |
| High | Known C&C IP | Yes | Daily batch review |
| High | Malware hash | Yes | Daily batch review |
| Medium | Suspicious domain | No | Immediate review |
| Low | Anomalous behavior | No | Investigation |

Blocking Mechanism:

FortiGate external dynamic lists (EDL)

Splunk SOAR (Security Orchestration) integration

Manual FortiGate policy updates for high-confidence blocks

### Related SOPs

| SOP | Relationship | When to Reference |
| --- | --- | --- |
| SOP-SEC-002 | Security incidents start with SIEM alerts | When alert is true positive |
| SOP-NET-001 | FortiGate logs feed Splunk | When investigating network events |
| SOP-MON-001 | Zabbix and Splunk complement each other | When alert could be either tool |

## SOP-SEC-002: Incident Response — Enhanced

### Why This Procedure Exists

Security incidents are high-stress, time-sensitive events where clear thinking is difficult. This SOP exists to provide structured guidance when adrenaline is high and stakes are higher.

Standardized Response: Ensures all incidents handled consistently regardless of who responds.

Evidence Preservation: Proper chain of custody for potential legal proceedings.

Regulatory Compliance: Timely notification requirements for data breaches.

Learning Organization: Post-incident review prevents recurrence.

### Why 6-Phase Response Model?

#### NIST Alignment

The 6-phase model aligns with NIST SP 800-61 (Computer Security Incident Handling Guide), the industry standard for incident response:

| Phase | NIST Equivalent | Purpose | Key Output |
| --- | --- | --- | --- |
| 1. Detection & Analysis | Detection & Analysis | Identify and assess | Incident classification |
| 2. Containment | Containment | Stop the bleeding | Isolated systems |
| 3. Eradication | Eradication | Remove threat | Clean environment |
| 4. Recovery | Recovery | Restore operations | Verified systems |
| 5. Post-Incident | Post-Incident | Learn and improve | Updated procedures |
| 6. Communication | Throughout | Keep stakeholders informed | Notification records |

Why Not Simpler (3-Phase)?

Insufficient granularity for complex media industry incidents

Evidence preservation gets inadequate attention

Recovery planning merges with containment (dangerous)

Why Not More Complex (8+ Phase)?

Cognitive overload during crisis

Diminishing returns on additional phases

Current model covers all critical activities

#### Each Phase's Purpose and Outputs

Phase 1: Detection & Analysis

Purpose: Understand what happened and how bad it is

Output: Incident classification (P1-P4), affected systems list, initial timeline

Duration: Minutes to hours

Phase 2: Containment

Purpose: Prevent further damage

Output: Isolated systems, stopped services, blocked accounts

Duration: Immediate to hours

Phase 3: Eradication

Purpose: Remove all threat actor presence

Output: Clean systems, patched vulnerabilities, reset credentials

Duration: Hours to days

Phase 4: Recovery

Purpose: Return to normal operations safely

Output: Restored services, verified systems, monitoring enhanced

Duration: Hours to days

Phase 5: Post-Incident

Purpose: Learn and improve

Output: Lessons learned report, updated procedures, training

Duration: Days to weeks

#### Phase Transitions and Criteria

flowchart LR
    A[Detection] -->|Classified| B[Containment]
    B -->|Threat contained| C[Eradication]
    C -->|Threat removed| D[Recovery]
    D -->|Services restored| E[Post-Incident]
    
    B -.->|New threat discovered| A
    C -.->|Residual threat found| B
    D -.->|Re-infection detected| C

Transition Criteria Examples:

Detection → Containment: Incident confirmed (not false positive)

Containment → Eradication: No new infections in 4 hours

Eradication → Recovery: All systems verified clean

Recovery → Post-Incident: Normal operations stable for 48 hours

### Evidence Preservation Procedures

#### Memory Capture Requirements

When to Capture Memory:

Confirmed malware infection

Suspicious process activity

System compromise suspected

Before any remediation (reboot kills volatile evidence)

Tools:

Magnet RAM Capture (Windows)

LiME (Linux)

Built-in FortiAnalyzer memory dumps (FortiGate)

Storage:

Write-once media (WORM) or encrypted container

Chain of custody documentation

Hash verification (SHA-256)

#### Log Preservation

| Log Source | Retention | Export Method | Storage |
| --- | --- | --- | --- |
| FortiGate | 3 years | FortiAnalyzer export | Encrypted NAS |
| Windows Events | 3 years | Splunk export | Encrypted NAS |
| Linux Syslog | 3 years | Splunk export | Encrypted NAS |
| Application Logs | 3 years | Manual export | Encrypted NAS |

Export Procedure:

Identify relevant time window (typically 7 days before incident)

Export from Splunk in CSV and raw format

Calculate and document SHA-256 hash

Store in incident-specific folder

Maintain chain of custody log

#### Chain of Custody

| Action | Required Documentation |
| --- | --- |
| Evidence collection | Who, when, what, where, how |
| Evidence transfer | From whom, to whom, when, why |
| Evidence access | Who accessed, when, purpose |
| Evidence storage | Location, security controls |
| Evidence analysis | Tools used, findings, analyst |

### Regulatory Notification Requirements

#### When to Notify Authorities

| Regulation | Trigger | Timeline | Authority |
| --- | --- | --- | --- |
| IT Act 2000 (India) | Unauthorized access to protected system | Without delay | CERT-In |
| SPDI Rules 2011 | Personal data breach | As soon as possible | Affected individuals |
| Client Contracts | Per contract terms | Per contract | Client designated contact |

#### Customer Notification Triggers

Must Notify:

Personal data of customers compromised

Content/client materials accessed by unauthorized party

Ransomware affecting client projects

Any breach of client confidentiality agreement

May Notify (Risk-Based):

Failed attacks (no confirmed access)

Internal security incidents with no external impact

Minor policy violations

#### Timeline Requirements

| Notification Type | Standard Timeline | Accelerated Timeline |
| --- | --- | --- |
| Internal IT Management | Immediate | Immediate |
| Executive Leadership | Within 1 hour | Within 30 minutes |
| Affected Users | Within 24 hours | Within 4 hours |
| External Clients | Per contract (typically 24-72 hours) | Within 8 hours if high impact |
| Regulatory Authorities | Per regulation (typically 72 hours) | Within 24 hours for major breaches |
| Law Enforcement | As warranted | Immediately for criminal activity |

### Related SOPs

| SOP | Relationship | When to Reference |
| --- | --- | --- |
| SOP-SEC-001 | Incidents often detected via SIEM | When investigating Splunk alerts |
| SOP-NET-001 | Network containment uses FortiGate | During containment phase |
| SOP-BKP-001 | Recovery may use backups | During recovery phase |
| SOP-DR-001 | Major incidents may trigger DR | When considering site failover |

## SOP-SEC-003: ISO 27001 Audit Prep — Enhanced

### Why This Procedure Exists

ISO 27001 certification demonstrates B2H Studios' commitment to information security—a competitive differentiator and often a client requirement. This SOP ensures readiness for certification audits.

Structured Evidence Collection: Auditors need proof of control effectiveness—this SOP ensures it's ready.

Gap Identification: Regular preparation identifies missing controls before external auditors find them.

Continuous Improvement: Audit prep is not just for auditors—it's for improving security posture.

Team Readiness: Ensures all personnel know their roles during audits.

### Why ISO 27001 (Not SOC 2, PCI-DSS)?

#### Industry Relevance for Media

| Standard | Primary Focus | Media Industry Fit |
| --- | --- | --- |
| **ISO 27001** | Information Security Management | Excellent — comprehensive coverage |
| SOC 2 | Service Organization Controls | Good — but US-centric |
| PCI-DSS | Payment Card Data | Poor — not applicable to B2H |

Why ISO 27001 Over SOC 2:

International recognition (SOC 2 is US-focused)

Broader security coverage (SOC 2 focuses on trust services)

Established presence in India (many auditors available)

Client preference in media industry (international clients)

#### Client Requirement Alignment

B2H Studios client contract analysis:

60% of contracts reference "industry standard security certifications"

30% specifically mention ISO 27001

10% mention SOC 2 (typically US-based clients)

0% require PCI-DSS (no payment processing)

Certification Roadmap:

| Phase | Activity | Timeline | Cost |
| --- | --- | --- | --- |
| 1 | Gap analysis | Month 1-2 | ₹2-3 Lakhs |
| 2 | ISMS implementation | Month 3-8 | ₹5-8 Lakhs |
| 3 | Internal audit | Month 9 | ₹1-2 Lakhs |
| 4 | Stage 1 audit (documentation) | Month 10 | ₹3-4 Lakhs |
| 5 | Stage 2 audit (implementation) | Month 11-12 | ₹5-7 Lakhs |
| 6 | Certification | Month 12 | Included in Stage 2 |
| **Total** | **12 months** | **₹16-24 Lakhs** |  |

### Evidence Quality Standards

#### What Makes Evidence "Audit-Ready"

| Characteristic | Audit-Ready | Not Audit-Ready |
| --- | --- | --- |
| **Completeness** | Covers entire audit period | Partial coverage, gaps |
| **Accuracy** | Matches actual implementation | Discrepancies found |
| **Timeliness** | Current (within review period) | Outdated (expired) |
| **Accessibility** | Organized, labeled, retrievable | Scattered, unlabeled |
| **Authenticity** | Original or verified copy | Unverified, questionable origin |
| **Integrity** | Tamper-evident (hashes, signatures) | Easily modified |

#### Documentation Requirements

| Document Type | Required Elements | Example |
| --- | --- | --- |
| Policies | Version, date, owner, approval signature | Information Security Policy v2.1 |
| Procedures | Step-by-step, roles, inputs/outputs | Backup Procedure with assigned owners |
| Records | Timestamp, who performed, results | Backup log with completion times |
| Logs | System-generated, tamper-resistant | Zabbix alert history |
| Reports | Analysis, conclusions, recommendations | Quarterly access review |

#### Timestamp and Integrity Verification

For Electronic Evidence:

System-generated timestamps (not user-editable)

Digital signatures where available

Hash verification for exported data

Immutable storage (WORM or equivalent)

For Physical Evidence:

Signed and dated by responsible party

Witness signatures for critical activities

Photographic evidence where appropriate

Secure storage with access logs

### Common Auditor Questions

#### Top 10 Questions and Prepared Answers

| # | Question | Prepared Answer | Evidence Location |
| --- | --- | --- | --- |
| 1 | How do you manage access reviews? | Quarterly access reviews with manager sign-off, automated for critical systems | Access review records folder |
| 2 | How do you test backups? | Monthly file-level restore tests, quarterly full DR tests per SOP-BKP-001 | Backup test log |
| 3 | How do you track assets? | Automated discovery via Zabbix plus manual verification quarterly | Asset inventory export |
| 4 | What is your patch management process? | Monthly OS patching, quarterly firmware updates per SOP-SRV-001 | Change records, patch logs |
| 5 | How do you detect security incidents? | Splunk SIEM with correlation rules, honeypot alerts, user reporting | Splunk dashboard, incident log |
| 6 | How do you manage third-party risk? | Vendor assessment questionnaire, contract security clauses, annual reviews | Vendor assessment records |
| 7 | What is your incident response time? | P1-Critical: 15 minutes, P2-High: 1 hour per SOP-SEC-002 | Incident response records |
| 8 | How do you ensure business continuity? | Active-standby DR site, tested quarterly per SOP-DR-001 | DR test reports |
| 9 | How do you control removable media? | USB blocking via Kaspersky, exceptions by approval only | Kaspersky policy export |
| 10 | How do you manage encryption keys? | HashiCorp Vault with role-based access, key rotation quarterly | Vault audit logs |

#### Demo Preparation Checklist

| System | Demo Scenario | Prepared Evidence |
| --- | --- | --- |
| Zabbix | Show active monitoring dashboard | Last 24 hours of alerts |
| Splunk | Show SIEM correlation rules | Recent true positive alert |
| FortiGate | Show ZTNA session management | Active sessions, posture checks |
| DSM | Show snapshot and replication | Replication status, snapshot list |
| Vault | Show secret management | Demo secret (non-production) |

#### Personnel Readiness

| Role | Audit Preparation | Expected Auditor Interaction |
| --- | --- | --- |
| IT Manager | Overall ISMS knowledge | High — primary point of contact |
| Security Admin | Security controls detailed knowledge | High — deep technical questions |
| Network Admin | Network security controls | Medium — specific to network |
| System Admin | Server and backup procedures | Medium — operational questions |
| End Users | Awareness of security policies | Low — may be interviewed for awareness |

Mock Audit Schedule:

Week before external audit: Internal mock audit

Day before: Final preparation meeting

During audit: Daily debrief meetings

After audit: Immediate lessons learned

### Related SOPs

| SOP | Relationship | When to Reference |
| --- | --- | --- |
| All SOPs | Are evidence of operational controls | During audit preparation |
| SOP-BKP-001 | Backup testing is audit requirement | For A.12 backup control |
| SOP-SEC-002 | Incident response is audit requirement | For A.16 incident control |
| SOP-DR-001 | DR testing is audit requirement | For A.17 continuity control |

## SOP-USR-001: End User Guide — Enhanced

### Why This Procedure Exists

Technology is only effective if users can use it. This SOP translates complex infrastructure into simple instructions for B2H Studios employees.

Self-Service Enablement: Reduces help desk load by enabling users to solve common issues.

Security Posture: Users who understand security are less likely to fall for phishing or bypass controls.

Consistent Experience: Standardized procedures ensure all users have same experience.

Onboarding Efficiency: New employees can get productive faster with clear instructions.

### Why User Education is Critical

#### Human Firewall Concept

flowchart TD
    A[Attack Vector] --> B{Technical Control?}
    B -->|Blocks| C[Attack Stopped]
    B -->|Bypasses| D{User Awareness?}
    D -->|Recognizes| E[Attack Reported]
    D -->|Falls For| F[Breach Occurs]
    
    C --> G[Technical Defense]
    E --> H[Human Defense]
    F --> I[Incident Response]

Statistics:

90%+ of successful breaches involve human error

Phishing is #1 initial access vector

Users with 4+ hours of security training are 70% less likely to click phishing links

#### Most Common User Errors

| Error | Frequency | Impact | Prevention |
| --- | --- | --- | --- |
| Clicking phishing links | High | Credential theft, malware | Training, email filtering |
| Weak passwords | Medium | Account compromise | Password policy, manager |
| Sharing credentials | Medium | Accountability loss, unauthorized access | Training, technical controls |
| Unattended unlocked computers | Medium | Unauthorized access | Auto-lock policy, training |
| Using personal USB drives | Low | Malware introduction | USB blocking, training |

#### Impact of Mistakes

| Mistake Type | Potential Impact | Recovery Time | Cost |
| --- | --- | --- | --- |
| Ransomware via phishing | All files encrypted | 3-7 days | ₹50L-2Cr |
| Credential compromise | Data breach, unauthorized access | Days to detect | Legal, reputational |
| Accidental deletion | Project file loss | Hours to restore | Productivity loss |
| Incorrect ZTNA use | Cannot work remotely | Minutes to hours | Productivity loss |

### Self-Service Troubleshooting

#### What Users Can Fix Themselves

| Issue | Self-Service Solution | Time to Fix |
| --- | --- | --- |
| ZTNA won't connect | Check internet, restart FortiClient | 2-5 minutes |
| Slow file access | Check internet speed, close other apps | 2-5 minutes |
| Can't see NAS shares | Disconnect/reconnect ZTNA | 2 minutes |
| Wi-Fi won't connect | Forget network, reconnect | 3 minutes |
| Posture check fails | Run Windows Update, update Kaspersky | 10-30 minutes |

#### When to Call IT (Decision Tree)

flowchart TD
    A[Problem Occurs] --> B[Try Self-Service?]
    B -->|No| C[Call IT Immediately]
    B -->|Yes| D[Self-Service Steps]
    
    D --> E{Resolved?}
    E -->|Yes| F[Continue Working]
    E -->|No| G{Impact Level?}
    
    G -->|Can't work at all| H[P1 - Call IT Now]
    G -->|Workaround exists| I[P2 - Open Ticket]
    G -->|Minor inconvenience| J[P3 - Open Ticket]
    
    C --> K[IT Responds]
    H --> K
    I --> K
    J --> K

Expected Response Times:

| Priority | Issue Type | Response Time | Resolution Target |
| --- | --- | --- | --- |
| P1 | Cannot work, deadline impact | 15 minutes | 1 hour |
| P2 | Workaround exists, but painful | 1 hour | 4 hours |
| P3 | Minor issue, not blocking | 4 hours | 1 day |

### Security Awareness Reminders

#### Phishing Red Flags

| Red Flag | Example | What To Do |
| --- | --- | --- |
| Urgent/scary language | "Your account will be deleted!" | Pause, verify through official channel |
| Suspicious sender | "amazon-security.com" vs "amazon.com" | Check email address carefully |
| Generic greeting | "Dear Customer" vs your name | Legitimate emails use your name |
| Unexpected attachments | Invoice you didn't expect | Don't open — verify first |
| Links to unfamiliar sites | Hover to see actual URL | Don't click suspicious links |
| Requests for credentials | "Verify your password" | No legitimate service does this |

B2H Studios Policy:

Forward suspicious emails to security@b2hstudios.com

When in doubt, call IT (don't click)

Report even if you already clicked (no punishment for reporting)

#### Password Hygiene

| Practice | Why It Matters | B2H Requirement |
| --- | --- | --- |
| Unique passwords per site | Prevents credential stuffing | Password manager required |
| Complex passwords | Harder to crack | 12+ characters, mixed case, numbers, symbols |
| No password sharing | Accountability | Sharing is policy violation |
| MFA use | Second factor protection | FortiToken required for ZTNA |
| No browser saving | Browser vulnerabilities | Use password manager instead |

#### Physical Security

| Practice | Why It Matters | B2H Requirement |
| --- | --- | --- |
| Lock computer when away | Prevents unauthorized access | Auto-lock after 5 minutes |
| Secure laptop transport | Prevent theft | Never leave unattended in public |
| Clean desk policy | Prevent information leakage | Secure documents when away |
| Tailgating awareness | Prevent unauthorized entry | Challenge strangers without badges |
| Report lost badge | Prevent unauthorized access | Report within 1 hour |

### Related SOPs

| SOP | Relationship | When to Reference |
| --- | --- | --- |
| SOP-NET-003 | Users connect to Wi-Fi | When Wi-Fi issues occur |
| SOP-NET-001 | Users connect via ZTNA | When ZTNA issues occur |
| SOP-SEC-002 | Users report security incidents | When user reports suspicious activity |

## Mandatory Flow Charts

### 1. SOP Execution Flow (Generic)

flowchart LR
    Start[Start SOP] --> Check{Pre-reqs Met?}
    Check -->|No| Prep[Complete Prep]
    Check -->|Yes| Execute[Execute Steps]
    Prep --> Execute
    Execute --> Verify{Verification?}
    Verify -->|Pass| Complete[Complete]
    Verify -->|Fail| Escalate[Escalate]
    Complete --> Document[Document]
    Escalate --> Document

### 2. Alert Response Decision Tree

flowchart TD
    Alert[Alert Received] --> Ack[Acknowledge]
    Ack --> Classify{Severity?}
    Classify -->|P1| P1[15min Response]
    Classify -->|P2| P2[1hr Response]
    Classify -->|P3| P3[4hr Response]
    Classify -->|P4| P4[Next Day]
    P1 & P2 & P3 & P4 --> Resolve[Attempt Resolution]
    Resolve -->|Success| Close[Close Alert]
    Resolve -->|Fail| Esc[Escalate]

### 3. Patching Decision Flow

flowchart TD
    Patch[Patch Available] --> Sev{Severity?}
    Sev -->|Critical| Emerg[Emergency Change]
    Sev -->|High| Plan[Schedule Within 7d]
    Sev -->|Medium| Normal[Next Maintenance]
    Emerg & Plan & Normal --> Test[Test in Lab]
    Test -->|Pass| Deploy[Deploy to Prod]
    Test -->|Fail| Delay[Delay & Investigate]

### 4. Backup Verification Flow

flowchart LR
    Backup[Backup Complete] --> Verify{Verify?}
    Verify -->|Automated| Auto[Check Logs]
    Verify -->|Manual| Restore[Test Restore]
    Auto -->|Pass| Log[Log Success]
    Auto -->|Fail| Alert[Alert Admin]
    Restore -->|Success| Log
    Restore -->|Fail| Escalate[Escalate]

### 5. DR Failover Decision Flow

flowchart TD
    Issue[Site A Issue] --> Assess{Severity?}
    Assess -->|Minor| Monitor[Monitor]
    Assess -->|Major| Stake[Notify Stakeholders]
    Stake --> Approve{Approval?}
    Approve -->|Yes| Failover[Execute Failover]
    Approve -->|No| Wait[Wait & Monitor]
    Failover --> Verify[Verify Site B]

## Document Control

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | March 22, 2026 | VConfi Solutions | Initial release |
| 2.0 | March 22, 2026 | VConfi Solutions | Enhanced edition with detailed reasoning, decision trees, and flowcharts |

### Approval

| Role | Name | Date | Signature |
| --- | --- | --- | --- |
| IT Manager |  |  |  |
| Security Officer |  |  |  |
| Operations Manager |  |  |  |

### Distribution

IT Operations Team

Security Team

All B2H Studios Employees (SOP-USR-001)

VConfi Support Team

Audit Team (as required)

End of Part 6: Enhanced Standard Operating Procedures