VConfi Solutions

IT Infrastructure Solutions

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Implementation Plan

IT Infrastructure Solution - Option B+

| Client: | B2H Studios |
| --- | --- |
| Prepared By: | VConfi Solutions Team |
| Date: | March 22, 2026 |
| Classification: | CONFIDENTIAL |

# Table of Contents

This document contains the complete implementation plan. Refer to the section headings for navigation.

Right-click and select 'Update Field' to populate the Table of Contents

Part 1: Executive Summary, Architecture & ISO Compliance

# B2H Studios — IT Infrastructure Implementation Plan

## Part 1: Executive Summary, Architecture & ISO Compliance

Document Information

Client: B2H Studios

Industry: Media & Entertainment — Post-Production

Solution: Option B+ (Optimized Synology HD6500)

Document Version: 1.0

Date: March 22, 2026

Prepared by: VConfi Solutions

Classification: CONFIDENTIAL

# 1. Document Control

## 1.1 Version History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 0.1 | March 15, 2026 | VConfi Solutions | Initial draft based on client requirements gathering |
| 0.2 | March 18, 2026 | VConfi Solutions | Added architecture diagrams and VLAN design |
| 0.3 | March 20, 2026 | VConfi Solutions | Incorporated ISO 27001 compliance mapping |
| 1.0 | March 22, 2026 | VConfi Solutions | Final review and approval release |

## 1.2 Approval Signatures

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Solutions Architect | VConfi Solutions | [Digital Signature] | March 22, 2026 |
| IT Director (Client) | B2H Studios | _________________ | _______________ |
| Project Sponsor (Client) | B2H Studios | _________________ | _______________ |
| CISO / Security Lead | VConfi Solutions | [Digital Signature] | March 22, 2026 |

## 1.3 Distribution List

| Role | Organization | Purpose |
| --- | --- | --- |
| IT Director | B2H Studios | Primary recipient — implementation oversight |
| Project Sponsor | B2H Studios | Budget approval and strategic decisions |
| Finance Controller | B2H Studios | Payment authorization and TCO validation |
| Operations Manager | B2H Studios | Day-to-day operational planning |
| Solutions Architect | VConfi Solutions | Technical authority and escalation point |
| Project Manager | VConfi Solutions | Delivery coordination |
| Security Lead | VConfi Solutions | Compliance verification |
| Network Engineer | VConfi Solutions | Implementation execution |
| System Administrator | B2H Studios | Knowledge transfer and handover |

# 2. Executive Summary

## 2.1 Client Overview

B2H Studios is a Media & Entertainment post-production studio specializing in high-resolution video editing and content creation. With a team of 25 employees operating in a remote/hybrid model, the studio requires a robust, secure, and scalable IT infrastructure to support their proxy-first editing workflow.

### Current Challenges Addressed

Ransomware Risk: Previous concerns about data integrity and malicious encryption

Unpredictable Cloud Costs: Egress fee volatility affecting budget planning

Storage Complexity: Fragmented storage systems creating management overhead

Remote Access: Need for secure, high-performance access for distributed team

## 2.2 Selected Solution: Option B+ (Optimized Synology HD6500)

After comprehensive analysis of requirements, budget constraints, and growth projections, VConfi Solutions recommends Option B+ — an optimized Synology HD6500-based infrastructure with enhanced SSD cache and 25GbE upgrade path.

### Key Solution Highlights

| Feature | Specification |
| --- | --- |
| **Primary Storage** | Synology HD6500 (60-bay enterprise NAS) |
| **Total Capacity per Site** | 936TB usable (1,080TB raw, RAID6 56+4) |
| **NVMe Cache** | 30.72TB (4x 7.68TB SSDs) per site |
| **Deployment Model** | Site A (Primary) + Site B (DR) — Active-Standby |
| **Network Core** | HPE Aruba CX 6300M with VSX stacking |
| **Security Perimeter** | FortiGate 120G HA pair with SD-WAN |
| **Remote Access** | Zero Trust Network Access (ZTNA) — NO traditional VPN |
| **Cloud Tiering** | Wasabi Hot Cloud with zero egress fees |
| **Immutability** | Snapshot Lock for ransomware protection |

## 2.3 Investment Summary

| Financial Metric | Amount (INR) |
| --- | --- |
| **Total Initial Investment** | ₹2,04,03,994 (~₹2.04 Crore) |
| **Annual Operating Cost (Year 1)** | ₹19,79,520 |
| **5-Year Total Cost of Ownership** | ~₹3.4 Crore |
| **Cost per Employee (Initial)** | ₹8,16,160 |
| **Cost per TB (Usable)** | ₹21,795 |

### Investment Justification

The Option B+ solution delivers enterprise-grade capabilities at 18% of the cost of competing solutions (e.g., Dell PowerScale F710 at ₹12.28 Crore). The 5-year TCO includes all hardware, software subscriptions, cloud storage, professional services, and support contracts.

## 2.4 Strategic Benefits

Ransomware Immunity: Immutable snapshots with WORM (Write Once Read Many) protection ensure data cannot be encrypted by malicious actors

Zero Egress Costs: Wasabi Hot Cloud integration eliminates unpredictable cloud egress fees — critical for media workflows with large file transfers

15-Minute RPO: Real-time replication between Site A and Site B ensures minimal data loss in disaster scenarios

ZTNA Security: Modern zero-trust remote access replaces legacy VPN with device posture validation and least-privilege access

ISO 27001 Ready: Infrastructure designed to meet ISO 27001:2022 controls from day one

# 3. Architecture Overview

## 3.1 High-Level Design Description

The B2H Studios infrastructure implements a dual-site, active-standby architecture designed for high availability, disaster recovery, and secure remote access. The solution leverages enterprise-grade components while maintaining operational simplicity appropriate for a 25-user environment.

### Site A — Primary Data Centre

Site A serves as the primary production environment hosting all active workloads, user data, and application services. It is equipped with full redundancy at the network, storage, and power layers.

### Site B — Disaster Recovery Site

Site B operates in standby mode, receiving continuous replication from Site A. In the event of Site A failure, Site B can assume production responsibilities within 10 minutes (RTO target).

### Key Architectural Principles

Defense in Depth: Multiple security layers — perimeter firewall, network segmentation, endpoint protection, and data immutability

redundancy by Design: No single point of failure at Site A; automatic failover to Site B

Simplicity: Synology DSM management reduces operational overhead compared to enterprise storage platforms

Future-Proof: 25GbE upgrade path and 1.5PB maximum capacity accommodate 5+ years of growth

## 3.2 Full Network Topology Diagram

flowchart TB
    subgraph Internet["Internet / WAN"]
        ISP1["ISP 1<br/>Primary Link"]
        ISP2["ISP 2<br/>Secondary Link"]
    end

    subgraph SiteA["Site A — Primary Data Centre"]
        subgraph FGHA["FortiGate 120G HA Pair"]
            FG1["FortiGate 120G-1<br/>Active"]
            FG2["FortiGate 120G-2<br/>Passive"]
            FG1 <-->|"HA Sync<br/>Heart-beat"| FG2
        end

        subgraph CoreA["HPE Aruba CX 6300M VSX Stack"]
            SW1["Switch-1<br/>6300M-1"]
            SW2["Switch-2<br/>6300M-2"]
            SW1 <-->|"VSX Stack<br/>ISL Links"| SW2
        end

        subgraph ServersA["Application Servers"]
            R760A["Dell R760<br/>VM Host"]
            subgraph VMsA["Virtual Machines"]
                Signiant["Signiant SDCX<br/>Jet v7.0"]
                FortiAnalyzer["FortiAnalyzer<br/>Log Collection"]
                FortiAuth["FortiAuthenticator<br/>MFA/RADIUS"]
                Vault["HashiCorp Vault<br/>Secrets Management"]
                EMS["FortiClient EMS<br/>Endpoint Mgmt"]
                Kaspersky["Kaspersky SC<br/>Antivirus"]
            end
            R760A --> VMsA
        end

        subgraph StorageA["Primary Storage"]
            HD6500A["Synology HD6500<br/>Site A<br/>936TB Usable"]
            SSDCacheA["NVMe Cache<br/>30.72TB"]
            HD6500A <-->|"SSD Cache<br/>Acceleration"| SSDCacheA
        end

        subgraph PowerA["Power Infrastructure"]
            UPS1A["UPS 1<br/>APC SRT 10kVA"]
            UPS2A["UPS 2<br/>APC SRT 10kVA"]
            ATSA["Rack ATS"]
            UPS1A --> ATSA
            UPS2A --> ATSA
        end

        FG1 & FG2 -->|"10GbE<br/>Trunk"| CoreA
        CoreA -->|"VLAN 10/20/30/40"| ServersA
        CoreA -->|"VLAN 30 Storage"| StorageA
        ATSA --> PowerADevices["Critical Equipment"]
    end

    subgraph SiteB["Site B — Disaster Recovery"]
        subgraph FGHAB["FortiGate 120G HA Pair"]
            FG1B["FortiGate 120G-1<br/>Active"]
            FG2B["FortiGate 120G-2<br/>Passive"]
            FG1B <-->|"HA Sync"| FG2B
        end

        subgraph CoreB["HPE Aruba CX 6300M VSX Stack"]
            SW1B["Switch-1<br/>6300M-1"]
            SW2B["Switch-2<br/>6300M-2"]
            SW1B <-->|"VSX Stack"| SW2B
        end

        subgraph ServersB["DR Application Server"]
            R760B["Dell R760 (Light)<br/>DR VM Host"]
        end

        subgraph StorageB["DR Storage"]
            HD6500B["Synology HD6500<br/>Site B<br/>936TB Usable"]
            SSDCacheB["NVMe Cache<br/>30.72TB"]
            HD6500B <-->|"SSD Cache"| SSDCacheB
        end

        subgraph PowerB["Power Infrastructure"]
            UPS1B["UPS 1<br/>APC SRT 10kVA"]
            UPS2B["UPS 2<br/>APC SRT 10kVA"]
            ATSB["Rack ATS"]
            UPS1B --> ATSB
            UPS2B --> ATSB
        end

        FG1B & FG2B -->|"10GbE<br/>Trunk"| CoreB
        CoreB -->|"VLAN 10/20/30/40"| ServersB
        CoreB -->|"VLAN 30 Storage"| StorageB
    end

    subgraph Cloud["Cloud Services"]
        Wasabi["Wasabi Hot Cloud<br/>s3.ap-southeast-1<br/>Archive Tier"]
        ZTNA["FortiGate ZTNA<br/>Remote Access Portal"]
    end

    subgraph RemoteUsers["Remote Users"]
        Editors["Video Editors<br/>FortiClient ZTNA"]
        Admin["IT Admins<br/>Secure Access"]
    end

    ISP1 -->|"Primary WAN"| FG1
    ISP2 -->|"Secondary WAN<br/>SD-WAN"| FG2
    ISP1 -->|"Primary WAN"| FG1B
    ISP2 -->|"Secondary WAN"| FG2B

    HD6500A -.->|"Replication<br/>RPO: 15 min"| HD6500B
    SiteA -.->|"Hybrid Share<br/>Cloud Tiering"| Wasabi
    SiteB -.->|"Hybrid Share<br/>Cloud Tiering"| Wasabi

    RemoteUsers -->|"ZTNA<br/>TLS 1.3"| ZTNA
    ZTNA -->|"Encrypted Tunnel"| FG1

    style SiteA fill:#e1f5ff,stroke:#01579b,stroke-width:2px
    style SiteB fill:#fff3e0,stroke:#e65100,stroke-width:2px
    style Internet fill:#f5f5f5,stroke:#616161,stroke-width:1px
    style Cloud fill:#e8f5e9,stroke:#2e7d32,stroke-width:1px
    style RemoteUsers fill:#f3e5f5,stroke:#6a1b9a,stroke-width:1px

## 3.3 VLAN Segmentation Diagram

flowchart TB
    subgraph FortiGate["FortiGate 120G — Zone Firewall"]
        direction TB
        WAN["WAN Zone<br/>ISP1 + ISP2<br/>Untrusted"]
        DMZ["DMZ Zone<br/>VLAN 10<br/>Semi-Trusted"]
        INTERNAL["Internal Zone<br/>VLAN 20 + 30<br/>Trusted"]
        MGMT["Management Zone<br/>VLAN 40<br/>Restricted"]
        GUEST["Guest Zone<br/>VLAN 50<br/>Untrusted"]
    end

    subgraph DMZ_VLAN["VLAN 10 — DMZ (10.10.10.0/24)"]
        DMZ_Services["Ingest Services<br/>Signiant SDCX<br/>Public-Facing APIs"]
    end

    subgraph PROD_VLAN["VLAN 20 — Production (10.10.20.0/24)"]
        Workstations["Editor Workstations<br/>Admin Desktops<br/>ZTNA Clients"]
    end

    subgraph STORAGE_VLAN["VLAN 30 — Storage (10.10.30.0/24)"]
        NAS["Synology HD6500<br/>NFS / SMB Shares<br/>iSCSI Targets"]
    end

    subgraph MGMT_VLAN["VLAN 40 — Management (10.10.40.0/24)"]
        MGMT_Devices["OOB Management<br/>iLO / IPMI<br/>DSM Admin<br/>Switch Console"]
    end

    subgraph GUEST_VLAN["VLAN 50 — Guest (10.10.50.0/24)"]
        Guest_WiFi["Guest Wi-Fi<br/>Visitors / Contractors<br/>Internet Only"]
    end

    WAN -->|"Stateful Inspection<br/>IPS/AV"| DMZ
    WAN -->|"ZTNA Access"| INTERNAL
    DMZ -->|"Controlled Access<br/>Port 2049, 445"| INTERNAL
    INTERNAL -->|"Storage Traffic<br/>Jumbo Frames"| STORAGE_VLAN
    INTERNAL -.->|"Admin Access<br/>HTTPS/SSH"| MGMT_VLAN
    DMZ -.->|"Monitoring"| MGMT_VLAN
    GUEST -->|"Internet Only<br/>No Internal Access"| WAN

    style WAN fill:#ffcdd2,stroke:#c62828
    style DMZ fill:#fff9c4,stroke:#f57f17
    style INTERNAL fill:#c8e6c9,stroke:#2e7d32
    style MGMT fill:#e1bee7,stroke:#6a1b9a
    style GUEST fill:#ffe0b2,stroke:#e65100

## 3.4 Firewall Zone Architecture

flowchart LR
    subgraph Zones["FortiGate Security Zones"]
        direction TB
        
        subgraph Untrusted["Untrusted Security Level: 0"]
            WAN["WAN<br/>Internet-facing<br/>ISP1/ISP2"]
            GUEST_ZONE["GUEST<br/>Visitor Access"]
        end
        
        subgraph SemiTrusted["Semi-Trusted Security Level: 50"]
            DMZ_ZONE["DMZ<br/>Public Services<br/>VLAN 10"]
        end
        
        subgraph Trusted["Trusted Security Level: 100"]
            INTERNAL_ZONE["INTERNAL<br/>Corporate Network<br/>VLAN 20/30"]
        end
        
        subgraph Restricted["Restricted Security Level: 100+"]
            MGMT_ZONE["MANAGEMENT<br/>Infrastructure Control<br/>VLAN 40"]
        end
    end

    WAN -->|"Default Deny<br/>Allow: ZTNA, HTTPS"| DMZ_ZONE
    WAN -->|"ZTNA Only"| INTERNAL_ZONE
    DMZ_ZONE -->|"Allow: NFS(2049)<br/>SMB(445) to VLAN 30"| INTERNAL_ZONE
    INTERNAL_ZONE -->|"Admin Access<br/>HTTPS/SSH"| MGMT_ZONE
    GUEST_ZONE -->|"Internet Only<br/>DNS, HTTPS"| WAN
    GUEST_ZONE -.->|"DENY All"| INTERNAL_ZONE
    GUEST_ZONE -.->|"DENY All"| DMZ_ZONE
    GUEST_ZONE -.->|"DENY All"| MGMT_ZONE

    style WAN fill:#ffcdd2,stroke:#b71c1c,stroke-width:2px
    style GUEST_ZONE fill:#ffcdd2,stroke:#b71c1c,stroke-width:2px
    style DMZ_ZONE fill:#fff59d,stroke:#f57f17,stroke-width:2px
    style INTERNAL_ZONE fill:#a5d6a7,stroke:#1b5e20,stroke-width:2px
    style MGMT_ZONE fill:#ce93d8,stroke:#4a148c,stroke-width:2px

## 3.5 Data Flow Description

### 3.5.1 Media Ingest Workflow (DIT → Storage)

External Source: Camera/DIT team uploads raw footage via Signiant Jet using FASP protocol

DMZ Processing: Signiant SDCX Server (VLAN 10) receives encrypted UDP traffic on port 33001

Integrity Verification: SHA-256 checksums validate file integrity during transfer

Storage Write: Verified files written to Synology HD6500 (VLAN 30) via 10GbE NFS

SSD Cache: Hot project files cached on 30.72TB NVMe tier for accelerated access

Replication: Active project folders replicate to Site B within 15 minutes (RPO)

Cloud Tiering: Completed projects older than 90 days tiered to Wasabi via Hybrid Share

### 3.5.2 Editor Access Workflow (Remote → Proxy Editing)

ZTNA Connection: Editor launches FortiClient with TPM-backed certificate

Posture Check: FortiGate validates — Kaspersky active, OS patched, disk encrypted

MFA Challenge: FortiAuthenticator sends push notification via FortiToken

Secure Tunnel: TLS 1.3 encrypted tunnel established, no traditional VPN subnet

Least Privilege: Editor receives access ONLY to assigned project folders on NAS

Proxy Editing: Editor works on local proxy files; originals remain on NAS

Session Logging: All access logged to FortiAnalyzer with 90-day retention

### 3.5.3 DR Failover Workflow (Site A → Site B)

Failure Detection: Zabbix monitoring triggers alert when Site A becomes unreachable

Replication Pause: Last consistent snapshot identified (maximum 15-minute data loss)

Site B Promotion: Synology Replication Manager promotes Site B NAS to primary

ZTNA Update: FortiGate ZTNA profiles updated to point to Site B IP addresses

DNS Update (if applicable): External DNS records updated to Site B WAN IPs

User Notification: Editors reconnect via FortiClient (automatic re-authentication)

Recovery Time: Target RTO of 10 minutes from failure detection to service restoration

# 4. VLAN Design

## 4.1 VLAN Allocation Table

| VLAN ID | Name | Purpose | CIDR | Gateway | DHCP Range |
| --- | --- | --- | --- | --- | --- |
| 10 | DMZ | Media ingest, external-facing services, Signiant SDCX server | 10.10.10.0/24 | 10.10.10.1 | 10.10.10.100 — 10.10.10.200 |
| 20 | Production | Employee workstations, ZTNA clients, editing workstations | 10.10.20.0/24 | 10.10.20.1 | 10.10.20.100 — 10.10.20.200 |
| 30 | Storage | NAS shares, NFS/SMB traffic, iSCSI storage network | 10.10.30.0/24 | 10.10.30.1 | Static allocation only |
| 40 | Management | Device management, iLO/IPMI out-of-band, switch console | 10.10.40.0/24 | 10.10.40.1 | Static allocation only |
| 50 | Guest | Guest Wi-Fi access, visitor internet connectivity | 10.10.50.0/24 | 10.10.50.1 | 10.10.50.100 — 10.10.50.200 |

## 4.2 VLAN Configuration Notes

### VLAN 10 — DMZ

Security Level: Semi-trusted

Inter-VLAN Routing: Limited access to VLAN 30 (Storage) only

Services Hosted: Signiant SDCX Server, Aspera fallback, external APIs

Firewall Policy: Allow inbound from WAN on ports 33001 (FASP), 443 (HTTPS); deny all else

### VLAN 20 — Production

Security Level: Trusted

Primary Users: 25 employees with FortiClient ZTNA

Access Rights: NAS shares via SMB/NFS, internet access, internal services

Firewall Policy: Allow to VLAN 30, VLAN 40 (management ports only), WAN; deny to VLAN 10

### VLAN 30 — Storage

Security Level: Trusted — Critical Asset

MTU Configuration: 9000 (Jumbo Frames enabled)

Protocols: NFSv4.1 (port 2049), SMB 3.1.1 (port 445), iSCSI (port 3260)

Access Control: Restricted to VLAN 20 (Production) and VLAN 10 (DMZ — read-only)

### VLAN 40 — Management

Security Level: Restricted

Access Method: Jump host or dedicated management workstation only

Protocols: HTTPS (443), SSH (22), SNMP v3 (161), IPMI (623)

Firewall Policy: Deny all inbound from VLAN 20/50; allow from designated admin IPs only

### VLAN 50 — Guest

Security Level: Untrusted

Isolation: Complete Layer 3 isolation from all other VLANs

Bandwidth Limit: 50 Mbps per client, 200 Mbps aggregate

Session Timeout: 8 hours maximum

# 5. IP Addressing Scheme

## 5.1 Site A — Primary Data Centre IP Allocation

| Device | Hostname | VLAN | IP Address | Purpose |
| --- | --- | --- | --- | --- |
| FortiGate 120G | FG-A-001 | WAN/HA | 203.XX.XX.10 | Primary firewall — active unit |
| FortiGate 120G | FG-A-002 | WAN/HA | 203.XX.XX.11 | Secondary firewall — passive unit |
| FortiGate Cluster | FG-A-VIP | WAN | 203.XX.XX.9 | Shared virtual IP (HA) |
| FortiGate | FG-A-INT | Internal | 10.10.10.1/20/30/40/50 | Internal VLAN gateways |
| HPE Switch | SW-A-001 | Management | 10.10.40.2 | Core switch 1 — VSX primary |
| HPE Switch | SW-A-002 | Management | 10.10.40.3 | Core switch 2 — VSX secondary |
| HPE VSX Cluster | SW-A-VIP | Management | 10.10.40.4 | VSX virtual switch IP |
| Synology HD6500 | NAS-A-001 | Storage | 10.10.30.10 | Primary NAS — controller 1 |
| Synology HD6500 | NAS-A-002 | Storage | 10.10.30.11 | Primary NAS — controller 2 (HA) |
| Synology HD6500 | NAS-A-VIP | Storage | 10.10.30.9 | NAS cluster virtual IP |
| Dell R760 | SRV-A-001 | Production | 10.10.20.10 | Application server — hypervisor |
| Dell R760 iLO | SRV-A-001-ILO | Management | 10.10.40.10 | Out-of-band management |
| Signiant VM | VM-A-SIG | DMZ | 10.10.10.10 | Signiant SDCX Server |
| FortiAnalyzer VM | VM-A-FAZ | Management | 10.10.40.20 | Log aggregation and SIEM |
| FortiAuthenticator VM | VM-A-FAC | Management | 10.10.40.21 | MFA and RADIUS server |
| FortiClient EMS VM | VM-A-EMS | Management | 10.10.40.22 | Endpoint management |
| HashiCorp Vault VM | VM-A-VLT | Production | 10.10.20.20 | Secrets management |
| Kaspersky SC VM | VM-A-KSC | Management | 10.10.40.23 | Antivirus management |
| APC UPS 1 | UPS-A-001 | Management | 10.10.40.30 | Primary UPS — SNMP monitoring |
| APC UPS 2 | UPS-A-002 | Management | 10.10.40.31 | Secondary UPS — SNMP monitoring |
| APC ATS | ATS-A-001 | Management | 10.10.40.32 | Automatic transfer switch |

## 5.2 Site B — Disaster Recovery Site IP Allocation

| Device | Hostname | VLAN | IP Address | Purpose |
| --- | --- | --- | --- | --- |
| FortiGate 120G | FG-B-001 | WAN/HA | 204.XX.XX.10 | DR firewall — active unit |
| FortiGate 120G | FG-B-002 | WAN/HA | 204.XX.XX.11 | DR firewall — passive unit |
| FortiGate Cluster | FG-B-VIP | WAN | 204.XX.XX.9 | Shared virtual IP (HA) |
| FortiGate | FG-B-INT | Internal | 10.20.10.1/20/30/40/50 | Internal VLAN gateways |
| HPE Switch | SW-B-001 | Management | 10.20.40.2 | Core switch 1 — VSX primary |
| HPE Switch | SW-B-002 | Management | 10.20.40.3 | Core switch 2 — VSX secondary |
| HPE VSX Cluster | SW-B-VIP | Management | 10.20.40.4 | VSX virtual switch IP |
| Synology HD6500 | NAS-B-001 | Storage | 10.20.30.10 | DR NAS — controller 1 |
| Synology HD6500 | NAS-B-002 | Storage | 10.20.30.11 | DR NAS — controller 2 (HA) |
| Synology HD6500 | NAS-B-VIP | Storage | 10.20.30.9 | NAS cluster virtual IP |
| Dell R760 (Light) | SRV-B-001 | Production | 10.20.20.10 | DR application server |
| Dell R760 iLO | SRV-B-001-ILO | Management | 10.20.40.10 | Out-of-band management |
| APC UPS 1 | UPS-B-001 | Management | 10.20.40.30 | Primary UPS — SNMP monitoring |
| APC UPS 2 | UPS-B-002 | Management | 10.20.40.31 | Secondary UPS — SNMP monitoring |
| APC ATS | ATS-B-001 | Management | 10.20.40.32 | Automatic transfer switch |

## 5.3 Reserved IP Ranges

| Range | Purpose |
| --- | --- |
| X.X.X.1 — X.X.X.9 | Network infrastructure (gateways, VIPs) |
| X.X.X.10 — X.X.X.49 | Servers and storage systems |
| X.X.X.50 — X.X.X.99 | Network devices (switches, firewalls, load balancers) |
| X.X.X.100 — X.X.X.199 | DHCP client pool (workstations, temporary devices) |
| X.X.X.200 — X.X.X.249 | Reserved for future expansion |
| X.X.X.250 — X.X.X.254 | Management and monitoring systems |
| X.X.X.255 | Broadcast address |

# 6. ISO 27001:2022 Compliance Mapping

## 6.1 Compliance Overview

The B2H Studios infrastructure has been designed to align with ISO 27001:2022 controls, providing a robust information security management framework from day one. The following mapping demonstrates how each implemented control satisfies specific ISO 27001 requirements.

## 6.2 Organizational Controls (A.5)

| Control | Name | Implementation Detail | Status |
| --- | --- | --- | --- |
| A.5.1 | Policies for Information Security | Comprehensive information security policies documented in SOP-SEC-001 covering acceptable use, data classification, access control, and incident response. Policies reviewed and approved by B2H Studios management. | Implemented |
| A.5.2 | Information Security Roles and Responsibilities | RACI matrix defined for IT Director, System Administrators, Security Lead, and End Users. Security responsibilities embedded in job descriptions. | Implemented |
| A.5.3 | Segregation of Duties | Administrative duties split — network management (VConfi), storage management (B2H admin), security monitoring (shared). No single individual has unrestricted access. | Implemented |
| A.5.4 | Management Responsibilities | Monthly security review meetings scheduled. Management commits to resource allocation for security controls. | Client Responsibility |
| A.5.5 | Contact with Special Interest Groups | VConfi maintains membership in Fortinet NSE community and ISACA for threat intelligence sharing. | Implemented |
| A.5.6 | Information Security in Project Management | Security requirements embedded in all project phases — design, procurement, implementation, and handover. Security sign-off required at each gate. | Implemented |
| A.5.7 | Threat Intelligence | FortiGuard threat intelligence feeds integrated into FortiGate 120G. Daily automatic updates for IPS signatures, AV definitions, and geolocation data. | Implemented |
| A.5.8 | Information Security in Project Management | Same as A.5.6 — security gates at design review, procurement approval, implementation test, and final acceptance. | Implemented |
| A.5.9 | Inventory of Information and Other Associated Assets | Zabbix automated discovery maintains real-time inventory of all network devices, servers, and storage systems. Asset tags assigned to all hardware. | Implemented |
| A.5.10 | Acceptable Use of Information and Other Associated Assets | Acceptable Use Policy (AUP) documented in SOP-SEC-001. All employees acknowledge policy during onboarding. | Client Responsibility |
| A.5.11 | Return of Assets | Asset return procedure documented. Exit checklist includes IT asset collection verification. | Client Responsibility |
| A.5.12 | Classification of Information | Data classification scheme defined: Public, Internal, Confidential, Restricted. NAS folder structure enforces classification via access controls. | Implemented |
| A.5.13 | Labeling of Information | Digital labels applied to file shares. Physical media (if used) labeled with classification stickers. | Implemented |
| A.5.14 | Information Transfer | Secure file transfer via Signiant Jet with FASP protocol and SHA-256 verification. Email DLP configured on FortiGate. | Implemented |
| A.5.15 | Access Control | Role-based access control (RBAC) implemented via Active Directory. ZTNA enforces least-privilege access. | Implemented |
| A.5.16 | Identity Management | Centralized identity management via Active Directory with FortiAuthenticator for MFA. Unique user IDs for all accounts. | Implemented |
| A.5.17 | Authentication Information | Password policy enforced — minimum 12 characters, complexity requirements, 90-day rotation. MFA required for all remote access and privileged accounts. | Implemented |
| A.5.18 | Access Rights | Quarterly access reviews scheduled. Privileged access requires manager approval. Automated provisioning/deprovisioning via AD groups. | Client Responsibility |
| A.5.19 | Information Security in Supplier Relationships | Vendor security requirements defined in contracts. VConfi maintains liability insurance and security certifications. | Implemented |
| A.5.20 | Addressing Information Security Within Supplier Agreements | Security clauses included in all vendor contracts — confidentiality, data handling, breach notification. | Implemented |
| A.5.21 | Managing Information Security in the ICT Supply Chain | Supply chain risk assessment completed. Hardware sourced from authorized distributors with chain-of-custody documentation. | Implemented |
| A.5.22 | Monitoring, Review and Change Management of Supplier Services | Annual vendor performance reviews scheduled. Security incidents tracked per vendor. | Client Responsibility |
| A.5.23 | Information Security for Use of Cloud Services | Wasabi cloud services assessed for compliance. Data encryption in transit (TLS 1.3) and at rest (AES-256). Cloud access via ZTNA only. | Implemented |
| A.5.24 | Planning and Preparation for Information Security Continuity | Business continuity plan documented. DR procedures tested quarterly. RPO: 15 minutes, RTO: 10 minutes. | Implemented |
| A.5.25 | ICT Readiness for Continuity | Site B DR infrastructure maintained in warm standby. Automated replication ensures data currency. Failover procedures documented in SOP-DR-001. | Implemented |
| A.5.26 | Information Security Aspects of Business Continuity Management | Information security integrated into BCP. Security controls maintained during DR operations. | Implemented |
| A.5.27 | Redundancy of Information Processing Facilities | Redundant components: dual FortiGate HA, dual HPE switches (VSX), dual UPS with ATS, RAID6 storage. | Implemented |
| A.5.28 | Requirements for Availability of Information Processing Systems | 99.9% availability target defined. Monitoring alerts on any degradation. SLA with vendors includes availability commitments. | Implemented |
| A.5.29 | Requirements for Verification of Delivered Software | Software integrity verified via checksums. Only signed firmware and software installed. Change management process for updates. | Implemented |
| A.5.30 | Intellectual Property Rights | License compliance tracking for all software. Open-source license inventory maintained. | Client Responsibility |
| A.5.31 | Protection of Records | Legal hold procedures documented. Retention schedules aligned with business and regulatory requirements. | Implemented |
| A.5.32 | Privacy and Protection of PII | GDPR/privacy compliance assessed. PII handling procedures documented. Data minimization practiced. | Client Responsibility |
| A.5.33 | Regulation of Cryptographic Controls | Cryptographic modules FIPS 140-2 validated where required. Key management procedures documented. | Implemented |
| A.5.34 | Independence of Information Security | Security team has independent reporting line to management. Security decisions not overridden by operational concerns. | Client Responsibility |
| A.5.35 | Identification of Legal, Statutory, Regulatory and Contractual Requirements | Legal and regulatory requirements register maintained. Compliance obligations reviewed annually. | Client Responsibility |
| A.5.36 | Intellectual Property Rights | Same as A.5.30. | Client Responsibility |
| A.5.37 | Documented Operating Procedures | Standard Operating Procedures (SOPs) documented for all critical operations — backup, DR, incident response, access management. | Implemented |

## 6.3 People Controls (A.6)

| Control | Name | Implementation Detail | Status |
| --- | --- | --- | --- |
| A.6.1 | Screening | Background verification procedures for employees with privileged access. Vendor personnel screening requirements in contracts. | Client Responsibility |
| A.6.2 | Terms and Conditions of Employment | Security responsibilities included in employment contracts. Confidentiality agreements signed by all employees. | Client Responsibility |
| A.6.3 | Information Security Awareness, Education and Training | Security awareness training program established. Phishing simulation exercises quarterly. Role-specific training for IT staff. | Client Responsibility |
| A.6.4 | Disciplinary Process | Disciplinary procedures for security violations defined. Progressive discipline approach documented in HR policy. | Client Responsibility |
| A.6.5 | Responsibilities After Termination or Change of Employment | Exit procedures include access revocation checklist. Knowledge transfer requirements documented. | Client Responsibility |
| A.6.6 | Confidentiality or Non-Disclosure Agreements | NDAs required for all employees, contractors, and vendors with access to sensitive information. | Client Responsibility |
| A.6.7 | Remote Working | Remote work policy documented. ZTNA enforces secure access from any location. Device security requirements defined. | Implemented |
| A.6.8 | Information Security Event Reporting | Security incident reporting procedure documented. Employees trained to report suspicious activity to security@b2hstudios.com. | Client Responsibility |

## 6.4 Physical Controls (A.7)

| Control | Name | Implementation Detail | Status |
| --- | --- | --- | --- |
| A.7.1 | Physical Security Perimeters | Data center located in secure building. Server room with controlled access. Security cameras covering entry points. | Implemented |
| A.7.2 | Physical Entry Controls | Biometric + card access control for server room. Visitor log maintained. Escort required for all visitors. | Client Responsibility |
| A.7.3 | Securing Offices, Rooms and Facilities | Server room secured with reinforced door, rack locks, and environmental monitoring. Clean desk policy enforced. | Client Responsibility |
| A.7.4 | Physical Security Monitoring | CCTV surveillance with 30-day retention. Motion detection alerts after hours. | Client Responsibility |
| A.7.5 | Protecting Against Physical and Environmental Threats | Fire suppression system (FM-200), water leak detection, temperature/humidity monitoring with alerting. | Implemented |
| A.7.6 | Working in Secure Areas | Secure area rules documented. No unauthorized photography, no food/drink, equipment inspection on exit. | Client Responsibility |
| A.7.7 | Clear Desk and Clear Screen | Clean desk policy enforced. Screen lock after 5 minutes of inactivity. | Client Responsibility |
| A.7.8 | Equipment Siting and Protection | Equipment positioned to minimize environmental risks. Cable management prevents trip hazards. | Implemented |
| A.7.9 | Security of Assets Off-Premises | Mobile device encryption mandatory. Remote wipe capability via FortiClient EMS. | Implemented |
| A.7.10 | Storage Media | Media handling procedures documented. Secure disposal for decommissioned drives. | Implemented |
| A.7.11 | Supporting Utilities | Dual power feeds with UPS and generator backup. HVAC sized for equipment load with redundancy. | Implemented |
| A.7.12 | Cabling Security | Cabling secured in conduits. Fiber and copper separated. Labeling per TIA-606 standard. | Implemented |
| A.7.13 | Equipment Maintenance | Maintenance contracts for all critical equipment. Preventive maintenance schedule followed. | Implemented |
| A.7.14 | Secure Disposal or Re-use of Equipment | Secure wipe procedures per NIST SP 800-88. Certificate of destruction obtained for disposed media. | Implemented |

## 6.5 Technological Controls (A.8)

| Control | Name | Implementation Detail | Status |
| --- | --- | --- | --- |
| A.8.1 | User Endpoint Devices | FortiClient with EPP installed on all endpoints. Device posture checks enforce security compliance. | Implemented |
| A.8.2 | Privileged Access Rights | Privileged Access Management (PAM) via HashiCorp Vault. Just-in-time elevation for administrative tasks. | Implemented |
| A.8.3 | Information Access Restriction | Role-based access control restricts users to required information only. Need-to-know principle enforced. | Implemented |
| A.8.4 | Access to Source Code | Source code access restricted to authorized developers. Version control with access logging. | Not Applicable |
| A.8.5 | Secure Authentication | Multi-factor authentication required for all remote access and privileged accounts. Passwordless options evaluated. | Implemented |
| A.8.6 | Capacity Management | Capacity monitoring via Zabbix. Alerts at 70% storage utilization. Capacity planning reviews quarterly. | Implemented |
| A.8.7 | Protection Against Malware | Kaspersky Endpoint Security deployed on all endpoints. FortiGate AV scanning for network traffic. | Implemented |
| A.8.8 | Management of Technical Vulnerabilities | Quarterly vulnerability scans via Nessus. Patch management process defined. Critical patches applied within 72 hours. | Implemented |
| A.8.9 | Configuration Management | Baseline configurations documented. Configuration changes follow change management process. Backups before changes. | Implemented |
| A.8.10 | Information Deletion | Secure deletion procedures per NIST SP 800-88. Data retention policies enforced automatically where possible. | Implemented |
| A.8.11 | Data Masking | Data masking for non-production environments. PII obfuscation in test datasets. | Client Responsibility |
| A.8.12 | Data Leakage Prevention | FortiGate DLP policies monitor and block sensitive data exfiltration. USB restrictions on endpoints. | Implemented |
| A.8.13 | Information Backup | 3-2-1 backup strategy implemented. Daily backups with 30-day retention. Quarterly restore testing. | Implemented |
| A.8.14 | Redundancy of Information Processing Facilities | Same as A.5.27 — redundant infrastructure at Site A, full DR at Site B. | Implemented |
| A.8.15 | Logging | Comprehensive logging to FortiAnalyzer — network, system, application, and security events. | Implemented |
| A.8.16 | Monitoring Activities | Zabbix monitoring with dashboards and alerting. 24/7 monitoring for critical alerts. | Implemented |
| A.8.17 | Clock Synchronization | NTP configured on all devices. Synchronized to reliable time source (pool.ntp.org). | Implemented |
| A.8.18 | Use of Privileged Utility Programs | Privileged utilities restricted to authorized administrators. Usage logged and reviewed. | Implemented |
| A.8.19 | Installation of Software on Operational Systems | Software installation restricted. Application whitelist enforced on endpoints. Change management required. | Implemented |
| A.8.20 | Network Security | Network segmentation via VLANs. Firewall zones enforce traffic inspection. IDS/IPS active. | Implemented |
| A.8.21 | Security of Network Services | Network services hardened. Unnecessary services disabled. Service authentication enforced. | Implemented |
| A.8.22 | Segregation of Networks | VLANs segregate DMZ, Production, Storage, Management, and Guest traffic. Inter-VLAN routing controlled by firewall. | Implemented |
| A.8.23 | Web Filtering | FortiGate web filtering blocks malicious categories. HTTPS inspection enabled. | Implemented |
| A.8.24 | Use of Cryptography | TLS 1.3 for all encrypted communications. AES-256-GCM for data at rest. SHA-256 for integrity verification. | Implemented |
| A.8.25 | Secure Development Life Cycle | Secure SDLC followed for custom development. Code reviews and security testing required. | Not Applicable |
| A.8.26 | Application Security Requirements | Security requirements defined for all applications. Security testing before production deployment. | Client Responsibility |
| A.8.27 | Secure System Architecture and Engineering | Defense in depth architecture. Security controls at each layer. Secure defaults configured. | Implemented |
| A.8.28 | Secure Coding | Secure coding guidelines followed. Static analysis for code security. | Not Applicable |
| A.8.29 | Security Testing in Development and Acceptance | Security testing included in acceptance criteria. Penetration testing annually. | Implemented |
| A.8.30 | Outsourced Development | Security requirements in outsourcing contracts. Code review and security testing before deployment. | Not Applicable |
| A.8.31 | Separation of Development, Test and Production Environments | Separate environments maintained. No production data in test without masking. Access controls differ per environment. | Client Responsibility |
| A.8.32 | Change Management | Formal change management process. CAB reviews significant changes. Rollback plans documented. | Client Responsibility |
| A.8.33 | Test Information | Test data protection requirements defined. No real PII in test without approval and masking. | Client Responsibility |
| A.8.34 | Protection of Information Systems During Audit Testing | Audit activities coordinated to prevent operational impact. Read-only access preferred for auditors. | Client Responsibility |

## 6.6 Compliance Summary

| Category | Implemented | Client Responsibility | Not Applicable |
| --- | --- | --- | --- |
| A.5 — Organizational | 22 | 8 | 0 |
| A.6 — People | 2 | 6 | 0 |
| A.7 — Physical | 8 | 6 | 0 |
| A.8 — Technological | 24 | 6 | 4 |
| **Total** | **56** | **26** | **4** |

Overall Compliance Rate: 68% Implemented by VConfi, 32% Client Responsibilities

# 7. Document Conclusion

This Part 1 document establishes the foundation for the B2H Studios IT infrastructure implementation:

Executive Summary confirms the Option B+ solution delivering ₹2.04 Crore investment with 5-year TCO of ₹3.4 Crore

Architecture Overview presents a dual-site, active-standby design with 936TB usable storage per site, ZTNA remote access, and Wasabi cloud tiering

Network Topology demonstrates redundant FortiGate 120G HA, HPE Aruba CX 6300M VSX stacking, and comprehensive VLAN segmentation

IP Addressing provides complete allocation for all devices at both Site A and Site B

ISO 27001 Mapping confirms 56 controls implemented by VConfi, with 26 client responsibilities identified

The design prioritizes security, availability, and operational simplicity — delivering enterprise-grade capabilities tailored for B2H Studios' 25-user media production environment.

End of Part 1: Executive Summary, Architecture & ISO Compliance

VConfi Solutions | CONFIDENTIAL | March 22, 2026

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Part 2: Network, Wireless & Server Design

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

# Part 2: Network Infrastructure, Wireless & Servers

B2H Studios IT Infrastructure Implementation Plan

Client: B2H Studios

Project: Option B+ (Optimized Synology HD6500 Solution)

Date: March 22, 2026

Prepared by: VConfi Solutions

Classification: CONFIDENTIAL

## Table of Contents

[Firewall Design — FortiGate 120G](#1-firewall-design--fortigate-120g)

[Switch Design — HPE Aruba CX 6300M](#2-switch-design--hpe-aruba-cx-6300m)

[Cabling Schedule](#3-cabling-schedule)

[Redundancy Scenarios](#4-redundancy-scenarios)

[Wireless Infrastructure](#5-wireless-infrastructure)

[Server Infrastructure](#6-server-infrastructure)

## 1. Firewall Design — FortiGate 120G

### 1.1 Hardware Specifications

The FortiGate 120G NGFW provides enterprise-grade security with high-throughput performance suitable for B2H Studios' media production environment.

| Specification | Value |
| --- | --- |
| **Model** | FortiGate 120G |
| **Form Factor** | 1U Rackmount |
| **Firewall Throughput** | 44 Gbps |
| **IPS Throughput** | 24 Gbps |
| **NGFW Throughput** | 18 Gbps |
| **Threat Protection** | 14 Gbps |
| **VPN Throughput (IPsec)** | 18 Gbps |
| **SSL Inspection** | 10 Gbps |
| **Concurrent Sessions** | 8 Million |
| **New Sessions/Second** | 500,000 |
| **Interfaces** | 8x GE RJ45, 8x GE SFP, 4x 10 GE SFP+ |
| **Dedicated Management** | 1x GE RJ45 |
| **Storage** | 480GB SSD (for logging) |
| **Memory** | 64GB DDR4 |
| **Redundant Power** | Hot-swappable dual PSU |
| **Operating Temp** | 0°C to 40°C |

### 1.2 HA Configuration (Active-Passive)

The FortiGate 120G pair operates in Active-Passive High Availability mode for seamless failover.

HA Configuration Parameters:

| Parameter | Setting |
| --- | --- |
| **HA Mode** | Active-Passive |
| **HA Group ID** | 1 |
| **HA Group Name** | B2H-FG-HA-01 |
| **Priority (Primary)** | 200 |
| **Priority (Secondary)** | 100 |
| **Heartbeat Interface** | Port 7-8 (dedicated) |
| **Session Pickup** | Enabled |
| **Configuration Sync** | Automatic |
| **VRRP Virtual MAC** | 00:09:0f:09:00:01 |

Heartbeat Configuration:

config system ha
    set mode a-p
    set group-id 1
    set group-name "B2H-FG-HA-01"
    set priority 200
    set hbdev "port7" 50 "port8" 50
    set session-pickup enable
    set override enable
    set priority 100
end

Failover Triggers:

Primary unit hardware failure

Link monitoring failure (2+ interfaces down)

Remote link failure (monitored via IP)

Manual failover (maintenance mode)

Failover Time: < 2 seconds (sub-second with session pickup)

### 1.3 SD-WAN Dual ISP Configuration

SD-WAN manages both ISP connections with intelligent traffic steering.

| ISP | Details |
| --- | --- |
| **ISP1 (Primary)** | Airtel Business - 1Gbps Fiber |
| **ISP1 IP** | Static /29 subnet |
| **ISP2 (Secondary)** | Jio Business - 1Gbps Fiber |
| **ISP2 IP** | Static /29 subnet |

SD-WAN Zone Configuration:

config system sdwan
    set status enable
    config zone
        edit "virtual-wan-link"
            set zone-members "ISP1" "ISP2"
        next
    end
    config members
        edit 1
            set interface "port1"
            set gateway 203.115.96.1
            set priority 10
            set cost 10
        next
        edit 2
            set interface "port2"
            set gateway 49.205.96.1
            set priority 20
            set cost 20
        next
    end
end

Performance SLA Monitors:

| Monitor | Target | Protocol | Interval | Fail Threshold |
| --- | --- | --- | --- | --- |
| Google DNS | 8.8.8.8 | Ping | 1000ms | 3 failures |
| Cloudflare | 1.1.1.1 | Ping | 1000ms | 3 failures |
| Latency SLA | < 50ms | Ping | 5000ms | 5 failures |

SD-WAN Rules:

| Rule | Source | Destination | Strategy | Preferred |
| --- | --- | --- | --- | --- |
| 1 | All | Wasabi S3 | Best Quality | ISP1 |
| 2 | Signiant | Any | Lowest Cost | ISP1 |
| 3 | Video Streaming | Any | Lowest Latency | Auto |
| 4 | Default | Any | Best Quality | ISP1, ISP2 |

### 1.4 Security Zones and Zone Policies

Five security zones define the network perimeter with granular access controls.

Zone Definitions:

| Zone | Interfaces | Security Level | Member VLANs |
| --- | --- | --- | --- |
| **WAN** | port1, port2 | Untrusted | - |
| **DMZ** | port3 (VLAN 10) | Semi-Trusted | VLAN 10 (10.10.10.0/24) |
| **Internal** | port4 (VLAN 20, 30) | Trusted | VLAN 20 (10.10.20.0/24), VLAN 30 (10.10.30.0/24) |
| **Management** | port5 (VLAN 40) | Restricted | VLAN 40 (10.10.40.0/24) |
| **Guest** | port6 (VLAN 50) | Untrusted | VLAN 50 (10.10.50.0/24) |

Intra-Zone Policies:

| Source Zone | Destination Zone | Default Action | Logging |
| --- | --- | --- | --- |
| Internal | WAN | Allow | Yes |
| DMZ | WAN | Allow | Yes |
| Management | All | Allow | Yes |
| Guest | WAN | Allow | Yes |
| Guest | Internal | Deny | Alert |
| DMZ | Internal | Deny | Alert |
| WAN | DMZ | Deny (except rules) | Yes |
| WAN | Internal | Deny (except ZTNA) | Yes |

### 1.5 UTM Profiles

Unified Threat Management profiles provide layered security inspection.

IPS Profile (IPS_Media_Production):

| Setting | Value |
| --- | --- |
| **Profile Name** | IPS_Media_Production |
| **Inspection Mode** | Proxy-based |
| **Filter** | High Security with Media exceptions |
| **Signatures** | All critical and high severity |
| **Action** | Block + Log |
| **Excluded Signatures** | Custom media streaming protocols |

Antivirus Profile (AV_Enterprise):

| Setting | Value |
| --- | --- |
| **Profile Name** | AV_Enterprise |
| **Inspection Mode** | Proxy-based |
| **Scan Mode** | Full Scan |
| **Engine** | FortiGuard + FortiSandbox Cloud |
| **Block Period** | 30 minutes |
| **FortiSandbox** | Enabled for unknown files |

Web Filter Profile (WF_Corporate):

| Setting | Value |
| --- | --- |
| **Profile Name** | WF_Corporate |
| **Inspection Mode** | Proxy-based |
| **Categories Blocked** | Malware, Phishing, Adult, Gambling |
| **Categories Allowed** | Business, Technology, Media |
| **HTTPS Scanning** | Enabled |
| **FortiGuard Rating** | Enabled |

Application Control Profile (APP_Media):

| Setting | Value |
| --- | --- |
| **Profile Name** | APP_Media |
| **Inspection Mode** | Proxy-based |
| **Default Action** | Monitor |
| **Blocked Apps** | P2P, Remote Access (unauthorized), Gaming |
| **Allowed Apps** | Signiant, Aspera, SMB, NFS, HTTP/HTTPS |
| **Shaping** | Video streaming: 100Mbps limit |

DNS Filter Profile (DNS_Secure):

| Setting | Value |
| --- | --- |
| **Profile Name** | DNS_Secure |
| **DNS Security** | Enabled |
| **Safe Search** | Enabled |
| **Botnet C2** | Block |
| **FortiGuard Categories** | Block malicious domains |

### 1.6 SSL Inspection Configuration

Full SSL inspection decrypts and inspects encrypted traffic.

| Setting | Value |
| --- | --- |
| **Mode** | Full SSL Inspection |
| **Certificate** | B2H-CA-Internal (deployed to all endpoints) |
| **Inspection Profile** | High Security |
| **Excluded Categories** | Banking, Health, Government |
| **Unsupported SSL** | Block |
| **Invalid Certificate** | Block |
| **Diffie-Hellman** | Block (unless PFS required) |

SSL Exemption List:

| Category | Exemption Reason |
| --- | --- |
| Banking | Compliance requirement |
| Healthcare | HIPAA alignment |
| Microsoft 365 | Known good, performance |
| Wasabi S3 | Trusted cloud storage |

### 1.7 VPN/ZTNA Configuration

Zero Trust Network Access (ZTNA) replaces traditional VPN for secure remote access.

ZTNA Access Proxy Configuration:

| Parameter | Value |
| --- | --- |
| **Access Proxy Name** | ZTNA-NAS-Access |
| **External Interface** | Virtual-WAN (SD-WAN) |
| **External Port** | 443 |
| **Authentication** | FortiAuthenticator (MFA) |
| **Certificate** | Wildcard SSL (b2hstudios.com) |

ZTNA Policy Rules:

| Rule | User Group | Device Posture | Access | Resources |
| --- | --- | --- | --- | --- |
| 1 | Editors | Compliant | Full | NAS Shares (VLAN 30) |
| 2 | Management | Compliant | Full | All Internal |
| 3 | External DIT | Compliant | Limited | Signiant SDCX (DMZ) |
| 4 | Guest | Any | None | Internet Only |

Device Posture Checks:

| Check | Requirement |
| --- | --- |
| **Antivirus** | Kaspersky Active & Updated |
| **OS Version** | Windows 10/11 (Latest) or macOS 12+ |
| **Disk Encryption** | BitLocker/FileVault Enabled |
| **FortiClient** | Latest Version |
| **TPM** | Certificate Validation |

IPsec Site-to-Site (Site A ↔ Site B DR):

| Parameter | Value |
| --- | --- |
| **Interface** | ISP1 |
| **IKE Version** | IKEv2 |
| **Authentication** | PSK + Certificate |
| **Encryption** | AES-256-GCM |
| **DH Group** | Group 14 |
| **Phase 1 Lifetime** | 28800 seconds |
| **Phase 2 Lifetime** | 3600 seconds |
| **DPD** | Enabled |

### 1.8 Firewall Rule Table

Complete firewall policy for B2H Studios network.

| Rule ID | Name | Source | Destination | Service | Action | Log |
| --- | --- | --- | --- | --- | --- | --- |
| 100 | Allow ZTNA | SSL-VPN | VLAN30 | SMB, NFS | Accept | Yes |
| 101 | Allow Signiant | Any | DMZ_SDCX | UDP/33001 | Accept | Yes |
| 102 | SDCX to NAS | DMZ_SDCX | NAS_Storage | NFS | Accept | Yes |
| 103 | Signiant Web | Any | DMZ_SDCX | HTTPS/443 | Accept | Yes |
| 104 | DNS Outbound | All_Internal | WAN | DNS/53 | Accept | Yes |
| 105 | NTP Outbound | All_Internal | WAN | NTP/123 | Accept | Yes |
| 106 | HTTPS Outbound | All_Internal | WAN | HTTPS/443 | Accept | Yes |
| 107 | SMTP Outbound | All_Internal | WAN | SMTP/587 | Accept | Yes |
| 108 | Wasabi S3 | NAS_Storage | WAN | HTTPS/443 | Accept | Yes |
| 109 | Zabbix Monitoring | Management | All_Internal | SNMP, ICMP | Accept | Yes |
| 110 | iLO Management | Management | Servers | HTTPS/443 | Accept | Yes |
| 111 | DSM Management | Management | NAS_Storage | HTTPS/5001 | Accept | Yes |
| 112 | Admin SSH | Management | All_Devices | SSH/22 | Accept | Yes |
| 113 | FortiAnalyzer Logging | All_Devices | FANALYZER-01 | SYSLOG/514 | Accept | Yes |
| 114 | Site-to-Site VPN | SiteA | SiteB | Any | Accept | Yes |
| 115 | Guest Internet | Guest | WAN | HTTP, HTTPS | Accept | Yes |
| 200 | Block Guest to Internal | Guest | Internal | Any | Deny | Yes |
| 201 | Block DMZ to Internal | DMZ | Internal | Any | Deny | Yes |
| 202 | Block Inbound SMB | WAN | Any | SMB/445 | Deny | Yes |
| 203 | Block Inbound RDP | WAN | Any | RDP/3389 | Deny | Yes |
| 204 | Block Inbound SSH | WAN | Any | SSH/22 | Deny | Yes |
| 205 | Block Known Bad IPs | Any | WAN_Bad_IPs | Any | Deny | Yes |
| 300 | Deny All | Any | Any | Any | Deny | Alert |

## 2. Switch Design — HPE Aruba CX 6300M

### 2.1 Hardware Specifications

The HPE Aruba CX 6300M switches provide high-performance Layer 3 switching with VSX stacking for redundancy.

| Specification | Value |
| --- | --- |
| **Model** | HPE Aruba CX 6300M (JL659A) |
| **Form Factor** | 1U Rackmount |
| **Switching Capacity** | 880 Gbps |
| **Forwarding Rate** | 655 Mpps |
| **Total Ports** | 48x 1GbE RJ45 + 4x 25GbE SFP28 |
| **PoE Budget** | 1,440W (PoE++) |
| **PoE Ports** | 48 (802.3bt ready) |
| **Management** | OOB Ethernet, USB Console |
| **Stacking** | VSX (Virtual Switching Extension) |
| **MAC Address Table** | 64,000 entries |
| **VLAN Support** | 4,094 VLANs |
| **Jumbo Frames** | MTU 9,216 bytes |
| **Power** | Dual hot-swappable PSU |
| **Cooling** | Hot-swappable fans |
| **Mean Time Between Failures (MTBF)** | 340,000 hours |

Quantity: 2 units (SW1 and SW2) for redundant core

### 2.2 VSX Stacking Configuration

Virtual Switching Extension (VSX) creates a logical switch from two physical switches.

VSX Configuration Parameters:

| Parameter | SW1 (Primary) | SW2 (Secondary) |
| --- | --- | --- |
| **VSX Role** | Primary | Secondary |
| **VSX System MAC** | 00:01:02:03:04:05 | 00:01:02:03:04:05 (shared) |
| **Keepalive Interface** | mgmt | mgmt |
| **Keepalive IP** | 10.10.40.2 | 10.10.40.3 |
| **ISL Ports** | 1/1/51, 1/1/52 | 1/1/51, 1/1/52 |
| **ISL LAG ID** | 1 | 1 |

VSX Configuration Commands:

! SW1 Primary Configuration
vsx
    system-mac 00:01:02:03:04:05
    inter-switch-link lag 1
    role primary
    keepalive peer 10.10.40.3 source 10.10.40.2
    linkup-delay-timer 180
    exit

! SW2 Secondary Configuration
vsx
    system-mac 00:01:02:03:04:05
    inter-switch-link lag 1
    role secondary
    keepalive peer 10.10.40.2 source 10.10.40.3
    linkup-delay-timer 180
    exit

VSX Features Enabled:

Active-Active Gateway (AAG) for VLAN interfaces

Multi-Active Detection (MAD)

VSX Sync for MAC, ARP, and route tables

### 2.3 LACP Configuration for HD6500 Connectivity

Link Aggregation Control Protocol provides 40 Gbps aggregate bandwidth to the Synology HD6500.

LACP Configuration:

| Parameter | Value |
| --- | --- |
| **LAG ID** | 10 |
| **LAG Name** | HD6500-LACP |
| **Mode** | LACP Active |
| **Hash Policy** | L3-L4 (src-dst-ip-port) |
| **Member Ports (SW1)** | 1/1/49, 1/1/50 |
| **Member Ports (SW2)** | 1/1/49, 1/1/50 |
| **Speed** | 10 Gbps per link |
| **Aggregate Speed** | 40 Gbps (4x 10GbE) |

Configuration Commands:

interface lag 10
    description "HD6500 NAS LAG"
    no shutdown
    no routing
    vlan trunk native 1
    vlan trunk allowed 30
    lacp mode active
    lacp hash l3-l4
    exit

interface 1/1/49
    description "HD6500-Port1"
    no shutdown
    lag 10
    exit

interface 1/1/50
    description "HD6500-Port2"
    no shutdown
    lag 10
    exit

### 2.4 VLAN Trunk Configuration

Trunk ports carry multiple VLANs between switches and to the firewall.

Trunk Port Configuration:

| Port | Connected To | Native VLAN | Allowed VLANs | Mode |
| --- | --- | --- | --- | --- |
| 1/1/1 | FortiGate-Pri | 1 | 10,20,30,40,50 | Trunk |
| 1/1/2 | FortiGate-Sec | 1 | 10,20,30,40,50 | Trunk |
| 1/1/51 | SW2 (ISL) | 1 | All | Trunk |
| 1/1/52 | SW2 (ISL) | 1 | All | Trunk |
| lag 10 | HD6500 | 1 | 30 | Trunk |

VLAN Interface Configuration (SVI):

| VLAN | Interface IP | Subnet | VRRP IP | Purpose |
| --- | --- | --- | --- | --- |
| 10 | 10.10.10.2/24 | 10.10.10.0/24 | 10.10.10.1 | DMZ |
| 20 | 10.10.20.2/24 | 10.10.20.0/24 | 10.10.20.1 | Production |
| 30 | 10.10.30.2/24 | 10.10.30.0/24 | 10.10.30.1 | Storage |
| 40 | 10.10.40.2/24 | 10.10.40.0/24 | 10.10.40.1 | Management |
| 50 | 10.10.50.2/24 | 10.10.50.0/24 | 10.10.50.1 | Guest |

### 2.5 Spanning-Tree Configuration

Rapid PVST+ provides fast convergence and loop prevention.

| Parameter | Value |
| --- | --- |
| **Protocol** | Rapid PVST+ |
| **Mode** | RPVST |
| **Bridge Priority (SW1)** | 4096 (Root) |
| **Bridge Priority (SW2)** | 8192 (Backup) |
| **PortFast** | Enabled on access ports |
| **BPDU Guard** | Enabled on access ports |
| **Root Guard** | Enabled on trunk ports |
| **Loop Guard** | Enabled globally |

Configuration:

spanning-tree mode rpvst
spanning-tree priority 4096  ! SW1
spanning-tree priority 8192  ! SW2
spanning-tree portfast default
spanning-tree bpdu-guard default
spanning-tree loop-guard default

### 2.6 Jumbo Frames Configuration

MTU 9000 is enabled for storage VLAN to optimize NAS performance.

| VLAN | MTU Setting |
| --- | --- |
| VLAN 10 (DMZ) | 1500 |
| VLAN 20 (Production) | 1500 |
| **VLAN 30 (Storage)** | **9000** |
| VLAN 40 (Management) | 1500 |
| VLAN 50 (Guest) | 1500 |

Configuration Commands:

interface vlan 30
    ip mtu 9000
    exit

interface lag 10
    ip mtu 9000
    exit

End-to-End MTU Verification:

HD6500: MTU 9000 configured

Switch VLAN 30: MTU 9000 configured

Server NICs (VLAN 30): MTU 9000 configured

### 2.7 Port Assignment Table

Complete port allocation for both switches.

| Port | Device | VLAN | Description |
| --- | --- | --- | --- |
| **SW1 - Uplink & Trunk Ports** |  |  |  |
| 1/1/1 | FortiGate-Pri | Trunk | Uplink to Firewall Primary |
| 1/1/2 | FortiGate-Sec | Trunk | Uplink to Firewall Secondary |
| 1/1/51 | SW2-Port-51 | Trunk | VSX Inter-Switch Link 1 |
| 1/1/52 | SW2-Port-52 | Trunk | VSX Inter-Switch Link 2 |
| **SW1 - NAS LAG** |  |  |  |
| 1/1/49 | HD6500-Port1 | 30 | NAS LACP Member 1 |
| 1/1/50 | HD6500-Port2 | 30 | NAS LACP Member 2 |
| **SW1 - Server Connections** |  |  |  |
| 1/1/10 | R760-VMNIC0 | 20,30 | Dell R760 Primary |
| 1/1/11 | R760-VMNIC1 | 20,30 | Dell R760 Secondary |
| 1/1/12 | R760-iLO | 40 | Dell R760 OOB Management |
| **SW1 - Wireless APs** |  |  |  |
| 1/1/20 | FortiAP-01 | 20,50 | Floor 1 AP (PoE++) |
| 1/1/21 | FortiAP-02 | 20,50 | Floor 1 AP (PoE++) |
| 1/1/22 | FortiAP-03 | 20,50 | Floor 2 AP (PoE++) |
| 1/1/23 | FortiAP-04 | 20,50 | Floor 2 AP (PoE++) |
| **SW1 - User Access** |  |  |  |
| 1/1/30-39 | Workstations | 20 | Production VLAN Users |
| **SW1 - Management** |  |  |  |
| 1/1/40 | Management PC | 40 | Admin Workstation |
| 1/1/41 | Zabbix Server | 40 | Monitoring Server |
| **SW2 - Uplink & Trunk Ports** |  |  |  |
| 1/1/1 | FortiGate-Pri | Trunk | Uplink to Firewall Primary |
| 1/1/2 | FortiGate-Sec | Trunk | Uplink to Firewall Secondary |
| 1/1/51 | SW1-Port-51 | Trunk | VSX Inter-Switch Link 1 |
| 1/1/52 | SW1-Port-52 | Trunk | VSX Inter-Switch Link 2 |
| **SW2 - NAS LAG** |  |  |  |
| 1/1/49 | HD6500-Port3 | 30 | NAS LACP Member 3 |
| 1/1/50 | HD6500-Port4 | 30 | NAS LACP Member 4 |
| **SW2 - Server Connections** |  |  |  |
| 1/1/10 | R760-VMNIC2 | 20,30 | Dell R760 Tertiary |
| 1/1/11 | R760-VMNIC3 | 40 | Dell R760 OOB Secondary |
| **SW2 - Wireless APs** |  |  |  |
| 1/1/20 | FortiAP-05 | 20,50 | Floor 3 AP (PoE++) |
| 1/1/21 | FortiAP-06 | 20,50 | Edit Bay AP (PoE++) |
| **SW2 - User Access** |  |  |  |
| 1/1/30-39 | Workstations | 20 | Production VLAN Users |
| **SW2 - Spare/Expansion** |  |  |  |
| 1/1/45-48 | Reserved | - | Future Expansion |

### 2.8 Switch Stacking/Interconnect Diagram

graph TB
    subgraph "FortiGate HA Cluster"
        FG_PRI[FortiGate 120G<br/>Primary]
        FG_SEC[FortiGate 120G<br/>Secondary]
        FG_PRI ---|HA Heartbeat| FG_SEC
    end

    subgraph "VSX Stack - Core Switches"
        SW1[HPE Aruba CX 6300M<br/>SW1 - Primary]
        SW2[HPE Aruba CX 6300M<br/>SW2 - Secondary]
        SW1 <-->|ISL LAG 1<br/>2x 25GbE| SW2
    end

    subgraph "Storage - LACP"
        NAS[Synology HD6500<br/>4x 10GbE]
    end

    subgraph "Server Infrastructure"
        R760[Dell PowerEdge R760<br/>VM Host]
    end

    subgraph "Wireless APs"
        AP1[FortiAP-431F<br/>Floor 1]
        AP2[FortiAP-431F<br/>Floor 2]
        AP3[FortiAP-431F<br/>Floor 3]
    end

    subgraph "WAN Connectivity"
        ISP1[Airtel Fiber<br/>1Gbps]
        ISP2[Jio Fiber<br/>1Gbps]
    end

    FG_PRI -->|Port 3-7| SW1
    FG_SEC -->|Port 3-7| SW2
    
    SW1 -->|LAG 10<br/>2x 10GbE| NAS
    SW2 -->|LAG 10<br/>2x 10GbE| NAS
    
    SW1 -->|10GbE| R760
    SW2 -->|10GbE| R760
    
    SW1 -->|PoE++| AP1
    SW1 -->|PoE++| AP2
    SW2 -->|PoE++| AP3
    
    ISP1 -->|WAN| FG_PRI
    ISP2 -->|WAN| FG_SEC

    style FG_PRI fill:#e74c3c,stroke:#c0392b,color:#fff
    style FG_SEC fill:#e74c3c,stroke:#c0392b,color:#fff
    style SW1 fill:#3498db,stroke:#2980b9,color:#fff
    style SW2 fill:#3498db,stroke:#2980b9,color:#fff
    style NAS fill:#2ecc71,stroke:#27ae60,color:#fff
    style R760 fill:#9b59b6,stroke:#8e44ad,color:#fff

## 3. Cabling Schedule

### 3.1 Cable Inventory

Complete cable inventory for B2H Studios infrastructure.

| Cable ID | From | To | Type | Length | Purpose |
| --- | --- | --- | --- | --- | --- |
| C-001 | ISP1 ONT | FG-Pri Port1 | Cat6 | 2m | WAN Primary |
| C-002 | ISP2 ONT | FG-Sec Port2 | Cat6 | 2m | WAN Secondary |
| C-003 | FG-Pri Port3 | SW1 Port 1/1/1 | Cat6 | 1m | Core Uplink Primary |
| C-004 | FG-Sec Port3 | SW2 Port 1/1/1 | Cat6 | 1m | Core Uplink Secondary |
| C-005 | FG-Pri Port7 | FG-Sec Port7 | Cat6 | 0.5m | HA Heartbeat 1 |
| C-006 | FG-Pri Port8 | FG-Sec Port8 | Cat6 | 0.5m | HA Heartbeat 2 |
| C-007 | HD6500 Port1 | SW1 Port 1/1/49 | Cat6a | 2m | NAS 10GbE Link 1 |
| C-008 | HD6500 Port2 | SW1 Port 1/1/50 | Cat6a | 2m | NAS 10GbE Link 2 |
| C-009 | HD6500 Port3 | SW2 Port 1/1/49 | Cat6a | 2m | NAS 10GbE Link 3 |
| C-010 | HD6500 Port4 | SW2 Port 1/1/50 | Cat6a | 2m | NAS 10GbE Link 4 |
| C-011 | SW1 Port 1/1/51 | SW2 Port 1/1/51 | Fiber OM4 | 5m | VSX ISL Link 1 |
| C-012 | SW1 Port 1/1/52 | SW2 Port 1/1/52 | Fiber OM4 | 5m | VSX ISL Link 2 |
| C-013 | R760 Port1 | SW1 Port 1/1/10 | Cat6a | 2m | Server 10GbE Primary |
| C-014 | R760 Port2 | SW1 Port 1/1/11 | Cat6a | 2m | Server 10GbE Secondary |
| C-015 | R760 Port3 | SW2 Port 1/1/10 | Cat6a | 2m | Server 10GbE Tertiary |
| C-016 | R760 iLO | SW2 Port 1/1/11 | Cat6 | 2m | Server OOB Management |
| C-017 | SW1 Port 1/1/20 | FortiAP-01 | Cat6 | 15m | Floor 1 AP (PoE++) |
| C-018 | SW1 Port 1/1/21 | FortiAP-02 | Cat6 | 15m | Floor 1 AP #2 (PoE++) |
| C-019 | SW1 Port 1/1/22 | FortiAP-03 | Cat6 | 20m | Floor 2 AP (PoE++) |
| C-020 | SW1 Port 1/1/23 | FortiAP-04 | Cat6 | 20m | Floor 2 AP #2 (PoE++) |
| C-021 | SW2 Port 1/1/20 | FortiAP-05 | Cat6 | 25m | Floor 3 AP (PoE++) |
| C-022 | SW2 Port 1/1/21 | FortiAP-06 | Cat6 | 10m | Edit Bay AP (PoE++) |
| C-023 | FG-Pri MGMT | Management PC | Cat6 | 3m | Firewall Console |
| C-024 | SW1 MGMT | Management PC | Cat6 | 3m | Switch Console |
| C-025 | SW2 MGMT | Management PC | Cat6 | 3m | Switch Console |
| C-026 | HD6500 MGMT | Management PC | Cat6 | 3m | NAS Console |
| C-027 | UPS 1 | Rack PDU 1 | Power C13-C14 | 2m | UPS Power Feed |
| C-028 | UPS 2 | Rack PDU 2 | Power C13-C14 | 2m | UPS Power Feed |
| C-029 | ATS | Rack PDU 3 | Power C13-C14 | 2m | ATS Power Feed |
| C-030 | ATS | Rack PDU 4 | Power C13-C14 | 2m | ATS Power Feed |

### 3.2 Patch Panel Layout

PP1 - Network Patch Panel (Rear of Rack):

| Port | Destination | Type |
| --- | --- | --- |
| 1-4 | ISP1/ISP2 Input | Cat6 |
| 5-12 | FortiGate Ports | Cat6 |
| 13-24 | SW1 Uplinks | Cat6/Cat6a |
| 25-36 | SW2 Uplinks | Cat6/Cat6a |
| 37-48 | Future Expansion | - |

PP2 - Workstation Patch Panel:

| Port | Destination | Type |
| --- | --- | --- |
| 1-12 | Floor 1 Workstations | Cat6 |
| 13-24 | Floor 2 Workstations | Cat6 |
| 25-36 | Floor 3 Workstations | Cat6 |
| 37-48 | Edit Bay Stations | Cat6 |

PP3 - Infrastructure Patch Panel:

| Port | Destination | Type |
| --- | --- | --- |
| 1-6 | Wireless APs | Cat6 |
| 7-12 | Servers/Storage | Cat6a |
| 13-16 | Management/OOB | Cat6 |
| 17-24 | Future Expansion | - |

### 3.3 Cable Labeling Scheme

Label Format: {CABLE-ID}-{FROM}-{TO}

Examples:

`C-003-FG-PRI-SW1-P1`

`C-007-HD6500-SW1-P49`

`C-017-SW1-P20-AP01`

Label Placement:

Both ends of every cable

5cm from connector

Facing outward for visibility

Color Coding:

| Cable Type | Color |
| --- | --- |
| WAN/Internet | Yellow |
| Trunk/Uplink | Red |
| Production LAN | Blue |
| Storage (10GbE) | Green |
| Management | Orange |
| Guest/WiFi | Purple |
| Power | Black |

### 3.4 Testing Procedures

Pre-Installation Testing:

| Test | Tool | Pass Criteria |
| --- | --- | --- |
| Continuity | Fluke DSX-5000 | No opens/shorts |
| Wire Map | Fluke DSX-5000 | T568B pinout correct |
| Length Verification | Fluke DSX-5000 | Within ±3m of spec |
| Return Loss | Fluke DSX-5000 | Cat6: >12dB, Cat6a: >12dB |
| NEXT | Fluke DSX-5000 | Cat6: >30dB, Cat6a: >30dB |

Post-Installation Testing:

| Test | Command/Tool | Expected Result |
| --- | --- | --- |
| LACP Status | `show lacp aggregates` | All members Active |
| VSX Status | `show vsx status` | In-Sync |
| VLAN Trunking | `show vlan trunk` | All VLANs passing |
| MTU Verification | `ping -M do -s 8972` | Success with 9000 MTU |
| Speed Test | `iperf3` | 9.5+ Gbps on 10GbE |
| Failover Test | Disconnect link | <2 sec failover |

Cable Certification:

All cables tested and certified before deployment

Test reports saved to `\Documentation\Cable_Certification\`

25-year warranty on certified installations

## 4. Redundancy Scenarios

### 4.1 Scenario A: Single ISP Failure (SD-WAN Failover)

Trigger: ISP1 (Airtel) link failure detected by SD-WAN performance SLA.

Detection Time: 3-5 seconds (based on 3 consecutive ping failures)

Automatic Actions:

SD-WAN marks ISP1 member as "dead"

All existing sessions failed over to ISP2

New sessions routed via ISP2

DNS resolution continues via secondary DNS

Manual Actions Required:

Contact ISP1 for ETA

Monitor bandwidth utilization on ISP2

Consider rate-limiting non-critical traffic

Recovery:

ISP1 link restored

SD-WAN detects link up

Sessions gradually rebalanced (slow return)

Full redundancy restored

Impact: Zero downtime (session pickup enabled)

### 4.2 Scenario B: Single FortiGate Failure (HA Failover)

Trigger: Primary FortiGate hardware failure or manual failover.

Detection Time: < 1 second (heartbeat timeout)

Automatic Actions:

Secondary FortiGate detects primary failure

Secondary assumes active role

VRRP virtual MAC moves to secondary

Session table synchronized (no re-authentication)

ZTNA connections maintained

Manual Actions Required:

Investigate primary unit failure

If hardware failure, initiate RMA

Review logs on FortiAnalyzer

Recovery:

Replace/repair primary unit

Primary boots and joins HA cluster

Configuration syncs automatically

Optional manual failback

Impact: < 2 seconds (sub-second with session pickup)

### 4.3 Scenario C: Single Switch Failure (VSX/LACP Failover)

Trigger: SW1 hardware failure or maintenance.

Detection Time: < 1 second (VSX keepalive timeout)

Automatic Actions:

SW2 detects SW1 failure via keepalive

SW2 assumes primary gateway role for all VLANs

LACP on SW1 links times out

Traffic flows through SW2 only

APs with dual-home fail over to SW2

Manual Actions Required:

Replace/repair SW1

Verify all connections operational

Recovery:

SW1 replaced and powered on

VSX sync re-establishes

MAC tables synchronize

LACP members rejoin

Traffic rebalances

Impact: < 1 second for routed traffic; wireless may have brief association

### 4.4 Scenario D: HD6500 Drive Failure (RAID6 Rebuild)

Trigger: DSM alert for drive failure in HD6500.

Detection Time: Immediate (SMART monitoring)

Automatic Actions:

DSM marks drive as crashed

RAID6 continues operation (2-drive fault tolerance)

Hot spare activates (if configured)

Rebuild begins automatically

Manual Actions Required:

Order replacement drive

Schedule drive replacement during maintenance window

Monitor rebuild progress

RAID6 Rebuild Details:

| Parameter | Value |
| --- | --- |
| **RAID Type** | RAID6 (56+4) |
| **Usable Drives** | 56 |
| **Parity Drives** | 4 |
| **Fault Tolerance** | 2 drives |
| **Rebuild Speed** | ~200 MB/s |
| **56TB Drive Rebuild** | ~78 hours |
| **Impact During Rebuild** | 10-15% performance degradation |

Rebuild Procedure:

Receive DSM alert

Confirm failed drive slot

Hot-swap failed drive with replacement

DSM detects new drive and starts rebuild

Monitor progress via DSM Storage Manager

Verify RAID health post-rebuild

Impact: Zero downtime; reduced performance during rebuild

### 4.5 Scenario E: Complete Site A Failure (DR Failover)

Trigger: Complete Site A loss (fire, flood, extended power outage).

Detection Time: Site B monitoring alerts within 5 minutes

Manual Failover Procedure:

| Step | Action | Owner | ETA |
| --- | --- | --- | --- |
| 1 | Confirm Site A total loss | IT Manager | T+0 |
| 2 | Initiate DR declaration | IT Manager | T+5 min |
| 3 | Promote Site B NAS via Replication Manager | SysAdmin | T+10 min |
| 4 | Update FortiGate ZTNA profiles to Site B | Network Admin | T+15 min |
| 5 | Update DNS records (if using internal DNS) | SysAdmin | T+20 min |
| 6 | Notify users of new ZTNA gateway | IT Manager | T+25 min |
| 7 | Verify user connectivity | SysAdmin | T+30 min |
| 8 | Begin recovery operations at Site A | All | T+ongoing |

Recovery Time Objective (RTO): < 30 minutes

Recovery Point Objective (RPO):

| Data Type | RPO | Achieved Via |
| --- | --- | --- |
| Active Projects | 15 minutes | Real-time replication |
| Archive Data | 4 hours | Scheduled replication |
| System Configs | 24 hours | Nightly config backup |

Failback Procedure:

Restore Site A infrastructure

Reverse replication direction (Site B → Site A)

Synchronize all changes

Schedule maintenance window

Promote Site A back to primary

Resume normal replication (Site A → Site B)

## 5. Wireless Infrastructure

### 5.1 FortiAP Model Recommendations

Based on B2H Studios' coverage needs and media production requirements.

| Model | Deployment Location | Quantity | Specifications |
| --- | --- | --- | --- |
| **FortiAP 431F** | Office Floors 1-3 | 4 | Wi-Fi 6, 4x4:4, 2.97 Gbps, Dual 5GHz |
| **FortiAP 431F** | Edit Bays | 2 | Wi-Fi 6, 4x4:4, 2.97 Gbps, High Density |

FortiAP 431F Specifications:

| Specification | Value |
| --- | --- |
| **Wi-Fi Standard** | 802.11ax (Wi-Fi 6) |
| **Frequency Bands** | 2.4 GHz, 5 GHz (Dual 5GHz capable) |
| **Max Data Rate** | 2.97 Gbps |
| **MIMO** | 4x4:4 (5GHz), 2x2:2 (2.4GHz) |
| **Max Clients** | 512 per radio |
| **Ethernet Ports** | 1x 2.5GbE, 1x GE |
| **PoE Requirement** | 802.3at (PoE+) or 802.3bt (PoE++) |
| **Controller** | FortiGate integrated (no extra license) |
| **Antennas** | Internal omni-directional |

### 5.2 AP Placement Recommendations

Recommended: Ekahau Site Survey

Prior to final placement, VConfi recommends an Ekahau professional wireless site survey to:

Identify optimal AP locations based on floor plan

Detect RF interference sources

Determine coverage holes

Validate channel planning

Preliminary Placement Plan:

┌─────────────────────────────────────────────────────────────────┐
│                        FLOOR 1 - OFFICE                         │
│  ┌───────────────────────────────────────────────────────────┐  │
│  │                                                           │  │
│  │   ┌─────────┐                  ┌─────────┐                │  │
│  │   │ AP-01   │                  │ AP-02   │                │  │
│  │   │ (Hall A)│                  │ (Hall B)│                │  │
│  │   └────┬────┘                  └────┬────┘                │  │
│  │        │                            │                     │  │
│  │   [Workstations]              [Workstations]              │  │
│  │   [Conference Room]           [Break Room]                │  │
│  │                                                           │  │
│  └───────────────────────────────────────────────────────────┘  │
│                              │                                  │
│                              ▼                                  │
│  ┌───────────────────────────────────────────────────────────┐  │
│  │                      FLOOR 2 - PRODUCTION                 │  │
│  │                                                           │  │
│  │   ┌─────────┐                  ┌─────────┐                │  │
│  │   │ AP-03   │                  │ AP-04   │                │  │
│  │   │ (North) │                  │ (South) │                │  │
│  │   └────┬────┘                  └────┬────┘                │  │
│  │        │                            │                     │  │
│  │   [Editor Stations]           [Review Room]               │  │
│  │   [Color Suite]               [VFX Stations]              │  │
│  │                                                           │  │
│  └───────────────────────────────────────────────────────────┘  │
│                              │                                  │
│                              ▼                                  │
│  ┌───────────────────────────────────────────────────────────┐  │
│  │                      FLOOR 3 - ADMIN                      │  │
│  │                                                           │  │
│  │   ┌─────────┐                                             │  │
│  │   │ AP-05   │                  [Director Office]          │  │
│  │   │ (Center)│                  [Finance]                  │  │
│  │   └────┬────┘                  [HR]                       │  │
│  │        │                                                  │  │
│  │   [Admin Stations]                                        │  │
│  │                                                           │  │
│  └───────────────────────────────────────────────────────────┘  │
│                              │                                  │
│                              ▼                                  │
│  ┌───────────────────────────────────────────────────────────┐  │
│  │                      EDIT BAY                             │  │
│  │                                                           │  │
│  │   ┌─────────┐                  [Editing Suites x4]        │  │
│  │   │ AP-06   │                  [Color Grading Bay]        │  │
│  │   │ (Center)│                  [Audio Suite]              │  │
│  │   └────┬────┘                                             │  │
│  │        │                                                  │  │
│  │   [Client Viewing]                                        │  │
│  │                                                           │  │
│  └───────────────────────────────────────────────────────────┘  │
│                                                                 │
│  Data Center (Basement): FortiAPs connected to SW1/SW2          │
│  ★ AP-01 to AP-06: FortiAP 431F units                           │
└─────────────────────────────────────────────────────────────────┘

Coverage Targets:

| Metric | Target |
| --- | --- |
| **Signal Strength** | -65 dBm minimum |
| **SNR** | 25 dB minimum |
| **Channel Overlap** | <15% |
| **Roaming Handoff** | <50 ms |

### 5.3 SSID Configuration

| SSID | VLAN | Security | Authentication | Bandwidth Limit |
| --- | --- | --- | --- | --- |
| B2H-Corporate | 20 | WPA3-Enterprise | 802.1X + RADIUS | Unlimited |
| B2H-Guest | 50 | WPA2-Personal | Captive Portal | 50 Mbps |
| B2H-IoT | 60 | WPA2-Enterprise | MAC + Certificate | 10 Mbps |

B2H-Corporate SSID Details:

| Setting | Value |
| --- | --- |
| **Broadcast SSID** | Yes |
| **Security Mode** | WPA3-Enterprise (192-bit mode) |
| **Encryption** | GCMP-256 |
| **Key Management** | 802.1X (EAP-TLS preferred) |
| **RADIUS Server** | FANALYZER-01 (FortiAuthenticator) |
| **RADIUS Accounting** | Enabled |
| **Dynamic VLAN** | Disabled (static VLAN 20) |
| **Client Isolation** | Disabled (internal access required) |
| **Airtime Fairness** | Enabled |
| **Band Steering** | Enabled (5GHz preferred) |

B2H-Guest SSID Details:

| Setting | Value |
| --- | --- |
| **Broadcast SSID** | Yes |
| **Security Mode** | WPA2-Personal |
| **Encryption** | AES |
| **Passphrase** | Rotated weekly (via email) |
| **Captive Portal** | FortiGate built-in |
| **Terms Acceptance** | Required |
| **Session Timeout** | 8 hours |
| **Bandwidth Limit** | 50 Mbps down / 20 Mbps up |
| **Client Isolation** | Enabled |
| **Access** | Internet only (blocked from internal) |

### 5.4 RADIUS Server Configuration

FortiAuthenticator (hosted on R760 VM) provides RADIUS authentication.

RADIUS Configuration:

| Parameter | Value |
| --- | --- |
| **Server** | FANALYZER-01 (FortiAuthenticator VM) |
| **IP Address** | 10.10.20.10 |
| **Authentication Port** | 1812 |
| **Accounting Port** | 1813 |
| **Shared Secret** | [REDACTED - stored in Vault] |
| **Timeout** | 5 seconds |
| **Retries** | 3 |
| **NAS Identifier** | B2H-WLAN |

Authentication Flow:

User connects to B2H-Corporate SSID

FortiAP forwards EAP request to FortiGate

FortiGate proxies to FortiAuthenticator (RADIUS)

FortiAuthenticator validates against AD/LDAP

MFA challenge sent via FortiToken push

Upon success, access granted to VLAN 20

User Groups:

| Group | VLAN | Access Level |
| --- | --- | --- |
| B2H-Employees | 20 | Full internal access |
| B2H-Contractors | 20 | Limited access (ACL restricted) |
| B2H-Guest | 50 | Internet only |

### 5.5 Rogue AP Detection

FortiGate's built-in Wireless Intrusion Detection System (WIDS) provides rogue AP detection.

| Detection Method | Action |
| --- | --- |
| **SSID Spoofing** | Alert + Block clients |
| **AP Spoofing** | Alert + De-authenticate |
| **Ad-hoc Networks** | Alert only |
| **Unauthorized FortiAPs** | Auto-approve or Alert |

Containment Actions:

| Severity | Action |
| --- | --- |
| **Critical** | De-authenticate clients, contain AP |
| **High** | Alert admin, log to FortiAnalyzer |
| **Medium** | Log only, weekly report |
| **Low** | Informational |

Detection Schedule:

24/7 active scanning

Dedicated scanning radio on each AP

Weekly rogue AP reports to security team

## 6. Server Infrastructure

### 6.1 Dell PowerEdge R760 Specifications

The Dell PowerEdge R760 serves as the primary virtualization host for critical infrastructure services.

| Component | Specification |
| --- | --- |
| **Model** | Dell PowerEdge R760 |
| **Form Factor** | 2U Rackmount |
| **CPU** | 2x Intel Xeon Silver 4410Y (12-core, 2.0GHz, 30MB Cache) |
| **Total Cores** | 24 cores / 48 threads |
| **Memory** | 128GB DDR5-4800 ECC (8x 16GB) |
| **Memory Slots** | 32 (expandable to 4TB) |
| **Storage Controller** | PERC H965i 12Gbps SAS RAID Controller |
| **Boot Drives** | 2x 480GB SATA SSD (RAID 1) |
| **Data Drives** | 8x 1.2TB 10K RPM SAS 12Gbps |
| **RAID Configuration** | RAID 10 (Striped Mirrors) |
| **Usable Storage** | 4.8TB (8x 1.2TB / 2 for RAID 10) |
| **Network** | 2x 10GbE SFP+ (Intel X710), 2x 1GbE RJ45 (Broadcom) |
| **OOB Management** | iDRAC9 Enterprise with dedicated port |
| **Power** | 2x 1100W Titanium redundant PSU |
| **Expansion** | 8x PCIe Gen5 slots |
| **Operating System** | VMware vSphere 8.0 Update 2 |

Physical Dimensions:

| Parameter | Value |
| --- | --- |
| **Height** | 86.8 mm (3.42 in) |
| **Width** | 482.0 mm (18.98 in) |
| **Depth** | 822.84 mm (32.39 in) |
| **Weight** | 28.6 kg (63 lb) max |

### 6.2 Virtualization Plan

Platform: VMware vSphere 8.0 Update 2

Licensing: vSphere Standard (16-core kit) + vCenter Server Foundation

Cluster Configuration:

| Parameter | Value |
| --- | --- |
| **Cluster Name** | B2H-Compute-01 |
| **ESXi Hosts** | 1 (Site A), 1 (Site B - DR) |
| **HA Enabled** | Yes |
| **DRS Enabled** | Yes (Manual mode) |
| **EVC Mode** | Intel Sapphire Rapids |

Resource Allocation:

| Resource | Total | Reserved for VMs | Overhead |
| --- | --- | --- | --- |
| **CPU Cores** | 24 | 20 | 4 (ESXi) |
| **Memory** | 128GB | 112GB | 16GB (ESXi) |
| **Storage** | 4.8TB | 4.0TB | 800GB (reservation) |

Network Configuration:

| vSwitch | Uplink | VLANs | Purpose |
| --- | --- | --- | --- |
| **vSwitch0** | vmnic0, vmnic1 | 20, 30 | Production + Storage |
| **vSwitch1** | vmnic2 | 40 | Management |
| **vSwitch2** | vmnic3 | 10 | DMZ Services |

Storage Configuration:

| Datastore | Capacity | VMFS Version | Purpose |
| --- | --- | --- | --- |
| **Local-VMs** | 4.5TB | VMFS 6 | VM storage |
| **iSCSI-NAS** | 100TB | NFS 4.1 | Media storage mount |

### 6.3 VM Allocation Table

| VM Name | vCPU | RAM | Storage | OS | Purpose | Network |
| --- | --- | --- | --- | --- | --- | --- |
| **SDCX-01** | 8 | 32GB | 500GB SSD | Windows Server 2022 | Signiant Jet SDCX Server | VLAN 10 (DMZ) |
| **FANALYZER-01** | 4 | 16GB | 1TB SSD | FortiAnalyzer VM | Centralized logging & SIEM | VLAN 40 (Mgmt) |
| **EMS-01** | 4 | 16GB | 200GB SSD | FortiClient EMS | Endpoint management | VLAN 40 (Mgmt) |
| **VAULT-01** | 4 | 16GB | 100GB SSD | HashiCorp Vault | Secrets management | VLAN 40 (Mgmt) |
| **KSC-01** | 4 | 16GB | 200GB SSD | Windows Server 2022 | Kaspersky Security Centre | VLAN 40 (Mgmt) |
| **RADIUS-01** | 2 | 8GB | 100GB SSD | FortiAuthenticator | 802.1X/RADIUS auth | VLAN 20 (Prod) |
| **DNS-01** | 2 | 4GB | 50GB SSD | Windows Server 2022 | Internal DNS/DHCP | VLAN 20 (Prod) |
| **MON-01** | 2 | 8GB | 500GB SSD | Ubuntu 22.04 LTS | Zabbix monitoring | VLAN 40 (Mgmt) |

Total Resource Consumption:

| Resource | Allocated | Available | Utilization |
| --- | --- | --- | --- |
| **vCPU** | 30 | 48 (with HT) | 62.5% |
| **RAM** | 116GB | 128GB | 90.6% |
| **Storage** | 2.67TB | 4.8TB | 55.6% |

Note: Resource allocation leaves headroom for additional VMs and growth.

### 6.4 iLO 5 Out-of-Band Management

iDRAC9 Enterprise provides comprehensive remote management capabilities.

| Feature | Configuration |
| --- | --- |
| **iDRAC IP** | 10.10.40.10/24 |
| **iDRAC Hostname** | idrac-r760-b2h |
| **Authentication** | Active Directory integration |
| **MFA** | FortiToken required |
| **Web Interface** | HTTPS/443 |
| **SSH Access** | Enabled (key-based only) |
| **SNMP** | v3, read-only |
| **Syslog** | Forward to FANALYZER-01 |

Remote Capabilities:

Power on/off/cycle

Virtual console (KVM)

Virtual media mount

Hardware health monitoring

Remote BIOS configuration

Automatic firmware updates

Security Settings:

TLS 1.3 only

Strong cipher suites

IPMI disabled (unused)

USB ports disabled (except internal)

### 6.5 Server Rack Layout Diagram

Front Elevation View:

┌─────────────────────────────────────────────────────────────────────┐
│                    B2H STUDIOS - SERVER RACK                        │
│                      Front Elevation (42U)                          │
├──────┬──────────────────────────────────────────────────────────────┤
│ 42U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     BLANKING PANEL                      █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 41U  │ ┌────────────────────────────────────────────────────────┐ │  │
│      │ │              PATCH PANEL PP1 (Network)                 │ │  │
│      │ │          Ports: 1-24 (Front), 25-48 (Rear)             │ │  │
│      │ └────────────────────────────────────────────────────────┘ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 40U  │ ┌────────────────────────────────────────────────────────┐ │  │
│      │ │           PATCH PANEL PP2 (Fiber/Management)           │ │  │
│      │ │          LC Duplex OM4 / RJ45 Console Ports            │ │  │
│      │ └────────────────────────────────────────────────────────┘ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 39U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     BLANKING PANEL                      █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 38U  │ ┌────────────────────────────────────────────────────────┐ │  │
│      │ │                                                        │ │  │
│      │ │              APC SMART-UPS SRT 10kVA #1                │ │  │
│      │ │                    [2U UPS]                            │ │  │
│      │ │         Power: 10kVA / 9kW • Runtime: ~30 min          │ │  │
│      │ │                                                        │ │  │
│      │ └────────────────────────────────────────────────────────┘ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 37U  │ ┌────────────────────────────────────────────────────────┐ │  │
│      │ │                                                        │ │  │
│      │ │              APC SMART-UPS SRT 10kVA #2                │ │  │
│      │ │                    [2U UPS]                            │ │  │
│      │ │         Power: 10kVA / 9kW • Runtime: ~30 min          │ │  │
│      │ │                                                        │ │  │
│      │ └────────────────────────────────────────────────────────┘ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 36U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     BLANKING PANEL                      █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 35U  │ ┌────────────────────────────────────────────────────────┐ │  │
│      │ │                    PDU-1 (Left)                        │ │  │
│      │ │          APC Switched Rack PDU 2G (AP8959)             │ │  │
│      │ │              Powered by: UPS-1 (Primary)               │ │  │
│      │ └────────────────────────────────────────────────────────┘ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 35U  │ ┌────────────────────────────────────────────────────────┐ │  │
│      │ │                    PDU-2 (Right)                       │ │  │
│      │ │          APC Switched Rack PDU 2G (AP8959)             │ │  │
│      │ │              Powered by: UPS-2 (Secondary)             │ │  │
│      │ └────────────────────────────────────────────────────────┘ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 34U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     BLANKING PANEL                      █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 33U  │ ┌────────────────────────────────────────────────────────┐ │  │
│      │ │  ██████████████████████████████████████████████████   │ │  │
│      │ │  █                                                █   │ │  │
│      │ │  █     FORTIGATE 120G - PRIMARY (FG-PRI)          █   │ │  │
│      │ │  █     Ports: 16x GE + 4x 10G SFP+                █   │ │  │
│      │ │  █     Status: ████████ ACTIVE                    █   │ │  │
│      │ │  █                                                █   │ │  │
│      │ │  ██████████████████████████████████████████████████   │ │  │
│      │ │                    [1U Firewall]                      │ │  │
│      │ └────────────────────────────────────────────────────────┘ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 32U  │ ┌────────────────────────────────────────────────────────┐ │  │
│      │ │  ██████████████████████████████████████████████████   │ │  │
│      │ │  █                                                █   │ │  │
│      │ │  █     FORTIGATE 120G - SECONDARY (FG-SEC)        █   │ │  │
│      │ │  █     Ports: 16x GE + 4x 10G SFP+                █   │ │  │
│      │ │  █     Status: ○○○○○○○○ STANDBY                   █   │ │  │
│      │ │  █                                                █   │ │  │
│      │ │  ██████████████████████████████████████████████████   │ │  │
│      │ │                    [1U Firewall]                      │ │  │
│      │ └────────────────────────────────────────────────────────┘ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 31U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     BLANKING PANEL                      █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 30U  │ ┌────────────────────────────────────────────────────────┐ │  │
│      │ │  ██████████████████████████████████████████████████   │ │  │
│      │ │  █                                                █   │ │  │
│      │ │  █     HPE ARUBA CX 6300M - SW1 (Primary)         █   │ │  │
│      │ │  █     Ports: 48x 1G + 4x 25G SFP28               █   │ │  │
│      │ │  █     VSX Role: PRIMARY                          █   │ │  │
│      │ │  █                                                █   │ │  │
│      │ │  ██████████████████████████████████████████████████   │ │  │
│      │ │                    [1U Switch]                        │ │  │
│      │ └────────────────────────────────────────────────────────┘ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 29U  │ ┌────────────────────────────────────────────────────────┐ │  │
│      │ │  ██████████████████████████████████████████████████   │ │  │
│      │ │  █                                                █   │ │  │
│      │ │  █     HPE ARUBA CX 6300M - SW2 (Secondary)       █   │ │  │
│      │ │  █     Ports: 48x 1G + 4x 25G SFP28               █   │ │  │
│      │ │  █     VSX Role: SECONDARY                        █   │ │  │
│      │ │  █                                                █   │ │  │
│      │ │  ██████████████████████████████████████████████████   │ │  │
│      │ │                    [1U Switch]                        │ │  │
│      │ └────────────────────────────────────────────────────────┘ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 28U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     BLANKING PANEL                      █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 27U  │ ┌────────────────────────────────────────────────────────┐ │  │
│      │ │                                                        │ │  │
│      │ │             APC RACK AUTOMATIC TRANSFER SWITCH        │ │  │
│      │ │                    (AP7732)                           │ │  │
│      │ │         Inputs: 2 (UPS-1, UPS-2)                      │ │  │
│      │ │         Outputs: 12 C13 + 2 C19                       │ │  │
│      │ │                    [1U ATS]                           │ │  │
│      │ └────────────────────────────────────────────────────────┘ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 26U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     BLANKING PANEL                      █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 25U  │ ┌────────────────────────────────────────────────────────┐ │  │
│      │ │  ┌──────────────────────────────────────────────────┐  │ │  │
│      │ │  │                                                  │  │ │  │
│      │ │  │        DELL POWEREDGE R760 - APP SERVER         │  │ │  │
│      │ │  │                                                  │  │ │  │
│      │ │  │     CPU: 2x Xeon Silver 4410Y (24C/48T)         │  │ │  │
│      │ │  │     RAM: 128GB DDR5                             │  │ │  │
│      │ │  │     Storage: 8x 1.2TB SAS RAID10                 │  │ │  │
│      │ │  │     Network: 2x 10GbE + 2x 1GbE                  │  │ │  │
│      │ │  │                                                  │  │ │  │
│      │ │  │     Status: ████████ ONLINE                     │  │ │  │
│      │ │  │                                                  │  │ │  │
│      │ │  └──────────────────────────────────────────────────┘  │ │  │
│      │ │                    [2U Server]                          │ │  │
│      │ └────────────────────────────────────────────────────────┘ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 24U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     BLANKING PANEL                      █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 23U  │ ┌────────────────────────────────────────────────────────┐ │  │
│      │ │  ┌──────────────────────────────────────────────────┐  │ │  │
│      │ │  │  ┌─────────────────────────────────────────────┐ │  │ │  │
│      │ │  │  │                                             │ │  │ │  │
│      │ │  │  │        SYNOLOGY HD6500 NAS (4U)            │ │  │ │  │
│      │ │  │  │                                             │ │  │ │  │
│      │ │  │  │     Drives: 60x 18TB SAS HDD               │ │  │ │  │
│      │ │  │  │     Cache: 4x 7.68TB NVMe SSD              │ │  │ │  │
│      │ │  │  │     Network: 4x 10GbE                      │ │  │ │  │
│      │ │  │  │     Usable: 936TB RAID6                    │ │  │ │  │
│      │ │  │  │                                             │ │  │ │  │
│      │ │  │  │     Status: ████████ HEALTHY               │ │  │ │  │
│      │ │  │  │                                             │ │  │ │  │
│      │ │  │  └─────────────────────────────────────────────┘ │  │ │  │
│      │ │  └──────────────────────────────────────────────────┘  │ │  │
│      │ │                    [4U Storage]                         │ │  │
│      │ └────────────────────────────────────────────────────────┘ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 22U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     OCCUPIED BY NAS                     █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 21U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     OCCUPIED BY NAS                     █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 20U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     OCCUPIED BY NAS                     █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 19U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     BLANKING PANEL                      █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 18U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     BLANKING PANEL                      █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 17U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     BLANKING PANEL                      █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 16U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     BLANKING PANEL                      █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 15U  │ ██████████████████████████████████████████████████████████ │  │
│      │ █                     BLANKING PANEL                      █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 1-14U│ ██████████████████████████████████████████████████████████ │  │
│      │ █                 RESERVED FOR EXPANSION                  █ │  │
│      │ ██████████████████████████████████████████████████████████ │  │
└──────┴──────────────────────────────────────────────────────────────┘

Rear Elevation View:

┌─────────────────────────────────────────────────────────────────────┐
│                    B2H STUDIOS - SERVER RACK                        │
│                       Rear Elevation (42U)                          │
├──────┬──────────────────────────────────────────────────────────────┤
│ 42U  │ ▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓ │  │
│      │ ▓▓                     CABLE MANAGEMENT                    ▓▓ │  │
│      │ ▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓ │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 38U  │ ◄═══ APC UPS #1 - Input: 32A 3-Phase, Output: C19/C13 ═══► │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 37U  │ ◄═══ APC UPS #2 - Input: 32A 3-Phase, Output: C19/C13 ═══► │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 33U  │ ◄═══ FG-PRI: PWR1→UPS-1, PWR2→UPS-2, MGMT, CONSOLE ═══►    │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 32U  │ ◄═══ FG-SEC: PWR1→UPS-2, PWR2→UPS-1, MGMT, CONSOLE ═══►    │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 30U  │ ◄═══ SW1: PWR1→PDU-1, PWR2→PDU-2, MGMT, CONSOLE, ISL ═══►  │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 29U  │ ◄═══ SW2: PWR1→PDU-2, PWR2→PDU-1, MGMT, CONSOLE, ISL ═══►  │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 27U  │ ◄═══ ATS: IN1→UPS-1, IN2→UPS-2, OUT→PDU-3, PDU-4 ═══►      │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 25U  │ ◄═══ R760: PSU-A→PDU-1, PSU-B→PDU-2, iDRAC, VGA ═══►       │  │
├──────┼──────────────────────────────────────────────────────────────┤
│ 23-20│ ◄═══ HD6500: PSU1→PDU-3, PSU2→PDU-4, MGMT, EXPANSION ═══►  │  │
└──────┴──────────────────────────────────────────────────────────────┘

LEGEND:
═══► = Cable direction / connections
PWR = Power supply connection
MGMT = Management port
CONSOLE = Serial console port
ISL = Inter-Switch Link (fiber)
PDU = Power Distribution Unit
ATS = Automatic Transfer Switch

## Document Information

| Field | Value |
| --- | --- |
| **Document Title** | Part 2: Network Infrastructure, Wireless & Servers |
| **Project** | B2H Studios IT Infrastructure Implementation |
| **Client** | B2H Studios |
| **Version** | 1.0 |
| **Date** | March 22, 2026 |
| **Prepared By** | VConfi Solutions |
| **Classification** | CONFIDENTIAL |
| **Status** | Final |

End of Part 2

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Part 3: DR/Backup, Monitoring/SIEM & Power/UPS

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

# Part 3 — Disaster Recovery, Monitoring & Power

## B2H Studios IT Infrastructure Implementation Plan

Client: B2H Studios

Project: Option B+ (Optimized Synology HD6500 Solution)

Prepared by: VConfi Solutions

Date: March 22, 2026

Version: 1.0

Classification: CONFIDENTIAL

## 1. Backup Architecture

### 1.1 3-2-1-1-0 Backup Strategy

B2H Studios implements an enhanced 3-2-1-1-0 backup strategy that provides comprehensive data protection against all common failure scenarios including ransomware, hardware failures, and site disasters.

| Component | Description | Implementation |
| --- | --- | --- |
| **3** — Three copies of data | Primary production data plus two backup copies | 1) Production data on HD6500 Site A, 2) Replica on HD6500 Site B, 3) Archive in Wasabi Cloud |
| **2** — Two different media types | Data stored on different storage technologies | 1) On-premises NAS (SAS HDD + NVMe SSD), 2) Cloud object storage (Wasabi S3) |
| **1** — One offsite copy | Geographic separation for disaster recovery | Site B DR NAS located at secondary data center (client to specify exact location) |
| **1** — One immutable copy | Write-once protection against ransomware | Wasabi Object Lock with 7-year WORM retention + DSM immutable snapshots |
| **0** — Zero errors after recovery testing | Verified recoverability through regular testing | Quarterly DR drills with automated integrity verification |

### 1.2 Backup Topology Diagram

flowchart TB
    subgraph "Site A — Primary Data Center"
        A[Editors & Workstations<br/>VLAN 20] -->|NFS/SMB| B[Synology HD6500<br/>Primary NAS]
        B -->|Snapshot Replication| C[Local Snapshots<br/>Every 2 hours]
        B -->|Real-time Sync| D[Replication Manager]
        B -->|Daily Archive| E[Hybrid Share<br/>Wasabi Tier]
    end
    
    subgraph "Site B — DR Site"
        F[Synology HD6500<br/>DR NAS] -->|Promote on Failover| G[DR Active Mode]
    end
    
    subgraph "Cloud — Wasabi Hot Cloud"
        H[Wasabi S3<br/>s3.ap-southeast-1] -->|Immutable| I[WORM Archive<br/>7-Year Retention]
    end
    
    D -->|Encrypted Replication<br/>Bandwidth Throttled| F
    E -->|Object Lock Enabled| H
    
    style B fill:#4a90d9,stroke:#2c5a8c,stroke-width:2px,color:#fff
    style F fill:#5cb85c,stroke:#3d7a3d,stroke-width:2px,color:#fff
    style H fill:#f0ad4e,stroke:#c6892b,stroke-width:2px,color:#000
    style I fill:#d9534f,stroke:#a9302a,stroke-width:2px,color:#fff

### 1.3 Backup Schedule

| Data Type | Source | Destination | Frequency | Retention | Encryption |
| --- | --- | --- | --- | --- | --- |
| Active Projects | HD6500 Site A | HD6500 Site B | Real-time (RTRR) | 30 days version history | AES-256 in transit & at rest |
| Archive Data | HD6500 Site A | HD6500 Site B | Daily at 2:00 AM IST | 90 days | AES-256 in transit & at rest |
| Cloud Archive | HD6500 Site A | Wasabi Cloud | Daily at 11:00 PM IST | 7 years (WORM) | AES-256 client-side encryption |
| Configuration | HD6500 DSM | HD6500 Site B | Hourly | 30 days | DSM encrypted replication |
| System Snapshots | HD6500 Site A | Local storage | Every 2 hours | 24 copies (48 hours) + 30 daily + 12 monthly | DSM native encryption |
| VM Backups | Dell R760 VMs | HD6500 Site A | Daily at 1:00 AM IST | 14 days | Veeam encryption |
| Database Backups | Vault, EMS, Analyzer | HD6500 Site A | Every 4 hours | 30 days | Application-level encryption |

### 1.4 Backup Flow Diagram (3-2-1 Visual)

flowchart LR
    subgraph "Primary Copy"
        P[Production Data<br/>HD6500 Site A<br/>Status: ACTIVE]
    end
    
    subgraph "Secondary Copy"
        S[DR Replica<br/>HD6500 Site B<br/>Status: STANDBY]
    end
    
    subgraph "Tertiary Copy"
        T[Cloud Archive<br/>Wasabi S3<br/>Status: IMMUTABLE]
    end
    
    subgraph "Media Types"
        M1[On-Premises NAS<br/>SAS + NVMe]
        M2[Cloud Object<br/>S3-Compatible]
    end
    
    P -->|Media Type 1| M1
    S -->|Media Type 1| M1
    T -->|Media Type 2| M2
    
    P -.->|Replication| S
    P -.->|Archive| T
    
    style P fill:#4a90d9,stroke:#2c5a8c,stroke-width:3px,color:#fff
    style S fill:#5cb85c,stroke:#3d7a3d,stroke-width:2px,color:#fff
    style T fill:#f0ad4e,stroke:#c6892b,stroke-width:2px,color:#000

## 2. RPO/RTO Targets

### 2.1 Recovery Objectives

B2H Studios has established the following Recovery Point Objectives (RPO) and Recovery Time Objectives (RTO) based on business criticality of systems and data.

| System | RPO | RTO | Method | Verification |
| --- | --- | --- | --- | --- |
| Active Projects | 15 minutes | 10 minutes | Real-time replication (RTRR) with automatic failover | Daily sync verification |
| Archive Data | 4 hours | 30 minutes | Daily scheduled replication + incremental sync | Weekly integrity check |
| Complete Site Failure | 15 minutes | 10 minutes | DR failover: Promote Site B, update ZTNA profiles | Quarterly DR drill |
| Configuration Data | 24 hours | 2 hours | Automated DSM configuration backup to Site B | Post-change validation |
| VM Infrastructure | 24 hours | 4 hours | Veeam VM replication + restoration | Monthly restore test |
| Signiant SDCX Server | 4 hours | 2 hours | VM snapshot + configuration backup | Weekly service check |
| FortiGate Configuration | 0 (real-time) | 5 minutes | HA pair configuration sync | Automatic (HA monitoring) |
| User Authentication | 1 hour | 30 minutes | FortiAuthenticator replication + AD sync | Daily auth test |
| Monitoring Systems | 24 hours | 1 hour | Zabbix database backup + VM snapshot | Weekly restore drill |
| SIEM Logs | 1 hour | 2 hours | Splunk forwarder buffer + indexer cluster | Daily log verification |

### 2.2 RPO/RTO Achievement Matrix

flowchart TB
    subgraph "Data Loss Tolerance RPO"
        RPO1[15 min<br/>Active Projects] 
        RPO2[4 hours<br/>Archive Data]
        RPO3[24 hours<br/>Configuration]
    end
    
    subgraph "Recovery Speed RTO"
        RTO1[5-10 min<br/>Critical Systems]
        RTO2[30 min<br/>Important Systems]
        RTO3[1-4 hours<br/>Standard Systems]
    end
    
    subgraph "Protection Methods"
        M1[Real-time Replication<br/>HA Pairs<br/>Continuous Sync]
        M2[Scheduled Replication<br/>Incremental Backup]
        M3[Daily Backup<br/>Configuration Export]
    end
    
    RPO1 --> M1 --> RTO1
    RPO2 --> M2 --> RTO2
    RPO3 --> M3 --> RTO3
    
    style RPO1 fill:#d9534f,stroke:#a9302a,color:#fff
    style RTO1 fill:#d9534f,stroke:#a9302a,color:#fff
    style RPO2 fill:#f0ad4e,stroke:#c6892b,color:#000
    style RTO2 fill:#f0ad4e,stroke:#c6892b,color:#000
    style RPO3 fill:#5cb85c,stroke:#3d7a3d,color:#fff
    style RTO3 fill:#5cb85c,stroke:#3d7a3d,color:#fff

## 3. DR Site Plan — Site B

### 3.1 Site B Overview

| Attribute | Specification |
| --- | --- |
| **Location** | Secondary data center (client to specify exact location) |
| **DR Tier** | Warm standby (active-passive) |
| **Distance from Site A** | Minimum 50km recommended for geographic separation |
| **Connectivity** | Dedicated MPLS or high-bandwidth VPN link |
| **Power** | Independent utility feed + generator backup |
| **Physical Security** | ISO 27001-aligned data center facility |

### 3.2 DR Replication Configuration

| Parameter | Configuration |
| --- | --- |
| **Replication Technology** | Synology Replication Manager (RTRR) |
| **Replication Mode** | Real-time for active projects, scheduled for archive |
| **Compression** | Enabled (LZ4 algorithm) — reduces bandwidth by ~40% |
| **Encryption** | AES-256-GCM for data in transit |
| **Bandwidth Throttling — Business Hours (9 AM — 7 PM IST)** | 80% of available WAN bandwidth |
| **Bandwidth Throttling — Off-Hours (7 PM — 9 AM IST)** | 100% of available WAN bandwidth |
| **Bandwidth Throttling — Weekends** | 100% of available WAN bandwidth |
| **Snapshot Schedule** | Every 2 hours with 30-minute application consistency checkpoint |
| **Replication Verification** | Automated integrity check every 6 hours |
| **Failover Trigger** | Manual (prevents split-brain scenarios) |

### 3.3 DR Replication Diagram (Site A ↔ Site B)

flowchart TB
    subgraph "Site A — Primary"
        A1[Editors Workstation<br/>VLAN 20]
        A2[HD6500 Primary<br/>60x 18TB SAS RAID6]
        A3[Replication Manager<br/>RTRR Server]
        A4[FortiGate 120G<br/>HA Primary]
        A5[Dell R760<br/>VM Host]
    end
    
    subgraph "WAN Link"
        W1[MPLS/VPN<br/>Encrypted Tunnel<br/>AES-256]
        W2[Bandwidth Control<br/>80% Biz / 100% Night]
    end
    
    subgraph "Site B — DR"
        B1[HD6500 DR<br/>60x 18TB SAS RAID6]
        B2[Replication Manager<br/>RTRR Target]
        B3[FortiGate 120G<br/>HA Secondary]
        B4[Dell R760<br/>DR VM Host]
        B5[Standby Mode<br/>Ready for Promotion]
    end
    
    A1 -->|NFS/SMB Access| A2
    A2 -->|Real-time Sync| A3
    A3 -->|Compressed<br/>Encrypted| W1
    W1 --> W2
    W2 -->|Replication Stream| B2
    B2 -->|Write to| B1
    A4 -.->|Config Sync| B3
    A5 -.->|VM Replica| B4
    
    style A2 fill:#4a90d9,stroke:#2c5a8c,stroke-width:2px,color:#fff
    style B1 fill:#5cb85c,stroke:#3d7a3d,stroke-width:2px,color:#fff
    style W1 fill:#f0ad4e,stroke:#c6892b,stroke-width:2px,color:#000
    style W2 fill:#f0ad4e,stroke:#c6892b,stroke-width:2px,color:#000

### 3.4 Failover Runbook

Trigger Condition: Site A is confirmed unavailable (unreachable for >15 minutes with no response from on-site contact)

| Step | Action | Owner | Duration | Verification |
| --- | --- | --- | --- | --- |
| 1 | Verify Site A is unavailable — check monitoring alerts, attempt remote access, contact on-site personnel | IT Manager | 5 minutes | Confirmation of site failure |
| 2 | Convene incident response team — notify IT staff via emergency contact list | IT Manager | 2 minutes | Team assembled on bridge |
| 3 | Promote Site B HD6500 to primary — access Replication Manager, execute "Promote to Primary" command | Senior Admin | 3 minutes | Site B NAS shows "Primary" status |
| 4 | Update FortiGate ZTNA profiles — change gateway IP from Site A to Site B public IP | Network Admin | 2 minutes | ZTNA gateway responds on Site B IP |
| 5 | Verify DNS/ZTNA propagation — confirm FortiClient connections route to Site B | Network Admin | 2 minutes | Test ZTNA connection successful |
| 6 | Notify all employees — send email/Slack notification with new access instructions | IT Manager | 2 minutes | Confirmation sent to all users |
| 7 | Verify data integrity — run automated consistency check on critical shares | Senior Admin | 5 minutes | Integrity check passes |
| 8 | Verify application services — confirm Signiant, Vault, EMS operational on DR VMs | System Admin | 5 minutes | All services responding |
| 9 | Document incident timeline — update incident log with all actions taken | IT Manager | 5 minutes | Incident record complete |
| 10 | **Total Estimated Failover Time** | **~10 minutes** |  |  |

### 3.5 Failback Runbook

Trigger Condition: Site A has been restored and is ready to resume primary operations

| Step | Action | Owner | Duration | Verification |
| --- | --- | --- | --- | --- |
| 1 | Verify Site A is fully restored — all hardware operational, network connectivity confirmed | IT Manager | 10 minutes | Site A health check passes |
| 2 | Create reverse replication schedule — Site B → Site A for delta synchronization | Senior Admin | 5 minutes | Replication job created successfully |
| 3 | Synchronize all changes made during outage — allow delta sync to complete | System | Variable | Sync completion notification |
| 4 | Verify data consistency — compare checksums between Site A and Site B | Senior Admin | 10 minutes | Checksums match |
| 5 | Schedule maintenance window — notify users of planned failback | IT Manager | 1 minute | Notifications sent |
| 6 | Stop user access to Site B — gracefully disconnect active sessions | Network Admin | 2 minutes | No active connections on Site B |
| 7 | Execute final delta sync — capture last-minute changes | System | 5 minutes | Final sync complete |
| 8 | Promote Site A back to primary — Replication Manager failback command | Senior Admin | 3 minutes | Site A shows "Primary" status |
| 9 | Restore normal replication direction — Site A → Site B | Senior Admin | 5 minutes | Replication job active |
| 10 | Update FortiGate ZTNA profiles — revert gateway to Site A public IP | Network Admin | 2 minutes | ZTNA gateway responds on Site A IP |
| 11 | Verify user connectivity — test access from sample workstations | Network Admin | 5 minutes | Users can access resources |
| 12 | Document failback completion — update incident log, close incident | IT Manager | 5 minutes | Incident closed |

### 3.6 DR Testing Schedule

| Test Type | Frequency | Duration | Scope | Success Criteria |
| --- | --- | --- | --- | --- |
| Replication Verification | Daily (automated) | 15 minutes | Data integrity check | 100% checksum match |
| Failover Simulation | Monthly | 2 hours | Partial failover (non-production data) | RTO < 15 minutes achieved |
| Full DR Drill | Quarterly | 4 hours | Complete site failover and failback | Full RPO/RTO targets met |
| Tabletop Exercise | Bi-annually | 1 hour | Walkthrough with IT team | All team members understand roles |
| Documentation Review | Annually | 2 hours | Update runbooks, contact lists | All documentation current |
| Vendor Coordination Test | Annually | 3 hours | Test ISP failover, support escalation | All vendor contacts responsive |

## 4. Zabbix Monitoring Setup

### 4.1 Zabbix Server Specifications

| Component | Specification |
| --- | --- |
| **Host** | Dell PowerEdge R760 (Virtual Machine) |
| **vCPU** | 4 cores |
| **RAM** | 8 GB |
| **Storage** | 200 GB (SSD) |
| **Operating System** | Ubuntu Server 22.04 LTS |
| **Zabbix Version** | 6.4 LTS |
| **Database** | PostgreSQL 15 |
| **Web Server** | Nginx |
| **High Availability** | Zabbix HA pair at Site A (primary) and Site B (standby) |

### 4.2 Monitored Devices and Metrics

| Device | Metrics Collected | Collection Interval | Alert Threshold | Severity |
| --- | --- | --- | --- | --- |
| FortiGate 120G | CPU utilization | 1 minute | > 80% sustained 5 min | High |
| FortiGate 120G | Memory utilization | 1 minute | > 85% | High |
| FortiGate 120G | Active sessions | 1 minute | > 1,000,000 sessions | Critical |
| FortiGate 120G | Interface bandwidth | 1 minute | > 80% of capacity | Warning |
| FortiGate 120G | HA status | 1 minute | HA not synchronized | Critical |
| Synology HD6500 | Disk health (SMART) | 5 minutes | Any predictive failure warning | Critical |
| Synology HD6500 | Temperature | 1 minute | > 45°C | Warning |
| Synology HD6500 | Volume utilization | 5 minutes | > 85% | Warning |
| Synology HD6500 | Volume utilization | 5 minutes | > 95% | Critical |
| Synology HD6500 | RAID status | 1 minute | Degraded or crashed | Critical |
| Synology HD6500 | Network throughput | 1 minute | > 90% of capacity | High |
| Synology HD6500 | Replication lag | 5 minutes | > 30 minutes behind | High |
| HPE Aruba CX 6300M | Port status | 1 minute | Link down on production port | Critical |
| HPE Aruba CX 6300M | Port bandwidth | 1 minute | > 80% utilization | Warning |
| HPE Aruba CX 6300M | CPU utilization | 1 minute | > 70% | Warning |
| HPE Aruba CX 6300M | Temperature | 1 minute | > 60°C | Warning |
| HPE Aruba CX 6300M | VSX stack status | 1 minute | VSX split or failure | Critical |
| APC Smart-UPS 10kVA | Battery charge level | 5 minutes | < 30% | Critical |
| APC Smart-UPS 10kVA | Load percentage | 5 minutes | > 80% | Warning |
| APC Smart-UPS 10kVA | Input voltage | 5 minutes | Out of nominal range | Warning |
| APC Smart-UPS 10kVA | UPS status | 1 minute | On battery or bypass | High |
| Dell R760 VMs | CPU utilization | 1 minute | > 90% sustained 10 min | Warning |
| Dell R760 VMs | Memory utilization | 1 minute | > 90% | Warning |
| Dell R760 VMs | Disk utilization | 5 minutes | > 85% | Warning |
| Dell R760 VMs | Service status | 1 minute | Critical service stopped | Critical |
| FortiAP 431F | Client count | 5 minutes | > 50 clients per AP | Warning |
| FortiAP 431F | Signal strength | 5 minutes | < -70 dBm average | Warning |
| Environmental | Rack temperature | 5 minutes | > 30°C | Warning |
| Environmental | Rack humidity | 5 minutes | > 70% RH | Warning |

### 4.3 SNMP Configuration

| Parameter | Configuration |
| --- | --- |
| **SNMP Version** | v3 (preferred) with fallback to v2c for legacy devices |
| **Authentication Protocol** | SHA-256 |
| **Privacy Protocol** | AES-256 |
| **Username** | zabbix-monitor (unique per device) |
| **Security Level** | authPriv (authentication + encryption) |
| **Context** | Device-specific contexts for multi-tenant where applicable |
| **Trap Reception** | Enabled on Zabbix server for asynchronous alerts |
| **Trap Sources** | FortiGate, HD6500, HPE switches, UPS |

### 4.4 Monitoring Architecture Diagram

flowchart TB
    subgraph "Zabbix Server"
        Z1[Zabbix Server<br/>4 vCPU / 8GB RAM<br/>Site A Primary]
        Z2[Zabbix Database<br/>PostgreSQL]
        Z3[Zabbix Web<br/>Dashboard]
    end
    
    subgraph "Data Collection"
        P1[SNMP Pollers<br/>v3 with Auth+Priv]
        P2[Zabbix Agents<br/>VMs & Servers]
        P3[SNMP Traps<br/>Async Alerts]
        P4[IPMI
         Hypervisors]
    end
    
    subgraph "Monitored Infrastructure"
        M1[FortiGate 120G<br/>SNMP v3]
        M2[HD6500 NAS<br/>SNMP + DSM API]
        M3[HPE Switches<br/>SNMP v3]
        M4[APC UPS<br/>SNMP v3]
        M5[Dell R760 VMs<br/>Zabbix Agent]
        M6[FortiAP<br/>FortiGate Integration]
    end
    
    subgraph "Alert Channels"
        A1[Email<br/>IT Team]
        A2[SMS<br/>On-Call]
        A3[Slack<br/>#infrastructure-alerts]
        A4[Webhook<br/>ServiceNow]
    end
    
    M1 -->|SNMP| P1
    M2 -->|SNMP/API| P1
    M3 -->|SNMP| P1
    M4 -->|SNMP| P1
    M5 -->|Agent| P2
    M6 -.->|Via FortiGate| M1
    
    P1 --> Z1
    P2 --> Z1
    P3 --> Z1
    
    Z1 --> Z2
    Z1 --> Z3
    
    Z1 -->|Triggers| A1
    Z1 -->|Triggers| A2
    Z1 -->|Triggers| A3
    Z1 -->|Triggers| A4
    
    style Z1 fill:#4a90d9,stroke:#2c5a8c,stroke-width:2px,color:#fff
    style Z3 fill:#5cb85c,stroke:#3d7a3d,stroke-width:2px,color:#fff
    style A2 fill:#d9534f,stroke:#a9302a,stroke-width:2px,color:#fff

### 4.5 Dashboard Configuration

| Dashboard | Widgets | Refresh Rate | Target Audience |
| --- | --- | --- | --- |
| **Executive Overview** | Overall health score, uptime %, incident count, SLA compliance | 5 minutes | IT Manager, C-level |
| **Network Operations** | FortiGate status, bandwidth graphs, VPN sessions, threat count | 1 minute | Network Admin |
| **Storage Health** | HD6500 disk status, capacity trends, replication lag, IOPS | 1 minute | Storage Admin |
| **Compute Resources** | VM CPU/memory, service status, hypervisor health | 1 minute | System Admin |
| **Security Overview** | Failed logins, blocked threats, honeypot alerts, ZTNA status | 1 minute | Security Admin |
| **Power & Environment** | UPS status, rack temperature, power consumption | 5 minutes | Facilities / IT |
| **DR Status** | Replication health, Site B sync status, last DR test date | 5 minutes | IT Manager |

### 4.6 Alert Channels

| Channel | Purpose | Configuration | Escalation |
| --- | --- | --- | --- |
| **Email** | All alert severities | SMTP via FortiMail/Exchange; Distribution lists per severity | Auto-escalate unacknowledged |
| **SMS** | Critical and High alerts only | Twilio integration; On-call rotation | Direct to IT Manager after 15 min |
| **Slack** | Real-time team notifications | #infrastructure-alerts channel; Thread per incident | Tag on-call engineer |
| **Webhook** | ServiceNow ticket creation | REST API; Auto-create incident tickets | Workflow-based escalation |
| **Mobile App** | Admin push notifications | Zabbix mobile app for iOS/Android | Direct notification |

### 4.7 Escalation Matrix

| Severity | Definition | Response Time | Initial Assignment | Escalation Path |
| --- | --- | --- | --- | --- |
| **P1 — Critical** | Complete service outage; Production down; Security breach | 15 minutes | On-call Senior Admin | 15 min → IT Manager → 30 min → CTO |
| **P2 — High** | Major functionality impaired; Significant performance degradation | 1 hour | On-call Admin | 2 hours → Senior Admin → 4 hours → IT Manager |
| **P3 — Medium** | Minor functionality affected; Workaround available | 4 hours | Admin (business hours) | Next business day → Senior Admin |
| **P4 — Low** | Cosmetic issues; Informational alerts | 24 hours | Admin (business hours) | Weekly review in team meeting |
| **P5 — Informational** | No action required; Logging only | N/A | Auto-close | N/A |

## 5. Splunk SIEM Configuration

### 5.1 Splunk Infrastructure

| Component | Specification |
| --- | --- |
| **License Tier** | 50 GB/day ingestion |
| **Deployment** | Splunk Enterprise 9.x |
| **Architecture** | Single-site indexer cluster (2 indexers) + Search Head |
| **Search Head** | 8 vCPU, 16 GB RAM, 500 GB storage |
| **Indexers** | 2x 8 vCPU, 16 GB RAM, 2 TB storage each |
| **Forwarders** | Universal Forwarders on all Windows/Linux systems |
| **Deployment Server** | Manages forwarder configuration |
| **High Availability** | Search head clustering for redundancy |

### 5.2 Log Sources

| Source | Log Type | Collection Method | Volume/Day | Retention Tier |
| --- | --- | --- | --- | --- |
| FortiGate 120G (Primary) | CEF (Common Event Format) | Syslog over TLS | 10 GB | 90 days hot |
| FortiGate 120G (Secondary) | CEF | Syslog over TLS | 2 GB | 90 days hot |
| FortiClient EMS | Syslog | Direct Splunk TA | 2 GB | 90 days hot |
| Synology HD6500 DSM | Syslog | DSM Log Center → Syslog | 5 GB | 90 days hot |
| Kaspersky Security Center | Syslog | Kaspersky Splunk TA | 3 GB | 90 days hot |
| HPE Aruba CX 6300M Switches | Syslog | Switch native syslog | 1 GB | 90 days hot |
| Windows Servers (R760 VMs) | WinEventLog + Sysmon | Splunk Universal Forwarder | 5 GB | 90 days hot |
| FortiAnalyzer | CEF | FortiAnalyzer → Splunk | 3 GB | 90 days hot |
| FortiAuthenticator | Syslog | Direct syslog | 1 GB | 90 days hot |
| HashiCorp Vault | Audit Logs | File monitor + API | 500 MB | 90 days hot |
| Zabbix | Alert History | Database query | 500 MB | 90 days hot |
| **Total Daily Volume** | **~33 GB** | Within 50 GB license |  |  |

### 5.3 Correlation Rules (Searches)

| Rule Name | Description | Detection Logic | Severity | Response Action |
| --- | --- | --- | --- | --- |
| **Brute Force Detection** | Multiple failed login attempts | > 5 failed logins from same src_ip within 5 minutes on any system | High | Alert SOC; Auto-block IP at FortiGate |
| **Honeypot Directory Access** | Potential ransomware activity | Any file access to /honeypot/ directories on HD6500 | Critical | Immediate alert; Isolate source IP; Initiate incident response |
| **Unusual Data Transfer Volume** | Potential data exfiltration | Outbound transfer > 100 GB in 1 hour or > 500 GB in 24 hours | High | Alert IT Manager; Require justification |
| **After-Hours Admin Access** | Insider threat indicator | Admin account login between 11 PM — 5 AM IST | Medium | Alert with approval workflow |
| **FortiGate Threat Detection** | Firewall blocked threats | High/Critical severity threats blocked by FortiGate | Medium | Daily digest + immediate for critical |
| **Multiple VPN Failures** | Compromised credentials or attack | > 3 failed ZTNA connections from same user within 10 min | High | Alert SOC; Force password reset |
| **DSM Snapshot Anomaly** | Ransomware snapshot deletion attempt | Snapshot deletion command from non-admin source | Critical | Block command; Alert security team |
| **Privilege Escalation** | Unauthorized privilege gain | New admin account created or permissions changed | High | Alert IT Manager; Audit trail review |
| **Geographic Impossibility** | Compromised account indicator | Same user login from different countries within 1 hour | Critical | Block second session; Force MFA re-auth |
| **Malware Detection** | Kaspersky threat alert | Malware detected and quarantined | High | Isolate endpoint; Alert admin |
| **Configuration Change** | Unauthorized config modification | FortiGate or HD6500 config change outside change window | Medium | Alert with change ticket verification |
| **Dormant Account Reactivation** | Suspicious account behavior | Login from account inactive > 90 days | Medium | Require manager approval |

### 5.4 Log Retention Policy

| Tier | Duration | Storage Location | Searchable | Cost Profile |
| --- | --- | --- | --- | --- |
| **Hot** | 90 days | Splunk indexers (SSD) | Yes — Full speed | High |
| **Warm** | 91 days — 1 year | Splunk indexers (HDD) | Yes — Reduced performance | Medium |
| **Cold** | 1 year — 3 years | Wasabi S3 archive | No — Restore required | Low |
| **Frozen** | > 3 years | Offline tape (optional) | No — Manual retrieval | Minimal |

### 5.5 Cold Storage Archive Process

| Step | Action | Frequency | Automation |
| --- | --- | --- | --- |
| 1 | Identify logs older than 1 year | Daily | Splunk scheduled search |
| 2 | Export to compressed format | Daily | Splunk archive script |
| 3 | Transfer to Wasabi S3 | Daily | Automated S3 sync |
| 4 | Verify integrity (checksum) | Daily | Automated verification |
| 5 | Delete from Splunk index | Daily | Automated deletion post-verification |
| 6 | Update retention registry | Daily | Automated logging |

## 6. UPS & Power Infrastructure

### 6.1 Power Load Calculation

| Device | Quantity | Watts Each | Total Watts | Notes |
| --- | --- | --- | --- | --- |
| Synology HD6500 (Primary) | 1 | 1,400W | 1,400W | Fully populated with 60 drives |
| Synology HD6500 (DR) | 1 | 1,400W | 1,400W | Site B equivalent |
| Dell PowerEdge R760 (Primary) | 1 | 1,100W | 1,100W | Peak load with all VMs |
| Dell PowerEdge R760 (DR) | 1 | 1,100W | 1,100W | Site B lighter spec |
| FortiGate 120G (Primary HA Pair) | 2 | 200W | 400W | Active-passive pair |
| FortiGate 120G (DR HA Pair) | 2 | 200W | 400W | Site B equivalent |
| HPE Aruba CX 6300M (Primary Stack) | 2 | 150W | 300W | VSX stack pair |
| HPE Aruba CX 6300M (DR Stack) | 2 | 150W | 300W | Site B equivalent |
| FortiAP 431F | 8 | 25W | 200W | 4 per site (PoE powered) |
| KVM Console | 1 | 50W | 50W | Rack mount console |
| Network PDUs | 4 | 25W | 100W | Monitored PDUs |
| Rack cooling fans | 2 | 100W | 200W | Thermal management |
| **Subtotal — Site A** | **~4,750W** | Actual calculated load |  |  |
| **Subtotal — Site B** | **~4,450W** | Lighter VM load |  |  |
| **With 20% headroom (Site A)** | **5,700W** | Recommended UPS sizing |  |  |
| **With 20% headroom (Site B)** | **5,340W** | Recommended UPS sizing |  |  |

Note: The following table consolidates representative load for documentation purposes based on typical deployment scenarios:

| Device | Quantity | Watts Each | Total Watts |
| --- | --- | --- | --- |
| Synology HD6500 | 2 | 1,400W | 2,800W |
| Dell PowerEdge R760 | 2 | 1,100W | 2,200W |
| FortiGate 120G | 4 | 200W | 800W |
| HPE Aruba CX 6300M | 4 | 150W | 600W |
| FortiAP 431F | 8 | 25W | 200W |
| Miscellaneous (PDUs, KVM, fans) | — | — | 400W |
| **Total Calculated Load** | **7,000W** |  |  |
| **With 20% Headroom** | **8,400W** |  |  |

### 6.2 UPS Recommendation

| Parameter | Site A Configuration | Site B Configuration |
| --- | --- | --- |
| **Model** | APC Smart-UPS SRT 10000VA | APC Smart-UPS SRT 10000VA |
| **Capacity** | 10 kVA / 10 kW | 10 kVA / 10 kW |
| **Quantity** | 2 units (N+1 redundant) | 2 units (N+1 redundant) |
| **Topology** | Online double-conversion | Online double-conversion |
| **Input Voltage** | 230V 1-phase | 230V 1-phase |
| **Output Voltage** | 230V (configurable) | 230V (configurable) |
| **Runtime at 70% load** | ~45 minutes | ~45 minutes |
| **Runtime at 50% load** | ~75 minutes | ~75 minutes |
| **Battery Type** | Maintenance-free sealed lead-acid | Maintenance-free sealed lead-acid |
| **Hot-swappable batteries** | Yes | Yes |
| **Network management card** | AP9641 (included) | AP9641 (included) |
| **SNMP monitoring** | Yes — v1/v2c/v3 | Yes — v1/v2c/v3 |
| **Environmental monitoring** | Optional temperature/humidity probe | Optional temperature/humidity probe |
| **Warranty** | 3 years (includes batteries) | 3 years (includes batteries) |
| **Estimated Cost (each)** | ₹2,80,000 | ₹2,80,000 |
| **Total Cost per site** | ₹5,60,000 | ₹5,60,000 |

### 6.3 Automatic Transfer Switch (ATS)

| Parameter | Configuration |
| --- | --- |
| **Model** | APC Rack ATS AP7750A |
| **Capacity** | 16A / 230V |
| **Input** | 2x IEC 309 (A and B sources) |
| **Output** | 8x IEC C13 + 2x IEC C19 |
| **Switching time** | < 15 ms (IT equipment compatible) |
| **Monitoring** | SNMP via network card |
| **Quantity per site** | 1 unit |
| **Purpose** | Automatic failover between UPS A and UPS B |
| **Cost** | ₹1,20,000 per unit |

### 6.4 Generator Integration

| Parameter | Specification |
| --- | --- |
| **Generator recommendation** | 15 kVA diesel generator (3-phase input, single-phase output) |
| **ATS for generator** | Automatic mains failure (AMF) panel |
| **Transfer time** | < 10 seconds |
| **Fuel capacity** | 100 liters minimum (8+ hours runtime) |
| **Exhaust** | External venting with silencer |
| **Maintenance** | Monthly test run; Quarterly service |
| **Note** | Client to arrange generator procurement and installation per site requirements |

### 6.5 Power Distribution Diagram

┌─────────────────────────────────────────────────────────────────────────┐
│                         POWER DISTRIBUTION ARCHITECTURE                 │
│                              Site A — Primary Data Center               │
└─────────────────────────────────────────────────────────────────────────┘

    UTILITY POWER                    GENERATOR (Optional)
         │                                 │
         │                                 │
         ▼                                 ▼
    ┌─────────┐                      ┌─────────┐
    │  Mains  │                      │  GenSet │
    │  Input  │                      │  Input  │
    └────┬────┘                      └────┬────┘
         │                                │
         └────────┬───────────────────────┘
                  │
                  ▼
         ┌─────────────────┐
         │   AMF Panel     │  ← Automatic Transfer Switch (Mains/Generator)
         │  (if generator  │
         │   installed)    │
         └────────┬────────┘
                  │
         ┌────────┴────────┐
         │                 │
         ▼                 ▼
    ┌─────────┐       ┌─────────┐
    │  UPS A  │◄─────►│  UPS B  │  ← APC Smart-UPS SRT 10kVA (N+1)
    │10kVA/10k│  ATS  │10kVA/10k│
    └────┬────┘       └────┬────┘
         │                 │
         └────────┬────────┘
                  │
                  ▼
         ┌─────────────────┐
         │   Rack ATS      │  ← APC AP7750A (Device-level redundancy)
         │  (AP7750A)      │
         └────────┬────────┘
                  │
         ┌────────┼────────┬────────┬────────┐
         │        │        │        │        │
         ▼        ▼        ▼        ▼        ▼
    ┌────────┐┌────────┐┌────────┐┌────────┐┌────────┐
    │ HD6500 ││R760 VM ││FortiGate││HPE    ││ PDUs   │
    │  NAS   ││ Host   ││  HA Pair││Switches││ & Misc │
    │1,400W  ││1,100W  ││  400W   ││ 300W   ││ 200W   │
    └────────┘└────────┘└────────┘└────────┘└────────┘

### 6.6 UPS Monitoring Setup

| Parameter | Configuration |
| --- | --- |
| **Management Interface** | APC Network Management Card 3 (AP9641) |
| **IP Assignment** | Static IP in Management VLAN (VLAN 40) |
| **SNMP Configuration** | v3 with SHA authentication and AES encryption |
| **Zabbix Integration** | APC UPS template imported; Auto-discovery enabled |
| **Monitored Parameters** | Battery capacity, runtime, load %, input voltage, output voltage, temperature, self-test results |
| **Alert Thresholds** | Battery < 30% (Critical), Load > 80% (Warning), On battery > 5 min (High), Self-test fail (Critical) |
| **Email Notifications** | Battery/low runtime alerts to facilities and IT |
| **Trap Destinations** | Zabbix server IP for async event notifications |

### 6.7 Power Distribution Unit (PDU) Layout

| Rack Position | PDU A (UPS A) | PDU B (UPS B) | Load Type |
| --- | --- | --- | --- |
| U42-U40 | HD6500 Controller A | HD6500 Controller B | Critical |
| U39-U30 | HD6500 Drive Bays | HD6500 Drive Bays | Critical |
| U28-U25 | Dell R760 PSU1 | Dell R760 PSU2 | Critical |
| U24-U23 | FortiGate Primary | FortiGate Secondary | Critical |
| U22-U21 | HPE Switch 1 | HPE Switch 2 | Critical |
| U20 | Rack ATS Input A | Rack ATS Input B | Infrastructure |
| U19-U18 | Monitored PDU A | Monitored PDU B | Distribution |
| U2-U1 | Bottom cable management | — | — |

## Appendix A: Related Documentation

| Document | Description | Location |
| --- | --- | --- |
| Design Decisions Document | Option B+ architecture decisions | `Design_Decisions.md` |
| Part 1 — Executive & Architecture | Project overview and ISO compliance | `Part1_Executive_Architecture_ISO.md` |
| Part 2 — Network & Wireless | Firewall, switches, wireless design | `Part2_Network_Wireless_Server.md` |
| Part 4 — BOM & Timeline | Full bill of materials and schedule | `Part4_BOM_Assets_Timeline.md` |
| Part 5 — Security Stress Test | Vulnerability assessment and hardening | `Part5_Security_Stress_Test.md` |
| Part 6 — SOPs | Standard operating procedures | `Part6_SOPs.md` |

## Document Control

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | March 22, 2026 | VConfi Solutions | Initial release |

VConfi Solutions

Secure IT Infrastructure for Modern Enterprises

CONFIDENTIAL — For Internal Use Only

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Part 4: Bill of Materials, Asset Lifecycle & Timeline

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

# Part 4 — Bill of Materials, Assets & Implementation Timeline

Document Version: 1.0

Date: March 22, 2026

Client: B2H Studios

Project: IT Infrastructure Implementation — Option B+ (Optimized Synology HD6500 Solution)

Prepared by: VConfi Solutions

## 1. Bill of Materials — Complete Hardware

This section provides a comprehensive Bill of Materials (BOM) for the B2H Studios infrastructure implementation. All pricing is in Indian Rupees (INR).

### 1.1 Site A — Primary Data Centre

| Item | Model/Description | Qty | Unit Price (INR) | Extended (INR) |
| --- | --- | --- | --- | --- |
| NAS Chassis | Synology HD6500 60-bay 4U | 1 | 18,50,000 | 18,50,000 |
| HDD | Seagate Exos 18TB SAS 12Gb/s | 60 | 21,000 | 12,60,000 |
| NVMe SSD | Samsung PM1733 7.68TB NVMe | 4 | 1,45,000 | 5,80,000 |
| Switch | HPE Aruba CX 6300M 48p 1GbE + 4p 25GbE | 2 | 4,20,000 | 8,40,000 |
| Firewall | FortiGate 120G | 2 | 7,10,000 | 14,20,000 |
| Firewall License | FortiGuard UTP Bundle 3-year | 2 | 2,13,000 | 4,26,000 |
| Server | Dell PowerEdge R760 (12C/128GB/8x1.2TB) | 1 | 6,80,000 | 6,80,000 |
| Server License | VMware vSphere Standard 8 | 1 | 1,85,000 | 1,85,000 |
| UPS | APC Smart-UPS SRT 10000VA | 2 | 2,80,000 | 5,60,000 |
| ATS | APC Rack ATS 16A | 1 | 1,20,000 | 1,20,000 |
| PDU | APC Rack PDU 2G Metered ZeroU 16A | 4 | 35,000 | 1,40,000 |
| Cabling | Cat6a/Cat6/Fiber patch cables | 1 | 1,50,000 | 1,50,000 |
| **Site A Subtotal** | **₹82,11,000** |  |  |  |

Site A Hardware Notes:

NAS configured in RAID6 56+4 for 936TB usable capacity

NVMe SSDs configured as read/write cache (30.72TB total cache)

Dell R760 configured with: 2x Intel Xeon Silver 4410Y (12C/24T), 128GB DDR5, 8x 1.2TB SAS 10K HDD

FortiGate 120G deployed in active-passive HA pair

HPE CX 6300M switches deployed with VSX stacking for redundancy

Dual 10kVA UPS with ATS provides N+1 power redundancy

### 1.2 Site B — Disaster Recovery

| Item | Model/Description | Qty | Unit Price (INR) | Extended (INR) |
| --- | --- | --- | --- | --- |
| NAS Chassis | Synology HD6500 60-bay 4U | 1 | 18,50,000 | 18,50,000 |
| HDD | Seagate Exos 18TB SAS 12Gb/s | 60 | 21,000 | 12,60,000 |
| NVMe SSD | Samsung PM1733 7.68TB NVMe | 4 | 1,45,000 | 5,80,000 |
| Switch | HPE Aruba CX 6300M 48p 1GbE + 4p 25GbE | 2 | 4,20,000 | 8,40,000 |
| Firewall | FortiGate 120G | 2 | 7,10,000 | 14,20,000 |
| Firewall License | FortiGuard UTP Bundle 3-year | 2 | 2,13,000 | 4,26,000 |
| Server | Dell PowerEdge R760 (8C/64GB/4x1.2TB) DR | 1 | 4,20,000 | 4,20,000 |
| **Site B Subtotal** | **₹67,96,000** |  |  |  |

Site B Hardware Notes:

Identical storage configuration to Site A for 1:1 replication

Dell R760 DR spec: 1x Intel Xeon Silver 4410Y (12C/24T), 64GB DDR5, 4x 1.2TB SAS 10K HDD

Reduced compute spec as DR site runs in standby mode

Power infrastructure shared with existing facility UPS

### 1.3 Software & Subscriptions (Annual)

| Item | Description | Qty | Annual Cost (INR) |
| --- | --- | --- | --- |
| Wasabi Cloud | Hot Cloud Storage 200TB | 1 | 1,19,520 |
| Signiant Jet | SDCX Server License + Support | 1 | 8,50,000 |
| Synology | Active Backup Suite Enterprise | 1 | 2,40,000 |
| Zabbix | Enterprise Support Contract | 1 | 1,20,000 |
| Splunk | 50GB/day Ingestion License | 1 | 6,50,000 |
| FortiAnalyzer VM | Virtual Appliance License | 1 | 2,10,000 |
| FortiClient EMS | Endpoint Management 100 endpoints | 1 | 1,80,000 |
| FortiAuthenticator | MFA/Identity License 100 users | 1 | 95,000 |
| Kaspersky | Endpoint Security Business 50 seats | 1 | 1,45,000 |
| HashiCorp Vault | Enterprise License | 1 | 3,50,000 |
| **Annual Subtotal** | **₹29,59,520** |  |  |

Software Notes:

Wasabi pricing: ₹498/TB/month with zero egress fees (200TB × ₹498 × 12 months)

Signiant Jet includes FASP protocol license and premium support

Splunk license covers log ingestion from all security devices and NAS audit logs

FortiGuard UTP Bundle includes: Anti-Virus, IPS, Application Control, Web Filtering, Anti-Spam, Security Rating

### 1.4 Professional Services

| Item | Description | Cost (INR) |
| --- | --- | --- |
| Implementation | Hardware installation, racking, cabling | 4,50,000 |
| Configuration | Firewall, switch, NAS, VM setup | 3,20,000 |
| Migration | Data migration, cutover support | 2,80,000 |
| Training | Admin training (2 days) + User training (1 day) | 1,50,000 |
| Documentation | SOPs, runbooks, network diagrams | 80,000 |
| Project Management | 12-week project oversight | 2,00,000 |
| **Services Subtotal** | **₹14,80,000** |  |

Services Notes:

Implementation includes physical installation at both sites

Configuration covers: FortiGate HA, VSX stacking, DSM hardening, ZTNA setup

Migration includes: data sync from existing storage, validation, cutover

Training: 2 days administrator training (5 participants), 1 day user training (25 participants)

Documentation includes: As-built drawings, SOPs, runbooks, DR procedures

### 1.5 Financial Summary

| Category | Amount (INR) |
| --- | --- |
| Hardware (Site A) | 82,11,000 |
| Hardware (Site B) | 67,96,000 |
| Software/Subscriptions (Year 1) | 29,59,520 |
| Professional Services | 14,80,000 |
| **Subtotal** | **1,94,46,520** |
| GST @ 18% | 35,00,374 |
| **Grand Total** | **₹2,29,46,894** |

Payment Schedule:

| Milestone | Payment % | Amount (INR) | Trigger |
| --- | --- | --- | --- |
| Purchase Order | 40% | 91,78,758 | PO signing |
| Site A Go-Live | 40% | 91,78,758 | AC-001 to AC-006 passed |
| Project Completion | 20% | 45,89,378 | Final sign-off |

## 2. Asset Lifecycle Management

The following table outlines the complete asset lifecycle for all major hardware components, including warranty periods, End of Life (EOL) dates, End of Support (EOS) dates, and estimated Annual Maintenance Contract (AMC) costs.

| Asset | Model | Warranty | EOL Date | EOS Date | AMC (Annual) |
| --- | --- | --- | --- | --- | --- |
| HD6500 Site A | Synology HD6500 | 5 years | Mar 2031 | Mar 2033 | ₹1,85,000 |
| HD6500 Site B | Synology HD6500 | 5 years | Mar 2031 | Mar 2033 | ₹1,85,000 |
| FortiGate 120G | FG-120G | 3 years | Mar 2029 | Mar 2031 | ₹2,84,000 |
| HPE CX 6300M | JL659A | Lifetime | Mar 2036 | Mar 2038 | ₹1,26,000 |
| Dell R760 | PowerEdge R760 | 3 years | Mar 2029 | Mar 2031 | ₹1,36,000 |
| UPS 10kVA | SRT10KXLI | 3 years | Mar 2029 | Mar 2031 | ₹84,000 |

Lifecycle Management Notes:

EOL (End of Life): Date when vendor stops selling the product. Parts available until EOS.

EOS (End of Support): Date when vendor stops providing support and security updates.

AMC Calculation: Typically 10-15% of hardware value for enterprise equipment post-warranty.

Warranty Extension: Available for all components; recommended for FortiGate and Dell servers.

Replacement Planning: Budget allocation for hardware refresh should begin 18 months before EOS.

## 3. TCO Analysis

This section presents the Total Cost of Ownership (TCO) analysis over 3-year and 5-year periods, including all hardware, software, services, and maintenance costs.

### 3.1 3-Year TCO

| Year | Hardware | Software | Services | AMC | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | 1,50,07,000 | 29,59,520 | 14,80,000 | - | 1,94,46,520 |
| 2 | - | 29,59,520 | - | 8,15,000 | 37,74,520 |
| 3 | - | 29,59,520 | - | 8,15,000 | 37,74,520 |
| **3-Year Total** | **₹2,69,95,560** |  |  |  |  |

Year 1 Breakdown:

Hardware (Site A + Site B): ₹1,50,07,000

Software/Subscriptions: ₹29,59,520

Professional Services: ₹14,80,000

Years 2-3 Notes:

AMC begins after warranty expiration for FortiGate and Dell servers (Year 4 for Synology)

Software subscriptions remain constant (annual contracts)

No additional hardware purchases anticipated

### 3.2 5-Year TCO

| Year | Hardware | Software | Services | AMC | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | 1,50,07,000 | 29,59,520 | 14,80,000 | - | 1,94,46,520 |
| 2 | - | 29,59,520 | - | 8,15,000 | 37,74,520 |
| 3 | - | 29,59,520 | - | 8,15,000 | 37,74,520 |
| 4 | - | 29,59,520 | - | 9,96,000 | 39,55,520 |
| 5 | - | 29,59,520 | - | 9,96,000 | 39,55,520 |
| **5-Year Total** | **₹3,49,06,600** |  |  |  |  |

5-Year TCO Summary:

| Category | Amount (INR) |
| --- | --- |
| Hardware (Initial) | 1,50,07,000 |
| Software (5 Years) | 1,47,97,600 |
| Professional Services | 14,80,000 |
| AMC (Years 2-5) | 36,22,000 |
| **5-Year TCO** | **₹3,49,06,600** |

AMC Escalation Notes:

Year 2-3: FortiGate + Dell R760 only (₹8,15,000/year)

Year 4-5: Includes Synology HD6500 (5-year warranty expires Mar 2031) → ₹9,96,000/year

Cost Per User (25 employees):

3-Year TCO: ₹10,79,822 per user

5-Year TCO: ₹13,96,264 per user

## 4. Implementation Timeline

The following Gantt chart illustrates the complete 12-week implementation timeline for the B2H Studios infrastructure project.

gantt
    title B2H Studios Implementation Timeline (12 Weeks)
    dateFormat  YYYY-MM-DD
    section Phase 1: Procurement
    Purchase Orders       :done, p1, 2026-04-01, 14d
    Vendor Coordination   :done, p2, 2026-04-01, 14d
    Site Survey           :p3, 2026-04-08, 7d
    section Phase 2: Site A Infrastructure
    Rack Installation     :p4, after p3, 7d
    Power Setup          :p5, after p3, 7d
    Network Deployment   :p6, after p4, 10d
    NAS Installation     :p7, after p5, 7d
    section Phase 3: Site A Services
    VM Deployment        :p8, after p7, 7d
    Security Config      :p9, after p6, 7d
    Monitoring Setup     :p10, after p8, 5d
    section Phase 4: Migration
    Data Migration       :p11, after p10, 7d
    UAT                  :p12, after p11, 3d
    Go-Live              :milestone, p13, after p12, 1d
    section Phase 5: Site B DR
    Site B Hardware      :p14, after p13, 10d
    Replication Config   :p15, after p14, 5d
    Failover Testing     :p16, after p15, 3d
    section Phase 6: Closure
    Documentation        :p17, after p10, 14d
    Training             :p18, after p13, 5d
    Project Sign-off     :milestone, p19, after p18, 1d

### Implementation Phase Details

| Phase | Duration | Key Activities | Deliverables |
| --- | --- | --- | --- |
| **Phase 1: Procurement** | Weeks 1-2 | Purchase orders, vendor coordination, site survey | PO confirmations, site readiness report |
| **Phase 2: Site A Infrastructure** | Weeks 3-6 | Rack installation, power setup, network deployment, NAS installation | Physical infrastructure ready, network baseline |
| **Phase 3: Site A Services** | Weeks 7-8 | VM deployment, security configuration, monitoring setup | All services operational, security baseline |
| **Phase 4: Migration** | Week 9 | Data migration, UAT, go-live | Data migrated, acceptance criteria met |
| **Phase 5: Site B DR** | Weeks 10-12 | Site B hardware installation, replication config, failover testing | DR site operational, RPO/RTO validated |
| **Phase 6: Closure** | Weeks 11-12 | Documentation finalization, training, project sign-off | Complete documentation, trained staff |

### Critical Path

Site Survey → Rack Installation → NAS Installation → VM Deployment → Monitoring Setup → Data Migration → UAT → Go-Live → Training → Project Sign-off

### Risk Mitigation

Week 6 Buffer: Network deployment and NAS installation have 3-day overlap buffer

Week 9 UAT: Short UAT window; priority testing on Day 1-2, fixes on Day 3

Week 12 Overlap: Site B setup and training run in parallel to compress timeline

## 5. Acceptance Criteria

The following acceptance criteria define the conditions for successful project completion. Each criterion includes a verification method and success metric.

| ID | Criterion | Verification Method | Success Metric |
| --- | --- | --- | --- |
| AC-001 | NAS accessible via ZTNA | Functional test | 25 users can connect |
| AC-002 | Replication RPO met | Log review | <15 minutes for active projects |
| AC-003 | DR failover test | DR drill | <10 minutes RTO achieved |
| AC-004 | Backup verification | Restore test | 100% successful restore |
| AC-005 | Security scan passed | Vulnerability scan | Zero critical findings |
| AC-006 | Performance benchmark | Iometer test | >1000 MB/s sequential read |
| AC-007 | User training completed | Attendance sheet | 100% staff trained |

### Acceptance Criteria Details

#### AC-001: NAS Accessible via ZTNA

Test Procedure: Each of 25 users connects to NAS shares via FortiClient ZTNA from remote locations

Verification: Successful file operations (read/write) from all 25 user accounts

Fail Criteria: >1 user unable to connect or perform file operations

#### AC-002: Replication RPO Met

Test Procedure: Review Snapshot Replication logs for 7-day period

Verification: All active project snapshots replicated within 15 minutes of creation

Fail Criteria: Any replication gap >15 minutes for active projects

#### AC-003: DR Failover Test

Test Procedure: Simulate Site A failure, promote Site B to active

Verification: DNS updated, ZTNA profiles switched, users can access DR NAS

Fail Criteria: RTO >10 minutes or data inconsistency detected

#### AC-004: Backup Verification

Test Procedure: Perform full restore test of 5 random files from each tier

Verification: All files restore successfully with integrity verified (checksum)

Fail Criteria: Any restore failure or checksum mismatch

#### AC-005: Security Scan Passed

Test Procedure: Run vulnerability scan (Nessus/OpenVAS) against all infrastructure

Verification: Zero critical vulnerabilities, CVSS >7.0 findings remediated

Fail Criteria: Any critical vulnerability unremediated

#### AC-006: Performance Benchmark

Test Procedure: Iometer sequential read test from 5 concurrent clients

Verification: Aggregate throughput >1000 MB/s (500 MB/s per HD6500 minimum)

Fail Criteria: Sustained throughput <1000 MB/s

#### AC-007: User Training Completed

Test Procedure: Review attendance sheets for admin training (2 days) and user training (1 day)

Verification: 100% of 25 staff members attended required sessions

Fail Criteria: <100% attendance without documented make-up plan

## Appendix A: Vendor Contact Information

| Vendor | Product | Contact | Support Portal |
| --- | --- | --- | --- |
| Synology | HD6500 | support@synology.com | https://account.synology.com |
| HPE | Aruba CX 6300M | support.hpe.com | https://support.hpe.com |
| Fortinet | FortiGate 120G | support@fortinet.com | https://support.fortinet.com |
| Dell | PowerEdge R760 | support.dell.com | https://www.dell.com/support |
| APC | Smart-UPS SRT | support.apc.com | https://www.se.com/support |

## Appendix B: Document Control

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | March 22, 2026 | VConfi Solutions | Initial release |

Distribution List:

B2H Studios — IT Management

B2H Studios — Finance

VConfi Solutions — Project Team

VConfi Solutions — Account Management

End of Part 4 — Bill of Materials, Assets & Implementation Timeline

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Part 5: Security Stress Test Results

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

# Part 5 — Security Stress Test & Hardening

## B2H Studios IT Infrastructure Implementation Plan

Client: B2H Studios

Project: Media & Entertainment Infrastructure — Option B+ (Optimized Synology HD6500)

Document Version: 1.0

Date: March 22, 2026

Prepared by: VConfi Solutions

Classification: CONFIDENTIAL

## 1. Executive Summary of Security Assessment

### 1.1 Overall Security Posture: STRONG

The B2H Studios infrastructure design demonstrates a strong security posture aligned with ISO 27001 principles and industry best practices for media and entertainment organizations. The architecture incorporates defense-in-depth principles with multiple layers of protection across network, endpoint, data, and access control domains.

### 1.2 Key Security Strengths

| Strength Area | Implementation | Security Value |
| --- | --- | --- |
| **Zero Trust Network Access (ZTNA)** | FortiClient with device posture checks, MFA via FortiAuthenticator | Eliminates implicit trust; every access request verified |
| **Immutable Backups** | Synology Snapshot Lock with WORM-enabled Wasabi tiering | Ransomware-proof backup architecture; 7-year retention compliance |
| **Network Segmentation** | 5-zone VLAN architecture with FortiGate zone-based firewall | Lateral movement containment; blast radius limitation |
| **Multi-Factor Authentication** | FortiToken push + TOTP for all admin access | Credential theft mitigation; strong authentication enforcement |
| **Dual-Site DR Architecture** | Active-standby with encrypted replication | Business continuity; geographic redundancy |
| **Endpoint Protection Stack** | FortiClient + Kaspersky + EMS centralized management | Defense-in-depth for remote workstations |
| **Security Monitoring** | Splunk SIEM + FortiAnalyzer + Zabbix | Comprehensive visibility; threat detection and response |

### 1.3 Areas Requiring Attention

While the foundational architecture is robust, the security stress test has identified 10 specific vulnerabilities requiring remediation before go-live or during post-deployment hardening. These findings are categorized and prioritized in Section 8 (Vulnerability Report).

### 1.4 Risk Rating Summary

| Risk Category | Rating | Justification |
| --- | --- | --- |
| **Network Security** | LOW | Strong segmentation, next-gen firewall, ZTNA implementation |
| **Data Protection** | LOW | Immutable snapshots, encryption at rest/transit, 3-2-1 backup strategy |
| **Access Control** | MEDIUM | MFA enabled; brute-force protection gaps identified |
| **Endpoint Security** | MEDIUM | Comprehensive stack; DLP gaps on egress traffic |
| **Physical Security** | UNVERIFIED | Data center controls not in scope; requires verification |
| **Human Factor** | MEDIUM | Security awareness training not yet implemented |
| **Overall Risk Rating** | **MEDIUM** | With controls implemented and gaps remediated |

## 2. Attack Surface Analysis

### 2.1 Attack Surface Overview Diagram

flowchart TB
    subgraph Internet["🌐 Internet Threat Landscape"]
        ATTACKER["Attacker"]
    end
    
    subgraph Perimeter["🛡️ Perimeter Layer"]
        FG_WAN["FortiGate 120G WAN<br/>ISP1 + ISP2<br/>Geo-filtering | IPS | DDoS"]
    end
    
    subgraph DMZ["📡 DMZ (VLAN 10)"]
        SIGNIANT["Signiant SDCX<br/>UDP/33001 FASP"]
        ZTNA["ZTNA Portal<br/>HTTPS/443"]
    end
    
    subgraph Internal["🏢 Internal Network"]
        subgraph PROD["Production (VLAN 20)"]
            WORKSTATIONS["Employee Workstations<br/>ZTNA Clients"]
        end
        
        subgraph STORAGE["Storage (VLAN 30)"]
            HD6500["Synology HD6500<br/>NFS/SMB Shares"]
        end
        
        subgraph MGMT["Management (VLAN 40)"]
            R760["Dell R760 VMs"]
            FAZ["FortiAnalyzer"]
            SPLUNK["Splunk SIEM"]
            DSM["DSM Management"]
        end
        
        subgraph GUEST["Guest (VLAN 50)"]
            GUEST_WIFI["Guest Wi-Fi"]
        end
    end
    
    subgraph Wireless["📶 Wireless"]
        FAP["FortiAP"]
    end
    
    ATTACKER --> FG_WAN
    FG_WAN --> SIGNIANT
    FG_WAN --> ZTNA
    FG_WAN --> FAP
    ZTNA --> WORKSTATIONS
    WORKSTATIONS --> HD6500
    R760 --> FAZ
    R760 --> SPLUNK
    R760 --> DSM
    FAP --> WORKSTATIONS
    FAP --> GUEST_WIFI

### 2.2 Comprehensive Attack Surface Table

| Asset | Exposure | Attack Vector | Current Control | Risk Level |
| --- | --- | --- | --- | --- |
| FortiGate 120G WAN | Internet-facing | Exploit, DoS, Brute-force | Geo-filtering, IPS, DDoS protection, HA pair | Low |
| Signiant SDCX Server | Internet-facing (UDP/33001) | Protocol exploit, DDoS | Geo-filtering to operational countries, ZTNA posture check | Medium |
| ZTNA Portal | Internet-facing (HTTPS/443) | Credential stuffing, Session hijacking | MFA (FortiToken push), device certificates, posture validation | Low |
| HD6500 NAS (Production) | Internal only (VLAN 30) | Lateral movement, Privilege escalation | VLAN isolation, firewall rules, NFS/SMB restrictions | Low |
| HD6500 NAS (Management) | Internal only (VLAN 40) | Admin compromise | DSM 2FA, named admin accounts, IP restrictions | Low |
| Employee Endpoints | Remote (ZTNA) | Phishing, malware, credential theft | FortiClient, Kaspersky, EMS, disk encryption | Medium |
| FortiAnalyzer | Internal (VLAN 40) | Log injection, Unauthorized access | VLAN isolation, authentication required, SSL | Low |
| Splunk SIEM | Internal (VLAN 40) | Data exfiltration, Query manipulation | VLAN isolation, SSL, role-based access | Low |
| Dell R760 Server | Internal (VLAN 10/40) | VM escape, Hypervisor exploit | VMware hardening, regular patching, monitoring | Low |
| HPE Aruba Switches | Internal (VLAN 40) | Management interface exploit | SNMP v3, SSH only, management VLAN isolation | Low |
| FortiAuthenticator | Internal (VLAN 40) | Authentication bypass | Hardened VM, backup codes, HA configuration | Low |
| HashiCorp Vault | Internal (VLAN 40) | Secret exfiltration | TLS encryption, Shamir seal, audit logging | Low |
| Guest Wi-Fi (VLAN 50) | Wireless (Internet-only) | Rogue AP, Evil twin | WPA3-Enterprise, rogue detection, client isolation | Medium |
| Wasabi Cloud Endpoint | Internet-facing (HTTPS/443) | Credential compromise, Bucket enumeration | IAM policies, bucket policies, encryption at rest | Low |

## 3. External Attack Scenarios

### 3.1 Scenario 1: Credential Stuffing on ZTNA Portal

Attack Description:

Automated login attempts using credentials harvested from third-party breaches. Attackers use credential stuffing tools to attempt username/password combinations against the ZTNA portal at high velocity.

Security Assessment:

| Aspect | Finding |
| --- | --- |
| **Current Protection** | MFA via FortiAuthenticator (FortiToken push) is mandatory for all ZTNA access |
| **Attack Effectiveness** | Single-factor authentication attempts will fail; MFA challenge blocks automated logins |
| **Residual Risk** | Account lockout not configured; attackers can enumerate valid usernames |

Gap Identified:

No explicit rate limiting or brute-force protection configured on FortiAuthenticator. While MFA prevents successful authentication, the lack of rate limiting allows attackers to:

Enumerate valid user accounts through response timing analysis

Consume authentication resources

Potentially trigger MFA fatigue attacks (repeated push notifications)

Recommendation:

# FortiAuthenticator Configuration
config system global
    set admin-login-max-retry 3
    set admin-login-lockout-threshold 3
    set admin-login-lockout-duration 900
end

# Enable rate limiting on authentication policies
config authentication rule
    edit "ZTNA-Portal-Policy"
        set rate-limit 5
        set rate-limit-duration 300
    next
end

Priority: HIGH (Pre-go-live)

### 3.2 Scenario 2: Signiant FASP Protocol Exploitation

Attack Description:

Malformed FASP (Fast Adaptive Secure Protocol) packets targeting the Signiant SDCX server. Attackers may attempt buffer overflows, protocol state machine manipulation, or denial of service through crafted UDP packets.

Security Assessment:

| Aspect | Finding |
| --- | --- |
| **Current Protection** | Geo-filtering restricts access to operational countries; ZTNA posture check required for management |
| **Attack Surface** | UDP/33001 is open to filtered IP ranges for FASP acceleration |
| **Protocol Security** | FASP uses AES-256 encryption; proprietary protocol reduces exploit availability |

Gap Identified:

No intrusion detection/prevention system (IPS) enabled on the DMZ segment firewall rules. While geo-filtering reduces exposure, sophisticated attackers using compromised infrastructure within allowed countries could:

Probe for FASP protocol vulnerabilities

Attempt DoS through malformed packets

Exploit unpatched SDCX server vulnerabilities

Recommendation:

# FortiGate IPS Configuration
config firewall policy
    edit 102
        set name "DMZ-to-Internal"
        set srcintf "dmz"
        set dstintf "internal"
        set srcaddr "SDCX-Server"
        set dstaddr "NAS-Storage"
        set action accept
        set schedule "always"
        set service "FASP" "HTTPS"
        set ips-sensor "default"
        set av-profile "default"
        set application-list "default"
        set logtraffic all
    next
end

# Create custom IPS filter for FASP
config ips sensor
    edit "FASP-Protection"
        config entries
            edit 1
                set rule "FASP.Protocol.Anomaly"
                set action block
                set log enable
            next
        end
    next
end

Priority: HIGH (Pre-go-live)

### 3.3 Scenario 3: DDoS on FortiGate WAN Interfaces

Attack Description:

Volumetric DDoS attack against internet-facing firewall interfaces. Attack vectors include UDP flood, SYN flood, ICMP flood, and reflected amplification attacks (NTP, DNS, SSDP).

Security Assessment:

| Aspect | Finding |
| --- | --- |
| **Current Protection** | Dual ISP provides resiliency; FortiGate has built-in DDoS protection |
| **Bandwidth Capacity** | 10G+ firewall throughput; ISP links likely 1Gbps or less |
| **Attack Risk** | Saturating both ISP links would cause complete outage |

Gap Identified:

ISP-level DDoS protection not confirmed. Without upstream scrubbing:

Volumetric attacks exceeding ISP link capacity cannot be mitigated at the perimeter

Attack traffic consumes bandwidth before reaching FortiGate defenses

No automatic failover to scrubbing centers

Recommendation:

Immediate: Verify DDoS protection with both ISPs

Request SLA documentation for DDoS mitigation

Confirm automatic detection and scrubbing capabilities

Validate maximum attack size ISP can handle

Post-deployment enhancement: Consider cloud DDoS protection

AWS Shield Advanced or Cloudflare Magic Transit

BGP-based traffic diversion for large attacks

Cost: ₹2,40,000/year for standard business protection

Priority: MEDIUM (Post-deployment)

### 3.4 Scenario 4: SSL/TLS Downgrade Attack

Attack Description:

Attackers force connections to use weaker TLS versions (1.0, 1.1) or weak cipher suites, then exploit known vulnerabilities (BEAST, POODLE, CRIME) to decrypt traffic or inject content.

Security Assessment:

| Aspect | Finding |
| --- | --- |
| **Current State** | FortiGate supports TLS 1.3 but legacy versions may be enabled |
| **Risk Exposure** | Downgrade attacks possible if TLS 1.0/1.1 accepted |
| **Affected Services** | ZTNA portal, Signiant SDCX management, FortiGate admin interface |

Gap Identified:

TLS configuration not explicitly hardened. Default FortiGate configurations often accept TLS 1.0/1.1 for legacy compatibility, creating downgrade vulnerability.

Recommendation:

# FortiGate TLS Hardening
config system global
    set admin-https-ssl-versions tlsv1-2 tlsv1-3
    set ssl-min-prot-ver tlsv1-2
end

# SSL/SSH Inspection Profile
config firewall ssl-ssh-profile
    edit "B2H-Deep-Inspection"
        config https
            set ports 443
            set status deep-inspection
            set unsupported-ssl-ciphers block
            set invalid-server-cert block
            set revoked-server-cert block
            set cert-validation-timeout ignore
            set cert-validation-failure block
        end
        config ssl
            set supported-algorithms tlsv1-2 tlsv1-3
        end
    next
end

# Apply to firewall policies
config firewall policy
    edit 100
        set ssl-ssh-profile "B2H-Deep-Inspection"
    next
end

Priority: HIGH (Pre-go-live)

## 4. Internal Attack Scenarios

### 4.1 Scenario 5: Lateral Movement from Compromised Workstation

Attack Description:

An employee device is compromised (malware, credential theft). The attacker attempts to move laterally from VLAN 20 (Production) to VLAN 30 (Storage) or VLAN 40 (Management) to access sensitive data.

Security Assessment:

| Aspect | Finding |
| --- | --- |
| **Current Protection** | VLAN segmentation with FortiGate inter-VLAN routing; firewall rules restrict traffic |
| **Attack Path** | Production → Storage requires explicit firewall rule; Production → Management requires jump host |
| **Vulnerability** | If VLAN hopping succeeds, DSM management interface accessible |

Gap Identified:

DSM management on VLAN 40 could be accessed if VLAN hopping or routing table manipulation succeeds. Current switch configuration lacks:

Private VLANs on access ports

Dynamic ARP inspection

DHCP snooping

Recommendation:

# HPE Aruba Switch Hardening
# Enable DHCP Snooping
ip dhcp snooping
ip dhcp snooping vlan 20,30,40,50

# Enable Dynamic ARP Inspection
ip arp inspection vlan 20,30,40,50
ip arp inspection validate src-mac dst-mac ip

# Enable Private VLANs on access ports
vlan 20
    private-vlan primary
    private-vlan association 201-210

# Restrict DSM access to specific admin IPs
# FortiGate policy addition:
config firewall policy
    edit 150
        set name "Admin-to-DSM"
        set srcintf "management"
        set dstintf "management"
        set srcaddr "Admin-Workstations"
        set dstaddr "HD6500-DSM"
        set action accept
        set schedule "always"
        set service "HTTPS"
        set logtraffic all
    next
end

Priority: MEDIUM (Post-deployment)

### 4.2 Scenario 6: Privilege Escalation on R760 Server

Attack Description:

Attacker gains access to a VM on the Dell R760 and attempts VM escape to access the hypervisor or other VMs. Alternatively, targets iLO for out-of-band server control.

Security Assessment:

| Aspect | Finding |
| --- | --- |
| **VMware Security** | vSphere provides strong isolation; regular patching required |
| **iLO Exposure** | iLO network on VLAN 40 shares segment with other management services |
| **Risk** | iLO compromise = full server control regardless of VM security |

Gap Identified:

iLO is not on a dedicated management VLAN. Shared VLAN 40 means:

iLO accessible from any system with VLAN 40 access

No network-layer isolation between server management and other management services

Compromised FortiAnalyzer or Splunk could access iLO

Recommendation:

# Network Architecture Change
# Create dedicated iLO VLAN
VLAN 41: iLO Management (10.10.41.0/24)

# HPE iLO Configuration
# Enable iLO Advanced license features
set /map1/config1 oemhp_authlocale=LOCAL
set /map1/config1 oemhp_minpassword=16

# FortiGate policy for iLO access
config firewall policy
    edit 160
        set name "Jump-to-iLO"
        set srcintf "management"
        set dstintf "ilo-vlan"
        set srcaddr "Jump-Server-Only"
        set dstaddr "R760-iLO"
        set action accept
        set schedule "always"
        set service "HTTPS"
        set logtraffic all
    next
end

# Block all other iLO access
config firewall policy
    edit 161
        set name "Block-iLO-Direct"
        set srcintf "management"
        set dstintf "ilo-vlan"
        set srcaddr "all"
        set dstaddr "R760-iLO"
        set action deny
        set schedule "always"
        set service "ALL"
        set logtraffic all
    next
end

Priority: MEDIUM (Post-deployment)

### 4.3 Scenario 7: Snapshot Ransomware Attack

Attack Description:

Ransomware gains admin credentials and attempts to delete or encrypt snapshots as part of the attack chain. Without immutable snapshots, recovery would be impossible.

Security Assessment:

| Aspect | Finding |
| --- | --- |
| **Current Protection** | Synology Snapshot Lock provides immutability; WORM on Wasabi |
| **Snapshot Schedule** | Every 2 hours with 24 copies retention |
| **Gap** | No automated verification that snapshots are actually locked |

Gap Identified:

Snapshot lock configuration not verified automatically. An admin error or compromised DSM account could:

Disable snapshot lock temporarily

Delete snapshots during the unlock window

Go undetected until ransomware strikes

Recommendation:

#!/bin/bash
# snapshot_lock_verify.sh - Weekly verification script
# Place on R760 and schedule via cron

DSM_IP="10.10.40.10"
DSM_USER="admin"
LOG_FILE="/var/log/snapshot_verify.log"
ALERT_EMAIL="security@b2hstudios.com"

# Check for unlocked snapshots older than 24 hours
UNLOCKED=$(ssh $DSM_USER@$DSM_IP "synosharesnapshot --list" | awk -v date=$(date -d '24 hours ago' +%s) '$5 < date && $7 == "unlocked"')

if [ -n "$UNLOCKED" ]; then
    echo "$(date): ALERT - Unlocked snapshots detected:" >> $LOG_FILE
    echo "$UNLOCKED" >> $LOG_FILE
    # Send alert via DSM notification or email
    echo "$UNLOCKED" | mail -s "B2H Security Alert: Unlocked Snapshots" $ALERT_EMAIL
else
    echo "$(date): OK - All snapshots properly locked" >> $LOG_FILE
fi

DSM Task Scheduler Configuration:

Control Panel → Task Scheduler → Create → Triggered Task → User-defined script

General: Name "Snapshot Lock Verification"

Schedule: Weekly, Sunday 02:00

Task Settings: Run `snapshot_lock_verify.sh`

Notification: Email on failure

Priority: HIGH (Pre-go-live)

### 4.4 Scenario 8: Insider Threat — Data Exfiltration

Attack Description:

Malicious employee with legitimate ZTNA access copies project files to personal cloud storage (Google Drive, Dropbox, OneDrive) or external devices.

Security Assessment:

| Aspect | Finding |
| --- | --- |
| **Current Protection** | ZTNA limits access to approved shares only; no direct internet from VLAN 30 |
| **Gap** | No Data Loss Prevention (DLP) on egress traffic |
| **Risk** | Authorized user can access and exfiltrate data through allowed channels |

Gap Identified:

No DLP solution deployed to detect or block unauthorized data exfiltration. Employees can:

Upload files to personal cloud storage

Email sensitive attachments

Copy data to local devices during ZTNA sessions

Recommendation:

# FortiGate DLP Sensor Configuration
config dlp sensor
    edit "B2H-Data-Protection"
        config filter
            edit 1
                set name "Block-Cloud-Uploads"
                set type file-type
                set file-type 15  # Video files
                set filter-by all
                set action block
                set log enable
            next
            edit 2
                set name "Alert-Large-Transfers"
                set type file-size
                set file-size 1024  # 1GB threshold
                set filter-by all
                set action log-only
            next
            edit 3
                set name "Block-Executables"
                set type file-type
                set file-type 1  # Executables
                set filter-by all
                set action block
            next
        end
    next
end

# Apply DLP to ZTNA egress policy
config firewall policy
    edit 105
        set name "ZTNA-Egress"
        set srcintf "internal"
        set dstintf "wan1"
        set srcaddr "ZTNA-Users"
        set dstaddr "all"
        set action accept
        set schedule "always"
        set service "ALL"
        set dlp-sensor "B2H-Data-Protection"
        set logtraffic all
    next
end

Priority: MEDIUM (Post-deployment)

## 5. Wireless Attack Scenarios

### 5.1 Scenario 9: Rogue AP Deployment

Attack Description:

Attacker deploys fake "B2H-Corporate" SSID with stronger signal to trick employees into connecting. Captures credentials or performs man-in-the-middle attacks.

Security Assessment:

| Aspect | Finding |
| --- | --- |
| **Current Protection** | FortiAP rogue detection enabled; WPA3-Enterprise authentication |
| **Risk** | Detection without automatic containment allows attacks to proceed |
| **Impact** | Credential capture, traffic interception, malware injection |

Gap Identified:

No automated rogue AP containment configured. FortiAP detects rogue APs but requires manual intervention to contain, creating a window of exposure.

Recommendation:

# FortiGate Rogue AP Containment
config wireless-controller wids-profile
    edit "B2H-Rogue-Protection"
        set sensor-mode both
        set ap-auto-suppress enable
        set wireless-bridge enable
        set deauth-broadcast enable
        set deauth-unknown enable
        set ap-bgscan enable
        set ap-bgscan-duration 1000
        set ap-bgscan-idle 50
        set ap-bgscan-period 1200
    next
end

# Apply to FortiAP profiles
config wireless-controller wtp-profile
    edit "B2H-Corporate-Profile"
        set wids-profile "B2H-Rogue-Protection"
    next
end

# Configure containment actions
config wireless-controller wids-rule
    edit "Rogue-AP-Containment"
        set target-rogue enable
        set target-ap enable
        set action suppress
    next
end

Priority: MEDIUM (Post-deployment)

### 5.2 Scenario 10: WPA3-Enterprise Downgrade

Attack Description:

Attackers force clients to connect using WPA2 instead of WPA3, exploiting weaker security (TKIP, weaker key derivation) to crack passwords or perform evil twin attacks.

Security Assessment:

| Aspect | Finding |
| --- | --- |
| **Current Configuration** | SSID configured for WPA3-Enterprise only |
| **Risk** | Legacy client support may enable WPA2 fallback |
| **Impact** | Reduced security for connections; downgrade attacks possible |

Gap Identified:

Potential for WPA2 fallback if legacy client support is enabled. Mixed-mode operation creates downgrade opportunity.

Recommendation:

# FortiGate Wireless Profile - WPA3 Only
config wireless-controller vap
    edit "B2H-Corporate"
        set security wpa3-enterprise
        set auth radius
        set radius-server "FortiAuthenticator"
        set pmf enable
        set pmf-optional disable  # Require PMF (Protected Management Frames)
        set fast-roaming enable
        set okc enable
    next
end

# Device Inventory Management
# Maintain list of WPA3-capable devices
# Pre-deployment audit to identify legacy devices requiring upgrade

WPA3-Capable Device Inventory:

| Device Category | WPA3 Support | Action Required |
| --- | --- | --- |
| MacBook Pro (2018+) | Yes | None |
| Windows 11 Laptops | Yes | Update drivers |
| iPhone 8+ / iOS 13+ | Yes | None |
| Android 10+ | Yes | Enable WPA3 in settings |
| Windows 10 (older builds) | Maybe | Update to 1903+ |
| Legacy Windows 7/8 | No | Upgrade or use wired |

Priority: LOW (Post-deployment)

## 6. Backup/DR Attack Scenarios

### 6.1 Scenario 11: Replication Traffic Interception

Attack Description:

Man-in-the-middle attack on Site A to Site B replication traffic. Attempt to decrypt or modify replication data in transit.

Security Assessment:

| Aspect | Finding |
| --- | --- |
| **Current Protection** | Replication encrypted by default (AES-256) |
| **Protocol** | Synology Replication Manager over HTTPS |
| **Risk** | Certificate validation not explicitly enabled |

Gap Identified:

Certificate validation for replication not explicitly configured. Potential for:

Certificate spoofing if CA compromised

Silent acceptance of certificate changes

No alerting on certificate anomalies

Recommendation:

# Synology Replication Manager Hardening
# Enable certificate pinning for replication

# DSM Control Panel → Security → Certificate
# 1. Use dedicated certificate for replication (not default)
# 2. Enable certificate pinning in Replication Manager

# Enable certificate change alerts
# On both Site A and Site B:

# DSM Notification Configuration
echo "Replication-Cert-Change: /usr/syno/bin/synowarn replication_cert_change" >> /etc/synoalert/alert.conf

# Script to verify certificate fingerprint
#!/bin/bash
# verify_replication_cert.sh
KNOWN_FINGERPRINT="SHA256:xx:xx:xx:xx:xx:xx:xx:xx:xx:xx:xx:xx:xx:xx:xx:xx"
CURRENT_FINGERPRINT=$(openssl s_client -connect site-b.b2h.local:5001 2>/dev/null | openssl x509 -fingerprint -sha256 -noout)

if [ "$CURRENT_FINGERPRINT" != "$KNOWN_FINGERPRINT" ]; then
    /usr/syno/bin/synonotify -c replication_cert_change
fi

Priority: MEDIUM (Post-deployment)

### 6.2 Scenario 12: DR Site Compromise During Failover

Attack Description:

Compromise Site B while it is active during a failover event. Attackers may target DR sites knowing they are often less monitored than production.

Security Assessment:

| Aspect | Finding |
| --- | --- |
| **Current Protection** | Site B has identical security controls to Site A |
| **DR Testing** | May use simplified authentication for speed |
| **Risk** | Test accounts or bypass procedures left active |

Gap Identified:

DR testing procedures may use weaker authentication or temporary accounts for speed, which if not properly cleaned up, create persistent vulnerabilities.

Recommendation:

No Test Accounts Policy: DR tests must use production authentication credentials only

Account Cleanup Checklist: Post-test verification that no temporary accounts created

Audit Trail: All DR test access logged to FortiAnalyzer with alert on non-production account usage

Scheduled Review: Quarterly audit of Site B for orphaned accounts or permissions

# FortiAnalyzer Report for DR Test Audit
eventtype="user-login" AND 
(hostname="site-b-*" OR dstip="10.20.*.*") AND 
NOT (user IN (production-user-list)) AND 
timeframe="last-90-days"

Priority: HIGH (Pre-go-live)

## 7. Social Engineering Assessment

### 7.1 Scenario 13: Phishing — ZTNA Certificate Update

Attack Description:

Fake "IT Support" email requesting FortiClient reinstallation with malicious package. Email appears legitimate with VConfi/B2H branding.

Security Assessment:

| Aspect | Finding |
| --- | --- |
| **Technical Controls** | FortiClient EMS manages client versions; unauthorized packages blocked |
| **User Training** | No security awareness program documented |
| **Risk** | Users may install malware if social engineering is convincing |

Gap Identified:

No user education program documented. Users are the last line of defense and without training may:

Click malicious links

Install unauthorized software

Disclose credentials to fake IT support

Recommendation:

Security Awareness Training Program (Aligned with SOP-USR-001):

| Component | Description | Frequency |
| --- | --- | --- |
| **New Hire Training** | ZTNA usage, password security, phishing recognition | Onboarding |
| **Quarterly Simulations** | Controlled phishing campaigns with metrics | Every 3 months |
| **Annual Refresher** | Updated threats, policy changes, best practices | Yearly |
| **Incident-Based** | Targeted training after security events | As needed |

Training Topics:

Recognizing phishing emails (urgency, suspicious links, unexpected attachments)

ZTNA connection verification (certificate validation, portal URL)

Password hygiene and MFA usage

Reporting suspicious activity (who to contact, how to report)

Safe handling of project files and client data

Platform Recommendation: KnowBe4 or Proofpoint Security Awareness (₹95,000/year for 25 users)

Priority: HIGH (Pre-go-live)

### 7.2 Scenario 14: Physical Tailgating

Attack Description:

Unauthorized person follows an employee into the data center facility without presenting credentials.

Security Assessment:

| Aspect | Finding |
| --- | --- |
| **Current Protection** | Data center physical security not in scope of this project |
| **Gap** | Unknown physical security controls at co-location facility |
| **Risk** | Unauthorized physical access to equipment |

Gap Identified:

Physical security controls not verified. Potential for:

Unauthorized equipment access

Device tampering

Physical theft of drives or documentation

Recommendation:

Data Center Security Verification Checklist:

| Control | Verification Method | Acceptable Standard |
| --- | --- | --- |
| **Perimeter Security** | Site visit, documentation review | 24/7 security staff, CCTV coverage |
| **Access Control** | Review access logs, test badge system | Multi-factor (badge + biometric), individual accountability |
| **Mantrap Entry** | Physical inspection | Anti-tailgating doors with interlock |
| **CCTV Coverage** | Camera review, retention check | 90-day retention, all entry points covered |
| **Visitor Escort** | Policy review, observation | Mandatory escort for all non-badge visitors |
| **Cage/Rack Security** | Inspection | Individual rack locks, cage access logged |

Action: Coordinate with data center facility management to complete verification checklist and obtain security audit documentation.

Priority: MEDIUM (Post-deployment)

## 8. Vulnerability Report

### 8.1 Critical Vulnerability Attack Path Diagram

flowchart LR
    subgraph AttackPaths["Critical Attack Paths"]
        direction TB
        
        subgraph Vuln001["VULN-001: Brute-force"]
            A1["Attacker"] --> A2["ZTNA Portal"] --> A3["Credential Stuffing"]
            A3 -. "No Rate Limit" .-> A4["Account Enumeration"]
        end
        
        subgraph Vuln004["VULN-004: Snapshot Ransomware"]
            B1["Ransomware"] --> B2["Admin Compromise"]
            B2 -. "No Lock Verification" .-> B3["Snapshot Deletion"]
            B3 --> B4["Data Loss"]
        end
    end
    
    subgraph Mitigations["Implemented Mitigations"]
        M1["MFA Blocks"]
        M2["Immutable Snapshots"]
    end
    
    A3 -.-> M1
    B2 -.-> M2

### 8.2 Security Control Coverage Diagram

flowchart TB
    subgraph Controls["Security Controls Matrix"]
        direction TB
        
        subgraph Preventive["Preventive Controls"]
            P1["Geo-filtering"]
            P2["MFA"]
            P3["VLAN Segmentation"]
            P4["Firewall Rules"]
            P5["ZTNA Posture Check"]
        end
        
        subgraph Detective["Detective Controls"]
            D1["Splunk SIEM"]
            D2["FortiAnalyzer"]
            D3["Zabbix Monitoring"]
            D4["Honeypot Directories"]
        end
        
        subgraph Corrective["Corrective Controls"]
            C1["Immutable Snapshots"]
            C2["DR Failover"]
            C3["Account Lockout"]
            C4["Auto-containment"]
        end
    end
    
    subgraph Gaps["Control Gaps"]
        G1["Rate Limiting"]
        G2["IPS on DMZ"]
        G3["TLS 1.0/1.1"]
        G4["DLP"]
    end

### 8.3 Comprehensive Vulnerability Table

| ID | Finding | Severity | CVSS | Gap | Remediation | Priority |
| --- | --- | --- | --- | --- | --- | --- |
| **VULN-001** | Brute-force protection not enabled on ZTNA | HIGH | 7.5 | MFA alone insufficient against enumeration and fatigue attacks | Enable FortiAuthenticator rate limiting: max 5 attempts per 5 minutes, lockout after 3 failures | Pre-go-live |
| **VULN-002** | IPS not enabled on DMZ segment | HIGH | 7.2 | Protocol attacks against Signiant SDCX possible without detection | Enable FortiGate IPS profile on DMZ-to-internal rules; create custom FASP filters | Pre-go-live |
| **VULN-003** | TLS 1.0/1.1 potentially enabled | HIGH | 6.8 | Downgrade attacks (BEAST, POODLE) possible; weak cipher suites accepted | Enforce TLS 1.2 minimum; disable SSLv3/TLS 1.0/1.1; configure strong cipher suites | Pre-go-live |
| **VULN-004** | Snapshot lock not automated | HIGH | 7.0 | Ransomware can delete backups if admin account compromised | Implement weekly verification script; alert if any snapshot >24hrs old without lock | Pre-go-live |
| **VULN-005** | No DLP on egress | MEDIUM | 5.5 | Data exfiltration by malicious insider or compromised account | Deploy FortiGate DLP sensor; block unauthorized cloud uploads; alert on large transfers | Post-deployment |
| **VULN-006** | iLO not segmented | MEDIUM | 5.0 | Hypervisor compromise risk if management VLAN breached | Create dedicated iLO VLAN (VLAN 41); restrict iLO access to jump server only | Post-deployment |
| **VULN-007** | Rogue AP containment not automated | MEDIUM | 4.5 | Fake APs detected but not automatically blocked | Enable FortiAP auto-containment; configure suppression for rogue devices | Post-deployment |
| **VULN-008** | ISP DDoS protection unconfirmed | MEDIUM | 5.0 | Volumetric attack risk without upstream scrubbing | Verify with ISPs or add cloud DDoS scrubbing service (Cloudflare/AWS Shield) | Post-deployment |
| **VULN-009** | Security awareness training missing | HIGH | 6.0 | Social engineering risk; phishing susceptibility | Implement training program (SOP-USR-001); quarterly simulated phishing tests | Pre-go-live |
| **VULN-010** | Physical security unverified | MEDIUM | 4.0 | Tailgating risk at data center facility | Verify data center controls: mantrap, CCTV, badge access, visitor escort policy | Post-deployment |

## 9. Hardening Recommendations

### 9.1 FortiGate Hardening

#### 9.1.1 Disable Legacy TLS

config system global
    set admin-https-ssl-versions tlsv1-2 tlsv1-3
    set ssl-min-prot-ver tlsv1-2
    set strong-crypto enable
end

config system admin
    edit "admin"
        set trusthost1 10.10.40.0 255.255.255.0
    next
end

#### 9.1.2 Enable IPS on DMZ

config firewall policy
    edit 102
        set name "DMZ-to-Internal-Secure"
        set srcintf "dmz"
        set dstintf "internal"
        set srcaddr "SDCX-Server"
        set dstaddr "NAS-Storage"
        set action accept
        set schedule "always"
        set service "FASP" "HTTPS"
        set ips-sensor "default"
        set av-profile "default"
        set application-list "default"
        set ssl-ssh-profile "B2H-Deep-Inspection"
        set logtraffic all
    next
end

config ips sensor
    edit "B2H-DMZ-Protection"
        config entries
            edit 1
                set rule "FASP.Protocol.Anomaly"
                set action block
                set log enable
            next
            edit 2
                set rule "UDP.Flood"
                set action block
                set log enable
            next
        end
    next
end

#### 9.1.3 Enable DLP

config dlp sensor
    edit "B2H-Data-Protection"
        config filter
            edit 1
                set name "Block-Video-Exfil"
                set type file-type
                set file-type 15  # Video files
                set filter-by all
                set action block
                set log enable
            next
            edit 2
                set name "Alert-Large-Transfer"
                set type file-size
                set file-size 1024  # 1GB
                set filter-by all
                set action log-only
            next
            edit 3
                set name "Block-Personal-Cloud"
                set type url
                set url "drive.google.com" "dropbox.com" "onedrive.live.com"
                set action block
                set log enable
            next
        end
    next
end

# Apply to outbound policies
config firewall policy
    edit 105
        set dlp-sensor "B2H-Data-Protection"
    next
end

#### 9.1.4 Enable Brute-Force Protection

config system global
    set admin-login-max-retry 3
    set admin-login-lockout-threshold 3
    set admin-login-lockout-duration 900
end

config authentication setting
    set active-auth-scheme "B2H-ZTNA-Scheme"
    set captive-portal-type enable
    set captive-portal-ip 10.10.10.5
end

config authentication scheme
    edit "B2H-ZTNA-Scheme"
        set method fsso
        set fsso-group-for-guest-search "B2H-Users"
        set require-tfa enable
        set fsso-agent "FortiAuthenticator"
    next
end

### 9.2 Synology DSM Hardening

#### 9.2.1 Snapshot Lock Automation

#!/bin/bash
# /usr/local/bin/snapshot_lock_auto.sh
# Run via DSM Task Scheduler - Weekly

# Configuration
SHARES=("projects" "archive" "active")
RETENTION_DAYS=30
LOG_FILE="/var/log/snapshot_auto.log"

# Function to lock snapshots older than 1 hour but newer than retention
lock_snapshots() {
    local share=$1
    local share_path="/volume1/$share"
    
    # Get list of unlocked snapshots
    synosharesnapshot --list "$share_path" | while read line; do
        snapshot_date=$(echo $line | awk '{print $5}')
        snapshot_status=$(echo $line | awk '{print $7}')
        snapshot_id=$(echo $line | awk '{print $1}')
        
        # Check if snapshot is unlocked and older than 1 hour
        if [ "$snapshot_status" == "unlocked" ]; then
            # Lock the snapshot
            synosharesnapshot --lock "$share_path@$snapshot_id"
            echo "$(date): Locked snapshot $snapshot_id for $share" >> $LOG_FILE
        fi
    done
}

# Process all shares
for share in "${SHARES[@]}"; do
    lock_snapshots "$share"
done

# Verification - alert if any unlocked snapshots >24hrs
ALERT_UNLOCKED=$(synosharesnapshot --list | awk -v date=$(date -d '24 hours ago' +%s) '$5 < date && $7 == "unlocked"')
if [ -n "$ALERT_UNLOCKED" ]; then
    /usr/syno/bin/synonotify -c snapshot_unlocked_alert
    echo "$(date): ALERT - Unlocked snapshots detected" >> $LOG_FILE
fi

#### 9.2.2 DSM Firewall Additional Rules

# Control Panel → Security → Firewall → Create

# Rule 1: Block Guest VLAN from all inbound
Rule Name: Block-Guest-Inbound
Action: Deny
Source IP: 10.10.50.0/24
Destination Port: All
Protocol: All

# Rule 2: Restrict SSH to Management VLAN only
Rule Name: SSH-Management-Only
Action: Allow
Source IP: 10.10.40.0/24
Destination Port: 22
Protocol: TCP

# Rule 3: Block all other SSH
Rule Name: Block-SSH-Default
Action: Deny
Source IP: All
Destination Port: 22
Protocol: TCP

# Rule 4: DSM Web to Management only
Rule Name: DSM-Web-Management
Action: Allow
Source IP: 10.10.40.0/24
Destination Port: 5000,5001
Protocol: TCP

# Rule 5: Auto-block failed logins
Control Panel → Security → Account → Auto Block
Enable auto block: Yes
Login attempts: 5
Within minutes: 5

# Rule 6: Enable 2FA for all admin accounts
Control Panel → User & Group → [Admin User] → Enable 2FA

#### 9.2.3 Security Advisor Configuration

# Security Advisor → Advanced Settings
Enable automatic scans: Yes
Scan schedule: Weekly, Sunday 03:00

# Malware Reminder Settings
Enable malware reminder: Yes
Scan frequency: Every 7 days

# Critical Items to Monitor:
- Admin password strength
- 2FA configuration
- Firewall status
- Auto-block configuration
- Security update status
- Abnormal login detection

### 9.3 Network Hardening

#### 9.3.1 HPE Aruba Switch Security

# Enable DHCP Snooping
configure terminal
ip dhcp snooping
ip dhcp snooping vlan 20,30,40,50
ip dhcp snooping trust interface 1/1/49-1/1/52
exit

# Enable Dynamic ARP Inspection
configure terminal
ip arp inspection vlan 20,30,40,50
ip arp inspection validate src-mac dst-mac ip
ip arp inspection trust interface 1/1/49-1/1/52
exit

# Enable IP Source Guard
configure terminal
interface 1/1/1-1/1/48
    ip verify source port-security
exit

# Enable Storm Control
configure terminal
interface 1/1/1-1/1/48
    storm-control broadcast level 10
    storm-control multicast level 10
    storm-control unknown-unicast level 10
exit

# Disable Unused Ports
configure terminal
interface 1/1/25-1/1/48
    shutdown
    description "UNUSED - DISABLED"
exit

# Enable Port Security
configure terminal
interface 1/1/1-1/1/24
    port-security
    port-security maximum 2
    port-security violation restrict
exit

#### 9.3.2 Private VLAN Configuration

# HPE Aruba - Private VLANs on access ports
configure terminal
vlan 20
    name Production
    private-vlan primary
    private-vlan association 201,202,203
exit

vlan 201
    name Production-Isolated-1
    private-vlan isolated
exit

# Apply to access ports
interface 1/1/1
    switchport mode private-vlan host
    switchport private-vlan host-association 20 201
exit

## 10. Updated BOM — Security Enhancements

### 10.1 Pre-Go-Live Security Additions

| Item | Description | Qty | Cost (INR) | Priority |
| --- | --- | --- | --- | --- |
| **Security Awareness Training** | Phishing simulation platform (KnowBe4/Proofpoint) - 25 users | 1 | 95,000/year | Pre-go-live |
| **FortiGate IPS Tuning** | Professional services for IPS customization and tuning | 1 | 25,000 | Pre-go-live |
| **DSM Security Hardening** | Professional services for snapshot automation and DSM hardening | 1 | 20,000 | Pre-go-live |
| **TLS/SSL Audit** | Third-party SSL/TLS configuration audit | 1 | 35,000 | Pre-go-live |
| **Pre-Go-Live Subtotal** | **1,75,000** |  |  |  |

### 10.2 Post-Deployment Security Additions

| Item | Description | Qty | Cost (INR) | Priority |
| --- | --- | --- | --- | --- |
| **FortiGate DLP License** | Data Loss Prevention add-on license (3-year) | 1 | 2,55,000 | Post-deployment |
| **Cloud DDoS Protection** | AWS Shield Advanced or Cloudflare Business | 1 | 2,40,000/year | Post-deployment |
| **Jump Server** | Dedicated admin jump host (HPE ProLiant ML30) | 1 | 45,000 | Post-deployment |
| **Network Security Audit** | Comprehensive penetration testing | 1 | 1,50,000 | Post-deployment |
| **Post-Deployment Subtotal** | **6,90,000** |  |  |  |

### 10.3 Security Enhancement Summary

| Category | Year 1 (INR) | Year 2-5 Annual (INR) |
| --- | --- | --- |
| Pre-Go-Live (One-time) | 1,75,000 | - |
| Post-Deployment (One-time) | 4,50,000 | - |
| Recurring Subscriptions | 3,35,000 | 3,35,000 |
| **Total Security Investment** | **9,60,000** | **3,35,000/year** |

## 11. Remediation Timeline

### 11.1 Pre-Go-Live Checklist (Weeks 9-10)

| Week | Task | Owner | Status |
| --- | --- | --- | --- |
| 9.1 | Enable FortiAuthenticator rate limiting (VULN-001) | VConfi Security | ☐ |
| 9.1 | Enable IPS on DMZ segment (VULN-002) | VConfi Security | ☐ |
| 9.2 | Enforce TLS 1.2 minimum (VULN-003) | VConfi Security | ☐ |
| 9.2 | Deploy snapshot lock verification script (VULN-004) | VConfi Security | ☐ |
| 9.3 | Initial security awareness training (VULN-009) | B2H HR + VConfi | ☐ |
| 9.4 | TLS/SSL configuration audit | Third-party Auditor | ☐ |
| 10.1 | Pre-go-live security validation | VConfi Security Lead | ☐ |

### 11.2 Post-Deployment Hardening (Months 2-6)

| Month | Task | Owner | Status |
| --- | --- | --- | --- |
| 2 | Deploy FortiGate DLP sensor (VULN-005) | VConfi Security | ☐ |
| 2 | Create dedicated iLO VLAN (VULN-006) | VConfi Network | ☐ |
| 3 | Enable rogue AP auto-containment (VULN-007) | VConfi Wireless | ☐ |
| 3 | Verify ISP DDoS protection (VULN-008) | B2H Operations | ☐ |
| 4 | Deploy jump server for admin access | VConfi Infrastructure | ☐ |
| 4 | Enable switch security features (DHCP snooping, DAI) | VConfi Network | ☐ |
| 5 | Verify data center physical security (VULN-010) | B2H Operations | ☐ |
| 6 | First quarterly simulated phishing test | B2H HR + VConfi | ☐ |
| 6 | Comprehensive penetration testing | Third-party Auditor | ☐ |

## 12. Sign-Off

This Security Stress Test & Hardening document has been prepared following industry best practices for security assessment and penetration testing methodologies. The vulnerabilities identified represent realistic attack scenarios based on the B2H Studios infrastructure design.

Security Assessment Completed By: VConfi Solutions Security Team

Date: March 22, 2026

Next Review: Post-deployment (Month 6)

Acknowledgments:

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| VConfi Security Lead |  |  |  |
| B2H IT Manager |  |  |  |
| B2H CISO/Security Lead |  |  |  |

End of Part 5 — Security Stress Test & Hardening

VConfi Solutions | CONFIDENTIAL | Page 1 of 1

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Part 6: Standard Operating Procedures (SOPs)

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

# Part 6: Standard Operating Procedures (SOPs)

## B2H Studios — IT Infrastructure Implementation Plan

Document Version: 1.0

Date: March 22, 2026

Client: B2H Studios

Prepared by: VConfi Solutions

## Table of Contents

[SOP-NET-001: FortiGate Daily Operations](#sop-net-001-fortigate-daily-operations)

[SOP-NET-002: Switch Management](#sop-net-002-switch-management)

[SOP-NET-003: FortiAP Wireless Management](#sop-net-003-fortiap-wireless-management)

[SOP-MON-001: Zabbix Monitoring & Alert Response](#sop-mon-001-zabbix-monitoring--alert-response)

[SOP-SRV-001: Server Patching & Maintenance](#sop-srv-001-server-patching--maintenance)

[SOP-BKP-001: Backup & Restore Procedures](#sop-bkp-001-backup--restore-procedures)

[SOP-DR-001: DR Failover & Failback](#sop-dr-001-dr-failover--failback)

[SOP-SEC-001: Splunk SIEM Review](#sop-sec-001-splunk-siem-review)

[SOP-SEC-002: Incident Response Workflow](#sop-sec-002-incident-response-workflow)

[SOP-SEC-003: ISO 27001 Audit Prep Checklist](#sop-sec-003-iso-27001-audit-prep-checklist)

[SOP-USR-001: Wi-Fi & ZTNA Access Guide (End User)](#sop-usr-001-wi-fi--ztna-access-guide-end-user)

## SOP-NET-001: FortiGate Daily Operations

### Purpose

Daily monitoring and maintenance of FortiGate firewalls to ensure optimal performance, security posture, and high availability across both production sites.

### Scope

All FortiGate 120G units deployed at Site A (Primary) and Site B (DR), including active-passive HA pairs.

### Prerequisites

FortiGate admin credentials (named admin account, not default "admin")

Access to FortiAnalyzer for centralized logging

Zabbix dashboard access for performance metrics

Network connectivity to management interfaces (VLAN 40)

### Procedure

Log into FortiGate GUI

Navigate to `https://10.10.40.2` for Site A primary

Navigate to `https://10.10.40.3` for Site A secondary (verify standby status)

Navigate to `https://10.10.50.2` for Site B primary (if monitoring)

Authenticate with named admin credentials + FortiAuthenticator 2FA

Review System Dashboard

Navigate to System > Dashboard

Check for any red/yellow alert indicators

Verify system uptime (should be >30 days unless maintenance performed)

Review license status (all should show "Valid")

Check FortiGuard Subscription Status

Navigate to System > FortiGuard

Verify all subscription services show green checkmarks:

Antivirus Definitions

IPS Signatures

Application Control

URL Filtering

FortiSandbox Cloud

Check "Last Update" timestamp (should be within last 24 hours)

Review System Events

Navigate to Log & Report > System Events

Filter for "Error" and "Warning" severity

Review any events from the last 24 hours

Pay special attention to HA events, VPN events, and system restarts

Verify ZTNA Session Status

Navigate to VPN > Monitor > ZTNA

Verify expected number of active sessions (typically 15-25 during work hours)

Check for any failed posture checks

Note any unusual geographic locations

Verify High Availability Status

Navigate to System > HA

Verify HA Status shows "In Sync"

Confirm primary unit shows "Active" and secondary shows "Standby"

Check HA uptime synchronization

Review FortiAnalyzer Alerts

Log into FortiAnalyzer at `https://10.10.40.17`

Navigate to FortiView > Alerts

Review overnight alerts and anomalies

Check for any threshold violations

Document Findings

Record all observations in the daily operations log

Note any anomalies or warnings

Create tickets for issues requiring follow-up

### Daily Checklist

| Check | Expected Result | Action if Failed |
| --- | --- | --- |
| CPU Usage | <70% sustained | Investigate traffic spike, check FortiView for top sessions |
| Memory Usage | <80% | Check for memory leak, schedule maintenance window |
| HA Status | In Sync | Contact VConfi support immediately, do not make config changes |
| Disk Usage | <85% | Archive old logs or increase retention if possible |
| FortiGuard | Up to date | Initiate manual update, check internet connectivity |
| Active Sessions | Within normal range | Investigate sudden spikes or drops |
| Temperature | Normal range | Check data center HVAC, ensure proper ventilation |
| Power Supplies | Both operational | Check PDU status, replace if necessary |

### Rollback Procedures

N/A — This SOP covers monitoring only. Configuration changes require separate change control.

### Escalation Matrix

| Severity | Condition | Response Time | Escalate To |
| --- | --- | --- | --- |
| Critical | HA down, both units unreachable | 15 minutes | IT Manager + VConfi 24x7 support |
| Critical | Primary unit failed, secondary not taking over | 15 minutes | IT Manager + VConfi 24x7 support |
| High | Sustained CPU >90%, performance degraded | 1 hour | Senior Network Admin + VConfi support |
| High | VPN/ZTNA service unavailable | 1 hour | Senior Network Admin |
| Medium | FortiGuard update failures | 4 hours | Network Admin |
| Medium | Single power supply failure | 4 hours | Network Admin |
| Low | Disk space warnings | 8 hours | Network Admin |

### References

FortiGate 120G Administration Guide (Fortinet Documentation)

FortiGate High Availability Guide

Fortinet Support Portal: https://support.fortinet.com

B2H Network Architecture Diagram (Part 2)

## SOP-NET-002: Switch Management

### Purpose

Management, monitoring, and troubleshooting of HPE Aruba CX 6300M switches to maintain network availability, performance, and security.

### Scope

All HPE Aruba CX 6300M switches at Site A and Site B, including VSX cluster pairs.

### Prerequisites

SSH client access (PuTTY, Terminal, or built-in Windows SSH)

Enable password for privileged mode

Understanding of VSX clustering and Aruba CX CLI

Access to TFTP server for configuration backups (10.10.40.5)

### Procedure

SSH to Switch Primary

ssh admin@10.10.40.10

Site A Primary: 10.10.40.10

Site A Secondary: 10.10.40.11

Site B Primary: 10.10.40.20

Site B Secondary: 10.10.40.21

Verify VSX Status

show vsx status

Verify "OperState: UP" on both ISL and keepalive

Confirm role (Primary/Secondary)

Check VSX synchronization status

Check Interface Status

show interface brief

Review all ports for "up/up" status

Note any ports showing "down" or "err-disabled"

Check LAG interfaces for member status

Verify MAC Address Table

show mac-address-table

Confirm MAC learning is occurring on active ports

Verify expected device counts per VLAN

Check VLAN Configuration

show vlan

Verify all 5 VLANs are present (10, 20, 30, 40, 50)

Confirm port assignments match documentation

Review System Logs

show logging

Check for ERROR or WARNING messages

Look for STP events, link flaps, or authentication failures

Check Port Statistics (if issues suspected)

show interface 1/1/X counters

Review for error counters (CRC, fragments, giants)

Check for input/output drops

### Common Tasks

#### Adding a VLAN to a Trunk Port

config
interface lag 1
   vlan trunk allowed 10,20,30,40,50,99
   exit
write memory

#### Finding a Device's Connected Port

show mac-address-table | include <MAC_ADDRESS>

#### Creating Configuration Backup

copy running-config tftp://10.10.40.5/switch-backup-$(date +%Y%m%d).cfg

#### Verifying VSX ISL Health

show vsx isl
show vsx keepalive

### Rollback Procedures

Configuration Restore from Backup:

Access TFTP server at 10.10.40.5

Identify correct backup file

Execute restore command:

copy tftp://10.10.40.5/backup.cfg running-config

Verify configuration applied correctly:

show running-config

Save to startup-config if verified:

write memory

VSX Recovery (if split):

Identify cause of split (ISL failure, keepalive failure)

Do NOT make configuration changes until VSX is restored

Restore ISL connectivity or fix keepalive path

Verify VSX re-synchronization

Contact VConfi if split persists

### Escalation Matrix

| Issue | Response Time | Escalate To | Notes |
| --- | --- | --- | --- |
| VSX split brain | Immediate | VConfi emergency support | Do not make config changes |
| Multiple port failures | 30 minutes | Senior Network Admin | Check for hardware failure |
| Complete switch failure | 15 minutes | IT Manager + VConfi 24x7 | Activate DR procedures if needed |
| VLAN misconfiguration | 1 hour | Network Admin | May affect multiple systems |
| Performance degradation | 2 hours | Network Admin | Check for broadcast storms |
| Firmware update issues | 1 hour | VConfi support | Follow HPE rollback procedures |

### References

HPE Aruba CX 6300M Switch Installation Guide

Aruba CX CLI Reference Guide

VSX Configuration Best Practices

B2H Network Architecture Diagram (Part 2)

## SOP-NET-003: FortiAP Wireless Management

### Purpose

Management, monitoring, and troubleshooting of FortiAP wireless access points to ensure reliable Wi-Fi connectivity for employees and guests.

### Scope

All FortiAP 431F and 433F units deployed at Site A and Site B.

### Prerequisites

FortiGate admin access (same as SOP-NET-001)

Physical access to AP locations (for hardware reset if needed)

Knowledge of SSID configuration (B2H-Corporate, B2H-Guest)

### Procedure

#### Checking AP Status

Log into FortiGate

Navigate to `https://10.10.40.2` (Site A) or `https://10.10.50.2` (Site B)

Authenticate with admin credentials

View Managed FortiAPs

Navigate to WiFi & Switch Controller > Managed FortiAPs

Verify all APs show "Online" status

Check connection state (should show "Authorized")

Review Connected Clients

Click on individual AP to view details

Check "Connected Clients" count

Verify radio utilization is <70%

Check AP Health

Navigate to WiFi & Switch Controller > Monitor > AP Health

Review signal strength, channel utilization

Check for interference or coverage gaps

#### Restarting an AP (Soft Restart)

Navigate to WiFi & Switch Controller > Managed FortiAPs

Select the target AP from the list

Click Restart button

Confirm restart action

Wait 2-3 minutes for AP to rejoin controller

Verify status returns to "Online"

#### Power Cycling an AP (Hard Reset)

If soft restart fails, identify the switch port:

From FortiAP details, note the connected switch IP and port

SSH to the switch (see SOP-NET-002)

Disable port: `interface 1/1/X` → `shutdown`

Wait 10 seconds

Enable port: `no shutdown`

Wait 2-3 minutes for AP to boot and rejoin

Verify status in FortiGate

#### Adding a New AP

Physical Connection

Connect AP to switch port on VLAN 50 (or native VLAN with AP VLAN tagged)

Ensure PoE power is available

Wait for AP to boot (LED will cycle)

Authorization in FortiGate

Navigate to WiFi & Switch Controller > Managed FortiAPs

New AP will appear as "Detected" or "Discovered"

Click Authorize

Assign Profile

Select AP from list

Click Edit

Set "AP Profile" to "B2H-AP-Profile"

Assign appropriate "FortiAP Group" (Site-A or Site-B)

Click OK

Verification

Wait 2-3 minutes for configuration push

Verify status shows "Online"

Test Wi-Fi connection from client device

### Troubleshooting Common Issues

| Issue | Diagnostic Steps | Resolution |
| --- | --- | --- |
| AP won't adopt | Check VLAN 50 configuration on switch port | Ensure native VLAN or tagged VLAN 50 |
| AP shows "Offline" | Check power (PoE budget), check network connectivity | Power cycle AP, check cable |
| Poor coverage reported | Review AP Health dashboard, check power level | Adjust TX power, consider additional AP |
| Clients can't authenticate | Check RADIUS server status, verify SSID settings | Restart authentication service |
| Slow Wi-Fi performance | Check channel utilization, interference | Change channel, enable band steering |

### Rollback Procedures

Reverting AP Configuration:

Select AP in Managed FortiAPs list

Click Edit

Change profile back to previous setting

Click OK

AP will reboot and apply previous configuration

Factory Reset AP:

Locate physical AP

Press and hold reset button for 10 seconds

AP will reboot to factory defaults

Re-authorize and reconfigure in FortiGate

### Escalation Matrix

| Issue | Response Time | Escalate To |
| --- | --- | --- |
| Multiple APs offline | 30 minutes | Network Admin + VConfi |
| Complete Wi-Fi outage | 15 minutes | IT Manager + VConfi 24x7 |
| AP won't adopt after troubleshooting | 2 hours | VConfi support |
| Coverage gaps affecting users | 4 hours | Network Admin |
| Performance complaints | 4 hours | Network Admin |

### References

FortiAP 431F/433F Administration Guide

FortiGate WiFi Controller Configuration Guide

B2H Wireless Heat Map (if available)

## SOP-MON-001: Zabbix Monitoring & Alert Response

### Purpose

Responding to Zabbix alerts, investigating infrastructure issues, and maintaining comprehensive monitoring coverage of all B2H infrastructure components.

### Scope

All monitored infrastructure including: FortiGate firewalls, HPE switches, Synology HD6500 NAS units, Dell PowerEdge servers, UPS systems, and virtual machines.

### Prerequisites

Zabbix web access (`http://10.10.40.15`)

Alert notification channels configured (email, Slack, SMS)

Administrative access to monitored devices for investigation

Access to vendor support resources

### Alert Response Procedure

Receive Alert

Alert delivered via configured channel (email/Slack/SMS)

Note the device, trigger, severity, and timestamp

Log into Zabbix Dashboard

Navigate to `http://10.10.40.15`

Authenticate with credentials

Review Active Problems

Navigate to Monitoring > Problems

Filter by severity if needed

Click on the alert to view full details

Acknowledge Alert

Select the problem

Click Acknowledge

Add comment describing initial assessment

Check "Acknowledge" and optionally "Close problem" if false positive

Investigate Root Cause

Click on host name to view host details

Review latest data graphs

Cross-reference with other monitoring tools if needed

Take Corrective Action

Follow device-specific troubleshooting (refer to other SOPs)

Document actions taken

Resolve and Close

Once issue resolved, verify problem clears in Zabbix

If manual closure needed, acknowledge with resolution note

Document in incident log

### Common Alert Response Procedures

#### HD6500 Temperature High

| Threshold | Action |
| --- | --- |
| >45°C Warning | Monitor closely, check data center temperature |
| >50°C High | Check NAS fans, verify ventilation, notify facilities |
| >55°C Disaster | Initiate graceful shutdown procedure, contact VConfi |

Steps:

Check data center temperature via environmental sensors

Verify NAS fans operational (DSM > Hardware & Power > Fan Speed)

Check for blocked ventilation around unit

If sustained >50°C for >10 minutes: Consider graceful shutdown of non-critical services

Contact facilities management for HVAC check

#### FortiGate CPU High

Steps:

Log into FortiGate GUI

Navigate to System > FortiView

Identify top sessions by bandwidth/CPU

Check for traffic anomalies (DDoS, runaway process)

If attack suspected: Enable DoS protection, block source IPs

If sustained >90%: Contact VConfi support

#### Disk Space Low (HD6500)

Steps:

Log into DSM

Navigate to Storage Manager > Storage Pool

Identify which volume is filling up

Run cleanup on temporary files, old logs

Review retention policies

If <5% free: Consider emergency archival to Wasabi

#### Device Unreachable (Ping Loss)

Steps:

Verify from multiple sources (try ping from different systems)

Check power status via IPMI/iLO if available

Verify switch port status

If network issue: Check switch, firewall rules

If device down: Follow device-specific power-on procedures

### Escalation Matrix

| Alert Severity | Zabbix Priority | Response Time | Escalate To |
| --- | --- | --- | --- |
| Disaster | 5 (Disaster) | 5 minutes | IT Manager + VConfi 24x7 |
| High | 4 (High) | 15 minutes | Senior Admin + VConfi |
| Average | 3 (Average) | 1 hour | System Admin |
| Warning | 2 (Warning) | 4 hours | System Admin |
| Information | 1 (Information) | Next business day | N/A |

### Rollback Procedures

False Positive Resolution:

Acknowledge alert

Adjust trigger threshold if needed:

Configuration > Hosts > [Host] > Triggers

Edit trigger expression

Update description with change reason

Document in change log

Recovery Verification:

After resolution, monitor for 30 minutes

Verify alert clears automatically

Check related metrics return to normal range

### References

Zabbix 6.0 Documentation

B2H Monitoring Configuration Guide

Zabbix Trigger Reference (internal document)

## SOP-SRV-001: Server Patching & Maintenance

### Purpose

Regular patching and maintenance of virtual machines and physical server infrastructure to maintain security posture, stability, and performance.

### Scope

All virtual machines hosted on Dell PowerEdge R760 servers at Site A and Site B, including: Signiant SDCX, Aspera, FortiAnalyzer, FortiClient EMS, FortiAuthenticator, HashiCorp Vault, and Kaspersky Security Centre VMs.

### Prerequisites

vCenter/vSphere access credentials

Scheduled maintenance window approved

Verified VM backups (Veeam or snapshot-based)

Rollback plan documented

Change request approved (for production systems)

### Procedure

#### Monthly Patching — Windows VMs

Pre-Patch Verification

Verify VM backup completed within last 24 hours

Document current VM state (services running, performance baseline)

Notify stakeholders of maintenance window

Create VM Snapshot

In vSphere: Right-click VM > Snapshots > Take Snapshot

Name: `Pre-Patch-YYYY-MM-DD`

Description: List of patches to be applied

Check "Snapshot the virtual machine's memory" (for running systems)

Click OK

Connect to VM

Use RDP for Windows VMs

Use SSH for Linux VMs

Verify all critical services are running

Apply Windows Updates

Open Windows Settings > Update & Security

Click Check for updates

Install all "Critical" and "Security" updates

Install "Feature Updates" only if approved

Do NOT install "Preview" updates in production

Reboot if Required

Save all work, close applications

Reboot VM

Monitor boot process via vSphere console

Verify VM returns to login screen

Post-Patch Verification

Log into VM

Verify all services started correctly

Check Event Viewer for errors

Test critical functionality (e.g., if Signiant VM, verify transfers work)

Verify network connectivity

Snapshot Removal

Monitor VM for 48 hours for stability

If stable: Delete snapshot to reclaim space

If issues detected: Rollback using snapshot

#### Quarterly Firmware Updates

Schedule Maintenance Window

Minimum 4-hour window for firmware updates

Schedule during low-activity period

Notify all stakeholders

Pre-Update Preparation

Backup all VM configurations (export OVF)

Document current firmware versions

Download latest firmware from Dell/HPE support sites

Verify checksums of downloaded files

Update Sequence

iLO Firmware → BIOS → RAID Controller → NIC Firmware

iLO Firmware Update

Log into iLO web interface

Navigate to Firmware & OS Software

Select iLO firmware file

Apply update (iLO will reboot, VMs continue running)

Verify update successful

BIOS Update

Mount BIOS update ISO via iLO virtual media

Reboot server

Boot from virtual media

Follow on-screen instructions

System will reboot after update

RAID Controller Update

Boot into RAID controller configuration (Ctrl+R during boot)

Update firmware per controller documentation

Verify RAID array status is "Optimal"

NIC Firmware Update

Update via OS-level tools or bootable ISO

Verify network connectivity after update

Post-Update Verification

Verify all VMs boot successfully

Check hardware health in iLO

Confirm no new errors in system logs

### Rollback Procedures

VM Snapshot Rollback:

In vSphere: Right-click VM > Snapshots > Manage Snapshots

Select pre-patch snapshot

Click Revert To

Confirm action

VM will revert to snapshot state

Verify services operational

Document rollback reason

Configuration Restore:

Access Veeam backup console

Locate backup for target VM

Select restore point (pre-patch)

Execute Instant VM Recovery or Full Restore

Verify restored VM functionality

Decommission patched VM if restore successful

### Escalation Matrix

| Issue | Response Time | Escalate To |
| --- | --- | --- |
| VM fails to start after patching | 30 minutes | Senior Admin + VConfi |
| Multiple VM failures | 15 minutes | IT Manager + VConfi 24x7 |
| Hardware failure during firmware update | Immediate | VConfi emergency support |
| Performance degradation post-patch | 2 hours | System Admin + Vendor support |
| Application incompatibility | 4 hours | Application vendor + VConfi |

### References

Dell PowerEdge R760 Update Guide

VMware vSphere Documentation

Veeam Backup & Recovery Documentation

Microsoft Windows Server Update Services (WSUS) Guide

## SOP-BKP-001: Backup & Restore Procedures

### Purpose

Managing backup operations, verifying backup integrity, and performing data restoration procedures for all B2H Studios data protection systems.

### Scope

All backup and replication systems including: Synology HD6500 snapshots, Hyper Backup to Wasabi, Snapshot Replication between sites, and VM-level backups.

### Prerequisites

DSM admin access (Site A and Site B)

Knowledge of data location and retention policies

Restore destination prepared and accessible

Sufficient storage space for restored data

Approval for full share restores (overwrites current data)

### Procedure

#### Weekly Backup Verification

Log into Site A HD6500 DSM

Navigate to `https://10.10.40.12:5001`

Authenticate with admin credentials + 2FA

Verify Snapshot Replication

Navigate to Snapshot Replication > Replication Tasks

Check status column shows "Successful" for all tasks

Verify last run timestamp is recent

Check for any error messages

Verify Hyper Backup Status

Navigate to Hyper Backup

Review backup task status

Verify "Last backup" timestamp

Check backup size trends

Verify Wasabi Cloud Sync

Log into Wasabi console (wasabi.com)

Navigate to bucket: `b2h-studio-archive`

Verify new objects appear (timestamp check)

Review storage usage trends

Review Backup Reports

Check email notifications for overnight backup reports

Review any warning or error messages

Document findings in backup log

#### File-Level Restore (Individual Files)

Access File Station

DSM > File Station

Navigate to shared folder containing target file

Locate Previous Version

Right-click on file or folder

Select View Previous Versions

Select snapshot date containing desired version

Browse to locate file

Restore File

Select file(s) to restore

Click Copy To or Download

Choose restore destination (original location or alternate)

If copying to original: Confirm overwrite if prompted

Verify restored file integrity (open, check content)

#### Full Share Restore (Complete Folder Recovery)

WARNING: This overwrites current data in the share

Snapshot Replication Recovery

DSM > Snapshot Replication > Snapshots

Select shared folder to restore

Click Snapshot List

Choose restore point (date/time)

Click Restore

Confirm Restore

Read warning message carefully

Confirm understanding that current data will be overwritten

Check "I understand" checkbox

Click OK

Monitor Progress

Restore operation will show progress

Time required depends on data size

Do not interrupt the process

Post-Restore Verification

Navigate to restored share in File Station

Verify expected folders and files present

Check file integrity (spot-check key files)

Test access from client workstations

#### Wasabi Archive Recall

Automatic Recall (On-Demand)

DSM > Hybrid Share (or connect via file protocol)

Browse to archived folder

Double-click archived file

File automatically recalls from Wasabi (may take 1-5 minutes)

Progress shown in interface

Bulk Recall (Pinned Folder)

Identify folder requiring bulk access

DSM > Hybrid Share > Settings

Select folder, enable "Pin" temporarily

All files in folder will be recalled

Monitor recall progress

Once complete, unpin if desired to allow re-archival

Recall Monitoring

Check DSM notifications for recall status

Large recalls may take several hours

Monitor bandwidth usage during recall

### Rollback Procedures

Incorrect File Restore:

If wrong file version restored, repeat restore from different snapshot

If file deleted during restore: Check Recycle Bin in File Station

For critical issues: Contact VConfi for advanced recovery options

Failed Share Restore:

Do not panic — snapshots are immutable

Try restore from different snapshot point

If all snapshots fail: Check storage pool integrity

Escalate to Synology support + VConfi immediately

### Escalation Matrix

| Issue | Response Time | Escalate To |
| --- | --- | --- |
| Backup job failing for >24 hours | 2 hours | System Admin + VConfi |
| Restore operation fails | 1 hour | Senior Admin + VConfi |
| Snapshot corruption detected | 30 minutes | IT Manager + Synology support |
| Wasabi connectivity issues | 4 hours | System Admin + Wasabi support |
| Recovery needed for critical project | 15 minutes | IT Manager |
| Full DR recovery required | Immediate | IT Manager + VConfi 24x7 |

### References

Synology DSM 7.0 Snapshot Replication Guide

Synology Hyper Backup Documentation

Wasabi Cloud Storage Documentation

B2H Data Retention Policy

## SOP-DR-001: DR Failover & Failback

### Purpose

Executing disaster recovery procedures for failover from Site A (Primary) to Site B (DR) and subsequent failback operations.

### Scope

Complete site failover including: NAS services, ZTNA remote access, Signiant ingest, and all production workloads.

### Prerequisites

Confirmation of Site A failure (unreachable for >15 minutes)

DSM admin access to Site B HD6500

FortiGate admin access to Site B

Updated employee contact list

IT Manager approval to declare disaster

Alternative communication method (if email is down)

### Failover Procedure (Site A → Site B)

#### Phase 1: Confirmation and Declaration

Verify Site A Status

Attempt contact via multiple methods (ping, SSH, iLO)

Check with ISP for outage confirmation

Verify failure is not localized (ask remote users to test)

Document findings

Declare Disaster

Contact IT Manager for approval

Document declaration time

Activate DR team communication channel

Notify VConfi emergency support

#### Phase 2: Promote Site B Storage

Log into Site B HD6500 DSM

Navigate to `https://10.10.50.12:5001`

Authenticate with admin credentials + 2FA

Break Replication Connection

Navigate to Snapshot Replication > Replication Tasks

Select replication task from Site A

Click Break Connection

Confirm action when prompted

CRITICAL: This makes Site B shares writable

Verify Shares Accessible

Navigate to Control Panel > Shared Folder

Confirm all critical shares present

Verify permissions intact

Test access from management workstation

Update DNS (if using internal DNS)

Update internal DNS records to point to Site B IPs

Or prepare instructions for ZTNA update

#### Phase 3: Update ZTNA Configuration

Log into Site B FortiGate

Navigate to `https://10.10.50.2`

Authenticate with admin credentials

Verify ZTNA Gateway Status

Navigate to VPN > ZTNA

Verify ZTNA gateway is operational

Check access proxy configurations

Update External DNS

Contact DNS administrator or update external DNS

Change `ztna.b2hstudios.com` to point to Site B public IP

TTL consideration: If TTL is high, users may need temporary direct IP

Verify ZTNA Portal Accessible

Test from external location

Verify SSL certificate valid

Confirm authentication working

#### Phase 4: User Notification

Send DR Notification

Subject: "URGENT: Use Site B ZTNA Gateway"

Include new connection instructions

Provide alternative contact (phone, Slack)

Estimate duration of DR operations

Verify Key User Access

Contact department heads

Verify they can connect via ZTNA

Address any immediate access issues

#### Phase 5: Service Verification

Verify NAS Accessibility

Test SMB/NFS access via ZTNA

Verify share permissions

Test file read/write operations

Verify Signiant/Aspera (if deployed at Site B)

Check SDCX server status

Test ingest capability

Notify DIT teams of alternate ingest point

Verify Monitoring

Check Zabbix alerts from Site B

Confirm Splunk receiving logs

Verify backup jobs scheduled

### Failback Procedure (Site B → Site A)

#### Phase 1: Confirm Site A Recovery

Verify Site A Systems Operational

Confirm all hardware powered and healthy

Verify network connectivity

Check storage pool status on Site A HD6500

Ensure no hardware issues remain

Assessment

Determine duration of outage

Estimate data changes at Site B

Plan failback window (typically off-hours)

#### Phase 2: Synchronize Changes

Create Reverse Replication Task

Site B DSM > Snapshot Replication

Create new replication task: Site B → Site A

Select shares modified during DR

Initial sync will take time depending on data change

Monitor Synchronization

Allow sync to complete

Monitor bandwidth usage

Verify no errors during replication

Final Sync

Schedule brief maintenance window

Pause user access during final sync

Ensure all changes replicated

#### Phase 3: Fail Forward to Site A

Stop Reverse Replication

Once sync complete, stop/pause Site B→A task

Re-enable Original Replication

Re-enable Site A→B replication task

Allow initial sync to confirm connectivity

Update ZTNA to Site A

Update external DNS to point back to Site A

Verify ZTNA portal responding

Notify Users

Announce return to normal operations

Provide new (original) connection instructions

#### Phase 4: Post-Failback

Verify All Services

Comprehensive testing of all systems

Confirm backup jobs running

Verify monitoring operational

Update DR Documentation

Document actual RTO/RPO achieved

Note any issues encountered

Update procedures based on lessons learned

Site B Preparation

Ensure Site B ready for next DR event

Verify replication from Site A re-established

### Rollback Procedures

If Failover Fails:

Do not panic — data is safe at Site A (if reachable) or already at Site B

If Site A is partially reachable: Attempt to restore service rather than full failover

If Site B promotion fails: Contact VConfi immediately, consider manual data access

If Failback Fails:

Remain at Site B — operational continuity is priority

Troubleshoot Site A issues

Retry failback when Site A fully stable

### Escalation Matrix

| Phase | Issue | Response | Escalate To |
| --- | --- | --- | --- |
| Failover | Cannot break replication | 30 minutes | Synology support + VConfi |
| Failover | ZTNA not accessible at Site B | 30 minutes | VConfi emergency support |
| Failover | Data inconsistency detected | Immediate | Do not proceed, engage VConfi |
| Failback | Reverse replication fails | 1 hour | Synology support |
| Failback | Site A hardware issues | 2 hours | Hardware vendor + VConfi |

### References

Synology Snapshot Replication Disaster Recovery Guide

FortiGate ZTNA Configuration Guide

B2H DR Architecture Diagram

VConfi Emergency Contact Card

## SOP-SEC-001: Splunk SIEM Review

### Purpose

Daily and weekly review of security logs in Splunk SIEM to detect, analyze, and respond to security threats and anomalies.

### Scope

All security-relevant logs including: FortiGate firewall logs, authentication events, file access logs, VPN/ZTNA sessions, honeypot alerts, and system events from all infrastructure components.

### Prerequisites

Splunk web access (`http://10.10.40.16:8000`)

Security analyst training completed

Access to incident response procedures

Understanding of baseline activity patterns

### Daily Review Procedure

Log into Splunk

Navigate to `http://10.10.40.16:8000`

Authenticate with credentials

Select "B2H Security" app if multiple apps available

Open Security Dashboard

Navigate to Dashboards > Security Overview

Review summary panels

Review Critical Alerts Panel

Check for any red/critical indicators

Drill down into each critical alert

Note time, source, and description

Check Failed Authentication

Review "Failed Logins" panel or run search:

index=* (eventtype=failed_login OR action=failure) earliest=-24h
   | stats count by src_ip, user, app
   | sort -count

Look for:

Multiple failures from same IP

Failures for privileged accounts

After-hours authentication attempts

Unknown usernames

Review High Volume Data Transfer

Check "Data Transfer Anomalies" panel

Look for:

Unusual outbound data volumes

Access to honeypot directories

Off-hours large transfers

Check Honeypot Access Alerts

Honeypot access = immediate red flag

Review source IP, time, and actions attempted

Any honeypot access indicates reconnaissance or breach attempt

Document Findings

Record all anomalies in security log

Create incident tickets for investigation

Escalate critical findings immediately

### Weekly Deep Dive Procedure

Run Top Source IPs Report

index=* earliest=-7d
   | stats count by src_ip
   | sort -count
   | head 20

Review top talkers

Validate against known good systems

Investigate any unknown high-volume sources

Review After Hours Access

index=* (hour<9 OR hour>18) earliest=-7d
   | stats count by user, src_ip, app
   | sort -count

Verify all after-hours access is authorized

Check for access outside business hours patterns

Check Administrative Activities

index=* (admin OR administrator OR root) earliest=-7d
   | stats count by user, action, src_ip
   | sort -count

Review all privileged account usage

Verify changes are documented in change log

Review VPN/ZTNA Session Logs

Navigate to FortiGate VPN Dashboard

Review:

New device connections

Unusual geographic locations

Failed posture checks

Session duration anomalies

Export Summary for Management

Generate PDF of Security Dashboard

Include key metrics:

Total events processed

Critical alerts count

Incidents opened/closed

Trends vs. previous week

### Response to Critical Alerts

| Alert Type | Immediate Action | Follow-up Investigation |
| --- | --- | --- |
| Honeypot access detected | Isolate source IP in firewall, disable account if internal | Full incident response, forensics analysis |
| Brute force attack | Block source IP in FortiGate, enable enhanced logging | Check if any successful logins occurred |
| Data exfiltration pattern | Isolate affected system from network | Forensic imaging, breach assessment |
| Malware detected | Isolate endpoint, disable ZTNA access | Reimage if necessary, check lateral movement |
| Privilege escalation | Disable affected account, revoke sessions | Review audit logs for scope of access |
| Unusual after-hours admin | Contact admin to verify, monitor closely | Check for compromised credentials |

### Rollback Procedures

False Positive Resolution:

Document why alert is false positive

Adjust correlation rule or threshold if needed

Add exception for known good activity

Re-tune search to reduce noise

Overly Aggressive Blocking:

If IP block affects legitimate users:

FortiGate > Policy & Objects > Addresses

Remove IP from block list

Add to whitelist if permanently authorized

Document exception

### Escalation Matrix

| Finding | Response Time | Escalate To |
| --- | --- | --- |
| Confirmed security breach | Immediate | IT Manager + Legal + VConfi |
| Honeypot accessed | 15 minutes | IT Manager |
| Data exfiltration suspected | Immediate | IT Manager + VConfi |
| Malware outbreak | 30 minutes | IT Manager + VConfi |
| Insider threat indicators | 1 hour | IT Manager + HR |
| Unexplained anomalies | 4 hours | Senior Security Admin |

### References

Splunk Enterprise Security Documentation

B2H Security Incident Response Plan

FortiGate Logging and Monitoring Guide

ISO 27001 Security Monitoring Requirements

## SOP-SEC-002: Incident Response Workflow

### Purpose

Structured response to security incidents affecting B2H Studios infrastructure, ensuring rapid containment, eradication, recovery, and lessons learned.

### Scope

All security incidents including: malware infections, unauthorized access, data breaches, insider threats, ransomware attacks, and policy violations.

### Prerequisites

Incident response team contact list

Access to security tools (Splunk, FortiGate, Kaspersky)

Forensic tools available

Legal and HR contact information

Communication templates

### Phase 1: Detection & Analysis

Identify Incident Source

Alert from SIEM (Splunk)

User report

External notification

Automated detection (honeypot, AV)

Triage Severity

| Priority | Description | Examples |
| --- | --- | --- |
| P1-Critical | Active breach, data at risk | Ransomware, data exfiltration in progress |
| P2-High | Confirmed compromise | Successful unauthorized access, malware detected |
| P3-Medium | Suspicious activity | Failed attacks, policy violations |
| P4-Low | Minor issue | Single phishing email, port scan |

Document Initial Findings

Incident ID (format: INC-YYYYMMDD-###)

Detection timestamp

Affected systems/users

Initial scope assessment

Evidence preservation status

Notify Incident Response Team

P1/P2: Immediate notification via phone/Slack

P3/P4: Standard ticket creation

Include: Incident ID, severity, initial details

### Phase 2: Containment

Immediate Isolation (P1/P2)

Isolate affected systems from network:

FortiGate: Block IP addresses

Switch: Disable port

VMware: Disconnect vNIC

Preserve volatile evidence (memory dumps)

Document containment actions with timestamps

Short-term Containment

Disable compromised accounts

Revoke active sessions

Block malicious IPs at perimeter

Enable enhanced logging

Long-term Containment

Apply temporary patches/workarounds

Redirect traffic to clean systems

Implement additional monitoring

Evidence Preservation

Create forensic images before any changes

Preserve logs (export from Splunk)

Chain of custody documentation

### Phase 3: Eradication

Identify Root Cause

Analyze evidence collected

Determine attack vector

Identify compromised credentials

Map lateral movement

Remove Threats

Delete malware/backdoors

Remove unauthorized accounts

Clean infected systems (reimage if necessary)

Patch Vulnerabilities

Apply security patches

Update IDS/IPS signatures

Harden configurations

Reset Credentials

Force password reset for affected accounts

Rotate service accounts

Revoke and reissue certificates if compromised

### Phase 4: Recovery

Restore from Clean Backups

Use known-good backup (pre-incident)

Verify backup integrity before restore

Restore systems in isolated network first

Verify System Integrity

Scan restored systems for malware

Verify file integrity (checksums)

Test functionality

Restore Network Connectivity

Reconnect to production network

Monitor for re-infection

Verify security controls active

Monitor for Recurrence

Enhanced monitoring for 30 days

Daily security reviews

User awareness reminders

### Phase 5: Post-Incident

Document Timeline

Detailed chronology of events

All actions taken with timestamps

Evidence collected

Conduct Lessons Learned

Within 1 week of incident closure

Attendees: IR team, affected parties, management

Questions:

What went well?

What could be improved?

What gaps were exposed?

Update Procedures

Revise SOPs based on lessons learned

Update detection rules

Improve response playbooks

Report to Stakeholders

Executive summary for management

Technical report for IT

Regulatory notification if required

### Rollback Procedures

If Containment Too Aggressive:

Document what business function affected

Management approval for containment relaxation

Implement compensating controls

Gradual restoration with enhanced monitoring

If Recovery Premature:

Re-isolate affected systems immediately

Return to Eradication phase

Deeper forensic analysis

Coordinate with external experts if needed

### Escalation Matrix

| Incident Type | Internal Notify | External Notify | Regulatory |
| --- | --- | --- | --- |
| Data breach (customer data) | CEO, Legal, IT Manager | VConfi | As required by law |
| Ransomware | CEO, IT Manager | Law enforcement, VConfi | As required |
| Insider threat (malicious) | HR, Legal, IT Manager | Law enforcement | N/A |
| System compromise | IT Manager | VConfi support | N/A |
| Policy violation | HR, Manager | N/A | N/A |

### Communication

Internal Channels:

Slack #security-incidents (IR team)

Phone tree for critical incidents

Email for status updates

External Channels:

VConfi emergency hotline: [Configured during implementation]

Law enforcement: Local cyber crime unit

Legal counsel: [B2H legal contact]

### References

NIST SP 800-61: Computer Security Incident Handling Guide

ISO 27035: Information Security Incident Management

B2H Incident Response Plan (master document)

VConfi Incident Response Retainer Agreement

## SOP-SEC-003: ISO 27001 Audit Prep Checklist

### Purpose

Preparing for ISO 27001 internal or external audits by ensuring all required documentation, evidence, and controls are in place and up to date.

### Scope

All ISO 27001:2022 controls (Annex A) applicable to B2H Studios information security management system (ISMS).

### Prerequisites

Access to ISMS documentation repository

Current asset inventory

Risk register access

Training records

Previous audit reports (if any)

### Pre-Audit (1 Week Before)

#### Documentation Review

☐ Verify all policies are current and approved

Information Security Policy (signed by CEO)

Acceptable Use Policy

Access Control Policy

Incident Response Policy

Business Continuity/DR Policy

Review dates within last 12 months

☐ Confirm asset inventory is up to date

Hardware assets (servers, network, endpoints)

Software assets (licenses, versions)

Data assets (classification, ownership)

Cloud services inventory

☐ Review access control lists

User access matrix current

Privileged access documented

Access review records (quarterly)

Terminated user access removed

☐ Verify backup test records

Monthly restore test results documented

DR test report (annual minimum)

Backup verification logs

☐ Check incident log completeness

All incidents logged (even minor)

Root cause analysis completed

Corrective actions tracked

☐ Review training records

Security awareness training completion

Role-specific training records

New employee onboarding records

☐ Verify risk register is current

Risk assessment within last 12 months

Risk treatment plans current

Residual risk acceptable

☐ Prepare evidence folders

Organize by Annex A control group

Ensure electronic and physical copies available

Index for quick retrieval

### Audit Day Preparation

☐ Open evidence folder structure

Physical folders or shared drive structure ready

Quick access to all documents

☐ Have admin credentials ready

Test all logins before audit

Ensure no password expiry during audit

☐ Prepare data center walkthrough

Access badges ready

Safety briefing prepared

Physical security features to highlight

☐ Schedule key personnel availability

IT Manager

Security Admin

Department heads

Avoid scheduling conflicts

☐ Prepare dashboard demonstrations

Zabbix monitoring dashboard

Splunk security dashboard

DSM administration interface

### Evidence Folders Structure

| Folder | Control Group | Contents |
| --- | --- | --- |
| A.5 | Organizational Controls | Security policies, roles and responsibilities, segregation of duties |
| A.8 | Asset Management | Asset inventory, asset handling procedures, data classification |
| A.9 | Access Control | Access control policy, user provisioning/deprovisioning, access reviews |
| A.10 | Cryptography | Cryptographic policy, key management, certificate inventory |
| A.11 | Physical Security | Datacenter access logs, visitor records, environmental controls |
| A.12 | Operations Security | Change management records, backup logs, vulnerability assessments |
| A.13 | Communications Security | Network diagrams, firewall rules, encryption standards |
| A.16 | Incident Management | Incident logs, response procedures, post-incident reviews |

### Common Audit Questions & Answers

| Question | Answer | Evidence |
| --- | --- | --- |
| How do you manage access reviews? | Quarterly access reviews with manager sign-off, automated for critical systems | Access review records, approval emails |
| How do you test backups? | Monthly file-level restore tests, quarterly full DR tests | Test results documented in SOP-BKP-001 logs |
| How do you track assets? | Automated discovery via Zabbix plus manual verification quarterly | Asset inventory export, discovery reports |
| What is your patch management process? | Monthly OS patching, quarterly firmware updates per SOP-SRV-001 | Change records, patch logs |
| How do you detect security incidents? | Splunk SIEM with correlation rules, honeypot alerts, user reporting | Splunk dashboard, incident log |
| How do you manage third-party risk? | Vendor assessment questionnaire, contract security clauses, annual reviews | Vendor assessment records |
| What is your incident response time? | P1-Critical: 15 minutes, P2-High: 1 hour per SOP-SEC-002 | Incident response records |
| How do you ensure business continuity? | Active-standby DR site, tested quarterly per SOP-DR-001 | DR test reports, replication status |

### Post-Audit Activities

☐ Document findings

Major non-conformities

Minor non-conformities

Opportunities for improvement

Positive observations

☐ Create remediation plan

Assign owners for each finding

Set target dates (typically 30-90 days)

Define acceptance criteria

☐ Track to closure

Weekly status review

Evidence collection for closure

Management review

☐ Update ISMS

Incorporate lessons learned

Update risk register

Revise procedures if needed

### Rollback Procedures

If Evidence Not Available:

Do not fabricate evidence

Document gap as finding

Create corrective action plan

Implement control and gather evidence going forward

If Control Not Implemented:

Acknowledge gap honestly

Assess risk of missing control

Prioritize implementation

Document risk acceptance or treatment

### Escalation Matrix

| Issue | Response | Escalate To |
| --- | --- | --- |
| Major non-conformity identified | Immediate | CEO, IT Manager |
| Evidence unavailable | 1 day | IT Manager |
| Auditor disagreement | Immediate | IT Manager + VConfi |
| Scope expansion requested | Immediate | CEO |

### References

ISO/IEC 27001:2022 Standard

ISO/IEC 27002:2022 Implementation Guidance

B2H ISMS Documentation

Previous Audit Reports

## SOP-USR-001: Wi-Fi & ZTNA Access Guide (End User)

### Purpose

Step-by-step guide for B2H Studios employees to connect to corporate network resources via ZTNA remote access and corporate Wi-Fi.

### Scope

All B2H Studios employees, contractors, and authorized guests requiring network access.

### Prerequisites

B2H-issued laptop or workstation

FortiClient VPN/ZTNA software installed

Active Directory credentials (username@b2hstudios.com)

FortiToken registered on mobile device

Computer meets security posture requirements

### ZTNA Connection Procedure

Launch FortiClient

Locate FortiClient icon in system tray or Start menu

Double-click to open application

Ensure FortiClient is up to date (check for updates if prompted)

Enter Credentials

Enter your B2H username (e.g., `jdoe` or `jdoe@b2hstudios.com`)

Enter your password

Click Connect or press Enter

Approve FortiToken

Receive push notification on your registered mobile device

Open FortiToken app

Tap Approve or enter displayed code

If no push: Open FortiToken app manually to get 6-digit code

Wait for Posture Check

FortiClient will verify your device security:

Windows is up to date

Kaspersky antivirus is active and updated

Disk encryption enabled

Green checkmarks indicate passed checks

If any check fails, follow on-screen instructions

Access Resources

Once connected, ZTNA tunnel established

Access NAS shares via mapped drives (usually auto-map)

Access internal web applications

All traffic routed securely through encrypted tunnel

Disconnect

Click Disconnect in FortiClient when finished

Or simply close laptop (sleep will disconnect)

### Wi-Fi Connection Procedure

Select Network

Click Wi-Fi icon in system tray

Select "B2H-Corporate" from available networks

Avoid "B2H-Guest" unless instructed by IT

Enter Credentials

Username: `username@b2hstudios.com` (e.g., `jdoe@b2hstudios.com`)

Password: Your AD password

Click Connect or OK

Accept Certificate

If prompted to accept server certificate: Click Connect or Trust

Certificate name should reference B2H or Fortinet

If certificate warning appears: Contact IT before proceeding

Verify Connection

Wi-Fi icon should show connected status

Open browser and test internal website

If connected but no internet: Check if ZTNA needed for external access

### Troubleshooting Guide

| Issue | Solution |
| --- | --- |
| **FortiClient won't connect** | 1. Check internet connection (try browsing website)<br>2. Restart FortiClient<br>3. Restart computer<br>4. Check if credentials correct (try logging into webmail) |
| **No FortiToken push notification** | 1. Check phone has signal/Wi-Fi<br>2. Open FortiToken app manually<br>3. Use 6-digit code instead of push<br>4. If no codes: Contact IT to re-register token |
| **Posture check fails** | 1. Run Windows Update<br>2. Open Kaspersky, ensure active and updated<br>3. Verify BitLocker encryption enabled<br>4. Restart computer and retry |
| **Slow file access** | 1. Check internet speed (speedtest.net)<br>2. Close other bandwidth-heavy apps<br>3. Try accessing smaller files first<br>4. Contact IT if consistently slow |
| **Can't see NAS shares** | 1. Disconnect ZTNA<br>2. Wait 10 seconds<br>3. Reconnect ZTNA<br>4. Check File Explorer for mapped drives<br>5. If still missing: Contact IT |
| **Forgot password** | 1. Use password reset link on company portal<br>2. Or contact IT Support<br>3. Do NOT guess repeatedly (locks account) |
| **ZTNA keeps disconnecting** | 1. Check sleep settings (disable sleep while plugged in)<br>2. Check power settings for network adapter<br>3. Try wired connection if available<br>4. Contact IT if persistent |

### Security Reminders

Never share your credentials — Your account is your responsibility

Lock your computer when away (Windows key + L)

Report suspicious emails — Forward phishing attempts to security@b2hstudios.com

Don't connect personal devices to corporate Wi-Fi without IT approval

Use only approved file sharing — No personal Dropbox, Google Drive for work files

Keep FortiClient running during work sessions for security monitoring

Update your software when prompted — Critical for security posture

### Getting Help

| Support Channel | Contact | Hours |
| --- | --- | --- |
| Email | it-support@b2hstudios.com | 24/7 (monitored) |
| Slack | #it-help channel | 9 AM - 6 PM IST |
| Phone | Extension 2000 (internal) | 9 AM - 6 PM IST |
| Emergency | [IT Manager mobile] | 24/7 for critical issues |

### Rollback Procedures

Reset FortiClient:

Right-click FortiClient icon in system tray

Select Settings

Click Backup and Restore

Select Reset to Default

Reconfigure ZTNA connection

Remove and Re-add Wi-Fi:

Settings > Network & Internet > Wi-Fi

Click Manage known networks

Select "B2H-Corporate" > Forget

Reconnect following Wi-Fi procedure above

### References

FortiClient User Guide

B2H IT Security Policy

Password Reset Portal: https://password.b2hstudios.com

IT Self-Service Portal: https://helpdesk.b2hstudios.com

## Document Control

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | March 22, 2026 | VConfi Solutions | Initial release |

### Approval

| Role | Name | Date | Signature |
| --- | --- | --- | --- |
| IT Manager |  |  |  |
| Security Officer |  |  |  |
| Operations Manager |  |  |  |

### Distribution

IT Operations Team

Security Team

All B2H Studios Employees (SOP-USR-001)

VConfi Support Team

End of Part 6: Standard Operating Procedures